## Info
Transmission Outage Planning Process EirGrid, in cooperation with ESB Networks, has implemented a new transmission outage planning process for 2016. In the past, all maintenance and capital work was scheduled at the start of the year. This process of early scheduling of outages sometimes up to nine months in advance led to a large number of alterations in outage dates due for example to changes in generator outage dates, capital project changes, forced outages of transmission plant and other factors. The new outage planning process aims to increase flexibility in the outage programme to the benefit of our customers by better accommodating project changes as they occur with the least disruption. In doing so it is hoped to maximise the amount of work which can be carried out on the transmission system in a given outage season with a nominal amount of schedule changes. A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Indicative'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer. Outages several months in the future will initially be classified as 'Indicative', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occuring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to. All planned outages until the end of the year are presented in this spreadsheet. For information on outages which have already taken place in 2016 please refer to the two week outage summary publications at the following link: http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/ The 'All' tab includes all planned outages while separate tabs are provided which list the outages in the various regions around the country. Outage Classification: Scheduled - Outage scheduled with specified start and end dates. Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates. Indicative - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season, for example works which are not expected to take place until several months in the future. These works are given an indicative outage window (date range) in which a fixed duration of work will be carried out. The 'Calendar Day' duration of indicative outages is 'Unknown' until specific start and end dates are proposed and scheduled. Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer. In some instances, there will be two overlapping outages for the same item of plant with a different status for each outage e.g. 'Proposed' and 'Indicative'. In these instances there are separate works to be completed on the same item of plant e.g. capital works and maintenance works, and both sets of work are in different stages of the outage confirmation process. It is EirGrid’s intention wherever possible/practicable to overlap maintenance/capital works on items of plant to minimise impact on customers and the transmission system. Date of publication: 8 June 2016 Update interval: The first week of each month

## All
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 92 | 62 | Scheduled | 22/03/2016 | 21/06/2016
TO-16-BVK-TB-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-TARBERT 220-1 | 102 | 72 | Scheduled | 29/03/2016 | 08/07/2016
TO-16-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 96 | 68 | Scheduled | 04/04/2016 | 08/07/2016
TO-16-MOY-TAW-2-06 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 74 | 51 | Scheduled | 10/04/2016 | 22/06/2016
TO-16-TAW-T102-05 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T102 | 74 | 51 | Reference | 10/04/2016 | 22/06/2016
TO-16-TAW-T3-03 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 74 | 51 | Reference | 10/04/2016 | 22/06/2016
TO-16-GAL-T141-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | 100 | 70 | Reference | 09/05/2016 | 16/08/2016
TO-16-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 71 | 50 | Scheduled | 16/05/2016 | 25/07/2016
TO-16-ARI,T-COS-1-07 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 51 | 36 | Scheduled | 02/06/2016 | 22/07/2016
TO-16-AA-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA 110-LIMERICK 110-1 | 64 | 8 | Scheduled | 07/06/2016 | 09/08/2016
TO-16-AA-LIM-1-02 | 110kV FEEDER - ARDNACRUSHA 110-LIMERICK 110-1 | 64 | 45 | Proposed | 07/06/2016 | 09/08/2016
TO-16-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 177 | 125 | Scheduled | 07/06/2016 | 30/11/2016
TO-16-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 20 | 5 | Scheduled | 08/06/2016 | 27/06/2016
TO-16-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 14 | 10 | Scheduled | 08/06/2016 | 21/06/2016
TO-16-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 13 | 9 | Scheduled | 08/06/2016 | 20/06/2016
TO-16-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 13 | 9 | Scheduled | 08/06/2016 | 20/06/2016
TO-16-CF-DRM-1-06 | 110kV FEEDER - CATHALEENS FALL 110-DRUMKEEN 110-1 | 88 | 61 | Scheduled | 10/06/2016 | 05/09/2016
TO-16-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 21 | 15 | Scheduled | 10/06/2016 | 30/06/2016
TO-16-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 9 | 7 | Scheduled | 13/06/2016 | 21/06/2016
TO-16-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 9 | 7 | Scheduled | 13/06/2016 | 21/06/2016
TO-16-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 9 | 7 | Reference | 13/06/2016 | 21/06/2016
TO-16-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 27 | 20 | Scheduled | 13/06/2016 | 09/07/2016
TO-16-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-110SA1-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-110SA2-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RYB-T104-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T104 | 32 | 24 | Scheduled | 14/06/2016 | 15/07/2016
TO-16-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 7 | 5 | Scheduled | 15/06/2016 | 21/06/2016
TO-16-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 7 | 5 | Scheduled | 15/06/2016 | 21/06/2016
TO-16-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 7 | 5 | Scheduled | 16/06/2016 | 22/06/2016
TO-16-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 8 | 6 | Scheduled | 17/06/2016 | 24/06/2016
TO-16-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 3 | 3 | Scheduled | 19/06/2016 | 21/06/2016
TO-16-CSH-GAL-1-08 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 26 | 20 | Proposed | 20/06/2016 | 15/07/2016
TO-16-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 26 | 5 | Proposed | 20/06/2016 | 15/07/2016
TO-16-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 3 | 3 | Scheduled | 20/06/2016 | 22/06/2016
TO-16-GAL-110K1-2-03 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-GAL-110K1-3-03 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | Scheduled | 20/06/2016 | 22/06/2016
TO-16-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 1 | 1 | Scheduled | 20/06/2016 | 20/06/2016
TO-16-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-110SA1-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-T141-01 | DISTRIBUTION TRANSFORMER - TIPPERARY 110-TIPPERARY 38-T141 | 1 | 1 | Reference | 21/06/2016 | 21/06/2016
TO-16-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 3 | 3 | Scheduled | 22/06/2016 | 24/06/2016
TO-16-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | Scheduled | 22/06/2016 | 24/06/2016
TO-16-MOY-110SA1-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-110SA2-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-CAP2-04 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-T142-04 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 1 | 1 | Reference | 22/06/2016 | 22/06/2016
TO-16-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 2 | 2 | Scheduled | 23/06/2016 | 24/06/2016
TO-16-AA-T142-03 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA 38-T142 | 2 | 2 | Reference (Proposed) | 25/06/2016 | 26/06/2016
TO-16-BK-CBR-1-12 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 2 | Scheduled | 25/06/2016 | 26/06/2016
TO-16-CBR-T142-08 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 2 | 2 | Reference | 25/06/2016 | 26/06/2016
TO-16-CBG-CBR-1-09 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 1 | Reference | 26/06/2016 | 26/06/2016
TO-16-CBG-T142-08 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 1 | Reference | 26/06/2016 | 26/06/2016
TO-16-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 16 | 11 | Proposed | 26/06/2016 | 11/07/2016
TO-16-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 13 | 10 | Proposed | 26/06/2016 | 08/07/2016
TO-16-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 5 | 5 | Scheduled | 27/06/2016 | 05/07/2016
TO-16-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 3 | 3 | Proposed | 27/06/2016 | 29/06/2016
TO-16-CAH-CAP2/4-02 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 3 | 3 | Tentative | 27/06/2016 | 29/06/2016
TO-16-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 5 | Tentative | 27/06/2016 | 01/07/2016
TO-16-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 47 | 34 | Proposed | 27/06/2016 | 12/08/2016
TO-16-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 3 | 3 | Scheduled | 27/06/2016 | 29/06/2016
TO-16-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | Scheduled | 27/06/2016 | 27/06/2016
TO-16-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 4 | 4 | Proposed | 27/06/2016 | 30/06/2016
TO-16-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 5 | 5 | Scheduled | 27/06/2016 | 01/07/2016
TO-16-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 15 | 11 | Proposed | 27/06/2016 | 11/07/2016
TO-16-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 2 | 2 | Scheduled | 27/06/2016 | 28/06/2016
TO-16-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 5 | 5 | Tentative | 27/06/2016 | 01/07/2016
TO-16-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 9 | 7 | Scheduled | 28/06/2016 | 06/07/2016
TO-16-DOO-110SA1-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 4 | 4 | Scheduled | 28/06/2016 | 01/07/2016
TO-16-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 4 | 4 | Scheduled | 28/06/2016 | 01/07/2016
TO-16-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 1 | 1 | Scheduled | 28/06/2016 | 28/06/2016
TO-16-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 8 | 6 | Scheduled | 29/06/2016 | 06/07/2016
TO-16-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 29/06/2016 | 01/07/2016
TO-16-DOO-T142-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 4 | 4 | Reference | 30/06/2016 | 01/07/2016
TO-16-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 57 | 40 | Proposed | 04/07/2016 | 29/08/2016
TO-16-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 1 | 1 | Reference (Tentative) | 04/07/2016 | 04/07/2016
TO-16-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 1 | 1 | Tentative | 04/07/2016 | 04/07/2016
TO-16-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 3 | Scheduled | 04/07/2016 | 10/07/2016
TO-16-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 5 | Tentative | 04/07/2016 | 10/07/2016
TO-16-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 1 | 1 | Tentative | 04/07/2016 | 04/07/2016
TO-16-BAR,T-KRA-1-04 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 1 | 1 | Proposed | 04/07/2016 | 04/07/2016
TO-16-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 57 | 40 | Reference (Proposed) | 04/07/2016 | 29/08/2016
TO-16-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 12 | 10 | Proposed | 04/07/2016 | 15/07/2016
TO-16-CBR-DLT-1-06 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 5 | 4 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | 15 | Indicative | July | July
TO-16-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 9 | 7 | Proposed | 04/07/2016 | 12/07/2016
TO-16-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-DLT-110SA1-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 2 | Proposed | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA1-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA2-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 2 | Proposed | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA2-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-DLT-CAP1-04 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | Proposed | 04/07/2016 | 05/07/2016
TO-16-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 8 | 6 | Scheduled | 04/07/2016 | 11/07/2016
TO-16-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-SKL-110SA1-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-110SA2-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-M/CAP2-01 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-T142-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 5 | 5 | Reference | 04/07/2016 | 08/07/2016
TO-16-CLW-110SA1-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 8 | 6 | Scheduled | 05/07/2016 | 12/07/2016
TO-16-CLW-T141-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 2 | 2 | Reference | 05/07/2016 | 06/07/2016
TO-16-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 18 | 14 | Proposed | 05/07/2016 | 22/07/2016
TO-16-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 43 | 30 | Proposed | 05/07/2016 | 16/08/2016
TO-16-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | Scheduled | 05/07/2016 | 05/07/2016
TO-16-MP-400K1-2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT 400-MONEYPOINT 400-400K1-2 | 3 | 3 | Scheduled | 05/07/2016 | 07/07/2016
TO-16-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 29 | 20 | Scheduled | 06/07/2016 | 03/08/2016
TO-16-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 29 | 20 | Scheduled | 06/07/2016 | 03/08/2016
TO-16-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | Scheduled | 06/07/2016 | 06/07/2016
TO-16-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 3 | 3 | Scheduled | 06/07/2016 | 08/07/2016
TO-16-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 2 | 2 | Reference (Tentative) | 09/07/2016 | 10/07/2016
TO-16-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 2 | 2 | Tentative | 09/07/2016 | 10/07/2016
TO-16-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 2 | 2 | Tentative | 09/07/2016 | 10/07/2016
TO-16-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 5 | 5 | Proposed | 11/07/2016 | 15/07/2016
TO-16-CBR-T142-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 2 | 2 | Reference (Proposed) | 11/07/2016 | 12/07/2016
TO-16-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 7 | 7 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND 220-1 | 7 | 7 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 7 | 5 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | Reference | 11/07/2016 | 11/07/2016
TO-16-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | Scheduled | 11/07/2016 | 11/07/2016
TO-16-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 11/07/2016 | 11/07/2016
TO-16-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 7 | Scheduled | 11/07/2016 | 25/07/2016
TO-16-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 10 | Proposed | 11/07/2016 | 25/07/2016
TO-16-DMY-MAC-1-06 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 15 | 11 | Proposed | 12/07/2016 | 26/07/2016
TO-16-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 1 | 1 | Proposed | 12/07/2016 | 12/07/2016
TO-16-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 12 | 9 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-CAP2-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-T142-02 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-CLW-110SA1-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-110SA2-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-T142-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | 2 | 2 | Reference | 13/07/2016 | 14/07/2016
TO-16-CSH-FLA-1-02 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-220K1-2-02 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-SRA-1-04 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-T2101-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 1 | 1 | Scheduled | 13/07/2016 | 13/07/2016
TO-16-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-RYB-RYB GIS-1-09 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 3 | 3 | Proposed | 13/07/2016 | 15/07/2016
TO-16-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 2 | 2 | Reference | 13/07/2016 | 14/07/2016
TO-16-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 1 | 1 | Scheduled | 13/07/2016 | 13/07/2016
TO-16-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 1 | 1 | Proposed | 15/07/2016 | 15/07/2016
TO-16-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 2 | 2 | Scheduled | 16/07/2016 | 17/07/2016
TO-16-FIN-FIN GIS-1-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | July | July
TO-16-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 10 | 8 | Scheduled | 18/07/2016 | 27/07/2016
TO-16-CF-110K1-2-03 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | 5 | Indicative | July | July
TO-16-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 |  | Scheduled | 18/07/2016 | 22/07/2016
TO-16-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | Unknown | 4 | Indicative | July | July
TO-16-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 11 | 9 | Scheduled | 18/07/2016 | 28/07/2016
TO-16-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-GI-110K1-2-11 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 15 | Indicative | July | August
TO-16-GI GIS-T2102-01 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | Unknown | 42 | Indicative | July | October
TO-16-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 15 | Indicative | July | August
TO-16-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 15 | Indicative | July | August
TO-16-KER-110SA1-01 | SECTIONALISING DISCONNECT - KNOCKEARAGH 110-KNOCKEARAGH 110-110SA1 | 3 | 3 | Scheduled | 18/07/2016 | 20/07/2016
TO-16-KER-110SA2-02 | SECTIONALISING DISCONNECT - KNOCKEARAGH 110-KNOCKEARAGH 110-110SA2 | 3 | 3 | Scheduled | 18/07/2016 | 20/07/2016
TO-16-KER-T141-01 | DISTRIBUTION TRANSFORMER - KNOCKEARAGH 110-KNOCKEARAGH 38-T141 | 3 | 3 | Reference | 18/07/2016 | 20/07/2016
TO-16-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | Unknown | 30 | Reference (Indicative) | July | August
TO-16-MAY-RYB-1-06 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK 110-1 | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 3 | 3 | Proposed | 19/07/2016 | 21/07/2016
TO-16-PB-TF4-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 3 | 3 | Reference (Proposed) | 19/07/2016 | 21/07/2016
TO-16-RYB-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-RYB-RYB GIS-1-10 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-RYB-T107-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T107 | 37 | 26 | Proposed | 19/07/2016 | 24/08/2016
TO-16-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 3 | 3 | Scheduled | 20/07/2016 | 22/07/2016
TO-16-ARI-T121-07 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 1 | 1 | Reference | 22/07/2016 | 22/07/2016
TO-16-ARI,T-ARI-1-07 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 1 | 1 | Scheduled | 22/07/2016 | 22/07/2016
TO-16-ARI,T-CDY-1-05 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 1 | Scheduled | 22/07/2016 | 22/07/2016
TO-16-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 8 | 6 | Scheduled | 22/07/2016 | 29/07/2016
TO-16-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 11 | 10 | Scheduled | 23/07/2016 | 02/08/2016
TO-16-ARV-COS-1-06 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | Scheduled | 23/07/2016 | 25/07/2016
TO-16-COS-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 | Scheduled | 23/07/2016 | 25/07/2016
TO-16-COS-T141-04 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 | Reference | 23/07/2016 | 25/07/2016
TO-16-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-CF-T141-01 | DISTRIBUTION TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL 38-T141 | Unknown | 10 | Reference (Indicative) | July | August
TO-16-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-DLT-CAP1-03 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | 15 | Indicative | July | August
TO-16-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-IKE-T141-04 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | Reference | 25/07/2016 | 25/07/2016
TO-16-IKE,T-IKE-1-04 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | Scheduled | 25/07/2016 | 25/07/2016
TO-16-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 25/07/2016 | 25/07/2016
TO-16-KNR-TB-1-220-01 | 220kV FEEDER - KNOCKANURE 220-TARBERT 220-1-220 | Unknown | 4 | Indicative | July | July
TO-16-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-NAV-M/CAP1-01 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-NAV-T141-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 5 | 5 | Reference | 25/07/2016 | 29/07/2016
TO-16-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 2 | 2 | Scheduled | 25/07/2016 | 26/07/2016
TO-16-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 2 | 2 | Scheduled | 25/07/2016 | 26/07/2016
TO-16-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 2 | 2 | Reference | 26/07/2016 | 27/07/2016
TO-16-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 4 | 4 | Scheduled | 26/07/2016 | 29/07/2016
TO-16-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 2 | 2 | Proposed | 27/07/2016 | 28/07/2016
TO-16-CD-KBY-1-03 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 16 | 11 | Proposed | 27/07/2016 | 11/08/2016
TO-16-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 2 | 2 | Scheduled | 28/07/2016 | 29/07/2016
TO-16-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 1 | 1 | Scheduled | 28/07/2016 | 28/07/2016
TO-16-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | Tentative | 28/07/2016 | 01/08/2016
TO-16-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | Reference (Tentative) | 28/07/2016 | 01/08/2016
TO-16-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 16 | 9 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 2 | Indicative | July | July
TO-16-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 2 | Indicative | July | July
TO-16-ARV-SKL-2-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 15 | 10 | Proposed | 01/08/2016 | 15/08/2016
TO-16-AA-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G1-T101 | Unknown | 3 | Indicative | August | August
TO-16-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | 3 | Indicative | August | August
TO-16-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | 3 | Indicative | August | August
TO-16-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-CDU-RYB-1-04 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 6 | Indicative | August | August
TO-16-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | 5 | Indicative | August | August
TO-16-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | 4 | Indicative | August | August
TO-16-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | 6 | Indicative | August | August
TO-16-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | 5 | Indicative | August | August
TO-16-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | 5 | Indicative | August | August
TO-16-RNW-110SA1-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | Unknown | 4 | Indicative | August | August
TO-16-RNW-110SA2-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | Unknown | 4 | Indicative | August | August
TO-16-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | 6 | Indicative | August | August
TO-16-RYB-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 3 | Indicative | August | August
TO-16-RYB-RYB GIS-2-06 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 3 | Indicative | August | August
TO-16-RYB-T101-04 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | Unknown | 3 | Indicative | August | August
TO-16-RYB-T103-04 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 3 | Indicative | August | August
TO-16-TB-TRL-2-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-2 | Unknown | 6 | Indicative | August | August
TO-16-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 7 | Indicative | August | August
TO-16-CSH-GAL-1-06 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 1 | 1 | Scheduled | 03/08/2016 | 03/08/2016
TO-16-FLA-LA-1-01 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 2 | Indicative | August | September
TO-16-FLA-LA-1-02 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 39 | Indicative | August | September
TO-16-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 6 | Indicative | August | August
TO-16-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-AA-AA GIS-1-01 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | 2 | 2 | Proposed | 08/08/2016 | 09/08/2016
TO-16-AA-ENN-1-06 | 110kV FEEDER - ARDNACRUSHA 110-ENNIS 110-1 | 2 | 2 | Proposed | 08/08/2016 | 09/08/2016
TO-16-DOO-CAP1-01 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | 2 | Indicative | August | August
TO-16-DOO-T141-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-KTL-110SA1-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-KTL-110SA2-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | Unknown | 3 | Indicative | August | August
TO-16-KTL-T141-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T141 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | 25 | Indicative | August | September
TO-16-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | 1 | Indicative | August | August
TO-16-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | 5 | Indicative | August | August
TO-16-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | 3 | Indicative | August | August
TO-16-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | 12 | Indicative | August | August
TO-16-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | 5 | Indicative | August | August
TO-16-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-CSH-GAL-1-09 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | Unknown | 70 | Indicative | August | November
TO-16-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 2 | Indicative | August | August
TO-16-GAL-110K1-2-04 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-GAL-110K1-3-04 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | 1 | Reference (Indicative) | August | August
TO-16-GRI,T-GCA-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | 8 | Indicative | August | August
TO-16-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 11 | Indicative | August | August
TO-16-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown | 11 | Indicative | August | August
TO-16-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | 11 | Indicative | August | August
TO-16-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | 11 | Indicative | August | August
TO-16-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 11 | Indicative | August | August
TO-16-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 17 | Indicative | August | August
TO-16-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | 11 | Indicative | August | August
TO-16-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | 11 | Indicative | August | August
TO-16-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | 5 | Indicative | August | August
TO-16-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | 10 | Indicative | August | August
TO-16-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | 10 | Indicative | August | August
TO-16-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | 9 | Indicative | August | August
TO-16-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 11 | 9 | Proposed | 16/08/2016 | 26/08/2016
TO-16-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | 9 | Indicative | August | August
TO-16-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | Unknown | 1 | Indicative | August | August
TO-16-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | 1 | Indicative | August | August
TO-16-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 8 | Indicative | August | August
TO-16-DSN-KLS-1-04 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-GI GIS-KLS-1-06 | 220kV FEEDER - GREAT ISLAND 220-KELLIS 220-1 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | 8 | Indicative | August | August
TO-16-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-KLS-T2102-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | 8 | Indicative | August | August
TO-16-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | 8 | Indicative | August | August
TO-16-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | 8 | Indicative | August | August
TO-16-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | 8 | Reference (Indicative) | August | August
TO-16-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | 8 | Indicative | August | August
TO-16-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | 8 | Indicative | August | August
TO-16-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | 8 | Indicative | August | August
TO-16-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | 1 | Indicative | August | August
TO-16-110 kV B1 @ AA-04 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110B1 | Unknown | 4 | Indicative | August | August
TO-16-AA-T141-01 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA 38-T141 | Unknown | 70 | Reference (Indicative) | August | November
TO-16-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | Unknown | 7 | Indicative | August | August
TO-16-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 5 | Indicative | August | August
TO-16-COW-WHI-1-02 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 2 | Indicative | August | August
TO-16-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | 10 | Indicative | August | September
TO-16-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Indicative | August | August
TO-16-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 2 | Indicative | August | August
TO-16-110 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | Unknown | 37 | Indicative | August | November
TO-16-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | 4 | Indicative | August | August
TO-16-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | Unknown | 45 | Indicative | August | November
TO-16-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 3 | Indicative | August | August
TO-16-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown | 5 | Indicative | August | August
TO-16-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | Unknown | 5 | Indicative | August | August
TO-16-RYB-RYB GIS-1-11 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 3 | 3 | Proposed | 22/08/2016 | 24/08/2016
TO-16-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | Unknown | 2 | Indicative | August | August
TO-16-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-TB-T2101-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | Unknown | 5 | Indicative | August | August
TO-16-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-WHI-110SA2-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | 5 | Indicative | August | August
TO-16-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 2 | Indicative | August | August
TO-16-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | 1 | Reference (Indicative) | August | August
TO-16-GRI,T-GCA-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-GRI-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | 1 | Indicative | August | August
TO-16-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | Unknown | 2 | Indicative | August | August
TO-16-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | Unknown | 2 | Indicative | August | August
TO-16-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-110 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | Unknown | 2 | Indicative | August | August
TO-16-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 7 | Indicative | August | August
TO-16-110 kV A1 @ AA-03 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110A1 | Unknown | 10 | Indicative | August | September
TO-16-AA-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA 110-ARDNACRUSHA 110-CAP1 | Unknown | 2 | Indicative | August | November
TO-16-AA-CAP1-02 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA 110-ARDNACRUSHA 110-CAP1 | Unknown | 40 | Indicative | August | November
TO-16-AA-T101-03 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G1-T101 | Unknown | 45 | Indicative | August | November
TO-16-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 1 | 1 | Reference (Proposed) | 29/08/2016 | 29/08/2016
TO-16-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 1 | 1 | Reference (Proposed) | 29/08/2016 | 29/08/2016
TO-16-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | 10 | Indicative | August | September
TO-16-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | 10 | Indicative | August | September
TO-16-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | 10 | Indicative | August | September
TO-16-CDU-RYB-1-06 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 4 | Indicative | August | September
TO-16-FIN-FIN GIS-1-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | August | August
TO-16-RYB-110SA1-2CB-11 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 4 | Indicative | August | September
TO-16-RYB-RYB GIS-2-09 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 4 | Indicative | August | September
TO-16-RYB-T101-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | Unknown | 33 | Indicative | August | October
TO-16-RYB-T103-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 4 | Indicative | August | September
TO-16-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | 3 | Indicative | August | August
TO-16-AA-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G4-T104 | Unknown | 3 | Indicative | August | September
TO-16-FIN-T2102-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | Unknown | 15 | Indicative | August | September
TO-16-FIN-T2102-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | Unknown | 15 | Indicative | August | September
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 64 | Indicative | September | November
TO-16-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 2 | Indicative | September | September
TO-16-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | 20 | Indicative | September | September
TO-16-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | Unknown | 5 | Indicative | September | September
TO-16-CSH-GAL-2-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | Unknown | 4 | Indicative | September | September
TO-16-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | 10 | Indicative | September | September
TO-16-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | Unknown | 3 | Indicative | September | September
TO-16-GI-110K1-2-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 10 | Indicative | September | October
TO-16-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 10 | Indicative | September | October
TO-16-GI-WEX-1-04 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 43 | Indicative | September | November
TO-16-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 25 | Indicative | September | November
TO-16-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | Unknown | 8 | Indicative | September | September
TO-16-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 4 | Indicative | September | September
TO-16-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | 3 | Indicative | September | September
TO-16-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | 3 | Indicative | September | September
TO-16-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | Unknown | 3 | Reference (Indicative) | September | September
TO-16-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | Unknown | 2 | Indicative | September | September
TO-16-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | Unknown | 8 | Indicative | September | September
TO-16-IA-MAC-1-05 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | 2 | Indicative | September | September
TO-16-MAC-110SA1-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | Unknown | 2 | Indicative | September | September
TO-16-MAC-110SA2-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | Unknown | 2 | Indicative | September | September
TO-16-MAC-T142-01 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | Unknown | 2 | Reference (Indicative) | September | September
TO-16-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | 3 | Indicative | September | September
TO-16-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | 3 | Indicative | September | September
TO-16-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | 40 | Indicative | September | November
TO-16-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | 40 | Reference (Indicative) | September | November
TO-16-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | 40 | Reference (Indicative) | September | November
TO-16-110 kV B1 @ AA-05 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110B1 | Unknown | 4 | Indicative | September | September
TO-16-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 7 | Indicative | September | September
TO-16-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 3 | Indicative | September | September
TO-16-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | 4 | Indicative | September | September
TO-16-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | Unknown | 5 | Indicative | September | September
TO-16-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | Unknown | 5 | Indicative | September | September
TO-16-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | 5 | Indicative | September | September
TO-16-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | 5 | Indicative | September | September
TO-16-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | 3 | Reference (Indicative) | September | September
TO-16-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | 7 | Reference (Indicative) | September | September
TO-16-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | Unknown | 8 | Indicative | September | September
TO-16-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 5 | Indicative | September | September
TO-16-MP-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT 110-MONEYPOINT 10-ST101 | Unknown | 5 | Indicative | September | September
TO-16-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | 10 | Indicative | September | September
TO-16-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | 4 | Indicative | September | September
TO-16-TBK-T142-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T142 | Unknown | 5 | Reference (Indicative) | September | September
TO-16-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 5 | Indicative | September | September
TO-16-TBK,T-MP-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT 110-1 | Unknown | 5 | Indicative | September | September
TO-16-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | 5 | Indicative | September | September
TO-16-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | 8 | Indicative | September | September
TO-16-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | Unknown | 3 | Indicative | September | September
TO-16-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | Unknown | 1 | Indicative | September | September
TO-16-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | 10 | Indicative | September | September
TO-16-AA-110K1-2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA 110-ARDNACRUSHA 110-110K1-2 | Unknown | 5 | Indicative | September | September
TO-16-AA-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA 110-SINGLAND 110-1 | Unknown | 4 | Indicative | September | September
TO-16-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | 10 | Indicative | September | October
TO-16-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | 5 | Indicative | September | September
TO-16-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | Unknown | 1 | Indicative | September | September
TO-16-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | 6 | Indicative | September | September
TO-16-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | 6 | Indicative | September | September
TO-16-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | 3 | Indicative | September | September
TO-16-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | 15 | Indicative | September | October
TO-16-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 4 | Indicative | September | September
TO-16-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 9 | Indicative | September | September
TO-16-DER-T1/T2-03 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | 1 | Indicative | September | September
TO-16-COS-FLA-1-08 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | Unknown | 1 | Indicative | September | September
TO-16-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 5 | Indicative | September | September
TO-16-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | 5 | Indicative | September | September
TO-16-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | Unknown | 3 | Indicative | September | September
TO-16-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | 5 | Indicative | September | September
TO-16-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-110SA1-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | 5 | Indicative | September | September
TO-16-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | 5 | Reference (Indicative) | September | September
TO-16-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | 6 | Indicative | September | October
TO-16-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | Unknown | 5 | Indicative | September | September
TO-16-CLG-MCE-1-01 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | Unknown | 7 | Indicative | September | October
TO-16-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 2 | Indicative | October | October
TO-16-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 5 | Indicative | October | October
TO-16-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | 5 | Indicative | October | October
TO-16-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | 10 | Indicative | October | October
TO-16-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 5 | Indicative | October | October
TO-16-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND G4-T2004 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | Unknown | 2 | Indicative | October | October
TO-16-MOY-TAW-1-05 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | 30 | Indicative | October | November
TO-16-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-TAW-T1/T2-03 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | 30 | Reference (Indicative) | October | November
TO-16-TAW-T101-05 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T101 | Unknown | 30 | Reference (Indicative) | October | November
TO-16-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | 2 | Indicative | October | October
TO-16-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | 2 | Indicative | October | October
TO-16-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 2 | Indicative | October | October
TO-16-BK-CBR-1-07 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 40 | Indicative | October | November
TO-16-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 3 | Indicative | October | October
TO-16-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | 6 | Indicative | October | October
TO-16-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | 2 | Indicative | October | October
TO-16-MAL-110SA1-01 | SECTIONALISING DISCONNECT - MALLOW 110-MALLOW 110-110SA1 | Unknown | 3 | Indicative | October | October
TO-16-MAL-110SA2-01 | SECTIONALISING DISCONNECT - MALLOW 110-MALLOW 110-110SA2 | Unknown | 3 | Indicative | October | October
TO-16-MAL-T141-01 | DISTRIBUTION TRANSFORMER - MALLOW 110-MALLOW 38-T141 | Unknown | 3 | Reference (Indicative) | October | October
TO-16-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | 3 | Indicative | October | October
TO-16-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | 8 | Indicative | October | November
TO-16-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-CF-1-01 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 8 | Indicative | October | November
TO-16-GOL,T-CF-1-05 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 10 | Indicative | October | November
TO-16-GOL,T-CF-1-06 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | 3 | Indicative | October | November
TO-16-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | 13 | Indicative | October | November
TO-16-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2101-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | 2 | Indicative | October | October
TO-16-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-CF-DRM-1-03 | 110kV FEEDER - CATHALEENS FALL 110-DRUMKEEN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | 5 | Indicative | October | October
TO-16-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | Unknown | 15 | Reference (Indicative) | October | October
TO-16-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 4 | Indicative | October | October
TO-16-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 4 | Indicative | October | October
TO-16-DGN-T141-02 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | Unknown | 4 | Reference (Indicative) | October | October
TO-16-DGN-WOH-1-03 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 4 | Indicative | October | October
TO-16-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | 21 | Indicative | October | November
TO-16-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | 21 | Indicative | October | November
TO-16-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | Unknown | 5 | Indicative | October | October
TO-16-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | 4 | Indicative | October | October
TO-16-RYB-RYB GIS-2-10 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | October | October
TO-16-CDU-RYB-1-07 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 2 | Indicative | October | October
TO-16-CUL-DGN-1-04 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-DGN-110SA1-03 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 2 | Indicative | October | October
TO-16-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 2 | Indicative | October | October
TO-16-DGN-T142-02 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 8 | Indicative | October | October
TO-16-RYB-110SA1-2CB-12 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 2 | Indicative | October | October
TO-16-RYB-RYB GIS-2-11 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | October | October
TO-16-RYB-T103-07 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 22 | Indicative | October | November
TO-16-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | 3 | Indicative | October | October
TO-16-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | 3 | Indicative | October | October
TO-16-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | Unknown | 7 | Indicative | October | October
TO-16-AA-AA GIS-1-05 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | Unknown | 2 | Indicative | October | November
TO-16-GI-110K1-2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 5 | Indicative | October | November
TO-16-GI GIS-T2102-02 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | Unknown | 5 | Indicative | October | November
TO-16-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 5 | Indicative | October | November
TO-16-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 4 | Indicative | October | November
TO-16-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 23 | Indicative | October | November
TO-16-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | 23 | Indicative | October | November
TO-16-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 3 | Indicative | November | November
TO-16-AD-LPT-1-02 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 20 | Indicative | November | November
TO-16-AD-LPT-1-03 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 12 | Indicative | November | November
TO-16-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | Unknown | 12 | Indicative | November | November
TO-16-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | 12 | Indicative | November | November
TO-16-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 3 | Indicative | November | November
TO-16-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 20 | Indicative | November | November
TO-16-LPT-T2002-03 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 12 | Indicative | November | November
TO-16-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | Unknown | 3 | Indicative | November | November
TO-16-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | 1 | Indicative | November | November
TO-16-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | Unknown | 10 | Indicative | November | November
TO-16-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 12 | Indicative | November | November
TO-16-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | Unknown | 5 | Indicative | November | November
TO-16-110 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | Unknown | 5 | Indicative | November | November
TO-16-KLN-SNG-1-02 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | 5 | Indicative | November | November
TO-16-RYB-RYB GIS-2-12 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | November | November
TO-16-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | 5 | Indicative | November | November
TO-16-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | 4 | Indicative | November | November
TO-16-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | 4 | Indicative | November | November
TO-16-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | 6 | Indicative | November | November
TO-16-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | 4 | Reference (Indicative) | November | November
TO-16-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | 6 | Indicative | November | November
TO-16-FIN-FIN GIS-1-04 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | November | November
TO-16-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | 4 | Indicative | November | November
TO-16-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | 3 | Indicative | November | November
TO-16-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | 4 | Indicative | November | November
TO-16-AA-AA GIS-1-06 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | Unknown | 2 | Indicative | November | November
TO-16-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | Proposed | 30/11/2016 | 30/11/2016
TO-16-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | 1 | Indicative | November | November

## SouthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 92 | 62 | Scheduled | 22/03/2016 | 21/06/2016
TO-16-BVK-TB-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-TARBERT 220-1 | 102 | 72 | Scheduled | 29/03/2016 | 08/07/2016
TO-16-AA-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA 110-LIMERICK 110-1 | 64 | 8 | Scheduled | 07/06/2016 | 09/08/2016
TO-16-AA-LIM-1-02 | 110kV FEEDER - ARDNACRUSHA 110-LIMERICK 110-1 | 64 | 45 | Proposed | 07/06/2016 | 09/08/2016
TO-16-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 21 | 15 | Scheduled | 10/06/2016 | 30/06/2016
TO-16-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 9 | 7 | Scheduled | 13/06/2016 | 21/06/2016
TO-16-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 9 | 7 | Reference | 13/06/2016 | 21/06/2016
TO-16-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 1 | 1 | Scheduled | 20/06/2016 | 20/06/2016
TO-16-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-110SA1-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-TIP-T141-01 | DISTRIBUTION TRANSFORMER - TIPPERARY 110-TIPPERARY 38-T141 | 1 | 1 | Reference | 21/06/2016 | 21/06/2016
TO-16-AA-T142-03 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA 38-T142 | 2 | 2 | Reference (Proposed) | 25/06/2016 | 26/06/2016
TO-16-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 5 | 5 | Tentative | 27/06/2016 | 01/07/2016
TO-16-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 29/06/2016 | 01/07/2016
TO-16-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 8 | 6 | Scheduled | 04/07/2016 | 11/07/2016
TO-16-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-MP-400K1-2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT 400-MONEYPOINT 400-400K1-2 | 3 | 3 | Scheduled | 05/07/2016 | 07/07/2016
TO-16-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | Reference | 11/07/2016 | 11/07/2016
TO-16-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | Scheduled | 11/07/2016 | 11/07/2016
TO-16-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 11/07/2016 | 11/07/2016
TO-16-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 10 | Proposed | 11/07/2016 | 25/07/2016
TO-16-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 7 | Scheduled | 11/07/2016 | 25/07/2016
TO-16-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 12 | 9 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-CAP2-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 12 | 10 | Proposed | 12/07/2016 | 23/07/2016
TO-16-THU-T142-02 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 12 | 10 | Reference (Proposed) | 12/07/2016 | 23/07/2016
TO-16-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 1 | 1 | Scheduled | 13/07/2016 | 13/07/2016
TO-16-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 |  | Scheduled | 18/07/2016 | 22/07/2016
TO-16-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | Unknown | 4 | Indicative | July | July
TO-16-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 11 | 9 | Scheduled | 18/07/2016 | 28/07/2016
TO-16-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-KER-110SA1-01 | SECTIONALISING DISCONNECT - KNOCKEARAGH 110-KNOCKEARAGH 110-110SA1 | 3 | 3 | Scheduled | 18/07/2016 | 20/07/2016
TO-16-KER-110SA2-02 | SECTIONALISING DISCONNECT - KNOCKEARAGH 110-KNOCKEARAGH 110-110SA2 | 3 | 3 | Scheduled | 18/07/2016 | 20/07/2016
TO-16-KER-T141-01 | DISTRIBUTION TRANSFORMER - KNOCKEARAGH 110-KNOCKEARAGH 38-T141 | 3 | 3 | Reference | 18/07/2016 | 20/07/2016
TO-16-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 3 | 3 | Scheduled | 20/07/2016 | 22/07/2016
TO-16-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-IKE-T141-04 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | Reference | 25/07/2016 | 25/07/2016
TO-16-IKE,T-IKE-1-04 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | Scheduled | 25/07/2016 | 25/07/2016
TO-16-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 25/07/2016 | 25/07/2016
TO-16-KNR-TB-1-220-01 | 220kV FEEDER - KNOCKANURE 220-TARBERT 220-1-220 | Unknown | 4 | Indicative | July | July
TO-16-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 2 | 2 | Scheduled | 25/07/2016 | 26/07/2016
TO-16-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 2 | 2 | Scheduled | 25/07/2016 | 26/07/2016
TO-16-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 3 | 3 | Scheduled | 26/07/2016 | 28/07/2016
TO-16-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-AA-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G1-T101 | Unknown | 3 | Indicative | August | August
TO-16-TB-TRL-2-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-2 | Unknown | 6 | Indicative | August | August
TO-16-AA-AA GIS-1-01 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | 2 | 2 | Proposed | 08/08/2016 | 09/08/2016
TO-16-AA-ENN-1-06 | 110kV FEEDER - ARDNACRUSHA 110-ENNIS 110-1 | 2 | 2 | Proposed | 08/08/2016 | 09/08/2016
TO-16-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | Unknown | 70 | Indicative | August | November
TO-16-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 11 | Indicative | August | August
TO-16-110 kV B1 @ AA-04 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110B1 | Unknown | 4 | Indicative | August | August
TO-16-AA-T141-01 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA 38-T141 | Unknown | 70 | Reference (Indicative) | August | November
TO-16-110 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | Unknown | 37 | Indicative | August | November
TO-16-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | 4 | Indicative | August | August
TO-16-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | Unknown | 45 | Indicative | August | November
TO-16-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown | 5 | Indicative | August | August
TO-16-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | Unknown | 5 | Indicative | August | August
TO-16-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | Unknown | 2 | Indicative | August | August
TO-16-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-TB-T2101-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | Unknown | 5 | Indicative | August | August
TO-16-110 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | Unknown | 2 | Indicative | August | August
TO-16-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 7 | Indicative | August | August
TO-16-110 kV A1 @ AA-03 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110A1 | Unknown | 10 | Indicative | August | September
TO-16-AA-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA 110-ARDNACRUSHA 110-CAP1 | Unknown | 2 | Indicative | August | November
TO-16-AA-CAP1-02 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA 110-ARDNACRUSHA 110-CAP1 | Unknown | 40 | Indicative | August | November
TO-16-AA-T101-03 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G1-T101 | Unknown | 45 | Indicative | August | November
TO-16-AA-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G4-T104 | Unknown | 3 | Indicative | August | September
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 64 | Indicative | September | November
TO-16-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 2 | Indicative | September | September
TO-16-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | Unknown | 5 | Indicative | September | September
TO-16-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 4 | Indicative | September | September
TO-16-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | 3 | Indicative | September | September
TO-16-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | 3 | Indicative | September | September
TO-16-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | Unknown | 3 | Reference (Indicative) | September | September
TO-16-110 kV B1 @ AA-05 | BUSBAR SECTION - ARDNACRUSHA 110-ARDNACRUSHA 110-110B1 | Unknown | 4 | Indicative | September | September
TO-16-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 7 | Indicative | September | September
TO-16-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 3 | Indicative | September | September
TO-16-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | 4 | Indicative | September | September
TO-16-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | Unknown | 5 | Indicative | September | September
TO-16-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | Unknown | 5 | Indicative | September | September
TO-16-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | 5 | Indicative | September | September
TO-16-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | 5 | Indicative | September | September
TO-16-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | 7 | Reference (Indicative) | September | September
TO-16-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | 3 | Reference (Indicative) | September | September
TO-16-MP-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT 110-MONEYPOINT 10-ST101 | Unknown | 5 | Indicative | September | September
TO-16-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | 10 | Indicative | September | September
TO-16-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | 4 | Indicative | September | September
TO-16-TBK-T142-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T142 | Unknown | 5 | Reference (Indicative) | September | September
TO-16-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 5 | Indicative | September | September
TO-16-TBK,T-MP-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT 110-1 | Unknown | 5 | Indicative | September | September
TO-16-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | 5 | Indicative | September | September
TO-16-AA-110K1-2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA 110-ARDNACRUSHA 110-110K1-2 | Unknown | 5 | Indicative | September | September
TO-16-AA-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA 110-SINGLAND 110-1 | Unknown | 4 | Indicative | September | September
TO-16-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-110SA1-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | 5 | Indicative | September | September
TO-16-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | 5 | Indicative | September | September
TO-16-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | 5 | Reference (Indicative) | September | September
TO-16-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | Unknown | 2 | Indicative | October | October
TO-16-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 3 | Indicative | October | October
TO-16-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | 2 | Indicative | October | October
TO-16-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-AA-AA GIS-1-05 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | Unknown | 2 | Indicative | October | November
TO-16-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | Unknown | 10 | Indicative | November | November
TO-16-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | Unknown | 5 | Indicative | November | November
TO-16-110 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | Unknown | 5 | Indicative | November | November
TO-16-KLN-SNG-1-02 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | 5 | Indicative | November | November
TO-16-AA-AA GIS-1-06 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | Unknown | 2 | Indicative | November | November
TO-16-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | 1 | Indicative | November | November

## SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 21/06/2016 | 21/06/2016
TO-16-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 3 | 3 | Scheduled | 22/06/2016 | 24/06/2016
TO-16-CAH-CAP2/4-02 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 3 | 3 | Tentative | 27/06/2016 | 29/06/2016
TO-16-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 5 | Tentative | 27/06/2016 | 01/07/2016
TO-16-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 3 | 3 | Scheduled | 27/06/2016 | 29/06/2016
TO-16-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | Scheduled | 27/06/2016 | 27/06/2016
TO-16-DOO-110SA1-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 4 | 4 | Scheduled | 28/06/2016 | 01/07/2016
TO-16-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 4 | 4 | Scheduled | 28/06/2016 | 01/07/2016
TO-16-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 8 | 6 | Scheduled | 29/06/2016 | 06/07/2016
TO-16-DOO-T142-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 4 | 4 | Reference | 30/06/2016 | 01/07/2016
TO-16-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 5 | Tentative | 04/07/2016 | 10/07/2016
TO-16-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 3 | Scheduled | 04/07/2016 | 10/07/2016
TO-16-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-CLW-110SA1-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 8 | 6 | Scheduled | 05/07/2016 | 12/07/2016
TO-16-CLW-T141-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 2 | 2 | Reference | 05/07/2016 | 06/07/2016
TO-16-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 7 | 7 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND 220-1 | 7 | 7 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 7 | 5 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-CLW-110SA1-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-110SA2-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-CLW-T142-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | 2 | 2 | Reference | 13/07/2016 | 14/07/2016
TO-16-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 2 | 2 | Reference | 13/07/2016 | 14/07/2016
TO-16-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 10 | 8 | Scheduled | 18/07/2016 | 27/07/2016
TO-16-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 4 | 4 | Scheduled | 18/07/2016 | 21/07/2016
TO-16-GI-110K1-2-11 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 15 | Indicative | July | August
TO-16-GI GIS-T2102-01 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | Unknown | 42 | Indicative | July | October
TO-16-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 15 | Indicative | July | August
TO-16-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 15 | Indicative | July | August
TO-16-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | Scheduled | 26/07/2016 | 27/07/2016
TO-16-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 2 | 2 | Reference | 26/07/2016 | 27/07/2016
TO-16-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 2 | 2 | Scheduled | 28/07/2016 | 29/07/2016
TO-16-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 7 | Indicative | August | August
TO-16-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 6 | Indicative | August | August
TO-16-DOO-CAP1-01 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | 2 | Indicative | August | August
TO-16-DOO-T141-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | 5 | Indicative | August | August
TO-16-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 2 | Indicative | August | August
TO-16-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | 5 | Indicative | August | August
TO-16-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | 5 | Reference (Indicative) | August | August
TO-16-DSN-KLS-1-04 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-GI GIS-KLS-1-06 | 220kV FEEDER - GREAT ISLAND 220-KELLIS 220-1 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-KLS-T2102-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | 8 | Reference (Indicative) | August | August
TO-16-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | 8 | Indicative | August | August
TO-16-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | 8 | Indicative | August | August
TO-16-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | 8 | Indicative | August | August
TO-16-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | 10 | Indicative | August | September
TO-16-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 2 | Indicative | August | August
TO-16-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | Unknown | 2 | Indicative | August | August
TO-16-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | Unknown | 2 | Indicative | August | August
TO-16-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | Unknown | 2 | Reference (Indicative) | August | August
TO-16-GI-110K1-2-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 10 | Indicative | September | October
TO-16-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 10 | Indicative | September | October
TO-16-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 25 | Indicative | September | November
TO-16-GI-WEX-1-04 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | Unknown | 43 | Indicative | September | November
TO-16-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | 10 | Indicative | September | October
TO-16-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | 3 | Indicative | September | September
TO-16-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 5 | Indicative | September | September
TO-16-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 5 | Indicative | October | October
TO-16-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND G4-T2004 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 4 | Indicative | October | October
TO-16-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 4 | Indicative | October | October
TO-16-DGN-T141-02 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | Unknown | 4 | Reference (Indicative) | October | October
TO-16-DGN-WOH-1-03 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 4 | Indicative | October | October
TO-16-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | Unknown | 5 | Indicative | October | October
TO-16-CUL-DGN-1-04 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-DGN-110SA1-03 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 2 | Indicative | October | October
TO-16-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 2 | Indicative | October | October
TO-16-DGN-T142-02 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | 2 | Reference (Indicative) | October | October
TO-16-GI-110K1-2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | Unknown | 5 | Indicative | October | November
TO-16-GI GIS-T2102-02 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | Unknown | 5 | Indicative | October | November
TO-16-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | Unknown | 5 | Indicative | October | November

## NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-MOY-TAW-2-06 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 74 | 51 | Scheduled | 10/04/2016 | 22/06/2016
TO-16-TAW-T102-05 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T102 | 74 | 51 | Reference | 10/04/2016 | 22/06/2016
TO-16-TAW-T3-03 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 74 | 51 | Reference | 10/04/2016 | 22/06/2016
TO-16-GAL-T141-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | 100 | 70 | Reference | 09/05/2016 | 16/08/2016
TO-16-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 71 | 50 | Scheduled | 16/05/2016 | 25/07/2016
TO-16-ARI,T-COS-1-07 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 51 | 36 | Scheduled | 02/06/2016 | 22/07/2016
TO-16-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 20 | 5 | Scheduled | 08/06/2016 | 27/06/2016
TO-16-CF-DRM-1-06 | 110kV FEEDER - CATHALEENS FALL 110-DRUMKEEN 110-1 | 88 | 61 | Scheduled | 10/06/2016 | 05/09/2016
TO-16-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 9 | 7 | Scheduled | 13/06/2016 | 21/06/2016
TO-16-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 7 | 5 | Scheduled | 16/06/2016 | 22/06/2016
TO-16-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 3 | 3 | Scheduled | 19/06/2016 | 21/06/2016
TO-16-CSH-GAL-1-08 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 3 | 3 | Scheduled | 20/06/2016 | 22/06/2016
TO-16-GAL-110K1-2-03 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-GAL-110K1-3-03 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 5 | 5 | Proposed | 20/06/2016 | 24/06/2016
TO-16-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | Scheduled | 20/06/2016 | 22/06/2016
TO-16-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-110SA1-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-110SA2-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-CAP2-04 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 1 | 1 | Scheduled | 22/06/2016 | 22/06/2016
TO-16-MOY-T142-04 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 1 | 1 | Reference | 22/06/2016 | 22/06/2016
TO-16-BK-CBR-1-12 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 2 | Scheduled | 25/06/2016 | 26/06/2016
TO-16-CBR-T142-08 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 2 | 2 | Reference | 25/06/2016 | 26/06/2016
TO-16-CBG-CBR-1-09 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 1 | Reference | 26/06/2016 | 26/06/2016
TO-16-CBG-T142-08 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 1 | Reference | 26/06/2016 | 26/06/2016
TO-16-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 12 | 10 | Proposed | 04/07/2016 | 15/07/2016
TO-16-CBR-DLT-1-06 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 19 | 15 | Scheduled | 04/07/2016 | 22/07/2016
TO-16-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | 15 | Indicative | July | July
TO-16-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 5 | 4 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA1-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 2 | Proposed | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA1-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA2-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 2 | Proposed | 04/07/2016 | 08/07/2016
TO-16-DLT-110SA2-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-DLT-CAP1-04 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 29 | 20 | Scheduled | 06/07/2016 | 03/08/2016
TO-16-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 29 | 20 | Scheduled | 06/07/2016 | 03/08/2016
TO-16-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 5 | 5 | Proposed | 11/07/2016 | 15/07/2016
TO-16-CBR-T142-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 2 | 2 | Reference (Proposed) | 11/07/2016 | 12/07/2016
TO-16-CSH-FLA-1-02 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-220K1-2-02 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-SRA-1-04 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-T2101-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 2 | 2 | Scheduled | 16/07/2016 | 17/07/2016
TO-16-CF-110K1-2-03 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | 5 | Indicative | July | July
TO-16-ARI-T121-07 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 1 | 1 | Reference | 22/07/2016 | 22/07/2016
TO-16-ARI,T-ARI-1-07 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 1 | 1 | Scheduled | 22/07/2016 | 22/07/2016
TO-16-ARI,T-CDY-1-05 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 1 | Scheduled | 22/07/2016 | 22/07/2016
TO-16-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 11 | 10 | Scheduled | 23/07/2016 | 02/08/2016
TO-16-ARV-COS-1-06 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | Scheduled | 23/07/2016 | 25/07/2016
TO-16-COS-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 | Scheduled | 23/07/2016 | 25/07/2016
TO-16-COS-T141-04 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 | Reference | 23/07/2016 | 25/07/2016
TO-16-CF-T141-01 | DISTRIBUTION TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL 38-T141 | Unknown | 10 | Reference (Indicative) | July | August
TO-16-DLT-CAP1-03 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | 15 | Indicative | July | August
TO-16-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | Tentative | 28/07/2016 | 01/08/2016
TO-16-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | Reference (Tentative) | 28/07/2016 | 01/08/2016
TO-16-CSH-GAL-1-06 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 1 | 1 | Scheduled | 03/08/2016 | 03/08/2016
TO-16-FLA-LA-1-02 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 39 | Indicative | August | September
TO-16-FLA-LA-1-01 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 2 | Indicative | August | September
TO-16-CSH-GAL-1-09 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-GAL-110K1-2-04 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-GAL-110K1-3-04 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 2 | 2 | Proposed | 15/08/2016 | 16/08/2016
TO-16-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 11 | Indicative | August | August
TO-16-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown | 11 | Indicative | August | August
TO-16-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | 11 | Indicative | August | August
TO-16-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | 11 | Indicative | August | August
TO-16-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 11 | Indicative | August | August
TO-16-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 17 | Indicative | August | August
TO-16-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | 11 | Indicative | August | August
TO-16-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | 11 | Indicative | August | August
TO-16-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | 10 | Indicative | August | September
TO-16-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | 10 | Indicative | August | September
TO-16-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | 10 | Indicative | August | September
TO-16-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 2 | Indicative | September | September
TO-16-CSH-GAL-2-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | Unknown | 4 | Indicative | September | September
TO-16-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | Unknown | 3 | Indicative | September | September
TO-16-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 4 | Indicative | September | September
TO-16-COS-FLA-1-08 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | Unknown | 1 | Indicative | September | September
TO-16-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 2 | Indicative | October | October
TO-16-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 5 | Indicative | October | October
TO-16-MOY-TAW-1-05 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | 30 | Indicative | October | November
TO-16-TAW-T1/T2-03 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | 30 | Reference (Indicative) | October | November
TO-16-TAW-T101-05 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T101 | Unknown | 30 | Reference (Indicative) | October | November
TO-16-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | 2 | Indicative | October | October
TO-16-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | 2 | Indicative | October | October
TO-16-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 2 | Indicative | October | October
TO-16-BK-CBR-1-07 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 40 | Indicative | October | November
TO-16-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | 3 | Indicative | October | October
TO-16-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | 8 | Indicative | October | November
TO-16-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-CF-1-05 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 10 | Indicative | October | November
TO-16-GOL,T-CF-1-06 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-CF-1-01 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | Unknown | 8 | Indicative | October | November
TO-16-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | 33 | Indicative | October | November
TO-16-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | 3 | Indicative | October | November
TO-16-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | 13 | Indicative | October | November
TO-16-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | 33 | Indicative | October | November
TO-16-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-CF-DRM-1-03 | 110kV FEEDER - CATHALEENS FALL 110-DRUMKEEN 110-1 | Unknown | 2 | Indicative | October | October
TO-16-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | Unknown | 15 | Reference (Indicative) | October | October
TO-16-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | 21 | Indicative | October | November
TO-16-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | 21 | Indicative | October | November
TO-16-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | 1 | Indicative | November | November

## NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 177 | 125 | Scheduled | 07/06/2016 | 30/11/2016
TO-16-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 4 | 4 | Proposed | 27/06/2016 | 30/06/2016
TO-16-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 9 | 7 | Scheduled | 28/06/2016 | 06/07/2016
TO-16-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 1 | 1 | Scheduled | 28/06/2016 | 28/06/2016
TO-16-SKL-110SA1-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-110SA2-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-M/CAP2-01 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 5 | 5 | Scheduled | 04/07/2016 | 08/07/2016
TO-16-SKL-T142-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 5 | 5 | Reference | 04/07/2016 | 08/07/2016
TO-16-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 11/07/2016 | 11/07/2016
TO-16-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 13/07/2016 | 14/07/2016
TO-16-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 | Scheduled | 18/07/2016 | 22/07/2016
TO-16-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 8 | 6 | Scheduled | 22/07/2016 | 29/07/2016
TO-16-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 11 | 10 | Scheduled | 23/07/2016 | 02/08/2016
TO-16-ARV-COS-1-06 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | Scheduled | 23/07/2016 | 25/07/2016
TO-16-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 1 | 1 | Scheduled | 25/07/2016 | 25/07/2016
TO-16-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-NAV-M/CAP1-01 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-NAV-T141-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 5 | 5 | Reference | 25/07/2016 | 29/07/2016
TO-16-ARV-SKL-2-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 15 | 10 | Proposed | 01/08/2016 | 15/08/2016
TO-16-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | 5 | Indicative | August | August
TO-16-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | 4 | Indicative | August | August
TO-16-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | 5 | Indicative | August | August
TO-16-FLA-LA-1-02 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 39 | Indicative | August | September
TO-16-FLA-LA-1-01 | 110kV FEEDER - FLAGFORD 110-LANESBORO 110-1 | Unknown | 2 | Indicative | August | September
TO-16-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | 1 | Indicative | August | August
TO-16-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | 5 | Indicative | August | August
TO-16-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 3 | Indicative | August | August
TO-16-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 7 | Indicative | August | August
TO-16-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 5 | Indicative | September | September
TO-16-DER-T1/T2-03 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | 1 | Indicative | September | September
TO-16-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | Unknown | 3 | Indicative | September | September
TO-16-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | 5 | Indicative | September | September
TO-16-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 5 | Indicative | October | October
TO-16-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | 6 | Indicative | October | October
TO-16-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2101-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | 5 | Indicative | November | November
TO-16-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | 4 | Indicative | November | November
TO-16-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | 4 | Indicative | November | November
TO-16-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | 6 | Indicative | November | November
TO-16-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | 4 | Reference (Indicative) | November | November
TO-16-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | 3 | Indicative | November | November
TO-16-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | Proposed | 30/11/2016 | 30/11/2016

## Dublin
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 14 | 10 | Scheduled | 08/06/2016 | 21/06/2016
TO-16-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 13 | 9 | Scheduled | 08/06/2016 | 20/06/2016
TO-16-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 13 | 9 | Scheduled | 08/06/2016 | 20/06/2016
TO-16-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 27 | 20 | Scheduled | 13/06/2016 | 09/07/2016
TO-16-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-110SA1-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-110SA2-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 10 | 8 | Scheduled | 14/06/2016 | 23/06/2016
TO-16-RYB-T104-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T104 | 32 | 24 | Scheduled | 14/06/2016 | 15/07/2016
TO-16-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 7 | 5 | Scheduled | 15/06/2016 | 21/06/2016
TO-16-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 7 | 5 | Scheduled | 15/06/2016 | 21/06/2016
TO-16-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 8 | 6 | Scheduled | 17/06/2016 | 24/06/2016
TO-16-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 26 | 20 | Proposed | 20/06/2016 | 15/07/2016
TO-16-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 26 | 5 | Proposed | 20/06/2016 | 15/07/2016
TO-16-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 16 | 11 | Proposed | 26/06/2016 | 11/07/2016
TO-16-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 13 | 10 | Proposed | 26/06/2016 | 08/07/2016
TO-16-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 5 | 5 | Scheduled | 27/06/2016 | 01/07/2016
TO-16-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 43 | 30 | Proposed | 05/07/2016 | 16/08/2016
TO-16-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 18 | 14 | Proposed | 05/07/2016 | 22/07/2016
TO-16-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | Scheduled | 05/07/2016 | 05/07/2016
TO-16-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | Scheduled | 06/07/2016 | 06/07/2016
TO-16-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 3 | 3 | Scheduled | 06/07/2016 | 08/07/2016
TO-16-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-RYB-RYB GIS-1-09 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 3 | 3 | Proposed | 13/07/2016 | 15/07/2016
TO-16-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 2 | 2 | Scheduled | 13/07/2016 | 14/07/2016
TO-16-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 1 | 1 | Proposed | 15/07/2016 | 15/07/2016
TO-16-FIN-FIN GIS-1-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | July | July
TO-16-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | Unknown | 30 | Reference (Indicative) | July | August
TO-16-MAY-RYB-1-06 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK 110-1 | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 3 | 3 | Proposed | 19/07/2016 | 21/07/2016
TO-16-PB-TF4-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 3 | 3 | Reference (Proposed) | 19/07/2016 | 21/07/2016
TO-16-RYB-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-RYB-RYB GIS-1-10 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 2 | 2 | Proposed | 19/07/2016 | 20/07/2016
TO-16-RYB-T107-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T107 | 37 | 26 | Proposed | 19/07/2016 | 24/08/2016
TO-16-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 4 | 4 | Scheduled | 26/07/2016 | 29/07/2016
TO-16-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 16 | 15 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 16 | 9 | Scheduled | 30/07/2016 | 14/08/2016
TO-16-CDU-RYB-1-04 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 6 | Indicative | August | August
TO-16-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | 4 | Indicative | August | August
TO-16-RNW-110SA1-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | Unknown | 4 | Indicative | August | August
TO-16-RNW-110SA2-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | Unknown | 4 | Indicative | August | August
TO-16-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | 6 | Indicative | August | August
TO-16-RYB-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 3 | Indicative | August | August
TO-16-RYB-RYB GIS-2-06 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 3 | Indicative | August | August
TO-16-RYB-T101-04 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | Unknown | 3 | Indicative | August | August
TO-16-RYB-T103-04 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 3 | Indicative | August | August
TO-16-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 6 | Indicative | August | August
TO-16-KTL-110SA1-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-KTL-110SA2-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | Unknown | 3 | Indicative | August | August
TO-16-KTL-T141-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T141 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | 12 | Indicative | August | August
TO-16-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | 1 | Reference (Indicative) | August | August
TO-16-GRI,T-GCA-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | 8 | Indicative | August | August
TO-16-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 17 | Indicative | August | August
TO-16-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | 10 | Indicative | August | August
TO-16-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | 10 | Indicative | August | August
TO-16-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | Unknown | 1 | Indicative | August | August
TO-16-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | 1 | Indicative | August | August
TO-16-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 8 | Indicative | August | August
TO-16-DSN-KLS-1-04 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | Trip Testing | 17/08/2016 | 18/08/2016
TO-16-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | 8 | Indicative | August | August
TO-16-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | 8 | Indicative | August | August
TO-16-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | 8 | Indicative | August | August
TO-16-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | 8 | Indicative | August | August
TO-16-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | 8 | Indicative | August | August
TO-16-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | Unknown | 7 | Indicative | August | August
TO-16-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 3 | Indicative | August | August
TO-16-RYB-RYB GIS-1-11 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 3 | 3 | Proposed | 22/08/2016 | 24/08/2016
TO-16-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | 1 | Reference (Indicative) | August | August
TO-16-GRI,T-GCA-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | 1 | Indicative | August | August
TO-16-GRI,T-GRI-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | 1 | Indicative | August | August
TO-16-CDU-RYB-1-06 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 4 | Indicative | August | September
TO-16-FIN-FIN GIS-1-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | August | August
TO-16-RYB-110SA1-2CB-11 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 4 | Indicative | August | September
TO-16-RYB-RYB GIS-2-09 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 4 | Indicative | August | September
TO-16-RYB-T101-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | Unknown | 33 | Indicative | August | October
TO-16-RYB-T103-06 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 4 | Indicative | August | September
TO-16-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | 3 | Indicative | August | August
TO-16-FIN-T2102-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | Unknown | 15 | Indicative | August | September
TO-16-FIN-T2102-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | Unknown | 15 | Indicative | August | September
TO-16-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | 20 | Indicative | September | September
TO-16-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | Unknown | 8 | Indicative | September | September
TO-16-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | Unknown | 8 | Indicative | September | September
TO-16-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | 3 | Indicative | September | September
TO-16-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | 3 | Indicative | September | September
TO-16-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | 5 | Indicative | September | September
TO-16-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | 8 | Indicative | September | September
TO-16-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | Unknown | 1 | Indicative | September | September
TO-16-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | 5 | Indicative | September | September
TO-16-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | Unknown | 1 | Indicative | September | September
TO-16-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | 6 | Indicative | September | September
TO-16-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | 6 | Indicative | September | September
TO-16-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | 15 | Indicative | September | October
TO-16-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | 5 | Indicative | September | September
TO-16-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | 6 | Indicative | September | October
TO-16-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | Unknown | 5 | Indicative | September | September
TO-16-CLG-MCE-1-01 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | Unknown | 7 | Indicative | September | October
TO-16-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | 6 | Indicative | October | October
TO-16-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | 2 | Indicative | October | October
TO-16-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 2 | Trip Testing | 05/10/2016 | 06/10/2016
TO-16-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | 4 | Indicative | October | October
TO-16-RYB-RYB GIS-2-10 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | October | October
TO-16-CDU-RYB-1-07 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | Unknown | 2 | Indicative | October | October
TO-16-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 8 | Indicative | October | October
TO-16-RYB-110SA1-2CB-12 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | Unknown | 2 | Indicative | October | October
TO-16-RYB-RYB GIS-2-11 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | October | October
TO-16-RYB-T103-07 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T103 | Unknown | 22 | Indicative | October | November
TO-16-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | Unknown | 12 | Indicative | November | November
TO-16-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | 12 | Indicative | November | November
TO-16-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | Unknown | 3 | Indicative | November | November
TO-16-RYB-RYB GIS-2-12 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | Unknown | 2 | Indicative | November | November
TO-16-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | 6 | Indicative | November | November
TO-16-FIN-FIN GIS-1-04 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | 2 | Indicative | November | November
TO-16-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | 4 | Indicative | November | November
TO-16-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | 4 | Indicative | November | November

## Cork
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 96 | 68 | Scheduled | 04/04/2016 | 08/07/2016
TO-16-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | Scheduled | 22/06/2016 | 24/06/2016
TO-16-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 2 | 2 | Scheduled | 23/06/2016 | 24/06/2016
TO-16-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 5 | 5 | Scheduled | 27/06/2016 | 05/07/2016
TO-16-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 3 | 3 | Proposed | 27/06/2016 | 29/06/2016
TO-16-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 47 | 34 | Proposed | 27/06/2016 | 12/08/2016
TO-16-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 15 | 11 | Proposed | 27/06/2016 | 11/07/2016
TO-16-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 2 | 2 | Scheduled | 27/06/2016 | 28/06/2016
TO-16-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 57 | 40 | Proposed | 04/07/2016 | 29/08/2016
TO-16-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 1 | 1 | Reference (Tentative) | 04/07/2016 | 04/07/2016
TO-16-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 1 | 1 | Tentative | 04/07/2016 | 04/07/2016
TO-16-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 5 | Tentative | 04/07/2016 | 10/07/2016
TO-16-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 7 | 3 | Scheduled | 04/07/2016 | 10/07/2016
TO-16-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 1 | 1 | Tentative | 04/07/2016 | 04/07/2016
TO-16-BAR,T-KRA-1-04 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 1 | 1 | Proposed | 04/07/2016 | 04/07/2016
TO-16-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 57 | 40 | Reference (Proposed) | 04/07/2016 | 29/08/2016
TO-16-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 9 | 7 | Proposed | 04/07/2016 | 12/07/2016
TO-16-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | Proposed | 04/07/2016 | 05/07/2016
TO-16-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 2 | 2 | Scheduled | 05/07/2016 | 06/07/2016
TO-16-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 2 | 2 | Reference (Tentative) | 09/07/2016 | 10/07/2016
TO-16-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 2 | 2 | Tentative | 09/07/2016 | 10/07/2016
TO-16-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 2 | 2 | Tentative | 09/07/2016 | 10/07/2016
TO-16-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 7 | 5 | Scheduled | 11/07/2016 | 17/07/2016
TO-16-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 1 | 1 | Proposed | 12/07/2016 | 12/07/2016
TO-16-DMY-MAC-1-06 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 15 | 11 | Proposed | 12/07/2016 | 26/07/2016
TO-16-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 1 | 1 | Scheduled | 13/07/2016 | 13/07/2016
TO-16-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 |  | Scheduled | 18/07/2016 | 22/07/2016
TO-16-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 5 | 5 | Scheduled | 25/07/2016 | 29/07/2016
TO-16-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 2 | 2 | Proposed | 27/07/2016 | 28/07/2016
TO-16-CD-KBY-1-03 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 16 | 11 | Proposed | 27/07/2016 | 11/08/2016
TO-16-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 1 | 1 | Scheduled | 28/07/2016 | 28/07/2016
TO-16-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 2 | Indicative | July | July
TO-16-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 2 | Indicative | July | July
TO-16-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | 3 | Indicative | August | August
TO-16-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | 3 | Indicative | August | August
TO-16-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | 3 | Indicative | August | August
TO-16-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | 3 | Indicative | August | August
TO-16-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | 3 | Reference (Indicative) | August | August
TO-16-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | 6 | Indicative | August | August
TO-16-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | 5 | Indicative | August | August
TO-16-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | 5 | Indicative | August | August
TO-16-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | 25 | Indicative | August | September
TO-16-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | 3 | Indicative | August | August
TO-16-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | 9 | Indicative | August | August
TO-16-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 11 | 9 | Proposed | 16/08/2016 | 26/08/2016
TO-16-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | 9 | Indicative | August | August
TO-16-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | 1 | Indicative | August | August
TO-16-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 5 | Indicative | August | August
TO-16-COW-WHI-1-02 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 2 | Indicative | August | August
TO-16-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Indicative | August | August
TO-16-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 2 | Indicative | August | August
TO-16-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | Unknown | 5 | Indicative | August | August
TO-16-WHI-110SA2-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA2 | Unknown | 5 | Indicative | August | August
TO-16-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | 5 | Indicative | August | August
TO-16-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 1 | 1 | Proposed | 29/08/2016 | 29/08/2016
TO-16-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 1 | 1 | Reference (Proposed) | 29/08/2016 | 29/08/2016
TO-16-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 1 | 1 | Reference (Proposed) | 29/08/2016 | 29/08/2016
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 64 | Indicative | September | November
TO-16-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | 10 | Indicative | September | September
TO-16-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | Unknown | 2 | Indicative | September | September
TO-16-IA-MAC-1-05 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | 2 | Indicative | September | September
TO-16-MAC-110SA1-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | Unknown | 2 | Indicative | September | September
TO-16-MAC-110SA2-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | Unknown | 2 | Indicative | September | September
TO-16-MAC-T142-01 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | Unknown | 2 | Reference (Indicative) | September | September
TO-16-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | 40 | Indicative | September | November
TO-16-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | 40 | Reference (Indicative) | September | November
TO-16-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | 40 | Reference (Indicative) | September | November
TO-16-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | Unknown | 8 | Indicative | September | September
TO-16-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | Unknown | 3 | Indicative | September | September
TO-16-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | 10 | Indicative | September | September
TO-16-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 4 | Indicative | September | September
TO-16-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 9 | Indicative | September | September
TO-16-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | 5 | Indicative | October | October
TO-16-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | 10 | Indicative | October | October
TO-16-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 3 | Indicative | October | October
TO-16-MAL-110SA1-01 | SECTIONALISING DISCONNECT - MALLOW 110-MALLOW 110-110SA1 | Unknown | 3 | Indicative | October | October
TO-16-MAL-110SA2-01 | SECTIONALISING DISCONNECT - MALLOW 110-MALLOW 110-110SA2 | Unknown | 3 | Indicative | October | October
TO-16-MAL-T141-01 | DISTRIBUTION TRANSFORMER - MALLOW 110-MALLOW 38-T141 | Unknown | 3 | Reference (Indicative) | October | October
TO-16-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | 5 | Indicative | October | October
TO-16-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | 3 | Indicative | October | October
TO-16-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | 3 | Indicative | October | October
TO-16-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | Unknown | 7 | Indicative | October | October
TO-16-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 4 | Indicative | October | November
TO-16-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 23 | Indicative | October | November
TO-16-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | 23 | Indicative | October | November
TO-16-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 3 | Indicative | November | November
TO-16-AD-LPT-1-02 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 20 | Indicative | November | November
TO-16-AD-LPT-1-03 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | 12 | Indicative | November | November
TO-16-LPT-T2002-03 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 12 | Indicative | November | November
TO-16-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 20 | Indicative | November | November
TO-16-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | 3 | Indicative | November | November
TO-16-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 12 | Indicative | November | November