## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2017 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Date of publication: 03 11 2017
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-MP-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G3-T4003 | 102 | 73 | Scheduled | 08/08/2017 | 17/11/2017
TO-17-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 85 | 60 | Reference | 23/08/2017 | 15/11/2017
TO-17-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-CBR-T142-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 71 | 49 | Reference | 26/08/2017 | 04/11/2017
TO-17-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 106 | 75 | Scheduled | 31/08/2017 | 14/12/2017
TO-17-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 106 | 75 | Scheduled | 31/08/2017 | 14/12/2017
TO-17-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 85 | 60 | Scheduled | 04/09/2017 | 27/11/2017
TO-17-MTH-T141-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 136 | 92 | Reference | 09/09/2017 | 22/01/2018
TO-17-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 45 | 32 | Scheduled | 18/09/2017 | 01/11/2017
TO-17-CSH-ENN-1-05 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 33 | 24 | Scheduled | 09/10/2017 | 10/11/2017
TO-17-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 50 | 35 | Proposed | 09/10/2017 | 27/11/2017
TO-17-DRU-ENN-1-05 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 33 | 24 | Scheduled | 09/10/2017 | 10/11/2017
TO-17-ENN-T101-06 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 33 | 24 | Reference | 09/10/2017 | 10/11/2017
TO-17-ENN-T141-05 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 33 | 24 | Reference | 09/10/2017 | 10/11/2017
TO-17-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-RNW-110SA1-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-RNW-T121-02 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 21 | 14 | Scheduled | 24/10/2017 | 13/11/2017
TO-17-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 9 | 6 | Scheduled | 24/10/2017 | 01/11/2017
TO-17-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 9 | 6 | Scheduled | 24/10/2017 | 01/11/2017
TO-17-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 9 | 6 | Reference | 24/10/2017 | 01/11/2017
TO-17-CBR-110SA1-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 5 | 4 | Scheduled | 30/10/2017 | 03/11/2017
TO-17-RYB GIS-T106-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 5 | 4 | Tentative | 30/10/2017 | 03/11/2017
TO-17-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 144 | 100 | Scheduled | 31/10/2017 | 23/03/2018
TO-17-CLA-KRA-1-03 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 2 | 2 | Scheduled | 31/10/2017 | 01/11/2017
TO-17-CUS-NEW-1-04 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 6 | 4 | Scheduled | 31/10/2017 | 05/11/2017
TO-17-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 4 |  | Tentative | 31/10/2017 | 03/11/2017
TO-17-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 10 | 8 | Scheduled | 31/10/2017 | 09/11/2017
TO-17-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | 6 | 4 | Scheduled | 31/10/2017 | 05/11/2017
TO-17-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 10 | 8 | Scheduled | 31/10/2017 | 09/11/2017
TO-17-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | 6 | 4 | Reference | 31/10/2017 | 05/11/2017
TO-17-RYB GIS-T104-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 1 | 1 | Scheduled | 01/11/2017 | 01/11/2017
TO-17-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 1 | 1 | Scheduled | 01/11/2017 | 01/11/2017
TO-17-CBG-CBR-1-05 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 0 | Reference | 04/11/2017 | 04/11/2017
TO-17-CBG-T142-05 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 0 | Reference | 04/11/2017 | 04/11/2017
TO-17-CBR-110SA1-10 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-110SA2-08 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-DLT-1-04 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-GI-110K1-2-08 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-BK-CBR-1-09 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-110SA1-08 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-110SA2-07 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-CLN-1-06 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-SVC-06 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-T141-06 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 1 | 0 | Reference | 05/11/2017 | 05/11/2017
TO-17-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017
TO-17-CKM-PST2201-06 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017
TO-17-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017
TO-17-KPG-KNR-1-220-05 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 1 | Scheduled | 10/11/2017 | 11/11/2017
TO-17-GI-110K1-2-09 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-T2102-04 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-WAT-2-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 0 | Scheduled | 12/11/2017 | 12/11/2017
TO-17-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 1 | 1 | Scheduled | 13/11/2017 | 13/11/2017
TO-17-KPG-KNR-1-220-06 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 2 | Scheduled | 13/11/2017 | 14/11/2017
TO-17-RYB GIS-T107-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 |  | Scheduled | 13/11/2017 | 14/11/2017
TO-17-ARK-T2102-03 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 3 | 3 | Scheduled | 14/11/2017 | 16/11/2017
TO-17-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 10 | 8 | Scheduled | 14/11/2017 | 23/11/2017
TO-17-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 4 | 4 | Scheduled | 14/11/2017 | 17/11/2017
TO-17-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 1 | 1 | Scheduled | 16/11/2017 | 16/11/2017
TO-17-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 1 | 1 | Scheduled | 16/11/2017 | 16/11/2017
TO-17-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 0 | Scheduled | 18/11/2017 | 19/11/2017
TO-17-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 20/11/2017 | 20/11/2017
TO-17-BLK,T-BLK-1-02 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 |  | Proposed | 20/11/2017 | 20/11/2017
TO-17-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 3 | Proposed | 20/11/2017 | 22/11/2017
TO-17-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA1-03 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA2-03 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | Reference (Proposed) | 20/11/2017 | 24/11/2017
TO-17-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-T131-03 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-TRI-1-03 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 33 | 25 | Proposed | 20/11/2017 | 22/12/2017
TO-17-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 9 | 7 | Scheduled | 20/11/2017 | 28/11/2017
TO-17-BLK-T142-05 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 22/11/2017 | 22/11/2017
TO-17-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Proposed | 22/11/2017 | 22/11/2017
TO-17-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 9 | 7 | Proposed | 22/11/2017 | 30/11/2017
TO-17-TY-220SA1-02 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 1 | 1 | Scheduled | 24/11/2017 | 24/11/2017
TO-17-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 1 | 1 | Scheduled | 24/11/2017 | 24/11/2017
TO-17-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 2 | 1 | Reference | 26/11/2017 | 27/11/2017
TO-17-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 2 | 1 | Reference | 26/11/2017 | 27/11/2017
TO-17-KPG-KNR-1-220-07 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 2 | Proposed | 28/11/2017 | 29/11/2017
TO-17-BLK-T142-06 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 30/11/2017 | 30/11/2017
TO-17-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Proposed | 30/11/2017 | 30/11/2017

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-MP-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G3-T4003 | 102 | 73 | Scheduled | 08/08/2017 | 17/11/2017
TO-17-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 85 | 60 | Scheduled | 04/09/2017 | 27/11/2017
TO-17-CSH-ENN-1-05 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 33 | 24 | Scheduled | 09/10/2017 | 10/11/2017
TO-17-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 50 | 35 | Proposed | 09/10/2017 | 27/11/2017
TO-17-DRU-ENN-1-05 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 33 | 24 | Scheduled | 09/10/2017 | 10/11/2017
TO-17-ENN-T101-06 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 33 | 24 | Reference | 09/10/2017 | 10/11/2017
TO-17-ENN-T141-05 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 33 | 24 | Reference | 09/10/2017 | 10/11/2017
TO-17-KPG-KNR-1-220-05 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 1 | Scheduled | 10/11/2017 | 11/11/2017
TO-17-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 0 | Scheduled | 12/11/2017 | 12/11/2017
TO-17-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 1 | 1 | Scheduled | 13/11/2017 | 13/11/2017
TO-17-KPG-KNR-1-220-06 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 2 | Scheduled | 13/11/2017 | 14/11/2017
TO-17-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 10 | 8 | Scheduled | 14/11/2017 | 23/11/2017
TO-17-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 4 | 4 | Scheduled | 14/11/2017 | 17/11/2017
TO-17-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 1 | 1 | Scheduled | 16/11/2017 | 16/11/2017
TO-17-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 1 | 1 | Scheduled | 16/11/2017 | 16/11/2017
TO-17-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 0 | Scheduled | 18/11/2017 | 19/11/2017
TO-17-CBA-110SA1-03 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-110SA2-03 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | Reference (Proposed) | 20/11/2017 | 24/11/2017
TO-17-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-T131-03 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CBA-TRI-1-03 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | Proposed | 20/11/2017 | 24/11/2017
TO-17-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017
TO-17-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 2 | 1 | Reference | 26/11/2017 | 27/11/2017
TO-17-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 2 | 1 | Reference | 26/11/2017 | 27/11/2017
TO-17-KPG-KNR-1-220-07 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 2 | 2 | Proposed | 28/11/2017 | 29/11/2017

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 21 | 14 | Scheduled | 24/10/2017 | 13/11/2017
TO-17-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 9 | 6 | Scheduled | 24/10/2017 | 01/11/2017
TO-17-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 9 | 6 | Scheduled | 24/10/2017 | 01/11/2017
TO-17-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 9 | 6 | Reference | 24/10/2017 | 01/11/2017
TO-17-CUS-NEW-1-04 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 6 | 4 | Scheduled | 31/10/2017 | 05/11/2017
TO-17-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | 6 | 4 | Scheduled | 31/10/2017 | 05/11/2017
TO-17-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 10 | 8 | Scheduled | 31/10/2017 | 09/11/2017
TO-17-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | 6 | 4 | Reference | 31/10/2017 | 05/11/2017
TO-17-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 1 | 1 | Scheduled | 01/11/2017 | 01/11/2017
TO-17-GI-110K1-2-08 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 04/11/2017 | 05/11/2017
TO-17-GI-110K1-2-09 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-T2102-04 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-WAT-2-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 11/11/2017 | 12/11/2017
TO-17-ARK-T2102-03 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 3 | 3 | Scheduled | 14/11/2017 | 16/11/2017
TO-17-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 20/11/2017 | 20/11/2017
TO-17-BLK,T-BLK-1-02 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 |  | Proposed | 20/11/2017 | 20/11/2017
TO-17-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 3 | Proposed | 20/11/2017 | 22/11/2017
TO-17-BLK-T142-05 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 22/11/2017 | 22/11/2017
TO-17-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Proposed | 22/11/2017 | 22/11/2017
TO-17-BLK-T142-06 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference (Proposed) | 30/11/2017 | 30/11/2017
TO-17-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Proposed | 30/11/2017 | 30/11/2017

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 85 | 60 | Reference | 23/08/2017 | 15/11/2017
TO-17-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 85 | 60 | Scheduled | 23/08/2017 | 15/11/2017
TO-17-CBR-T142-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 71 | 49 | Reference | 26/08/2017 | 04/11/2017
TO-17-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 106 | 75 | Scheduled | 31/08/2017 | 14/12/2017
TO-17-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 106 | 75 | Scheduled | 31/08/2017 | 14/12/2017
TO-17-CSH-ENN-1-05 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 33 | 24 | Scheduled | 09/10/2017 | 10/11/2017
TO-17-CBR-110SA1-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 5 | 4 | Scheduled | 30/10/2017 | 03/11/2017
TO-17-CBG-CBR-1-05 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 0 | Reference | 04/11/2017 | 04/11/2017
TO-17-CBG-T142-05 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 0 | Reference | 04/11/2017 | 04/11/2017
TO-17-CBR-110SA1-10 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-110SA2-08 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-CBR-DLT-1-04 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 1 | 0 | Scheduled | 04/11/2017 | 04/11/2017
TO-17-BK-CBR-1-09 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-110SA1-08 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-110SA2-07 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-CLN-1-06 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-SVC-06 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 1 | 0 | Scheduled | 05/11/2017 | 05/11/2017
TO-17-CBR-T141-06 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 1 | 0 | Reference | 05/11/2017 | 05/11/2017
TO-17-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 0 | Scheduled | 12/11/2017 | 12/11/2017
TO-17-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 9 | 7 | Scheduled | 20/11/2017 | 28/11/2017
TO-17-TY-220SA1-02 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 1 | 1 | Scheduled | 24/11/2017 | 24/11/2017
TO-17-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 1 | 1 | Scheduled | 24/11/2017 | 24/11/2017
TO-17-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 1 | Scheduled | 26/11/2017 | 27/11/2017

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-MTH-T141-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 136 | 92 | Reference | 09/09/2017 | 22/01/2018
TO-17-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 4 |  | Tentative | 31/10/2017 | 03/11/2017
TO-17-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-MP-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT 400-1 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 95 | 68 | Scheduled | 15/08/2017 | 17/11/2017
TO-17-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-RNW-110SA1-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-RNW-T121-02 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 63 | 44 | Scheduled | 12/10/2017 | 13/12/2017
TO-17-RYB GIS-T106-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 5 | 4 | Tentative | 30/10/2017 | 03/11/2017
TO-17-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 144 | 100 | Scheduled | 31/10/2017 | 23/03/2018
TO-17-RYB GIS-T104-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 1 | 1 | Scheduled | 01/11/2017 | 01/11/2017
TO-17-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017
TO-17-CKM-PST2201-06 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 1 | 1 | Scheduled | 08/11/2017 | 08/11/2017
TO-17-RYB GIS-T107-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 |  | Scheduled | 13/11/2017 | 14/11/2017
TO-17-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 33 | 25 | Proposed | 20/11/2017 | 22/12/2017
TO-17-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 9 | 7 | Proposed | 22/11/2017 | 30/11/2017

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-17-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 45 | 32 | Scheduled | 18/09/2017 | 01/11/2017
TO-17-CLA-KRA-1-03 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 2 | 2 | Scheduled | 31/10/2017 | 01/11/2017
TO-17-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 10 | 8 | Scheduled | 31/10/2017 | 09/11/2017