## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2019 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TB-TRL-1-04 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 120 | 83 | 83 | Scheduled | 23/04/2019 | 20/08/2019
TO-19-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 187 | 131 | 131 | Scheduled | 29/04/2019 | 01/11/2019
TO-19-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 187 | 131 | 131 | Scheduled | 29/04/2019 | 01/11/2019
TO-19-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 181 | 125 | 125 | Reference | 02/05/2019 | 29/10/2019
TO-19-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 91 | 63 | 63 | Scheduled | 10/05/2019 | 08/08/2019
TO-19-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 71 | 50 | 50 | Scheduled | 10/05/2019 | 19/07/2019
TO-19-FIN-T142-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T142 | 64 | 45 | 45 | Reference | 29/05/2019 | 31/07/2019
TO-19-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 111 | 77 | 77 | Scheduled | 29/05/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 111 | 77 | 77 | Scheduled | 29/05/2019 | 16/09/2019
TO-19-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 |  | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-PRO-1-03 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 120 | 84 | 84 | Scheduled | 03/06/2019 | 30/09/2019
TO-19-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 64 | 45 | 45 | Scheduled | 04/06/2019 | 06/08/2019
TO-19-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 43 | 31 | 31 | Scheduled | 17/06/2019 | 29/07/2019
TO-19-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 113 | 80 | 80 | Scheduled | 18/06/2019 | 08/10/2019
TO-19-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA1-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA2-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 99 | 70 | 70 | Reference | 18/06/2019 | 24/09/2019
TO-19-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 99 | 70 | 70 | Reference | 18/06/2019 | 24/09/2019
TO-19-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 26 | 20 | 20 | Scheduled | 24/06/2019 | 19/07/2019
TO-19-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 65 | 46 | 46 | Scheduled | 25/06/2019 | 28/08/2019
TO-19-AD-T2011/12-04 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 4 | 4 | 4 | Scheduled | 01/07/2019 | 04/07/2019
TO-19-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-220 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-220 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 5 | 5 | 5 | Reference | 01/07/2019 | 05/07/2019
TO-19-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 5 | 5 | 5 | Reference | 01/07/2019 | 05/07/2019
TO-19-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 9 | 7 |  | Scheduled | 01/07/2019 | 09/07/2019
TO-19-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-220 kV A2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A2 | 19 | 15 | 15 | Scheduled | 01/07/2019 | 19/07/2019
TO-19-220 kV B2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B2 | 19 | 15 | 15 | Scheduled | 01/07/2019 | 19/07/2019
TO-19-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 4 | 4 | 4 | Scheduled | 01/07/2019 | 04/07/2019
TO-19-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 01/07/2019 | 03/07/2019
TO-19-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-MUN-2-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 138 | 98 | 98 | Proposed | 01/07/2019 | 15/11/2019
TO-19-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 12 | 10 | 10 | Scheduled | 01/07/2019 | 12/07/2019
TO-19-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 3 | 3 | 3 | Scheduled | 02/07/2019 | 04/07/2019
TO-19-MON-T102-01 | DISTRIBUTION TRANSFORMER - MONREAD 110-MONREAD 10-T102 | 2 | 2 | 2 | Reference | 03/07/2019 | 04/07/2019
TO-19-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 7 | 5 |  | Scheduled | 04/07/2019 | 10/07/2019
TO-19-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 7 | 5 |  | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-LA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-LA-RIC-2-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 1 | 1 | 1 | Reference (Tentative) | 05/07/2019 | 05/07/2019
TO-19-LA-SLB-1-03 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 3 | 1 |  | Tentative | 06/07/2019 | 08/07/2019
TO-19-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 3 | 1 | 1 | Reference (Tentative) | 06/07/2019 | 08/07/2019
TO-19-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 08/07/2019 | 09/07/2019
TO-19-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Tentative | 08/07/2019 | 11/07/2019
TO-19-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 9 | 7 | 7 | Scheduled | 08/07/2019 | 16/07/2019
TO-19-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-PB-220K2-3-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 1 | 1 | 1 | Scheduled | 08/07/2019 | 08/07/2019
TO-19-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 8 | 6 | 6 | Reference | 08/07/2019 | 15/07/2019
TO-19-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 09/07/2019 | 10/07/2019
TO-19-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 9 | 7 | 7 | Reference | 09/07/2019 | 17/07/2019
TO-19-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 2 | 2 | 2 | Scheduled | 09/07/2019 | 10/07/2019
TO-19-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 2 | 2 | 2 | Scheduled | 10/07/2019 | 11/07/2019
TO-19-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 11 | 7 | 7 | Scheduled | 12/07/2019 | 22/07/2019
TO-19-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 12/07/2019 | 12/07/2019
TO-19-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Scheduled | 15/07/2019 | 19/07/2019
TO-19-CSH-220K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Scheduled | 15/07/2019 | 26/07/2019
TO-19-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 5 | 5 | 5 | Scheduled | 15/07/2019 | 19/07/2019
TO-19-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 3 | 3 | 3 | Reference | 15/07/2019 | 17/07/2019
TO-19-220 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Proposed | 15/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-08 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Proposed | 15/07/2019 | 19/07/2019
TO-19-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 2 | 2 | Scheduled | 16/07/2019 | 17/07/2019
TO-19-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 4 | 4 | 4 | Scheduled | 16/07/2019 | 19/07/2019
TO-19-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 2 | 2 | 2 | Scheduled | 17/07/2019 | 18/07/2019
TO-19-INC-220K4-6-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Proposed | 17/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-07 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Proposed | 22/07/2019 | 29/07/2019
TO-19-BLK-T142-02 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 22/07/2019 | 22/07/2019
TO-19-BLK,T-BLK-1-02 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-BLK,T-NEW-1-03 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 6 | 5 | 5 | Proposed | 22/07/2019 | 27/07/2019
TO-19-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 6 | 5 | 5 | Proposed | 22/07/2019 | 27/07/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 4 | 4 | 4 | Scheduled | 22/07/2019 | 25/07/2019
TO-19-CLH-TRL-1-05 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 9 | 7 | 7 | Scheduled | 22/07/2019 | 30/07/2019
TO-19-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-DMY-MAC-1-05 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 12 | 10 | 10 | Proposed | 22/07/2019 | 02/08/2019
TO-19-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference | 22/07/2019 | 24/07/2019
TO-19-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-KPG-TRL-1-04 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-220 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-KRA-RAF-1-09 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-LOU-T2102-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MCE-110SA2-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | 5 | 5 | 5 | Reference | 22/07/2019 | 26/07/2019
TO-19-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 1 | 1 | 1 | Scheduled | 22/07/2019 | 22/07/2019
TO-19-REM-110SA1-04 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-REM-110SA2-04 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-REM-T141-04 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-REM-T142-04 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-REM-TRL-1-04 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-TB-TRL-1-08 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-TRL-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-TRL-T141-04 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 4 | 4 | 4 | Scheduled | 23/07/2019 | 26/07/2019
TO-19-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 9 | 7 | 7 | Proposed | 23/07/2019 | 31/07/2019
TO-19-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 24/07/2019 | 26/07/2019
TO-19-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 8 | 6 | 6 | Scheduled | 24/07/2019 | 31/07/2019
TO-19-CUL-DGN-1-03 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 2 | 0 | 0 | Proposed | 27/07/2019 | 28/07/2019
TO-19-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 10 | 7 | 7 | Proposed | 29/07/2019 | 07/08/2019
TO-19-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 |  | Proposed | 29/07/2019 | 02/08/2019
TO-19-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Proposed | 29/07/2019 | 02/08/2019
TO-19-CSH-FLA-1-02 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 12 | 9 |  | Scheduled | 29/07/2019 | 09/08/2019
TO-19-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-GOL-T101-02 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-GOL-1-02 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference | 29/07/2019 | 30/07/2019
TO-19-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 57 | 40 | 40 | Proposed | 29/07/2019 | 23/09/2019
TO-19-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-LOU-AT3-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 10 | 7 | 7 | Proposed | 29/07/2019 | 07/08/2019
TO-19-MP-PRO-1-02 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-MP-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 4 | 4 | 4 | Scheduled | 29/07/2019 | 01/08/2019
TO-19-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Proposed | 30/07/2019 | 01/08/2019
TO-19-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 2 | 2 | 2 | Proposed | 31/07/2019 | 01/08/2019
TO-19-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | 3 | 3 | 3 | Scheduled | 31/07/2019 | 02/08/2019
TO-19-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 31/07/2019 | 02/08/2019
TO-19-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 01/08/2019 | 01/08/2019
TO-19-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-BLK,T-NEW-1-05 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 42 | 29 | 29 | Reference (Proposed) | 01/08/2019 | 11/09/2019
TO-19-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | 8 | 5 | 5 | Proposed | 01/08/2019 | 08/08/2019
TO-19-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 5 | 2 | 2 | Proposed | 02/08/2019 | 06/08/2019
TO-19-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-CLO-1-03 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-LET-1-04 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 3 | 0 | 0 | Proposed | 03/08/2019 | 05/08/2019
TO-19-KBY-MAL-1-03 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 0 | 0 | Proposed | 05/08/2019 | 05/08/2019
TO-19-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 4 | 4 | 4 | Proposed | 06/08/2019 | 09/08/2019
TO-19-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 5 | 4 | 4 | Proposed | 06/08/2019 | 10/08/2019
TO-19-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 06/08/2019 | 09/08/2019
TO-19-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 14 | 10 | 10 | Scheduled | 06/08/2019 | 19/08/2019
TO-19-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Proposed | 06/08/2019 | 09/08/2019
TO-19-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 5 | 4 | 4 | Scheduled | 06/08/2019 | 10/08/2019
TO-19-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 3 | 3 | 3 | Scheduled | 06/08/2019 | 08/08/2019
TO-19-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 3 | 3 | 3 | Reference | 06/08/2019 | 08/08/2019
TO-19-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 3 | 3 | 3 | Proposed | 07/08/2019 | 09/08/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 | 3 | Scheduled | 07/08/2019 | 09/08/2019
TO-19-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 3 | 3 | 3 | Scheduled | 07/08/2019 | 09/08/2019
TO-19-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | 1 | 0 | 0 | Reference (Proposed) | 11/08/2019 | 11/08/2019
TO-19-DSN-TH-1-03 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 5 | 5 | 5 | Proposed | 12/08/2019 | 16/08/2019
TO-19-CSH-T2102-04 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 10 | 8 | 8 | Scheduled | 12/08/2019 | 21/08/2019
TO-19-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | 2 | Scheduled | 12/08/2019 | 13/08/2019
TO-19-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 10 | 8 | 8 | Scheduled | 12/08/2019 | 21/08/2019
TO-19-CDU-110K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 1 | 1 | 1 | Scheduled | 12/08/2019 | 12/08/2019
TO-19-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 1 | 1 | 1 | Scheduled | 12/08/2019 | 12/08/2019
TO-19-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 12/08/2019 | 23/08/2019
TO-19-DSN-400K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 12 | 10 | 10 | Scheduled | 12/08/2019 | 23/08/2019
TO-19-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 12 | 10 | 10 | Proposed | 12/08/2019 | 23/08/2019
TO-19-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 2 | 2 | 2 | Scheduled | 12/08/2019 | 13/08/2019
TO-19-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 8 | 6 | 6 | Scheduled | 12/08/2019 | 19/08/2019
TO-19-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 3 | 3 | 3 | Scheduled | 14/08/2019 | 16/08/2019
TO-19-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 2 | 2 | 2 | Scheduled | 15/08/2019 | 16/08/2019
TO-19-MAY-T2103-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | 5 | 3 | 3 | Scheduled | 16/08/2019 | 20/08/2019
TO-19-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-AD-220K1-2-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 2 | 2 | 2 | Scheduled | 19/08/2019 | 20/08/2019
TO-19-AD-220K1-2-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 4 | 4 | 4 | Scheduled | 19/08/2019 | 22/08/2019
TO-19-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 5 | 5 | 5 | Scheduled | 19/08/2019 | 23/08/2019
TO-19-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 4 | 4 | 4 | Scheduled | 19/08/2019 | 22/08/2019
TO-19-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 8 | 6 | 6 | Scheduled | 19/08/2019 | 26/08/2019
TO-19-TBK-T141-02 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 19/08/2019 | 20/08/2019
TO-19-TBK,T-MP GIS-1-02 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 2 | 2 | 2 | Proposed | 19/08/2019 | 20/08/2019
TO-19-TBK,T-TBK-1-02 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 2 | 2 | 2 | Proposed | 19/08/2019 | 20/08/2019
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 2 | 2 | 2 | Reference | 20/08/2019 | 21/08/2019
TO-19-GRI,T-GCA-1-04 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-110SA1-02 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-110SA2-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 9 | 7 | 7 | Scheduled | 20/08/2019 | 28/08/2019
TO-19-KTL-MAY-1-02 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference | 20/08/2019 | 21/08/2019
TO-19-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-BOL-110SA1-02 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-110SA2-02 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-T121-02 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 2 | 2 | 2 | Scheduled | 21/08/2019 | 22/08/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 22/08/2019 | 23/08/2019
TO-19-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 23/08/2019 | 23/08/2019
TO-19-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Scheduled | 26/08/2019 | 28/08/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 5 | Planned | August | August
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 26/08/2019 | 02/09/2019
TO-19-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 1 | 1 | 1 | Scheduled | 26/08/2019 | 26/08/2019
TO-19-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 26/08/2019 | 30/08/2019
TO-19-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 4 | 4 | 4 | Scheduled | 26/08/2019 | 29/08/2019
TO-19-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-SAL-T101-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T101 | 2 | 2 | 2 | Reference | 26/08/2019 | 27/08/2019
TO-19-SAL-T141-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T141 | 2 | 2 | 2 | Reference | 26/08/2019 | 27/08/2019
TO-19-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 3 | 3 | 3 | Scheduled | 26/08/2019 | 28/08/2019
TO-19-TY-220SA1-03 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-TY-220SA2-03 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-AD-LPT-1-02 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 3 | 3 | 3 | Scheduled | 28/08/2019 | 30/08/2019
TO-19-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 3 | 3 | 3 | Scheduled | 28/08/2019 | 30/08/2019
TO-19-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 2 | 2 | 2 | Scheduled | 28/08/2019 | 29/08/2019
TO-19-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 2 | 2 | 2 | Scheduled | 28/08/2019 | 29/08/2019
TO-19-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 29/08/2019 | 30/08/2019
TO-19-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 29/08/2019 | 30/08/2019
TO-19-220 kV A2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-220 kV B2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220K2-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 6 | 4 | 4 | Scheduled | 29/08/2019 | 03/09/2019
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 14 | 10 | 10 | Proposed | 29/08/2019 | 11/09/2019
TO-19-SAL-T102-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T102 | 2 | 2 | 2 | Reference | 29/08/2019 | 30/08/2019
TO-19-SAL-T142-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T142 | 2 | 2 | 2 | Reference | 29/08/2019 | 30/08/2019
TO-19-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-19-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-04 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-03 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 2 | Planned | September | September
TO-19-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Proposed | 02/09/2019 | 03/09/2019
TO-19-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-FIN GIS-110K2-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | 64 | 45 | 45 | Reference (Proposed) | 02/09/2019 | 04/11/2019
TO-19-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 5 | 5 | 5 | Proposed | 02/09/2019 | 06/09/2019
TO-19-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 3 | Planned | September | September
TO-19-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 1 | 1 | 1 | Proposed | 04/09/2019 | 04/09/2019
TO-19-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 04/09/2019 | 04/09/2019
TO-19-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | September | September
TO-19-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 2 | 2 | 2 | Proposed | 09/09/2019 | 10/09/2019
TO-19-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DSN-MAY-1-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 5 | Planned | September | September
TO-19-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 3 | Planned | September | September
TO-19-LOU-RRU-1-04 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Proposed | 10/09/2019 | 12/09/2019
TO-19-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-19-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 34 | Planned | September | November
TO-19-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 10 | Planned | September | September
TO-19-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-GOL,T-LET-1-06 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-110SA1-2-SA1-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-110SA1-2-SA2-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-CAP2-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-T142-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 17/09/2019 | 19/09/2019
TO-19-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-2-SA1-05 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-2-SA2-05 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-M/CAP1-04 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-T141-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 4 | 2 | 2 | Reference (Proposed) | 20/09/2019 | 23/09/2019
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 40 | Planned | September | November
TO-19-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-19-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | Unknown | Unknown | 4 | Planned | September | September
TO-19-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | September | September
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-19-BIN-110SA1-03 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-110SA2-03 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-CF-1-02 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-T142-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | Unknown | Unknown | 6 | Reference (Planned) | September | October
TO-19-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 45 | Planned | September | November
TO-19-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 0 | Planned | September | September
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 1 | 1 | Proposed | 29/09/2019 | 30/09/2019
TO-19-MP-T4202-05 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 1 | 1 | Proposed | 29/09/2019 | 30/09/2019
TO-19-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 20 | Planned | September | October
TO-19-ATE-DRO-1-03 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 20 | Planned | September | October
TO-19-DRO-T121-03 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | September | October
TO-19-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 5 | Planned | September | October
TO-19-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | Unknown | Unknown | 5 | Planned | September | October
TO-19-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 4 | 4 | 4 | Proposed | 30/09/2019 | 03/10/2019
TO-19-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | October
TO-19-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 3 | Planned | October | October
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-LET-1-02 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-WEX-110SA1-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-WEX-110SA2-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-WEX-T141-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-19-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 5 | Planned | October | October
TO-19-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 5 | Planned | October | October
TO-19-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-CLE-CDU-1-02 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-SOM,T-SH-1-01 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-220 kV B2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-CKM-PST2201-03 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | Unknown | 2 | Planned | October | October
TO-19-GI-ST101-01 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | Unknown | Unknown | 4 | Planned | October | October
TO-19-MP GIS-220K2-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 235 | Planned | October | September
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 235 | Planned | October | September
TO-19-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 3 | Planned | October | October
TO-19-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 3 | Planned | October | October
TO-19-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA1-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA2-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-CLA-1-03 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-19-BGH-CLA-1-04 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-T121-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown |  | Reference (Planned) | October | October
TO-19-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-19-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | Unknown | 5 | Planned | October | October
TO-19-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown | 9 | Planned | October | November
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 4 | Planned | October | October
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 4 | Planned | October | October
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | October | October
TO-19-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 3 | Planned | October | October
TO-19-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 8 | 6 | 6 | Scheduled | 29/10/2019 | 05/11/2019
TO-19-GLR-MOY-1-04 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-MOY-CAP1-04 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-MOY-T141-03 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | October | November
TO-19-MOY-TAW-1-05 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | Unknown | 2 | Planned | October | November
TO-19-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 0 | Planned | November | November
TO-19-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | November | November
TO-19-ATE-DRO-1-02 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-KNR-1-02 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 4 | Planned | November | November
TO-19-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-T121-02 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 1 | Planned | November | November
TO-19-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-19-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | Unknown | Unknown | 3 | Reference (Planned) | November | November
TO-19-DRO-T121-02 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 10 | Planned | November | November
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-19-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | Unknown | 20 | Planned | November | November
TO-19-MOY-CAP1-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 2 | 2 |  | Proposed | 14/11/2019 | 15/11/2019
TO-19-MP-T4002-04 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 2 | 2 | 2 | Proposed | 14/11/2019 | 15/11/2019
TO-19-BYH-BVK-1-04 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 1 | 1 | 1 | Tentative | 15/11/2019 | 15/11/2019
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | Unknown | 5 | Planned | November | November
TO-19-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown |  | Planned | November | November
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | Unknown | 0 | Planned | November | December

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TB-TRL-1-04 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 154 | 105 | 105 | Scheduled | 25/02/2019 | 28/07/2019
TO-19-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 120 | 83 | 83 | Scheduled | 23/04/2019 | 20/08/2019
TO-19-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 119 | 82 | 82 | Scheduled | 24/04/2019 | 20/08/2019
TO-19-MP-PRO-1-03 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 |  | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 120 | 84 | 84 | Scheduled | 03/06/2019 | 30/09/2019
TO-19-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 43 | 31 | 31 | Scheduled | 17/06/2019 | 29/07/2019
TO-19-220 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-220 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 9 | 7 |  | Scheduled | 01/07/2019 | 09/07/2019
TO-19-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MTN-MUN-2-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 138 | 98 | 98 | Proposed | 01/07/2019 | 15/11/2019
TO-19-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 9 | 7 | 7 | Scheduled | 08/07/2019 | 16/07/2019
TO-19-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 8 | 6 | 6 | Reference | 08/07/2019 | 15/07/2019
TO-19-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 9 | 7 | 7 | Reference | 09/07/2019 | 17/07/2019
TO-19-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 9 | 7 | 7 | Scheduled | 09/07/2019 | 17/07/2019
TO-19-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 2 | 2 | 2 | Scheduled | 09/07/2019 | 10/07/2019
TO-19-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Scheduled | 15/07/2019 | 19/07/2019
TO-19-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Scheduled | 15/07/2019 | 17/07/2019
TO-19-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 3 | 3 | 3 | Reference | 15/07/2019 | 17/07/2019
TO-19-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Scheduled | 16/07/2019 | 16/07/2019
TO-19-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 6 | 5 | 5 | Proposed | 22/07/2019 | 27/07/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 4 | 4 | 4 | Scheduled | 22/07/2019 | 25/07/2019
TO-19-CLH-TRL-1-05 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-KPG-TRL-1-04 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 1 | 1 | 1 | Scheduled | 22/07/2019 | 22/07/2019
TO-19-REM-110SA1-04 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-REM-110SA2-04 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-REM-T141-04 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-REM-T142-04 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-REM-TRL-1-04 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-TB-TRL-1-08 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-TRL-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-TRL-T141-04 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 22/07/2019 | 26/07/2019
TO-19-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 2 | 0 | 0 | Proposed | 27/07/2019 | 28/07/2019
TO-19-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 57 | 40 | 40 | Proposed | 29/07/2019 | 23/09/2019
TO-19-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-MP-PRO-1-02 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-MP-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 4 | 4 | 4 | Scheduled | 29/07/2019 | 01/08/2019
TO-19-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 12 | 10 | 10 | Scheduled | 12/08/2019 | 23/08/2019
TO-19-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 2 | 2 | 2 | Scheduled | 12/08/2019 | 13/08/2019
TO-19-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 8 | 6 | 6 | Scheduled | 19/08/2019 | 26/08/2019
TO-19-TBK-T141-02 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 19/08/2019 | 20/08/2019
TO-19-TBK,T-MP GIS-1-02 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 2 | 2 | 2 | Proposed | 19/08/2019 | 20/08/2019
TO-19-TBK,T-TBK-1-02 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 2 | 2 | 2 | Proposed | 19/08/2019 | 20/08/2019
TO-19-BOL-110SA1-02 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-110SA2-02 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-BOL-T121-02 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 2 | 2 | 2 | Proposed | 21/08/2019 | 22/08/2019
TO-19-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 3 | 3 | 3 | Scheduled | 26/08/2019 | 28/08/2019
TO-19-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 3 | 3 | 3 | Scheduled | 28/08/2019 | 30/08/2019
TO-19-220 kV A2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-220 kV B2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220K2-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Proposed | 29/08/2019 | 30/08/2019
TO-19-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-19-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-19-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | September | September
TO-19-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 3 | 2 | 2 | Proposed | 08/09/2019 | 10/09/2019
TO-19-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 2 | 2 | 2 | Proposed | 09/09/2019 | 10/09/2019
TO-19-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 5 | Planned | September | September
TO-19-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-19-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 10 | Planned | September | September
TO-19-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 34 | Planned | September | November
TO-19-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | Unknown | Unknown | 4 | Planned | September | September
TO-19-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 45 | Planned | September | November
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 1 | 1 | Proposed | 29/09/2019 | 30/09/2019
TO-19-MP-T4202-05 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 1 | 1 | Proposed | 29/09/2019 | 30/09/2019
TO-19-ATE-DRO-1-03 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 20 | Planned | September | October
TO-19-DRO-T121-03 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | September | October
TO-19-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 20 | Planned | September | October
TO-19-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 4 | Planned | September | October
TO-19-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 4 | 4 | 4 | Proposed | 30/09/2019 | 03/10/2019
TO-19-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | October
TO-19-MP GIS-220K2-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 2 | Planned | October | October
TO-19-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 1 | Planned | October | October
TO-19-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-ATE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | November | November
TO-19-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-DRO-1-02 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-KNR-1-02 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 4 | Planned | November | November
TO-19-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 10 | Planned | November | November
TO-19-ATE-T121-02 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 1 | Planned | November | November
TO-19-DRO-T121-02 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 10 | Planned | November | November
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 2 | 2 |  | Proposed | 14/11/2019 | 15/11/2019
TO-19-MP-T4002-04 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 2 | 2 | 2 | Proposed | 14/11/2019 | 15/11/2019
TO-19-BYH-BVK-1-04 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 1 | 1 | 1 | Tentative | 15/11/2019 | 15/11/2019
TO-19-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | Unknown | 0 | Planned | November | December

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 113 | 80 | 80 | Scheduled | 18/06/2019 | 08/10/2019
TO-19-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA1-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-110SA2-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 99 | 70 | 70 | Scheduled | 18/06/2019 | 24/09/2019
TO-19-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 99 | 70 | 70 | Reference | 18/06/2019 | 24/09/2019
TO-19-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 99 | 70 | 70 | Reference | 18/06/2019 | 24/09/2019
TO-19-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 26 | 20 | 20 | Scheduled | 24/06/2019 | 19/07/2019
TO-19-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 9 | 7 |  | Scheduled | 01/07/2019 | 09/07/2019
TO-19-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 01/07/2019 | 02/07/2019
TO-19-MON-T102-01 | DISTRIBUTION TRANSFORMER - MONREAD 110-MONREAD 10-T102 | 2 | 2 | 2 | Reference | 03/07/2019 | 04/07/2019
TO-19-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 11 | 7 | 7 | Scheduled | 12/07/2019 | 22/07/2019
TO-19-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Proposed | 22/07/2019 | 29/07/2019
TO-19-BLK-T142-02 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 22/07/2019 | 22/07/2019
TO-19-BLK,T-BLK-1-02 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-BLK,T-NEW-1-03 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 9 | 7 | 7 | Proposed | 23/07/2019 | 31/07/2019
TO-19-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 24/07/2019 | 26/07/2019
TO-19-CUL-DGN-1-03 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 3 | 3 | 3 | Proposed | 24/07/2019 | 26/07/2019
TO-19-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 10 | 7 | 7 | Proposed | 29/07/2019 | 07/08/2019
TO-19-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 01/08/2019 | 01/08/2019
TO-19-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-BLK,T-NEW-1-05 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 3 | 3 | 3 | Scheduled | 14/08/2019 | 16/08/2019
TO-19-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 4 | 4 | 4 | Scheduled | 19/08/2019 | 22/08/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 22/08/2019 | 23/08/2019
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 26/08/2019 | 02/09/2019
TO-19-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 2 | 2 | 2 | Scheduled | 28/08/2019 | 29/08/2019
TO-19-BDA-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-04 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-03 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 2 | Planned | September | September
TO-19-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 2 | Planned | September | September
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-WEX-110SA1-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-WEX-110SA2-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-WEX-T141-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-19-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 1 | Planned | October | October
TO-19-GI-ST101-01 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | Unknown | Unknown | 4 | Planned | October | October
TO-19-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 0 | Planned | November | November
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-19-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | Unknown | 20 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 187 | 131 | 131 | Scheduled | 29/04/2019 | 01/11/2019
TO-19-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 187 | 131 | 131 | Scheduled | 29/04/2019 | 01/11/2019
TO-19-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 181 | 125 | 125 | Reference | 02/05/2019 | 29/10/2019
TO-19-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 181 | 125 | 125 | Scheduled | 02/05/2019 | 29/10/2019
TO-19-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 111 | 77 | 77 | Scheduled | 29/05/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 111 | 77 | 77 | Scheduled | 29/05/2019 | 16/09/2019
TO-19-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 3 | 3 | 3 | Scheduled | 02/07/2019 | 04/07/2019
TO-19-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 09/07/2019 | 10/07/2019
TO-19-CSH-220K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Scheduled | 15/07/2019 | 26/07/2019
TO-19-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 6 | 5 | 5 | Proposed | 22/07/2019 | 27/07/2019
TO-19-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 6 | 5 | 5 | Proposed | 22/07/2019 | 27/07/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 4 | 4 | 4 | Scheduled | 22/07/2019 | 25/07/2019
TO-19-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference | 22/07/2019 | 24/07/2019
TO-19-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Proposed | 29/07/2019 | 02/08/2019
TO-19-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-CSH-FLA-1-02 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 12 | 9 |  | Scheduled | 29/07/2019 | 09/08/2019
TO-19-GOL-T101-02 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-GOL-1-02 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 29/07/2019 | 29/07/2019
TO-19-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Proposed | 30/07/2019 | 01/08/2019
TO-19-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 42 | 29 | 29 | Reference (Proposed) | 01/08/2019 | 11/09/2019
TO-19-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-CLO-1-03 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-GOL,T-LET-1-04 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 02/08/2019 | 02/08/2019
TO-19-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 4 | 4 | 4 | Proposed | 06/08/2019 | 09/08/2019
TO-19-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 5 | 4 | 4 | Proposed | 06/08/2019 | 10/08/2019
TO-19-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Proposed | 06/08/2019 | 09/08/2019
TO-19-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 3 | 3 | 3 | Scheduled | 06/08/2019 | 08/08/2019
TO-19-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 3 | 3 | 3 | Reference | 06/08/2019 | 08/08/2019
TO-19-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | 2 | Scheduled | 12/08/2019 | 13/08/2019
TO-19-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-CSH-T2102-04 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 10 | 8 | 8 | Scheduled | 12/08/2019 | 21/08/2019
TO-19-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 5 | 5 | 5 | Proposed | 12/08/2019 | 16/08/2019
TO-19-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 10 | 8 | 8 | Scheduled | 12/08/2019 | 21/08/2019
TO-19-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 2 | 2 | 2 | Scheduled | 21/08/2019 | 22/08/2019
TO-19-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 23/08/2019 | 23/08/2019
TO-19-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 26/08/2019 | 30/08/2019
TO-19-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 4 | 4 | 4 | Scheduled | 26/08/2019 | 29/08/2019
TO-19-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2019 | 30/08/2019
TO-19-SAL-T101-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T101 | 2 | 2 | 2 | Reference | 26/08/2019 | 27/08/2019
TO-19-SAL-T141-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T141 | 2 | 2 | 2 | Reference | 26/08/2019 | 27/08/2019
TO-19-TY-220SA1-03 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-TY-220SA2-03 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 2 | 2 | 2 | Scheduled | 26/08/2019 | 27/08/2019
TO-19-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 29/08/2019 | 30/08/2019
TO-19-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 29/08/2019 | 30/08/2019
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 14 | 10 | 10 | Proposed | 29/08/2019 | 11/09/2019
TO-19-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 6 | 4 | 4 | Scheduled | 29/08/2019 | 03/09/2019
TO-19-SAL-T102-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T102 | 2 | 2 | 2 | Reference | 29/08/2019 | 30/08/2019
TO-19-SAL-T142-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T142 | 2 | 2 | 2 | Reference | 29/08/2019 | 30/08/2019
TO-19-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Proposed | 02/09/2019 | 03/09/2019
TO-19-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 1 | 1 | 1 | Proposed | 04/09/2019 | 04/09/2019
TO-19-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 04/09/2019 | 04/09/2019
TO-19-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 10 | Planned | September | September
TO-19-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 34 | Planned | September | November
TO-19-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-GOL,T-LET-1-06 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-110SA1-2-SA1-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-110SA1-2-SA2-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-CAP2-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 3 | 3 | 3 | Proposed | 17/09/2019 | 19/09/2019
TO-19-LET-T142-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 17/09/2019 | 19/09/2019
TO-19-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-2-SA1-05 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-2-SA2-05 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-M/CAP1-04 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 4 | 2 | 2 | Proposed | 20/09/2019 | 23/09/2019
TO-19-LET-T141-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 4 | 2 | 2 | Reference (Proposed) | 20/09/2019 | 23/09/2019
TO-19-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-19-BIN-110SA1-03 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-110SA2-03 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-CF-1-02 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-19-BIN-T142-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | Unknown | Unknown | 6 | Reference (Planned) | September | October
TO-19-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | Unknown | Unknown | 5 | Planned | September | October
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-LET-1-02 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | Unknown | 5 | Planned | October | October
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown | 9 | Planned | October | November
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 4 | Planned | October | October
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 4 | Planned | October | October
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | October | October
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-GLR-MOY-1-04 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-MOY-CAP1-04 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-MOY-T141-03 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | October | November
TO-19-MOY-TAW-1-05 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 3 | Planned | October | November
TO-19-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-19-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | Unknown | Unknown | 3 | Reference (Planned) | November | November
TO-19-MOY-CAP1-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | Unknown | 5 | Planned | November | November

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 01/07/2019 | 03/07/2019
TO-19-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-LA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-LA-RIC-2-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 1 | 1 | 1 | Reference (Tentative) | 05/07/2019 | 05/07/2019
TO-19-LA-SLB-1-03 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 1 | 1 | 1 | Tentative | 05/07/2019 | 05/07/2019
TO-19-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Tentative | 08/07/2019 | 11/07/2019
TO-19-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 8 | 6 | 6 | Scheduled | 08/07/2019 | 15/07/2019
TO-19-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 2 | 2 | 2 | Scheduled | 10/07/2019 | 11/07/2019
TO-19-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 4 | 4 | 4 | Scheduled | 16/07/2019 | 19/07/2019
TO-19-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-LOU-T2102-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-LOU-AT3-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 10 | 7 | 7 | Proposed | 29/07/2019 | 07/08/2019
TO-19-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 2 | 2 | 2 | Proposed | 30/07/2019 | 31/07/2019
TO-19-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | 8 | 5 | 5 | Proposed | 01/08/2019 | 08/08/2019
TO-19-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 5 | 4 | 4 | Scheduled | 06/08/2019 | 10/08/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 | 3 | Scheduled | 07/08/2019 | 09/08/2019
TO-19-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 3 | 3 | 3 | Scheduled | 07/08/2019 | 09/08/2019
TO-19-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 10 | 8 | 8 | Scheduled | 12/08/2019 | 21/08/2019
TO-19-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 1 | 1 | 1 | Scheduled | 12/08/2019 | 12/08/2019
TO-19-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 1 | 1 | 1 | Scheduled | 12/08/2019 | 12/08/2019
TO-19-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 2 | 2 | 2 | Scheduled | 15/08/2019 | 16/08/2019
TO-19-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 5 | 5 | 5 | Scheduled | 19/08/2019 | 23/08/2019
TO-19-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 1 | 1 | 1 | Scheduled | 26/08/2019 | 26/08/2019
TO-19-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 5 | 5 | 5 | Proposed | 02/09/2019 | 06/09/2019
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-LOU-RRU-1-04 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Proposed | 10/09/2019 | 11/09/2019
TO-19-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Proposed | 10/09/2019 | 12/09/2019
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | September | September
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-19-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-01 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-19-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 1 | Planned | October | October

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 91 | 63 | 63 | Scheduled | 10/05/2019 | 08/08/2019
TO-19-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 71 | 50 | 50 | Scheduled | 10/05/2019 | 19/07/2019
TO-19-FIN-T142-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T142 | 64 | 45 | 45 | Reference | 29/05/2019 | 31/07/2019
TO-19-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 65 | 46 | 46 | Scheduled | 25/06/2019 | 28/08/2019
TO-19-220 kV A2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A2 | 19 | 15 | 15 | Scheduled | 01/07/2019 | 19/07/2019
TO-19-220 kV B2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B2 | 19 | 15 | 15 | Scheduled | 01/07/2019 | 19/07/2019
TO-19-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 4 | 4 | 4 | Scheduled | 01/07/2019 | 04/07/2019
TO-19-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 7 | 5 |  | Scheduled | 04/07/2019 | 10/07/2019
TO-19-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 7 | 5 |  | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 7 | 5 | 5 | Scheduled | 04/07/2019 | 10/07/2019
TO-19-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 3 | 1 |  | Tentative | 06/07/2019 | 08/07/2019
TO-19-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 3 | 1 | 1 | Reference (Tentative) | 06/07/2019 | 08/07/2019
TO-19-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Tentative | 08/07/2019 | 11/07/2019
TO-19-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-PB-220K2-3-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 1 | 1 | 1 | Scheduled | 08/07/2019 | 08/07/2019
TO-19-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 3 | 3 | 3 | Scheduled | 08/07/2019 | 10/07/2019
TO-19-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 12/07/2019 | 12/07/2019
TO-19-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 2 | 2 | Scheduled | 16/07/2019 | 17/07/2019
TO-19-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 2 | 2 | 2 | Scheduled | 17/07/2019 | 18/07/2019
TO-19-INC-220K4-6-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | 1 | Proposed | 22/07/2019 | 22/07/2019
TO-19-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 3 | 3 | 3 | Scheduled | 22/07/2019 | 24/07/2019
TO-19-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 9 | 7 | 7 | Scheduled | 22/07/2019 | 30/07/2019
TO-19-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MCE-110SA2-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | 5 | 5 | 5 | Reference | 22/07/2019 | 26/07/2019
TO-19-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 5 | 5 | 5 | Scheduled | 22/07/2019 | 26/07/2019
TO-19-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 8 | 6 | 6 | Scheduled | 24/07/2019 | 31/07/2019
TO-19-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 |  | Proposed | 29/07/2019 | 02/08/2019
TO-19-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference | 29/07/2019 | 30/07/2019
TO-19-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 3 | 3 | 3 | Scheduled | 29/07/2019 | 31/07/2019
TO-19-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 31/07/2019 | 02/08/2019
TO-19-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | 1 | Proposed | 01/08/2019 | 01/08/2019
TO-19-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 14 | 10 | 10 | Scheduled | 06/08/2019 | 19/08/2019
TO-19-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 3 | 3 | 3 | Proposed | 07/08/2019 | 09/08/2019
TO-19-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | 1 | 0 | 0 | Reference (Proposed) | 11/08/2019 | 11/08/2019
TO-19-DSN-TH-1-03 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Proposed | 11/08/2019 | 11/08/2019
TO-19-CDU-110K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 12/08/2019 | 23/08/2019
TO-19-DSN-400K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 12 | 10 | 10 | Scheduled | 12/08/2019 | 23/08/2019
TO-19-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 12 | 10 | 10 | Proposed | 12/08/2019 | 23/08/2019
TO-19-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 12/08/2019 | 14/08/2019
TO-19-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 3 | 3 | 3 | Scheduled | 14/08/2019 | 16/08/2019
TO-19-MAY-T2103-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | 5 | 3 | 3 | Scheduled | 16/08/2019 | 20/08/2019
TO-19-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 2 | 2 | 2 | Reference | 20/08/2019 | 21/08/2019
TO-19-GRI,T-GCA-1-04 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-110SA1-02 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-110SA2-01 | SECTIONALISING DISCONNECT - KILTEEL 110-KILTEEL 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/08/2019 | 21/08/2019
TO-19-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 9 | 7 | 7 | Scheduled | 20/08/2019 | 28/08/2019
TO-19-KTL-MAY-1-02 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference | 20/08/2019 | 21/08/2019
TO-19-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Scheduled | 26/08/2019 | 28/08/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 5 | Planned | August | August
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 14 | 10 | 10 | Proposed | 29/08/2019 | 11/09/2019
TO-19-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 6 | 4 | 4 | Scheduled | 29/08/2019 | 03/09/2019
TO-19-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 1 | Planned | September | September
TO-19-FIN GIS-110K2-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 3 | Planned | September | September
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | 64 | 45 | 45 | Reference (Proposed) | 02/09/2019 | 04/11/2019
TO-19-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 3 | Planned | September | September
TO-19-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 3 | Planned | September | September
TO-19-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-DSN-MAY-1-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 3 | Planned | September | September
TO-19-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 3 | Planned | September | September
TO-19-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 2 | Planned | September | September
TO-19-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 40 | Planned | September | November
TO-19-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-19-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 0 | Planned | September | September
TO-19-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | Unknown | Unknown | 10 | Planned | September | October
TO-19-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | Unknown | Unknown | 1 | Planned | September | September
TO-19-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 5 | Planned | September | October
TO-19-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 3 | Planned | October | October
TO-19-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-19-CLE-CDU-1-02 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-220 kV B2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-CKM-PST2201-03 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | Unknown | 2 | Planned | October | October
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 235 | Planned | October | September
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 235 | Planned | October | September
TO-19-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-19-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-19-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 8 | 6 | 6 | Scheduled | 29/10/2019 | 05/11/2019
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | Unknown | Unknown | 2 | Planned | October | November
TO-19-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 0 | Planned | November | November
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 64 | 45 | 45 | Scheduled | 04/06/2019 | 06/08/2019
TO-19-AD-T2011/12-04 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 4 | 4 | 4 | Scheduled | 01/07/2019 | 04/07/2019
TO-19-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2019 | 05/07/2019
TO-19-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 5 | 5 | 5 | Reference | 01/07/2019 | 05/07/2019
TO-19-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 5 | 5 | 5 | Reference | 01/07/2019 | 05/07/2019
TO-19-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 12 | 10 | 10 | Scheduled | 01/07/2019 | 12/07/2019
TO-19-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 2 | 2 | 2 | Scheduled | 08/07/2019 | 09/07/2019
TO-19-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2019 | 12/07/2019
TO-19-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 08/07/2019 | 09/07/2019
TO-19-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 5 | 5 | 5 | Scheduled | 15/07/2019 | 19/07/2019
TO-19-220 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Proposed | 15/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-08 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Proposed | 15/07/2019 | 19/07/2019
TO-19-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-07 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Scheduled | 17/07/2019 | 19/07/2019
TO-19-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 3 | 3 | 3 | Proposed | 17/07/2019 | 19/07/2019
TO-19-DMY-MAC-1-05 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 12 | 10 | 10 | Proposed | 22/07/2019 | 02/08/2019
TO-19-220 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-KRA-RAF-1-09 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Proposed | 22/07/2019 | 26/07/2019
TO-19-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 4 | 4 | 4 | Scheduled | 23/07/2019 | 26/07/2019
TO-19-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Scheduled | 29/07/2019 | 30/07/2019
TO-19-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 2 | 2 | 2 | Proposed | 31/07/2019 | 01/08/2019
TO-19-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | 3 | 3 | 3 | Scheduled | 31/07/2019 | 02/08/2019
TO-19-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 5 | 2 | 2 | Proposed | 02/08/2019 | 06/08/2019
TO-19-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 3 | 0 | 0 | Proposed | 03/08/2019 | 05/08/2019
TO-19-KBY-MAL-1-03 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 0 | 0 | Proposed | 05/08/2019 | 05/08/2019
TO-19-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 06/08/2019 | 09/08/2019
TO-19-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 12/08/2019 | 16/08/2019
TO-19-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 65 | 47 | 47 | Proposed | 12/08/2019 | 15/10/2019
TO-19-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 8 | 6 | 6 | Scheduled | 12/08/2019 | 19/08/2019
TO-19-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-AD-220K1-2-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 4 | 4 | 4 | Scheduled | 19/08/2019 | 22/08/2019
TO-19-AD-220K1-2-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 2 | 2 | 2 | Scheduled | 19/08/2019 | 20/08/2019
TO-19-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 12 | 10 | 10 | Proposed | 19/08/2019 | 30/08/2019
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 20/08/2019 | 23/08/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 22/08/2019 | 23/08/2019
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 26/08/2019 | 02/09/2019
TO-19-AD-LPT-1-02 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 3 | 3 | 3 | Scheduled | 28/08/2019 | 30/08/2019
TO-19-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 2 | 2 | 2 | Scheduled | 28/08/2019 | 29/08/2019
TO-19-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-19-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 5 | Planned | October | October
TO-19-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 5 | Planned | October | October
TO-19-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 3 | Planned | October | October
TO-19-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 3 | Planned | October | October
TO-19-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA1-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-110SA2-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-CLA-1-03 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-19-BGH-CLA-1-04 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-T121-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 2 | Planned | October | October
TO-19-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown |  | Reference (Planned) | October | October
TO-19-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 3 | Planned | October | October
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown |  | Planned | November | November
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 1 | Planned | November | November
TO-19-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | Unknown | 0 | Planned | November | December