## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2019 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 174 | 121 | 121 | Scheduled | 02/05/2019 | 22/10/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 174 | 121 | 121 | Scheduled | 02/05/2019 | 22/10/2019
TO-19-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 174 | 121 | 121 | Reference | 02/05/2019 | 22/10/2019
TO-19-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 174 | 121 |  | Scheduled | 02/05/2019 | 22/10/2019
TO-19-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-MOY-110SA1-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-MOY-110SA2-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-LET-110SA1-2-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA2-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 110 | 76 | 76 | Reference | 29/05/2019 | 15/09/2019
TO-19-MP-PRO-1-03 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-PRO-1-04 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 143 | 101 | 101 | Scheduled | 03/06/2019 | 23/10/2019
TO-19-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 |  | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 143 | 101 | 101 | Scheduled | 03/06/2019 | 23/10/2019
TO-19-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 113 | 80 | 80 | Scheduled | 21/06/2019 | 11/10/2019
TO-19-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA1-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA2-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 103 | 72 | 72 | Reference | 21/06/2019 | 01/10/2019
TO-19-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 103 | 72 | 72 | Reference | 21/06/2019 | 01/10/2019
TO-19-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 85 | 60 | 60 | Scheduled | 25/06/2019 | 17/09/2019
TO-19-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 138 | 98 | 98 | Scheduled | 01/07/2019 | 15/11/2019
TO-19-LET-T142-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 46 | 31 | 31 | Reference | 01/08/2019 | 15/09/2019
TO-19-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 28 | 20 | 20 | Scheduled | 06/08/2019 | 02/09/2019
TO-19-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 28 | 20 | 20 | Scheduled | 06/08/2019 | 02/09/2019
TO-19-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-MTN-MUN-2-03 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 18 | 12 | 12 | Scheduled | 16/08/2019 | 02/09/2019
TO-19-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 18 | 12 | 12 | Reference | 16/08/2019 | 02/09/2019
TO-19-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 13 | 9 | 9 | Scheduled | 21/08/2019 | 02/09/2019
TO-19-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 3 | 3 | Scheduled | 29/08/2019 | 02/09/2019
TO-19-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 |  | Scheduled | 02/09/2019 | 06/09/2019
TO-19-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 02/09/2019 | 02/09/2019
TO-19-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 4 | 4 | 4 | Scheduled | 02/09/2019 | 05/09/2019
TO-19-110 kV A2 @ CRO-01 | BUSBAR SECTION - COOLROE 110-COOLROE 110-110A2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 02/09/2019 | 06/09/2019
TO-19-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 02/09/2019 | 03/09/2019
TO-19-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 10 | 8 | 8 | Scheduled | 02/09/2019 | 11/09/2019
TO-19-LA-RIC-1-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-1 | 6 | 5 | 5 | Reference | 02/09/2019 | 07/09/2019
TO-19-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/09/2019 | 06/09/2019
TO-19-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-SHL-T2015-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 4 | 4 | 4 | Scheduled | 02/09/2019 | 05/09/2019
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 11 | 9 | 9 | Scheduled | 03/09/2019 | 13/09/2019
TO-19-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 4 | 4 | 4 | Reference | 03/09/2019 | 06/09/2019
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 3 | 3 | 3 | Scheduled | 03/09/2019 | 05/09/2019
TO-19-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 05/09/2019 | 05/09/2019
TO-19-ATE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 89 | 62 | 62 | Scheduled | 06/09/2019 | 03/12/2019
TO-19-RAF-T2102-03 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 5 | 3 | 3 | Scheduled | 06/09/2019 | 10/09/2019
TO-19-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP-PRO-1-02 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 |  | Scheduled | 09/09/2019 | 13/09/2019
TO-19-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 12 | 10 | 10 | Scheduled | 09/09/2019 | 20/09/2019
TO-19-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2019 | 12/09/2019
TO-19-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 5 | 5 | 5 | Reference | 09/09/2019 | 13/09/2019
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-FIN GIS-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2103 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-LA-RIC-2-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 5 | 5 | 5 | Reference | 09/09/2019 | 13/09/2019
TO-19-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Scheduled | 10/09/2019 | 12/09/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 11/09/2019 | 12/09/2019
TO-19-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 3 | 3 | 3 | Scheduled | 11/09/2019 | 13/09/2019
TO-19-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-CLG-110K2-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-CD-MAC-1-04 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 13/09/2019 | 13/09/2019
TO-19-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 3 |  | Scheduled | 13/09/2019 | 17/09/2019
TO-19-MAC-110SA1-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 1 | 1 | 1 | Scheduled | 13/09/2019 | 13/09/2019
TO-19-DSN-MP GIS-1-06 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 11 | 7 | 7 | Scheduled | 14/09/2019 | 24/09/2019
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 5 | 5 |  | Scheduled | 16/09/2019 | 20/09/2019
TO-19-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 16/09/2019 | 27/09/2019
TO-19-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-FIN GIS-110K2-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | Unknown | Unknown | 45 | Reference (Planned) | September | November
TO-19-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA2-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-T142-04 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 1 | 1 | 1 | Reference | 16/09/2019 | 16/09/2019
TO-19-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 4 | 4 | 4 | Reference | 16/09/2019 | 19/09/2019
TO-19-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-2-SA1-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-2-SA2-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 | 2 | Reference | 17/09/2019 | 18/09/2019
TO-19-KBY-KRA-1-03 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Tentative | 18/09/2019 | 20/09/2019
TO-19-LOU-AT2-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 28 | 20 |  | Scheduled | 18/09/2019 | 15/10/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 9 | 7 | 7 | Scheduled | 18/09/2019 | 26/09/2019
TO-19-LOU-TAN-2-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 28 | 20 | 20 | Scheduled | 18/09/2019 | 15/10/2019
TO-19-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | 5 | 3 | 3 | Scheduled | 19/09/2019 | 23/09/2019
TO-19-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | 5 | 3 | 3 | Scheduled | 19/09/2019 | 23/09/2019
TO-19-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 3 | 2 | 2 | Scheduled | 19/09/2019 | 21/09/2019
TO-19-SRA-T2102-01 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | 1 | 1 | 1 | Scheduled | 20/09/2019 | 20/09/2019
TO-19-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-ARK-BEG-1-02 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 4 | 4 | 4 | Proposed | 23/09/2019 | 26/09/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 23/09/2019 | 27/09/2019
TO-19-DMY-MAC-1-06 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 57 | 40 | 40 | Proposed | 23/09/2019 | 18/11/2019
TO-19-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 3 | 3 | 3 | Scheduled | 23/09/2019 | 25/09/2019
TO-19-GAL-SAL-1-04 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 4 | 4 |  | Scheduled | 23/09/2019 | 26/09/2019
TO-19-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-MAC-110SA2-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-MAC-T142-07 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 2 | 2 | 2 | Reference | 23/09/2019 | 24/09/2019
TO-19-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-110 kV A1 @ MID-01 | BUSBAR SECTION - MIDLETON 110-MIDLETON 110-110A1 | 2 | 2 | 2 | Proposed | 23/09/2019 | 24/09/2019
TO-19-MID-110SA1-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 2 | 2 | 2 | Proposed | 23/09/2019 | 24/09/2019
TO-19-MID-T141-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 23/09/2019 | 24/09/2019
TO-19-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Scheduled | 23/09/2019 | 27/09/2019
TO-19-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 23/09/2019 | 23/09/2019
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2019 | 23/09/2019
TO-19-SOM,T-SH-1-02 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 23/09/2019 | 23/09/2019
TO-19-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2019 | 23/09/2019
TO-19-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 1 | 1 | 1 | Scheduled | 24/09/2019 | 24/09/2019
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 14 | 10 |  | Scheduled | 24/09/2019 | 07/10/2019
TO-19-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 64 | 45 |  | Proposed | 26/09/2019 | 28/11/2019
TO-19-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 1 | 1 | Proposed | 27/09/2019 | 27/09/2019
TO-19-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 64 | 45 | 45 | Proposed | 27/09/2019 | 29/11/2019
TO-19-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 1 | 1 | 1 | Proposed | 30/09/2019 | 30/09/2019
TO-19-220 kV A1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-220 kV B1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 1 | 1 | 1 | Scheduled | 30/09/2019 | 30/09/2019
TO-19-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2019 | 04/10/2019
TO-19-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 4 | 4 |  | Scheduled | 30/09/2019 | 03/10/2019
TO-19-KNY-UGL-1-02 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 30/09/2019 | 04/10/2019
TO-19-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | 4 | 4 | 4 | Reference | 30/09/2019 | 03/10/2019
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 12 | 10 |  | Scheduled | 30/09/2019 | 11/10/2019
TO-19-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 3 | 3 | 3 | Scheduled | 30/09/2019 | 02/10/2019
TO-19-UGL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Proposed | 01/10/2019 | 04/10/2019
TO-19-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 3 | 3 | 3 | Scheduled | 01/10/2019 | 03/10/2019
TO-19-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-T2102-03 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-ARK-CKM GIS-1-02 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 2 | 2 | 2 | Proposed | 03/10/2019 | 04/10/2019
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 14 | 10 | 10 | Proposed | 03/10/2019 | 16/10/2019
TO-19-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 8 | 6 | 6 | Scheduled | 03/10/2019 | 10/10/2019
TO-19-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-KRA-1-08 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-LPT-1-04 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 7 | 5 | 5 | Proposed | 07/10/2019 | 13/10/2019
TO-19-LPT-T2002-04 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 07/10/2019 | 07/10/2019
TO-19-SOM-T142-05 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 4 | 4 | Reference | 07/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-CSH-1-06 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-SH-1-06 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-SOM-1-05 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-BVK-T2102-04 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Proposed | 08/10/2019 | 09/10/2019
TO-19-CLE-CDU-1-02 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 1 | 1 | 1 | Scheduled | 09/10/2019 | 09/10/2019
TO-19-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-110SA1-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-110SA2-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-T141-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 09/10/2019 | 10/10/2019
TO-19-BVK-COT-1-03 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 1 | 1 | 1 | Proposed | 10/10/2019 | 10/10/2019
TO-19-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-220 kV B2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-BVK-COT-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-GI-WEX-1-07 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 5 | 3 | 3 | Scheduled | 11/10/2019 | 15/10/2019
TO-19-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 0 | 0 | Reference | 11/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-SOM,T-SH-1-01 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 11 | 7 | 7 | Scheduled | 11/10/2019 | 22/10/2019
TO-19-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 14/10/2019 | 25/10/2019
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 12 | 10 | 10 | Reference (Proposed) | 14/10/2019 | 25/10/2019
TO-19-BIN-TIV-1-04 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-BGH-T132-04 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 19 | 14 | 14 | Scheduled | 14/10/2019 | 01/11/2019
TO-19-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 5 | 5 | 5 | Proposed | 14/10/2019 | 18/10/2019
TO-19-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 5 | 5 | 5 | Proposed | 14/10/2019 | 18/10/2019
TO-19-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 3 | 3 | 3 | Scheduled | 14/10/2019 | 16/10/2019
TO-19-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 4 | 4 | 4 | Scheduled | 14/10/2019 | 17/10/2019
TO-19-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2019 | 18/10/2019
TO-19-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 14/10/2019 | 18/10/2019
TO-19-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 14/10/2019 | 18/10/2019
TO-19-MP GIS-220K2-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 332 | 235 | 235 | Proposed | 14/10/2019 | 09/09/2020
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 332 | 235 | 235 | Proposed | 14/10/2019 | 09/09/2020
TO-19-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-LOU-AT2-06 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 17/10/2019 | 18/10/2019
TO-19-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 | 3 | 3 | Scheduled | 19/10/2019 | 23/10/2019
TO-19-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 29 | 19 | 19 | Proposed | 19/10/2019 | 16/11/2019
TO-19-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 4 | 3 | 3 | Scheduled | 20/10/2019 | 23/10/2019
TO-19-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA1-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA1-06 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA2-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA2-05 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-06 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-03 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-04 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-T121-07 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-T121-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 | 5 |  | Reference | 21/10/2019 | 25/10/2019
TO-19-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 2 | 2 | 2 | Reference | 21/10/2019 | 22/10/2019
TO-19-BGH-T142-05 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 10 | 7 |  | Reference | 21/10/2019 | 30/10/2019
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 3 | 3 | 3 | Scheduled | 21/10/2019 | 23/10/2019
TO-19-CLA-110K1-2-07 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-CLA-T2101-07 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Scheduled | 21/10/2019 | 25/10/2019
TO-19-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 21/10/2019 | 23/10/2019
TO-19-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 21/10/2019 | 21/10/2019
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 12 | 9 | 9 | Scheduled | 21/10/2019 | 01/11/2019
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 7 | 4 | 4 | Proposed | 23/10/2019 | 29/10/2019
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 7 | 4 | 4 | Proposed | 23/10/2019 | 29/10/2019
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 7 | 4 | 4 | Reference (Proposed) | 23/10/2019 | 29/10/2019
TO-19-CBT-INC-1-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 70 | 47 | 47 | Proposed | 23/10/2019 | 31/12/2019
TO-19-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 23/10/2019 | 23/10/2019
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 24/10/2019 | 25/10/2019
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 24/10/2019 | 25/10/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 2 | 2 | Proposed | 24/10/2019 | 25/10/2019
TO-19-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 0 | 0 | Scheduled | 26/10/2019 | 26/10/2019
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 3 | 3 | 3 | Scheduled | 29/10/2019 | 31/10/2019
TO-19-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 8 | 6 | 6 | Scheduled | 29/10/2019 | 05/11/2019
TO-19-BGH-110SA1-04 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-110SA2-04 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-05 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T121-05 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T132-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T142-04 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 1 | 1 | 1 | Reference | 30/10/2019 | 30/10/2019
TO-19-CLA-110K1-2-06 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-CLA-T2101-04 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 4 | 2 | 2 | Proposed | 01/11/2019 | 04/11/2019
TO-19-ATE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | November | November
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-19-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | Unknown | 20 | Planned | November | November
TO-19-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 3 | 2 | 2 | Scheduled | 14/11/2019 | 16/11/2019
TO-19-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 2 | 2 |  | Proposed | 14/11/2019 | 15/11/2019
TO-19-MP-T4002-03 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 2 | 2 | 2 | Proposed | 14/11/2019 | 15/11/2019
TO-19-BYH-BVK-1-04 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 1 | 1 | 1 | Tentative | 15/11/2019 | 15/11/2019
TO-19-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 1 | 1 | Proposed | 17/11/2019 | 18/11/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 1 | 1 | Proposed | 17/11/2019 | 18/11/2019
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | Unknown | 5 | Planned | November | November
TO-19-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-MP-PRO-1-06 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown |  | Planned | November | November
TO-19-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-110K2-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-CDU-1-03 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-110 kV B1/B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1-B2 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-DMY-MAC-1-07 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-IA-MAC-1-08 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-MAC-110SA2-04 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-MAC-T142-08 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 2 | 0 | 0 | Reference | 30/11/2019 | 01/12/2019
TO-19-CLA-MAC-1-06 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 02/12/2019 | 03/12/2019

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-MP-PRO-1-04 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 143 | 101 | 101 | Scheduled | 03/06/2019 | 23/10/2019
TO-19-MP-PRO-1-03 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 170 | 119 |  | Scheduled | 03/06/2019 | 19/11/2019
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 143 | 101 | 101 | Scheduled | 03/06/2019 | 23/10/2019
TO-19-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 138 | 98 | 98 | Scheduled | 01/07/2019 | 15/11/2019
TO-19-MTN-MUN-2-03 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 18 | 12 | 12 | Scheduled | 16/08/2019 | 02/09/2019
TO-19-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 18 | 12 | 12 | Reference | 16/08/2019 | 02/09/2019
TO-19-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/09/2019 | 06/09/2019
TO-19-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 4 | 4 | 4 | Reference | 03/09/2019 | 06/09/2019
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 05/09/2019 | 05/09/2019
TO-19-ATE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 89 | 62 | 62 | Scheduled | 06/09/2019 | 03/12/2019
TO-19-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-MP-PRO-1-02 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 3 | 2 | 2 | Scheduled | 08/09/2019 | 10/09/2019
TO-19-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 |  | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 5 | 5 | 5 | Reference | 09/09/2019 | 13/09/2019
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-DSN-MP GIS-1-06 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 11 | 7 | 7 | Scheduled | 14/09/2019 | 24/09/2019
TO-19-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 4 | 4 |  | Scheduled | 23/09/2019 | 26/09/2019
TO-19-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Scheduled | 23/09/2019 | 27/09/2019
TO-19-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 1 | 1 | 1 | Scheduled | 24/09/2019 | 24/09/2019
TO-19-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 64 | 45 | 45 | Proposed | 27/09/2019 | 29/11/2019
TO-19-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2019 | 04/10/2019
TO-19-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 4 | 4 |  | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 4 | 4 | 4 | Scheduled | 30/09/2019 | 03/10/2019
TO-19-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | 4 | 4 | 4 | Reference | 30/09/2019 | 03/10/2019
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 12 | 10 |  | Scheduled | 30/09/2019 | 11/10/2019
TO-19-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-T2102-03 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 3 | 3 | 3 | Proposed | 02/10/2019 | 04/10/2019
TO-19-BVK-T2102-04 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Proposed | 08/10/2019 | 09/10/2019
TO-19-BVK-COT-1-03 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 1 | 1 | 1 | Proposed | 10/10/2019 | 10/10/2019
TO-19-BVK-COT-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-MP GIS-220K2-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Scheduled | 14/10/2019 | 15/10/2019
TO-19-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 1 | 1 | 1 | Scheduled | 16/10/2019 | 16/10/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 17/10/2019 | 18/10/2019
TO-19-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 21/10/2019 | 21/10/2019
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 24/10/2019 | 25/10/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 2 | 2 | Proposed | 24/10/2019 | 25/10/2019
TO-19-ATE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | November | November
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 2 | 2 |  | Proposed | 14/11/2019 | 15/11/2019
TO-19-MP-T4002-03 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | 2 | 2 | 2 | Proposed | 14/11/2019 | 15/11/2019
TO-19-BYH-BVK-1-04 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 1 | 1 | 1 | Tentative | 15/11/2019 | 15/11/2019
TO-19-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-MP-PRO-1-06 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | 2 | 2 | 2 | Proposed | 18/11/2019 | 19/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | November | November
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 1 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 113 | 80 | 80 | Scheduled | 21/06/2019 | 11/10/2019
TO-19-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA1-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-110SA2-03 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 103 | 72 | 72 | Scheduled | 21/06/2019 | 01/10/2019
TO-19-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 103 | 72 | 72 | Reference | 21/06/2019 | 01/10/2019
TO-19-WEX-T141-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 103 | 72 | 72 | Reference | 21/06/2019 | 01/10/2019
TO-19-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 3 | 3 | Scheduled | 29/08/2019 | 02/09/2019
TO-19-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 |  | Scheduled | 02/09/2019 | 06/09/2019
TO-19-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 11 | 9 | 9 | Scheduled | 03/09/2019 | 13/09/2019
TO-19-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 11/09/2019 | 12/09/2019
TO-19-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 16/09/2019 | 27/09/2019
TO-19-ARK-BEG-1-02 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 4 | 4 | 4 | Proposed | 23/09/2019 | 26/09/2019
TO-19-ARK-CKM GIS-1-02 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 2 | 2 | 2 | Proposed | 03/10/2019 | 04/10/2019
TO-19-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-110SA1-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-110SA2-04 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 2 | 2 | 2 | Proposed | 09/10/2019 | 10/10/2019
TO-19-WEX-T141-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 09/10/2019 | 10/10/2019
TO-19-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-GI-WEX-1-07 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 1 | 1 | 1 | Proposed | 11/10/2019 | 11/10/2019
TO-19-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 14/10/2019 | 18/10/2019
TO-19-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 21/10/2019 | 23/10/2019
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-19-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown |  | Planned | November | November
TO-19-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 20 | Planned | November | November
TO-19-GI-WEX-1-05 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | Unknown | 20 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 174 | 121 | 121 | Scheduled | 02/05/2019 | 22/10/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 174 | 121 | 121 | Scheduled | 02/05/2019 | 22/10/2019
TO-19-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 174 | 121 | 121 | Reference | 02/05/2019 | 22/10/2019
TO-19-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 174 | 121 |  | Scheduled | 02/05/2019 | 22/10/2019
TO-19-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-MOY-110SA1-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-MOY-110SA2-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-LET-110SA1-2-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA2-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 110 | 76 | 76 | Scheduled | 29/05/2019 | 15/09/2019
TO-19-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 110 | 76 | 76 | Reference | 29/05/2019 | 15/09/2019
TO-19-LET-T142-03 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 46 | 31 | 31 | Reference | 01/08/2019 | 15/09/2019
TO-19-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 02/09/2019 | 02/09/2019
TO-19-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 4 | 4 | 4 | Scheduled | 02/09/2019 | 05/09/2019
TO-19-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 10 | 8 | 8 | Scheduled | 02/09/2019 | 11/09/2019
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 5 | 5 |  | Scheduled | 16/09/2019 | 20/09/2019
TO-19-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-110SA1-2-SA2-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LET-T142-04 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 1 | 1 | 1 | Reference | 16/09/2019 | 16/09/2019
TO-19-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 4 | 4 | 4 | Scheduled | 16/09/2019 | 19/09/2019
TO-19-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 4 | 4 | 4 | Reference | 16/09/2019 | 19/09/2019
TO-19-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-2-SA1-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-2-SA2-04 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 17/09/2019 | 18/09/2019
TO-19-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 | 2 | Reference | 17/09/2019 | 18/09/2019
TO-19-SRA-T2102-01 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | 1 | 1 | 1 | Scheduled | 20/09/2019 | 20/09/2019
TO-19-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 3 | 3 | 3 | Scheduled | 23/09/2019 | 25/09/2019
TO-19-GAL-SAL-1-04 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2019 | 23/09/2019
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 14 | 10 |  | Scheduled | 24/09/2019 | 07/10/2019
TO-19-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-KNY-UGL-1-02 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 30/09/2019 | 04/10/2019
TO-19-UGL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 5 | 5 | 5 | Proposed | 30/09/2019 | 04/10/2019
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 14 | 10 | 10 | Proposed | 03/10/2019 | 16/10/2019
TO-19-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 7 | 5 | 5 | Proposed | 07/10/2019 | 13/10/2019
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-CSH-1-06 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 14/10/2019 | 25/10/2019
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 12 | 10 | 10 | Reference (Proposed) | 14/10/2019 | 25/10/2019
TO-19-BIN-TIV-1-04 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 12 | 10 | 10 | Proposed | 14/10/2019 | 25/10/2019
TO-19-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2019 | 18/10/2019
TO-19-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 14/10/2019 | 18/10/2019
TO-19-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Scheduled | 21/10/2019 | 25/10/2019
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 12 | 9 | 9 | Scheduled | 21/10/2019 | 01/11/2019
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 7 | 4 | 4 | Proposed | 23/10/2019 | 29/10/2019
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 7 | 4 | 4 | Proposed | 23/10/2019 | 29/10/2019
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 7 | 4 | 4 | Reference (Proposed) | 23/10/2019 | 29/10/2019
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | Unknown | 5 | Planned | November | November

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-LA-RIC-1-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-1 | 6 | 5 | 5 | Reference | 02/09/2019 | 07/09/2019
TO-19-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-LA-RIC-2-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 5 | 5 | 5 | Reference | 09/09/2019 | 13/09/2019
TO-19-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Scheduled | 10/09/2019 | 12/09/2019
TO-19-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 5 | 5 |  | Scheduled | 16/09/2019 | 20/09/2019
TO-19-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-LOU-AT2-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 28 | 20 |  | Scheduled | 18/09/2019 | 15/10/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 9 | 7 | 7 | Scheduled | 18/09/2019 | 26/09/2019
TO-19-LOU-TAN-2-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 28 | 20 | 20 | Scheduled | 18/09/2019 | 15/10/2019
TO-19-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 3 | 2 | 2 | Scheduled | 19/09/2019 | 21/09/2019
TO-19-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 23/09/2019 | 27/09/2019
TO-19-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 23/09/2019 | 23/09/2019
TO-19-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2019 | 23/09/2019
TO-19-SOM,T-SH-1-02 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Proposed | 23/09/2019 | 23/09/2019
TO-19-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2019 | 23/09/2019
TO-19-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 14 | 10 |  | Scheduled | 24/09/2019 | 07/10/2019
TO-19-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 3 | 3 | 3 | Scheduled | 30/09/2019 | 02/10/2019
TO-19-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 8 | 6 | 6 | Scheduled | 03/10/2019 | 10/10/2019
TO-19-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 07/10/2019 | 07/10/2019
TO-19-SOM-T142-05 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 4 | 4 | Reference | 07/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-06 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-SH-1-06 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 07/10/2019 | 07/10/2019
TO-19-SOM,T-SOM-1-05 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 4 | 4 | Scheduled | 07/10/2019 | 11/10/2019
TO-19-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 5 | 3 | 3 | Scheduled | 11/10/2019 | 15/10/2019
TO-19-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 0 | 0 | Reference | 11/10/2019 | 11/10/2019
TO-19-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-SOM,T-SH-1-01 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 11 | 7 | 7 | Scheduled | 11/10/2019 | 22/10/2019
TO-19-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 0 | 0 | Scheduled | 11/10/2019 | 11/10/2019
TO-19-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 3 | 3 | 3 | Scheduled | 14/10/2019 | 16/10/2019
TO-19-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-LOU-AT2-06 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 2 | 2 | Proposed | 16/10/2019 | 17/10/2019
TO-19-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 29 | 19 | 19 | Proposed | 19/10/2019 | 16/11/2019
TO-19-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 1 | 1 | 1 | Reference | 23/10/2019 | 23/10/2019
TO-19-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 1 | 1 | Proposed | 17/11/2019 | 18/11/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 1 | 1 | Proposed | 17/11/2019 | 18/11/2019

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 166 | 116 | 116 | Scheduled | 10/05/2019 | 22/10/2019
TO-19-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 85 | 60 | 60 | Scheduled | 25/06/2019 | 17/09/2019
TO-19-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 28 | 20 | 20 | Scheduled | 06/08/2019 | 02/09/2019
TO-19-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 28 | 20 | 20 | Scheduled | 06/08/2019 | 02/09/2019
TO-19-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 02/09/2019 | 04/09/2019
TO-19-SHL-T2015-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 4 | 4 | 4 | Scheduled | 02/09/2019 | 05/09/2019
TO-19-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 03/09/2019 | 06/09/2019
TO-19-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 2 | 2 | 2 | Scheduled | 03/09/2019 | 04/09/2019
TO-19-FIN GIS-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2103 | 5 | 5 | 5 | Scheduled | 09/09/2019 | 13/09/2019
TO-19-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 09/09/2019 | 11/09/2019
TO-19-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-CLG-110K2-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 12/09/2019 | 13/09/2019
TO-19-DSN-MP GIS-1-06 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 11 | 7 | 7 | Scheduled | 14/09/2019 | 24/09/2019
TO-19-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 16/09/2019 | 17/09/2019
TO-19-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 16/09/2019 | 16/09/2019
TO-19-FIN GIS-110K2-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 5 | 5 | 5 | Scheduled | 16/09/2019 | 20/09/2019
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | Unknown | Unknown | 45 | Reference (Planned) | September | November
TO-19-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 3 | 3 | 3 | Scheduled | 16/09/2019 | 18/09/2019
TO-19-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | 5 | 3 | 3 | Scheduled | 19/09/2019 | 23/09/2019
TO-19-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | 5 | 3 | 3 | Scheduled | 19/09/2019 | 23/09/2019
TO-19-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 3 | 2 | 2 | Scheduled | 19/09/2019 | 21/09/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 57 | 40 | 40 | Proposed | 23/09/2019 | 18/11/2019
TO-19-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 64 | 45 |  | Proposed | 26/09/2019 | 28/11/2019
TO-19-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 1 | 1 | Proposed | 27/09/2019 | 27/09/2019
TO-19-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 1 | 1 | 1 | Proposed | 30/09/2019 | 30/09/2019
TO-19-220 kV A1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-220 kV B1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Proposed | 30/09/2019 | 01/10/2019
TO-19-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 12 | 10 | 10 | Proposed | 30/09/2019 | 11/10/2019
TO-19-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 1 | 1 | 1 | Scheduled | 30/09/2019 | 30/09/2019
TO-19-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 12 | 10 |  | Scheduled | 30/09/2019 | 11/10/2019
TO-19-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 3 | 3 | 3 | Scheduled | 01/10/2019 | 03/10/2019
TO-19-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Proposed | 02/10/2019 | 02/10/2019
TO-19-ARK-CKM GIS-1-02 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 2 | 2 | 2 | Proposed | 03/10/2019 | 04/10/2019
TO-19-CLE-CDU-1-02 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 1 | 1 | 1 | Scheduled | 09/10/2019 | 09/10/2019
TO-19-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-220 kV B2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 2 | 2 | 2 | Proposed | 10/10/2019 | 11/10/2019
TO-19-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 3 | 3 | 3 | Scheduled | 14/10/2019 | 16/10/2019
TO-19-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 4 | 4 | 4 | Scheduled | 14/10/2019 | 17/10/2019
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 332 | 235 | 235 | Proposed | 14/10/2019 | 09/09/2020
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 332 | 235 | 235 | Proposed | 14/10/2019 | 09/09/2020
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 8 | 5 | 5 | Scheduled | 22/10/2019 | 29/10/2019
TO-19-CBT-INC-1-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 70 | 47 | 47 | Proposed | 23/10/2019 | 31/12/2019
TO-19-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2019 | 23/10/2019
TO-19-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 24/10/2019 | 25/10/2019
TO-19-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 8 | 6 | 6 | Scheduled | 29/10/2019 | 05/11/2019
TO-19-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 4 | 2 | 2 | Proposed | 01/11/2019 | 04/11/2019
TO-19-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 3 | 2 | 2 | Scheduled | 14/11/2019 | 16/11/2019
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 2 | Planned | November | November
TO-19-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | November | November
TO-19-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-110K2-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-CDU-1-03 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 60 | 44 | 44 | Scheduled | 12/08/2019 | 10/10/2019
TO-19-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 13 | 9 | 9 | Scheduled | 21/08/2019 | 02/09/2019
TO-19-110 kV A2 @ CRO-01 | BUSBAR SECTION - COOLROE 110-COOLROE 110-110A2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 2 | 2 | 2 | Scheduled | 02/09/2019 | 03/09/2019
TO-19-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 02/09/2019 | 06/09/2019
TO-19-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 02/09/2019 | 03/09/2019
TO-19-CUL-KRA-1-05 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 11 | 9 | 9 | Scheduled | 03/09/2019 | 13/09/2019
TO-19-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 3 | 3 | 3 | Scheduled | 03/09/2019 | 05/09/2019
TO-19-RAF-T2102-03 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 5 | 3 | 3 | Scheduled | 06/09/2019 | 10/09/2019
TO-19-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 12 | 10 | 10 | Scheduled | 09/09/2019 | 20/09/2019
TO-19-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2019 | 12/09/2019
TO-19-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Scheduled | 11/09/2019 | 12/09/2019
TO-19-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 3 | 3 | 3 | Scheduled | 11/09/2019 | 13/09/2019
TO-19-CD-MAC-1-04 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 13/09/2019 | 13/09/2019
TO-19-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 3 |  | Scheduled | 13/09/2019 | 17/09/2019
TO-19-MAC-110SA1-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 1 | 1 | 1 | Scheduled | 13/09/2019 | 13/09/2019
TO-19-KBY-KRA-1-03 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Tentative | 18/09/2019 | 20/09/2019
TO-19-DMY-MAC-1-06 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 5 | 5 | 5 | Proposed | 23/09/2019 | 27/09/2019
TO-19-MAC-110SA2-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 2 | 2 | 2 | Scheduled | 23/09/2019 | 24/09/2019
TO-19-MAC-T142-07 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 2 | 2 | 2 | Reference | 23/09/2019 | 24/09/2019
TO-19-110 kV A1 @ MID-01 | BUSBAR SECTION - MIDLETON 110-MIDLETON 110-110A1 | 2 | 2 | 2 | Proposed | 23/09/2019 | 24/09/2019
TO-19-MID-110SA1-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 2 | 2 | 2 | Proposed | 23/09/2019 | 24/09/2019
TO-19-MID-T141-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 23/09/2019 | 24/09/2019
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Proposed | 01/10/2019 | 04/10/2019
TO-19-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-KRA-1-08 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-LPT-1-04 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-LPT-T2002-04 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Proposed | 07/10/2019 | 11/10/2019
TO-19-BGH-T132-04 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 19 | 14 | 14 | Scheduled | 14/10/2019 | 01/11/2019
TO-19-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 5 | 5 | 5 | Proposed | 14/10/2019 | 18/10/2019
TO-19-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 5 | 5 | 5 | Proposed | 14/10/2019 | 18/10/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 17/10/2019 | 18/10/2019
TO-19-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 | 3 | 3 | Scheduled | 19/10/2019 | 23/10/2019
TO-19-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 4 | 3 | 3 | Scheduled | 20/10/2019 | 23/10/2019
TO-19-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA1-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA1-06 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA2-03 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-110SA2-05 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-03 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-04 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-CLA-1-06 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 10 | 7 | 7 | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-T121-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 2 | 2 | 2 | Scheduled | 21/10/2019 | 22/10/2019
TO-19-BGH-T121-07 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 | 5 |  | Reference | 21/10/2019 | 25/10/2019
TO-19-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 2 | 2 | 2 | Reference | 21/10/2019 | 22/10/2019
TO-19-BGH-T142-05 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 10 | 7 |  | Reference | 21/10/2019 | 30/10/2019
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 3 | 3 | 3 | Scheduled | 21/10/2019 | 23/10/2019
TO-19-CLA-110K1-2-07 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-CLA-T2101-07 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 10 | 7 |  | Scheduled | 21/10/2019 | 30/10/2019
TO-19-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 0 | 0 | Scheduled | 26/10/2019 | 26/10/2019
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 3 | 3 | 3 | Scheduled | 29/10/2019 | 31/10/2019
TO-19-BGH-110SA1-04 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-110SA2-04 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-CLA-1-05 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T121-05 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T132-03 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-BGH-T142-04 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 1 | 1 | 1 | Reference | 30/10/2019 | 30/10/2019
TO-19-CLA-110K1-2-06 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-CLA-T2101-04 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 1 | 1 | 1 | Scheduled | 30/10/2019 | 30/10/2019
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown |  | Planned | November | November
TO-19-110 kV B1/B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1-B2 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | Unknown | 1 | Planned | November | November
TO-19-DMY-MAC-1-07 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-IA-MAC-1-08 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-MAC-110SA2-04 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 2 | 0 | 0 | Scheduled | 30/11/2019 | 01/12/2019
TO-19-MAC-T142-08 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 2 | 0 | 0 | Reference | 30/11/2019 | 01/12/2019
TO-19-CLA-MAC-1-06 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 02/12/2019 | 03/12/2019