## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2019 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 205 | 143 | 143 | Scheduled | 02/05/2019 | 22/11/2019
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 178 | 123 | 123 | Tentative | 10/05/2019 | 03/11/2019
TO-19-MOY-110SA1-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-110SA2-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 197 | 138 | 138 | Reference | 10/05/2019 | 22/11/2019
TO-19-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-ATE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 89 | 62 | 62 | Scheduled | 06/09/2019 | 03/12/2019
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | 64 | 45 | 45 | Reference | 16/09/2019 | 18/11/2019
TO-19-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 64 | 45 |  | Scheduled | 26/09/2019 | 28/11/2019
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 61 | 44 | 44 | Scheduled | 30/09/2019 | 29/11/2019
TO-19-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 42 | 29 | 29 | Scheduled | 18/10/2019 | 28/11/2019
TO-19-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 42 | 29 | 29 | Scheduled | 18/10/2019 | 28/11/2019
TO-19-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 40 | 27 | 27 | Scheduled | 18/10/2019 | 26/11/2019
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 12 | 9 | 9 | Scheduled | 21/10/2019 | 01/11/2019
TO-19-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 7 | 4 | 4 | Scheduled | 26/10/2019 | 01/11/2019
TO-19-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 7 | 4 | 4 | Scheduled | 26/10/2019 | 01/11/2019
TO-19-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 7 | 4 | 4 | Reference | 26/10/2019 | 01/11/2019
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 11 | 9 | 9 | Reference | 29/10/2019 | 08/11/2019
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 11 | 9 | 9 | Reference | 29/10/2019 | 08/11/2019
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 18 | 14 | 14 | Reference | 29/10/2019 | 15/11/2019
TO-19-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 30/10/2019 | 01/11/2019
TO-19-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 14 | 10 | 10 | Scheduled | 30/10/2019 | 12/11/2019
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 04/11/2019 | 07/11/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Scheduled | 04/11/2019 | 08/11/2019
TO-19-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 1 | 1 | 1 | Scheduled | 04/11/2019 | 04/11/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 9 | 7 | 7 | Scheduled | 04/11/2019 | 12/11/2019
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 338 | 240 | 240 | Scheduled | 04/11/2019 | 06/10/2020
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 338 | 240 | 240 | Scheduled | 04/11/2019 | 06/10/2020
TO-19-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-MLN-T122-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Tentative | 11/11/2019 | 15/11/2019
TO-19-AD-ST101-03 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-AD-T2102-03 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 12 | 10 | 10 | Scheduled | 11/11/2019 | 22/11/2019
TO-19-DSN-220K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 3 | 3 |  | Scheduled | 11/11/2019 | 13/11/2019
TO-19-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 3 | 3 | 3 | Scheduled | 12/11/2019 | 14/11/2019
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 12/11/2019 | 12/11/2019
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Scheduled | 12/11/2019 | 12/11/2019
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Proposed | 18/11/2019 | 22/11/2019
TO-19-CKM GIS-DSN-1-03 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 4 | 4 | 4 | Proposed | 18/11/2019 | 21/11/2019
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 18/11/2019 | 22/11/2019
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 19/11/2019 | 22/11/2019
TO-19-CLA-110K1-2-06 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Proposed | 22/11/2019 | 22/11/2019
TO-19-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 3 | 3 | 3 | Reference (Proposed) | 25/11/2019 | 27/11/2019
TO-19-CKM-R2001-02 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 2 | 2 | 2 | Scheduled | 25/11/2019 | 26/11/2019
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-MAC-1-07 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-T2102-03 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Proposed | 25/11/2019 | 28/11/2019
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 5 | 5 | 5 | Proposed | 25/11/2019 | 29/11/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 26/11/2019 | 27/11/2019
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-110K2-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-CDU-1-03 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 7 | 5 | 5 | Proposed | 27/11/2019 | 03/12/2019
TO-19-GLR-MOY-1-03 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-GLR-MOY-1-04 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-MOY-110SA1-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-110SA1-05 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-110SA2-05 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-110SA2-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-CAP1-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 27/11/2019 | 29/11/2019
TO-19-MOY-T141-03 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 27/11/2019 | 05/12/2019
TO-19-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-CLA-T2101-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 1 | 1 | 1 | Scheduled | 28/11/2019 | 28/11/2019
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 28/11/2019 | 28/11/2019
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Proposed | 29/11/2019 | 29/11/2019
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 1 | 1 | 1 | Scheduled | 29/11/2019 | 29/11/2019
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 29/11/2019 | 29/11/2019
TO-19-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 1 | 1 | 1 | Proposed | 29/11/2019 | 29/11/2019
TO-19-AD-KRA-1-09 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 0 | 0 | Proposed | 30/11/2019 | 01/12/2019
TO-19-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 3 | 3 | 3 | Proposed | 09/12/2019 | 11/12/2019

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-MP-T4202-01 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 170 | 119 | 119 | Scheduled | 03/06/2019 | 19/11/2019
TO-19-ATE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 89 | 62 | 62 | Scheduled | 06/09/2019 | 03/12/2019
TO-19-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 7 | 4 | 4 | Scheduled | 26/10/2019 | 01/11/2019
TO-19-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 7 | 4 | 4 | Scheduled | 26/10/2019 | 01/11/2019
TO-19-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 7 | 4 | 4 | Reference | 26/10/2019 | 01/11/2019
TO-19-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 14 | 10 | 10 | Scheduled | 30/10/2019 | 12/11/2019
TO-19-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 12/11/2019 | 12/11/2019
TO-19-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Scheduled | 12/11/2019 | 12/11/2019
TO-19-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-MP-T4202-03 | TRANSFORMER - MONEYPOINT 400-MONEYPOINT 220-T4202 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 26/11/2019 | 27/11/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 1 | 1 | 1 | Scheduled | 28/11/2019 | 28/11/2019
TO-19-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 28/11/2019 | 28/11/2019
TO-19-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 1 | 1 | 1 | Scheduled | 29/11/2019 | 29/11/2019
TO-19-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 29/11/2019 | 29/11/2019
TO-19-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 1 | 1 | 1 | Proposed | 29/11/2019 | 29/11/2019

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 18 | 14 | 14 | Reference | 29/10/2019 | 15/11/2019
TO-19-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 30/10/2019 | 01/11/2019
TO-19-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 1 | 1 | 1 | Scheduled | 04/11/2019 | 04/11/2019
TO-19-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 3 | 3 |  | Scheduled | 11/11/2019 | 13/11/2019
TO-19-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 5 | 5 | 5 | Proposed | 25/11/2019 | 29/11/2019

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 205 | 143 | 143 | Scheduled | 02/05/2019 | 22/11/2019
TO-19-MOY-110SA1-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-110SA2-03 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 197 | 138 | 138 | Reference | 10/05/2019 | 22/11/2019
TO-19-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 197 | 138 | 138 | Scheduled | 10/05/2019 | 22/11/2019
TO-19-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 12 | 9 | 9 | Scheduled | 21/10/2019 | 01/11/2019
TO-19-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 11 | 9 | 9 | Reference | 29/10/2019 | 08/11/2019
TO-19-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 11 | 9 | 9 | Reference | 29/10/2019 | 08/11/2019
TO-19-BIN-TVB-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Scheduled | 29/10/2019 | 08/11/2019
TO-19-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 12 | 10 | 10 | Scheduled | 11/11/2019 | 22/11/2019
TO-19-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 18/11/2019 | 22/11/2019
TO-19-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 19/11/2019 | 22/11/2019
TO-19-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 19/11/2019 | 22/11/2019
TO-19-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 3 | 3 | 3 | Reference (Proposed) | 25/11/2019 | 27/11/2019
TO-19-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 7 | 5 | 5 | Proposed | 27/11/2019 | 03/12/2019
TO-19-GLR-MOY-1-04 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-GLR-MOY-1-03 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-110SA1-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-110SA1-05 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-110SA2-04 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-110SA2-05 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-MOY-CAP1-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-T141-03 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 27/11/2019 | 05/12/2019
TO-19-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 27/11/2019 | 29/11/2019
TO-19-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Proposed | 27/11/2019 | 29/11/2019
TO-19-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Proposed | 27/11/2019 | 05/12/2019
TO-19-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 3 | 3 | 3 | Proposed | 09/12/2019 | 11/12/2019

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 42 | 29 | 29 | Scheduled | 18/10/2019 | 28/11/2019
TO-19-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 42 | 29 | 29 | Scheduled | 18/10/2019 | 28/11/2019
TO-19-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 40 | 27 | 27 | Scheduled | 18/10/2019 | 26/11/2019
TO-19-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 9 | 7 | 7 | Scheduled | 04/11/2019 | 12/11/2019
TO-19-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-MLN-T122-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 2 | 2 | 2 | Scheduled | 07/11/2019 | 08/11/2019
TO-19-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-LOU-AT3-05 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 178 | 123 | 123 | Tentative | 10/05/2019 | 03/11/2019
TO-19-FIN-T141-02 | DISTRIBUTION TRANSFORMER - FINGLAS 110-FINGLAS 38-T141 | 64 | 45 | 45 | Reference | 16/09/2019 | 18/11/2019
TO-19-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 64 | 45 |  | Scheduled | 26/09/2019 | 28/11/2019
TO-19-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 61 | 44 | 44 | Scheduled | 30/09/2019 | 29/11/2019
TO-19-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 18 | 14 | 14 | Scheduled | 29/10/2019 | 15/11/2019
TO-19-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Scheduled | 04/11/2019 | 08/11/2019
TO-19-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 338 | 240 | 240 | Scheduled | 04/11/2019 | 06/10/2020
TO-19-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 338 | 240 | 240 | Scheduled | 04/11/2019 | 06/10/2020
TO-19-DSN-220K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 11/11/2019 | 15/11/2019
TO-19-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 16 | 12 | 12 | Scheduled | 11/11/2019 | 26/11/2019
TO-19-CKM GIS-DSN-1-03 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 4 | 4 | 4 | Proposed | 18/11/2019 | 21/11/2019
TO-19-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 2 | 2 | 2 | Scheduled | 18/11/2019 | 19/11/2019
TO-19-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | 2 | 2 | 2 | Proposed | 19/11/2019 | 20/11/2019
TO-19-CKM-R2001-02 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 2 | 2 | 2 | Scheduled | 25/11/2019 | 26/11/2019
TO-19-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Proposed | 25/11/2019 | 26/11/2019
TO-19-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Proposed | 25/11/2019 | 28/11/2019
TO-19-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-110K2-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLG-CDU-1-03 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-19-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 04/11/2019 | 07/11/2019
TO-19-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Tentative | 11/11/2019 | 15/11/2019
TO-19-AD-ST101-03 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-AD-T2102-03 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 1 | 1 | 1 | Scheduled | 11/11/2019 | 11/11/2019
TO-19-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 3 | 3 | 3 | Scheduled | 12/11/2019 | 14/11/2019
TO-19-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Proposed | 18/11/2019 | 22/11/2019
TO-19-CLA-110K1-2-06 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Proposed | 22/11/2019 | 22/11/2019
TO-19-CLA-110K1-2-05 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-CKN-1-05 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-MAC-1-07 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-T2102-03 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 3 | 3 | 3 | Proposed | 25/11/2019 | 27/11/2019
TO-19-CLA-CKN-1-06 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Proposed | 26/11/2019 | 27/11/2019
TO-19-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Proposed | 27/11/2019 | 28/11/2019
TO-19-CLA-T2101-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 2 | 2 | 2 | Scheduled | 28/11/2019 | 29/11/2019
TO-19-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Proposed | 29/11/2019 | 29/11/2019
TO-19-AD-KRA-1-09 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 0 | 0 | Proposed | 30/11/2019 | 01/12/2019