## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2020 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 3 | 1 | 1 | Tentative | 21/02/2020 | 23/02/2020
TO-20-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 12 | 10 | 10 | Scheduled | 24/02/2020 | 06/03/2020
TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 |  | Scheduled | 24/02/2020 | 28/02/2020
TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 2 | 2 | 2 | Reference | 24/02/2020 | 25/02/2020
TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 156 | 107 | 107 | Scheduled | 24/02/2020 | 28/07/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 61 | 42 | 42 | Scheduled | 24/02/2020 | 24/04/2020
TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 46 | 33 | 33 | Scheduled | 24/02/2020 | 09/04/2020
TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 88 | 60 | 60 | Scheduled | 24/02/2020 | 21/05/2020
TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 152 | 105 | 105 | Scheduled | 24/02/2020 | 24/07/2020
TO-20-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 89 | 61 | 61 | Scheduled | 24/02/2020 | 22/05/2020
TO-20-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 136 | 93 | 93 | Scheduled | 24/02/2020 | 08/07/2020
TO-20-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 136 | 93 | 93 | Scheduled | 24/02/2020 | 08/07/2020
TO-20-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 3 | 3 | 3 | Reference | 24/02/2020 | 26/02/2020
TO-20-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 7 | 5 | 5 | Scheduled | 25/02/2020 | 02/03/2020
TO-20-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 1 | 1 | 1 | Reference | 25/02/2020 | 25/02/2020
TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-CAP1-03 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 2 | 2 | 2 | Reference | 25/02/2020 | 26/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 86 | 58 | 58 | Scheduled | 26/02/2020 | 21/05/2020
TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 10 | 8 | 8 | Scheduled | 26/02/2020 | 06/03/2020
TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 16 | 12 | 12 | Scheduled | 26/02/2020 | 12/03/2020
TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 124 | 85 | 85 | Scheduled | 02/03/2020 | 03/07/2020
TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/03/2020 | 06/03/2020
TO-20-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference | 02/03/2020 | 10/03/2020
TO-20-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 19 | 14 | 14 | Scheduled | 02/03/2020 | 20/03/2020
TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 7 | 5 | 5 | Scheduled | 04/03/2020 | 10/03/2020
TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 3 | 3 | Scheduled | 04/03/2020 | 06/03/2020
TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/03/2020 | 13/03/2020
TO-20-220 kV A1 @ CKM-02 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 1 | 1 | 1 | Scheduled | 09/03/2020 | 09/03/2020
TO-20-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 9 | 9 | Scheduled | 09/03/2020 | 20/03/2020
TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-MAC-110SA2-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 22 | 15 | 15 | Scheduled | 09/03/2020 | 30/03/2020
TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 117 | 80 | 80 | Scheduled | 09/03/2020 | 03/07/2020
TO-20-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 117 | 80 | 80 | Reference | 09/03/2020 | 03/07/2020
TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 117 | 80 | 80 | Scheduled | 09/03/2020 | 03/07/2020
TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-RRU-110SA2-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 4 | 4 |  | Reference | 10/03/2020 | 13/03/2020
TO-20-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 2 | 2 | 2 | Scheduled | 12/03/2020 | 13/03/2020
TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 1 | 1 | 1 | Scheduled | 12/03/2020 | 12/03/2020
TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 9 | 6 | 6 | Scheduled | 16/03/2020 | 24/03/2020
TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 30 | 20 | 20 | Scheduled | 18/03/2020 | 16/04/2020
TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 18/03/2020 | 18/03/2020
TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/03/2020 | 19/03/2020
TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2020 | 20/03/2020
TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 19 | 14 | 14 | Scheduled | 23/03/2020 | 10/04/2020
TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 24/03/2020 | 25/03/2020
TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 26/03/2020 | 26/03/2020
TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 26/03/2020 | 02/04/2020
TO-20-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 109 | 75 | 75 | Scheduled | 30/03/2020 | 16/07/2020
TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 2 | Planned | March | March
TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 2 | 2 | 2 | Scheduled | 30/03/2020 | 31/03/2020
TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 01/04/2020 | 02/04/2020
TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Scheduled | 02/04/2020 | 09/04/2020
TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 02/04/2020 | 03/04/2020
TO-20-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 7 | 5 | 5 | Scheduled | 03/04/2020 | 09/04/2020
TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 4 | 4 | Proposed | 06/04/2020 | 10/04/2020
TO-20-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 | 2 | Proposed | 07/04/2020 | 08/04/2020
TO-20-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 08/04/2020 | 09/04/2020
TO-20-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 2 | 2 | 2 | Scheduled | 08/04/2020 | 09/04/2020
TO-20-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 08/04/2020 | 09/04/2020
TO-20-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 | 2 | Proposed | 08/04/2020 | 09/04/2020
TO-20-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 2 | 2 | 2 | Proposed | 08/04/2020 | 09/04/2020
TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Proposed | 09/04/2020 | 09/04/2020
TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 7 | 5 | 5 | Proposed | 14/04/2020 | 20/04/2020
TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 58 | 40 |  | Proposed | 14/04/2020 | 10/06/2020
TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 63 | 43 | 43 | Proposed | 14/04/2020 | 15/06/2020
TO-20-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Proposed | 14/04/2020 | 14/04/2020
TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 72 | 50 | 50 | Proposed | 14/04/2020 | 24/06/2020
TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 7 | 5 | 5 | Proposed | 14/04/2020 | 20/04/2020
TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 10 | 8 | 8 | Proposed | 14/04/2020 | 23/04/2020
TO-20-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 4 | 4 | 4 | Scheduled | 14/04/2020 | 17/04/2020
TO-20-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 1 | 1 | 1 | Proposed | 16/04/2020 | 16/04/2020
TO-20-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 2 | 2 | 2 | Proposed | 16/04/2020 | 17/04/2020
TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 22 | 15 | 15 | Scheduled | 17/04/2020 | 08/05/2020
TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 5 | 5 | 5 | Proposed | 20/04/2020 | 24/04/2020
TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-BUT-T142-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 20/04/2020 | 21/04/2020
TO-20-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 8 | 6 | 6 | Scheduled | 20/04/2020 | 27/04/2020
TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-CSH-TY-1-07 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 4 | 4 | 4 | Scheduled | 20/04/2020 | 23/04/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Proposed | 20/04/2020 | 24/04/2020
TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | Unknown | Unknown | 1 | Planned | April | April
TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 20/04/2020 | 21/04/2020
TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 22/04/2020 | 24/04/2020
TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 2 | 2 | 2 | Scheduled | 22/04/2020 | 23/04/2020
TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 2 | 2 | 2 | Proposed | 22/04/2020 | 23/04/2020
TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | April | April
TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 5 | 3 | 3 | Proposed | 23/04/2020 | 27/04/2020
TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 1 | 1 | 1 | Proposed | 23/04/2020 | 23/04/2020
TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 1 | 1 | 1 | Proposed | 24/04/2020 | 24/04/2020
TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 3 | 3 | 3 | Scheduled | 27/04/2020 | 29/04/2020
TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 5 | 5 | 5 | Proposed | 27/04/2020 | 01/05/2020
TO-20-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 12 | 9 | 9 | Proposed | 27/04/2020 | 08/05/2020
TO-20-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 12 | 9 | 9 | Proposed | 27/04/2020 | 08/05/2020
TO-20-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-110SA2-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 2 | 2 | 2 | Reference | 27/04/2020 | 28/04/2020
TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 2 | 2 | 2 | Proposed | 27/04/2020 | 28/04/2020
TO-20-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-CKM-220K1-2-01 | COUPLER/SECTIONALISING CB - CARRICKMINES 220-CARRICKMINES 220-220K1-2 | 2 | 2 | 2 | Scheduled | 29/04/2020 | 30/04/2020
TO-20-MOY-TAW-2-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | April | May
TO-20-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 1 | 1 | 1 | Proposed | 05/05/2020 | 05/05/2020
TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Proposed | 05/05/2020 | 07/05/2020
TO-20-KLN-TB-1-07 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 3 | 3 | 3 | Proposed | 05/05/2020 | 07/05/2020
TO-20-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 1 | 1 | 1 | Proposed | 06/05/2020 | 06/05/2020
TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 3 | 3 | 3 | Proposed | 06/05/2020 | 08/05/2020
TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 1 | 1 | 1 | Proposed | 06/05/2020 | 06/05/2020
TO-20-KPG-MP GIS-2-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 8 | 6 | 6 | Proposed | 08/05/2020 | 15/05/2020
TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 19 | 15 | 15 | Proposed | 11/05/2020 | 29/05/2020
TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-110SA1-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-110SA2-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 54 | 39 | 39 | Proposed | 11/05/2020 | 03/07/2020
TO-20-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-RRU-110SA1-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-RRU-SKL-1-02 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 6 | 5 | 5 | Proposed | 11/05/2020 | 16/05/2020
TO-20-SKL-110SA1-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-SKL-110SA2-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-SKL-T141-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 12 | 10 | 10 | Proposed | 11/05/2020 | 22/05/2020
TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 8 | 6 | 6 | Proposed | 12/05/2020 | 19/05/2020
TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 8 | 6 | 6 | Proposed | 13/05/2020 | 20/05/2020
TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 13 | 9 | 9 | Proposed | 14/05/2020 | 26/05/2020
TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 36 | 25 | 25 | Proposed | 15/05/2020 | 19/06/2020
TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 18/05/2020 | 22/05/2020
TO-20-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 8 | 6 | 6 | Proposed | 18/05/2020 | 25/05/2020
TO-20-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 2 | 2 | 2 | Proposed | 18/05/2020 | 19/05/2020
TO-20-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 2 | 2 | 2 | Proposed | 20/05/2020 | 21/05/2020
TO-20-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Proposed | 20/05/2020 | 20/05/2020
TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 88 | 60 | 60 | Proposed | 22/05/2020 | 17/08/2020
TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-GI-KKY-1-06 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-110SA1-03 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-110SA1-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-110SA2-03 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-KKY-CAP2-04 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-T142-03 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 25/05/2020 | 27/05/2020
TO-20-KKY-T142-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 142 | 100 | 100 | Reference (Proposed) | 25/05/2020 | 13/10/2020
TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Proposed | 25/05/2020 | 28/05/2020
TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 2 | 2 | 2 | Proposed | 26/05/2020 | 27/05/2020
TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 15 | 10 | 10 | Proposed | 27/05/2020 | 10/06/2020
TO-20-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | June | June
TO-20-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 1 | Planned | June | June
TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 4 | Planned | June | June
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-20-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 9 | Planned | June | June
TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 9 | Planned | June | June
TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 9 | Planned | June | June
TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CLW-KLS-2-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-AGL-DYN-1-03 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 1 | Planned | June | June
TO-20-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | Unknown | Unknown | 14 | Planned | June | July
TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | Unknown | Unknown | 3 | Planned | June | June
TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 15 | Planned | June | July
TO-20-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV B2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 5 | Planned | June | June
TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 4 | Planned | June | June
TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | Unknown | 4 | Planned | June | June
TO-20-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 5 | Planned | June | June
TO-20-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | Unknown | Unknown | 5 | Planned | June | June
TO-20-KPG-TB-2-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown |  | Planned | June | June
TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 2 | Planned | June | June
TO-20-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 20 | Planned | June | July
TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 7 | Planned | June | July
TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 4 | Planned | June | July
TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | Unknown | Unknown | 5 | Planned | June | July
TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | Unknown | Unknown | 5 | Planned | June | July
TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 15 | Planned | June | July
TO-20-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 6 | Planned | June | July
TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown | 2 | Planned | June | July
TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 3 | Planned | June | July
TO-20-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 8 | Planned | June | July
TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 4 | Planned | June | July
TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 4 | Planned | June | July
TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | Unknown | Unknown | 5 | Planned | July | July
TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | July | July
TO-20-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 20 | Planned | July | July
TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | Unknown | 4 | Planned | July | July
TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-BIN-CF-1-05 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | Unknown | 8 | Planned | July | July
TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | Unknown | Unknown | 5 | Planned | July | July
TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 10 | Planned | July | July
TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | Unknown | Unknown | 7 | Reference (Planned) | July | July
TO-20-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | Unknown | Unknown | 7 | Reference (Planned) | July | July
TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 5 | Planned | July | July
TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-MUL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | Unknown | Unknown | 4 | Planned | July | July
TO-20-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | Unknown | Unknown | 4 | Reference (Planned) | July | July
TO-20-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | July | July
TO-20-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 2 | Planned | July | July
TO-20-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 5 | Planned | July | July
TO-20-FIN GIS-T2101-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | Unknown | Unknown | 8 | Planned | July | July
TO-20-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA1-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 12 | Planned | July | July
TO-20-KLN-TB-1-06 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 1 | Planned | July | July
TO-20-220 kV B1/B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 0 | Planned | July | July
TO-20-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 0 | Planned | July | July
TO-20-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 0 | Planned | July | July
TO-20-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 0 | Planned | July | July
TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | Unknown | Unknown | 1 | Planned | July | July
TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 5 | Planned | July | July
TO-20-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA2-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-CAP1-01 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | Unknown | Unknown | 3 | Planned | July | July
TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 1 | Planned | July | July
TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | Unknown | Unknown | 1 | Planned | July | July
TO-20-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 1 | Planned | July | July
TO-20-KLN-TB-1-04 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 0 | Planned | July | December
TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | Unknown | 4 | Planned | July | July
TO-20-CKM GIS-ISH-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | Unknown | 7 | Planned | July | July
TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | Unknown | Unknown | 5 | Planned | July | July
TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown |  | Planned | July | September
TO-20-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 40 | Planned | July | September
TO-20-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | July | July
TO-20-KLN-TB-1-05 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown |  | Planned | July | July
TO-20-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-220K1-2-03 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2003-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 2 | Planned | July | July
TO-20-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | Unknown | Unknown | 1 | Planned | July | July
TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-20-TB-T2102-06 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 1 | Planned | July | July
TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | Unknown | Unknown | 88 | Planned | July | November
TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown | 6 | Planned | July | August
TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 5 | Planned | July | July
TO-20-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-FIN-T2104-08 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 43 | Planned | July | September
TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 43 | Planned | July | September
TO-20-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | Unknown | 5 | Planned | July | August
TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2102-04 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 1 | Planned | July | July
TO-20-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-TB-T2102-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown |  | Planned | July | July
TO-20-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-220 kV A1/A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1-A2 | Unknown | Unknown | 29 | Planned | August | September
TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | Unknown | Unknown | 6 | Planned | August | August
TO-20-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 40 | Planned | August | September
TO-20-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 1 | Planned | August | August
TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 4 | Planned | August | August
TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | August | August
TO-20-CVW-KRA-1-03 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 6 | Planned | August | August
TO-20-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | Unknown | Unknown | 10 | Planned | August | August
TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-20-DMY-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | August | August
TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 2 | Planned | August | August
TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | August | September
TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | Unknown | Unknown | 6 | Planned | August | August
TO-20-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | Unknown | 3 | Reference (Planned) | August | August
TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | August | August
TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | Unknown | Unknown | 2 | Planned | August | August
TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-20-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 13 | Planned | August | September
TO-20-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 10 | Planned | August | August
TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown |  | Planned | August | August
TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 60 | Planned | August | November
TO-20-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 20 | Planned | August | September
TO-20-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 20 | Planned | August | September
TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | Unknown | 1 | Reference (Planned) | August | August
TO-20-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | Unknown | 1 | Reference (Planned) | August | August
TO-20-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 1 | Planned | August | August
TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | Unknown | 1 | Planned | August | August
TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 8 | Planned | August | September
TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-FLA-220K1-2-04 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-20-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 21 | Reference (Planned) | August | September
TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | Unknown | 45 | Planned | August | November
TO-20-AD-ST101-02 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | Unknown | 45 | Planned | August | November
TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | Unknown | Unknown | 5 | Planned | August | September
TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | Unknown | Unknown | 5 | Planned | August | September
TO-20-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | August | September
TO-20-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 2 | Planned | August | September
TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 3 | Planned | August | September
TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 3 | Planned | August | September
TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 55 | Planned | September | November
TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | Unknown | 4 | Planned | September | September
TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 1 | Planned | September | September
TO-20-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | Unknown | Unknown | 8 | Planned | September | September
TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | Unknown | 8 | Planned | September | September
TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | Unknown | Unknown | 5 | Planned | September | September
TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 2 | Planned | September | September
TO-20-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | September | September
TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-20-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 10 | Planned | September | September
TO-20-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | Unknown | 5 | Planned | September | September
TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 15 | Planned | September | October
TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | Unknown | Unknown | 2 | Planned | September | September
TO-20-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN-T2104-05 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV A2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-FIN-T2104-06 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 2 | Planned | September | September
TO-20-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-SRA-2-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-20-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | Unknown | 1 | Planned | September | September
TO-20-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 0 | Planned | September | September
TO-20-FIN-T2104-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 0 | Planned | September | September
TO-20-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | Unknown | Unknown | 43 | Planned | September | November
TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 3 | Planned | September | September
TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-KNR-220K2-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | Unknown | 1 | Planned | October | October
TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | Unknown | Unknown | 1 | Planned | October | October
TO-20-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 10 | Planned | October | October
TO-20-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 2 | Planned | October | October
TO-20-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-110SA1-04 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-110SA2-04 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-T141-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-20-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | Unknown | Unknown |  | Planned | October | October
TO-20-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | Unknown | 10 | Planned | October | November
TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 5 | Planned | November | November
TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 4 | Planned | November | November
TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 3 | Planned | November | November
TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | Unknown | 1 | Planned | November | November
TO-20-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | November | November
TO-20-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-220 kV B1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | Unknown | Unknown | 5 | Planned | November | November
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 88 | 60 | 60 | Scheduled | 24/02/2020 | 21/05/2020
TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 89 | 61 | 61 | Scheduled | 24/02/2020 | 22/05/2020
TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 7 | 5 | 5 | Scheduled | 25/02/2020 | 02/03/2020
TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-CAP1-03 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 2 | 2 | 2 | Reference | 25/02/2020 | 26/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 86 | 58 | 58 | Scheduled | 26/02/2020 | 21/05/2020
TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 16 | 12 | 12 | Scheduled | 26/02/2020 | 12/03/2020
TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/03/2020 | 06/03/2020
TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 7 | 5 | 5 | Scheduled | 04/03/2020 | 10/03/2020
TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/03/2020 | 13/03/2020
TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 4 | 4 |  | Reference | 10/03/2020 | 13/03/2020
TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 26/03/2020 | 26/03/2020
TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 26/03/2020 | 02/04/2020
TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 01/04/2020 | 02/04/2020
TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 02/04/2020 | 03/04/2020
TO-20-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Proposed | 20/04/2020 | 24/04/2020
TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown | 2 | Planned | April | April
TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-20-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 1 | 1 | 1 | Proposed | 05/05/2020 | 05/05/2020
TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Proposed | 05/05/2020 | 07/05/2020
TO-20-KLN-TB-1-07 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Proposed | 05/05/2020 | 06/05/2020
TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 3 | 3 | 3 | Proposed | 05/05/2020 | 07/05/2020
TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 1 | 1 | 1 | Proposed | 06/05/2020 | 06/05/2020
TO-20-KPG-MP GIS-2-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 8 | 6 | 6 | Proposed | 08/05/2020 | 15/05/2020
TO-20-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 54 | 39 | 39 | Proposed | 11/05/2020 | 03/07/2020
TO-20-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 8 | 6 | 6 | Proposed | 18/05/2020 | 25/05/2020
TO-20-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 2 | 2 | 2 | Proposed | 20/05/2020 | 21/05/2020
TO-20-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Proposed | 20/05/2020 | 20/05/2020
TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 88 | 60 | 60 | Proposed | 22/05/2020 | 17/08/2020
TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 1 | Planned | June | June
TO-20-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | Unknown | Unknown | 2 | Planned | June | June
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | Unknown | Unknown | 3 | Planned | June | June
TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-20-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-KPG-TB-2-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown |  | Planned | June | June
TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 20 | Planned | June | July
TO-20-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 8 | Planned | June | July
TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-KLN-TB-1-06 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 1 | Planned | July | July
TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | Unknown | Unknown | 1 | Planned | July | July
TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 1 | Planned | July | July
TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 1 | Planned | July | July
TO-20-KLN-TB-1-04 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 0 | Planned | July | December
TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | Unknown | 4 | Planned | July | July
TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | Unknown | Unknown | 5 | Planned | July | July
TO-20-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown |  | Planned | July | September
TO-20-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 40 | Planned | July | September
TO-20-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-KLN-TB-1-05 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown |  | Planned | July | July
TO-20-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-220K1-2-03 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2003-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | Unknown | 2 | Planned | July | July
TO-20-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-TB-T2102-06 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 1 | Planned | July | July
TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | Unknown | Unknown | 88 | Planned | July | November
TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-TB-T2102-04 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 1 | Planned | July | July
TO-20-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-TB-T2102-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown |  | Planned | July | July
TO-20-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | Unknown | Unknown | 6 | Planned | August | August
TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | August | August
TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 60 | Planned | August | November
TO-20-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | Unknown | 20 | Planned | August | September
TO-20-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | Unknown | 20 | Planned | August | September
TO-20-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-20-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | August | September
TO-20-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 2 | Planned | August | September
TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 3 | Planned | August | September
TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 3 | Planned | August | September
TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | Unknown | 4 | Planned | September | September
TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 15 | Planned | September | October
TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-20-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-KNR-220K2-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | Unknown | Unknown | 1 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 10 | Planned | October | October
TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 4 | Planned | November | November
TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 3 | Planned | November | November
TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 3 | 1 | 1 | Tentative | 21/02/2020 | 23/02/2020
TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 |  | Scheduled | 24/02/2020 | 28/02/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 61 | 42 | 42 | Scheduled | 24/02/2020 | 24/04/2020
TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 19 | 14 | 14 | Scheduled | 02/03/2020 | 20/03/2020
TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 109 | 75 | 75 | Scheduled | 30/03/2020 | 16/07/2020
TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Proposed | 09/04/2020 | 09/04/2020
TO-20-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Proposed | 14/04/2020 | 14/04/2020
TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 5 | 5 | 5 | Proposed | 20/04/2020 | 24/04/2020
TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-BUT-T142-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 20/04/2020 | 21/04/2020
TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 2 | 2 | 2 | Proposed | 20/04/2020 | 21/04/2020
TO-20-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 20/04/2020 | 21/04/2020
TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 22/04/2020 | 24/04/2020
TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 3 | 3 | 3 | Scheduled | 27/04/2020 | 29/04/2020
TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 5 | 5 | 5 | Proposed | 27/04/2020 | 01/05/2020
TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-110SA1-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-110SA2-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 18/05/2020 | 22/05/2020
TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-GI-KKY-1-06 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-KKY-110SA1-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-110SA1-03 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-110SA2-03 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 142 | 100 | 100 | Proposed | 25/05/2020 | 13/10/2020
TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-KKY-CAP2-04 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 3 | 3 | 3 | Proposed | 25/05/2020 | 27/05/2020
TO-20-KKY-T142-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 142 | 100 | 100 | Reference (Proposed) | 25/05/2020 | 13/10/2020
TO-20-KKY-T142-03 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 25/05/2020 | 27/05/2020
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CLW-KLS-2-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | Unknown | Unknown | 14 | Planned | June | July
TO-20-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | Unknown | Unknown | 5 | Planned | June | July
TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | July | July
TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | Unknown | 4 | Planned | July | July
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | Unknown | 5 | Planned | August | August
TO-20-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | Unknown | 1 | Reference (Planned) | August | August
TO-20-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | Unknown | 1 | Reference (Planned) | August | August
TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 8 | Planned | August | September
TO-20-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 21 | Reference (Planned) | August | September
TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | Unknown | 1 | Planned | October | October
TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-110SA1-04 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-110SA2-04 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-KKY-T141-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-20-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 2 | 2 | 2 | Reference | 24/02/2020 | 25/02/2020
TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 156 | 107 | 107 | Scheduled | 24/02/2020 | 28/07/2020
TO-20-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 89 | 61 | 61 | Scheduled | 24/02/2020 | 22/05/2020
TO-20-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 136 | 93 | 93 | Scheduled | 24/02/2020 | 08/07/2020
TO-20-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 136 | 93 | 93 | Scheduled | 24/02/2020 | 08/07/2020
TO-20-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 3 | 3 | 3 | Reference | 24/02/2020 | 26/02/2020
TO-20-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 | 3 | Scheduled | 24/02/2020 | 26/02/2020
TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 124 | 85 | 85 | Scheduled | 02/03/2020 | 03/07/2020
TO-20-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference | 02/03/2020 | 10/03/2020
TO-20-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 117 | 80 | 80 | Scheduled | 09/03/2020 | 03/07/2020
TO-20-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 117 | 80 | 80 | Reference | 09/03/2020 | 03/07/2020
TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 117 | 80 | 80 | Scheduled | 09/03/2020 | 03/07/2020
TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 1 | 1 | 1 | Scheduled | 12/03/2020 | 12/03/2020
TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 4 | 4 | Proposed | 06/04/2020 | 10/04/2020
TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 | 2 | Proposed | 07/04/2020 | 08/04/2020
TO-20-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 08/04/2020 | 09/04/2020
TO-20-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 2 | 2 | 2 | Scheduled | 08/04/2020 | 09/04/2020
TO-20-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 08/04/2020 | 09/04/2020
TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 7 | 5 | 5 | Proposed | 14/04/2020 | 20/04/2020
TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 58 | 40 |  | Proposed | 14/04/2020 | 10/06/2020
TO-20-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 8 | 6 | 6 | Scheduled | 20/04/2020 | 27/04/2020
TO-20-CSH-TY-1-07 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 4 | 4 | 4 | Scheduled | 20/04/2020 | 23/04/2020
TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 2 | 2 | 2 | Proposed | 22/04/2020 | 23/04/2020
TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | April | April
TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 3 | 3 | 3 | Proposed | 22/04/2020 | 24/04/2020
TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 1 | 1 | 1 | Proposed | 23/04/2020 | 23/04/2020
TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 1 | 1 | 1 | Proposed | 24/04/2020 | 24/04/2020
TO-20-MOY-TAW-2-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | April | May
TO-20-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-DYN-1-03 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-20-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | Unknown | Unknown | 2 | Planned | June | June
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 2 | Planned | June | June
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-20-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 7 | Planned | June | July
TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 4 | Planned | June | July
TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | Unknown | Unknown | 5 | Planned | July | July
TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-BIN-CF-1-05 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 2 | Planned | July | July
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 5 | Planned | July | July
TO-20-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-20-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | July | July
TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | Unknown | Unknown | 6 | Planned | August | August
TO-20-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 40 | Planned | August | September
TO-20-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | August | August
TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | Unknown | 3 | Reference (Planned) | August | August
TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 13 | Planned | August | September
TO-20-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 10 | Planned | August | August
TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown |  | Planned | August | August
TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 1 | Planned | August | August
TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | Unknown | 1 | Planned | August | August
TO-20-FLA-220K1-2-04 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 1 | Planned | September | September
TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | Unknown | Unknown | 8 | Planned | September | September
TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | Unknown | 8 | Planned | September | September
TO-20-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-SRA-2-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 5 | Planned | October | October
TO-20-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 2 | Planned | October | October
TO-20-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | Unknown | Unknown |  | Planned | October | October

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 12 | 10 | 10 | Scheduled | 24/02/2020 | 06/03/2020
TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 3 | 3 | Scheduled | 04/03/2020 | 06/03/2020
TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 9 | 9 | Scheduled | 09/03/2020 | 20/03/2020
TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-RRU-110SA2-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 18/03/2020 | 18/03/2020
TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/03/2020 | 19/03/2020
TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2020 | 20/03/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 19 | 14 | 14 | Scheduled | 23/03/2020 | 10/04/2020
TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 24/03/2020 | 25/03/2020
TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 2 | Planned | March | March
TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 2 | 2 | 2 | Scheduled | 30/03/2020 | 31/03/2020
TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 4 | 4 | Proposed | 06/04/2020 | 10/04/2020
TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 7 | 5 | 5 | Proposed | 14/04/2020 | 20/04/2020
TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 7 | 5 | 5 | Proposed | 14/04/2020 | 20/04/2020
TO-20-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 2 | 2 | 2 | Proposed | 16/04/2020 | 17/04/2020
TO-20-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-110SA2-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 2 | 2 | 2 | Reference | 27/04/2020 | 28/04/2020
TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-RRU-110SA1-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-RRU-SKL-1-02 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 3 | 3 | 3 | Proposed | 11/05/2020 | 13/05/2020
TO-20-SKL-110SA1-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-SKL-110SA2-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-SKL-T141-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 13 | 9 | 9 | Proposed | 14/05/2020 | 26/05/2020
TO-20-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 2 | 2 | 2 | Proposed | 26/05/2020 | 27/05/2020
TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 15 | 10 | 10 | Proposed | 27/05/2020 | 10/06/2020
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 1 | Planned | June | June
TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 1 | Planned | June | June
TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 5 | Planned | June | June
TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | June | June
TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | Unknown | Unknown | 5 | Planned | June | July
TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 15 | Planned | June | July
TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown | 2 | Planned | June | July
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | Unknown | Unknown | 5 | Planned | July | July
TO-20-MUL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | Unknown | Unknown | 4 | Planned | July | July
TO-20-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | Unknown | Unknown | 4 | Reference (Planned) | July | July
TO-20-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | July | July
TO-20-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA1-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-110SA2-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-CAP1-01 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | Unknown | Unknown | 3 | Planned | July | July
TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 5 | Planned | July | July
TO-20-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | Unknown | 5 | Planned | July | August
TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | Unknown | Unknown | 2 | Planned | August | August
TO-20-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | Unknown | Unknown | 2 | Planned | August | August
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 13 | Planned | August | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 3 | 1 | 1 | Tentative | 21/02/2020 | 23/02/2020
TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 46 | 33 | 33 | Scheduled | 24/02/2020 | 09/04/2020
TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 10 | 8 | 8 | Scheduled | 26/02/2020 | 06/03/2020
TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-220 kV A1 @ CKM-02 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 1 | 1 | 1 | Scheduled | 09/03/2020 | 09/03/2020
TO-20-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 11/03/2020 | 11/03/2020
TO-20-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 2 | 2 | 2 | Scheduled | 12/03/2020 | 13/03/2020
TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 30 | 20 | 20 | Scheduled | 18/03/2020 | 16/04/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 19 | 14 | 14 | Scheduled | 23/03/2020 | 10/04/2020
TO-20-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 7 | 5 | 5 | Scheduled | 03/04/2020 | 09/04/2020
TO-20-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 | 2 | Proposed | 08/04/2020 | 09/04/2020
TO-20-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 2 | 2 | 2 | Proposed | 08/04/2020 | 09/04/2020
TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 63 | 43 | 43 | Proposed | 14/04/2020 | 15/06/2020
TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 72 | 50 | 50 | Proposed | 14/04/2020 | 24/06/2020
TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 10 | 8 | 8 | Proposed | 14/04/2020 | 23/04/2020
TO-20-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 4 | 4 | 4 | Scheduled | 14/04/2020 | 17/04/2020
TO-20-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 1 | 1 | 1 | Proposed | 16/04/2020 | 16/04/2020
TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 22 | 15 | 15 | Scheduled | 17/04/2020 | 08/05/2020
TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 5 | 3 | 3 | Proposed | 23/04/2020 | 27/04/2020
TO-20-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 2 | 2 | 2 | Proposed | 27/04/2020 | 28/04/2020
TO-20-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-CKM-220K1-2-01 | COUPLER/SECTIONALISING CB - CARRICKMINES 220-CARRICKMINES 220-220K1-2 | 2 | 2 | 2 | Scheduled | 29/04/2020 | 30/04/2020
TO-20-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 6 | 5 | 5 | Proposed | 11/05/2020 | 16/05/2020
TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 12 | 10 | 10 | Proposed | 11/05/2020 | 22/05/2020
TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 36 | 25 | 25 | Proposed | 15/05/2020 | 19/06/2020
TO-20-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 5 | 5 | 5 | Proposed | 18/05/2020 | 22/05/2020
TO-20-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 2 | 2 | 2 | Proposed | 18/05/2020 | 19/05/2020
TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 15 | 10 | 10 | Proposed | 25/05/2020 | 08/06/2020
TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Proposed | 25/05/2020 | 28/05/2020
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-20-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 9 | Planned | June | June
TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 9 | Planned | June | June
TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 9 | Planned | June | June
TO-20-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 15 | Planned | June | July
TO-20-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV B2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-20-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 5 | Planned | June | June
TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 4 | Planned | June | June
TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | Unknown | 4 | Planned | June | June
TO-20-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | Unknown | Unknown | 5 | Planned | June | June
TO-20-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-220 kV B2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-20-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | Unknown | 2 | Planned | June | June
TO-20-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 6 | Planned | June | July
TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 3 | Planned | June | July
TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 4 | Planned | June | July
TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 4 | Planned | June | July
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | Unknown | 8 | Planned | July | July
TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 10 | Planned | July | July
TO-20-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | Unknown | Unknown | 7 | Reference (Planned) | July | July
TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | Unknown | Unknown | 7 | Reference (Planned) | July | July
TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 5 | Planned | July | July
TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 5 | Planned | July | July
TO-20-FIN GIS-T2101-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | Unknown | Unknown | 8 | Planned | July | July
TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | Unknown | Unknown | 3 | Planned | July | July
TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CKM GIS-ISH-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | Unknown | 7 | Planned | July | July
TO-20-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 43 | Planned | July | September
TO-20-FIN-T2104-08 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 43 | Planned | July | September
TO-20-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | Unknown | Unknown | 3 | Planned | August | August
TO-20-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 1 | Planned | August | August
TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 4 | Planned | August | August
TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | August | September
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 21 | Planned | August | September
TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | Unknown | Unknown | 5 | Planned | August | September
TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | Unknown | Unknown | 5 | Planned | August | September
TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | Unknown | Unknown | 5 | Planned | September | September
TO-20-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | September | September
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 10 | Planned | September | September
TO-20-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN-T2104-05 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV A2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-FIN-T2104-06 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 2 | Planned | September | September
TO-20-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | Unknown | 1 | Planned | September | September
TO-20-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 0 | Planned | September | September
TO-20-FIN-T2104-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 0 | Planned | September | September
TO-20-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | Unknown | Unknown | 43 | Planned | September | November
TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 3 | Planned | September | September
TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | Unknown | 10 | Planned | October | November
TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 5 | Planned | November | November
TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | Unknown | 1 | Planned | November | November
TO-20-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-220 kV B1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | Unknown | Unknown | 5 | Planned | November | November
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 61 | 42 | 42 | Scheduled | 24/02/2020 | 24/04/2020
TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 152 | 105 | 105 | Scheduled | 24/02/2020 | 24/07/2020
TO-20-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 1 | 1 | 1 | Reference | 25/02/2020 | 25/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 86 | 58 | 58 | Scheduled | 26/02/2020 | 21/05/2020
TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-MAC-110SA2-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | 22 | 15 | 15 | Scheduled | 09/03/2020 | 30/03/2020
TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 9 | 6 | 6 | Scheduled | 16/03/2020 | 24/03/2020
TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Scheduled | 02/04/2020 | 09/04/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Proposed | 20/04/2020 | 24/04/2020
TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | Unknown | Unknown | 1 | Planned | April | April
TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 2 | 2 | 2 | Scheduled | 22/04/2020 | 23/04/2020
TO-20-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 2 | 2 | 2 | Scheduled | 27/04/2020 | 28/04/2020
TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 12 | 9 | 9 | Proposed | 27/04/2020 | 08/05/2020
TO-20-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 12 | 9 | 9 | Proposed | 27/04/2020 | 08/05/2020
TO-20-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 4 | 4 | 4 | Proposed | 05/05/2020 | 08/05/2020
TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 1 | 1 | 1 | Proposed | 06/05/2020 | 06/05/2020
TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 3 | 3 | 3 | Proposed | 06/05/2020 | 08/05/2020
TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 19 | 15 | 15 | Proposed | 11/05/2020 | 29/05/2020
TO-20-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 54 | 39 | 39 | Proposed | 11/05/2020 | 03/07/2020
TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 8 | 6 | 6 | Proposed | 12/05/2020 | 19/05/2020
TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 8 | 6 | 6 | Proposed | 13/05/2020 | 20/05/2020
TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/05/2020 | 29/05/2020
TO-20-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | June | June
TO-20-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 1 | Planned | June | June
TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 4 | Planned | June | June
TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 20 | Planned | July | July
TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 2 | Planned | July | July
TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 12 | Planned | July | July
TO-20-220 kV B1/B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 0 | Planned | July | July
TO-20-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 0 | Planned | July | July
TO-20-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 0 | Planned | July | July
TO-20-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 0 | Planned | July | July
TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | Unknown | Unknown | 1 | Planned | July | July
TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-20-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | Unknown | Unknown | 1 | Planned | July | July
TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown | 6 | Planned | July | August
TO-20-220 kV A1/A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1-A2 | Unknown | Unknown | 29 | Planned | August | September
TO-20-CVW-KRA-1-03 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 6 | Planned | August | August
TO-20-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | Unknown | Unknown | 10 | Planned | August | August
TO-20-DMY-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | August | August
TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 2 | Planned | August | August
TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-20-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | Unknown | 45 | Planned | August | November
TO-20-AD-ST101-02 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | Unknown | 45 | Planned | August | November
TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 55 | Planned | September | November
TO-20-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | Unknown | Unknown | 3 | Planned | September | September
TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-20-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | Unknown | Unknown | 44 | Planned | September | November
TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | Unknown | Unknown | 2 | Planned | September | September
TO-20-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 1 | Planned | November | November