## GEN_ALL
Kindly note that items in this report are subject to change. The remainder of the TOP outage season is in the process of being re-planned due to postponement of works caused by COVID-19 restrictions
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 12 | 10 | 10 | Scheduled | 24/02/2020 | 06/03/2020
TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 |  | Scheduled | 24/02/2020 | 28/02/2020
TO-20-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 215 | 149 | 149 | Scheduled | 24/02/2020 | 25/09/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 67 | 46 |  | Scheduled | 24/02/2020 | 30/04/2020
TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 159 | 110 | 110 | Scheduled | 24/02/2020 | 31/07/2020
TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 90 | 61 | 61 | Scheduled | 24/02/2020 | 23/05/2020
TO-20-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 194 | 134 | 134 | Scheduled | 24/02/2020 | 04/09/2020
TO-20-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 194 | 134 | 134 | Scheduled | 24/02/2020 | 04/09/2020
TO-20-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 3 | 3 |  | Reference | 24/02/2020 | 26/02/2020
TO-20-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 7 | 5 | 5 | Scheduled | 25/02/2020 | 02/03/2020
TO-20-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 1 | 1 | 1 | Reference | 25/02/2020 | 25/02/2020
TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-CAP1-03 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 2 | 2 | 2 | Reference | 25/02/2020 | 26/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 96 | 64 | 64 | Scheduled | 26/02/2020 | 31/05/2020
TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 10 | 8 | 8 | Scheduled | 26/02/2020 | 06/03/2020
TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 16 | 12 | 12 | Scheduled | 26/02/2020 | 12/03/2020
TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 185 | 127 | 127 | Scheduled | 02/03/2020 | 02/09/2020
TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/03/2020 | 06/03/2020
TO-20-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference | 02/03/2020 | 10/03/2020
TO-20-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 19 | 14 | 14 | Scheduled | 02/03/2020 | 20/03/2020
TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 7 | 5 | 5 | Scheduled | 04/03/2020 | 10/03/2020
TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 3 | 3 | Scheduled | 04/03/2020 | 06/03/2020
TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/03/2020 | 13/03/2020
TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 9 | 9 | Scheduled | 09/03/2020 | 20/03/2020
TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 178 | 122 | 122 | Scheduled | 09/03/2020 | 02/09/2020
TO-20-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 178 | 122 | 122 | Reference | 09/03/2020 | 02/09/2020
TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 178 | 122 | 122 | Scheduled | 09/03/2020 | 02/09/2020
TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-RRU-110SA2-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 4 | 4 |  | Reference | 10/03/2020 | 13/03/2020
TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 1 | 1 | 1 | Scheduled | 12/03/2020 | 12/03/2020
TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 78 | 52 |  | Scheduled | 13/03/2020 | 29/05/2020
TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 9 | 6 | 6 | Scheduled | 16/03/2020 | 24/03/2020
TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 30 | 20 | 20 | Scheduled | 18/03/2020 | 16/04/2020
TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 18/03/2020 | 18/03/2020
TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/03/2020 | 19/03/2020
TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2020 | 20/03/2020
TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 24/03/2020 | 25/03/2020
TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 26/03/2020 | 26/03/2020
TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 26/03/2020 | 02/04/2020
TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 2 | Planned | March | March
TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 2 | 2 | 2 | Scheduled | 30/03/2020 | 31/03/2020
TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 02/04/2020 | 03/04/2020
TO-20-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 06/04/2020 | 07/04/2020
TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 3 | 3 | 3 | Scheduled | 06/04/2020 | 08/04/2020
TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 |  | Scheduled | 07/04/2020 | 08/04/2020
TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Tentative | 14/04/2020 | 21/04/2020
TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 36 | 25 | 25 | Scheduled | 16/04/2020 | 21/05/2020
TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 20/04/2020 | 20/04/2020
TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 19 | 14 |  | Scheduled | 20/04/2020 | 08/05/2020
TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 4 | 4 | 4 | Scheduled | 05/05/2020 | 08/05/2020
TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 4 | 4 | 4 | Scheduled | 05/05/2020 | 08/05/2020
TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 78 | 55 | 55 | Scheduled | 11/05/2020 | 27/07/2020
TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 18 | 14 | 14 | Scheduled | 11/05/2020 | 28/05/2020
TO-20-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 5 | 5 |  | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 18/05/2020 | 18/05/2020
TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-RRU-110SA1-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 9 | 7 | 7 | Scheduled | 18/05/2020 | 26/05/2020
TO-20-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Scheduled | 19/05/2020 | 19/05/2020
TO-20-KPG-KNR-1-110-03 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Tentative | 21/05/2020 | 22/05/2020
TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 128 | 90 |  | Scheduled | 21/05/2020 | 25/09/2020
TO-20-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 8 | 6 | 6 | Tentative | 22/05/2020 | 29/05/2020
TO-20-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 8 | 6 | 6 | Tentative | 22/05/2020 | 29/05/2020
TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 25/05/2020 | 29/05/2020
TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 5 | 5 | 5 | Tentative | 25/05/2020 | 29/05/2020
TO-20-FIN-SHL-1-03 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Tentative | 25/05/2020 | 29/05/2020
TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-KKY-110SA1-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 3 | 3 | 3 | Scheduled | 25/05/2020 | 27/05/2020
TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 3 | 3 | 3 | Scheduled | 25/05/2020 | 27/05/2020
TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-KKY-T142-03 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 3 | 3 | 3 | Reference | 25/05/2020 | 27/05/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 26 | 19 |  | Scheduled | 25/05/2020 | 19/06/2020
TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Tentative | 26/05/2020 | 27/05/2020
TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 8 | 5 | 5 | Scheduled | 26/05/2020 | 02/06/2020
TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 15 | 10 | 10 | Scheduled | 27/05/2020 | 10/06/2020
TO-20-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-T2016-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 1 | 1 | 1 | Scheduled | 02/06/2020 | 02/06/2020
TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 4 | 4 | 4 | Scheduled | 02/06/2020 | 05/06/2020
TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 59 | 43 |  | Scheduled | 02/06/2020 | 30/07/2020
TO-20-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 170 | 120 | 120 | Scheduled | 02/06/2020 | 18/11/2020
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 02/06/2020 | 08/06/2020
TO-20-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 11 | 9 | 9 | Scheduled | 02/06/2020 | 12/06/2020
TO-20-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 1 | 1 | 1 | Scheduled | 03/06/2020 | 03/06/2020
TO-20-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 03/06/2020 | 03/06/2020
TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 3 | 3 | 3 | Scheduled | 03/06/2020 | 05/06/2020
TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 04/06/2020 | 05/06/2020
TO-20-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 1 | 1 | Scheduled | 04/06/2020 | 04/06/2020
TO-20-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 2 | 2 | Tentative | 04/06/2020 | 06/06/2020
TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 4 | 4 | 4 | Scheduled | 08/06/2020 | 11/06/2020
TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 4 | 4 | 4 | Scheduled | 08/06/2020 | 11/06/2020
TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 4 | 4 | 4 | Proposed | 08/06/2020 | 11/06/2020
TO-20-CSH-GAL-2-06 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 3 | 3 | 3 | Scheduled | 09/06/2020 | 11/06/2020
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 09/06/2020 | 10/06/2020
TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | 2 | 2 | 2 | Reference | 09/06/2020 | 10/06/2020
TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 10/06/2020 | 11/06/2020
TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 8 | 6 | 6 | Scheduled | 10/06/2020 | 17/06/2020
TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 10/06/2020 | 10/06/2020
TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 3 | 3 | 3 | Scheduled | 10/06/2020 | 12/06/2020
TO-20-110 kV A1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 11/06/2020 | 11/06/2020
TO-20-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 11/06/2020 | 11/06/2020
TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 20 | 14 | 14 | Scheduled | 12/06/2020 | 01/07/2020
TO-20-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 1 | 1 | 1 | Scheduled | 12/06/2020 | 12/06/2020
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 15/06/2020 | 19/06/2020
TO-20-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 12 | 10 | 10 | Scheduled | 15/06/2020 | 26/06/2020
TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 1 | 1 | 1 | Scheduled | 16/06/2020 | 16/06/2020
TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 8 | 6 | 6 | Scheduled | 16/06/2020 | 23/06/2020
TO-20-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 2 | 2 | 2 | Scheduled | 16/06/2020 | 17/06/2020
TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 8 | 6 | 6 | Scheduled | 17/06/2020 | 24/06/2020
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 9 | 7 | 7 | Scheduled | 18/06/2020 | 26/06/2020
TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 22/06/2020 | 26/06/2020
TO-20-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 22/06/2020 | 23/06/2020
TO-20-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 11 | 9 | 9 | Scheduled | 22/06/2020 | 02/07/2020
TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 22/06/2020 | 26/06/2020
TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/06/2020 | 24/06/2020
TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 2 | 2 | 2 | Scheduled | 23/06/2020 | 24/06/2020
TO-20-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 3 | 3 | 3 | Scheduled | 24/06/2020 | 26/06/2020
TO-20-220 kV A1 @ CKM-02 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 3 | 3 | 3 | Scheduled | 24/06/2020 | 26/06/2020
TO-20-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 10 | 8 | 8 | Scheduled | 24/06/2020 | 03/07/2020
TO-20-110 kV A2 @ CLN-01 | BUSBAR SECTION - CLOON 110-CLOON 110-110A2 | 2 | 2 | 2 | Tentative | 25/06/2020 | 26/06/2020
TO-20-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 2 | 2 | 2 | Tentative | 25/06/2020 | 26/06/2020
TO-20-CLN-T142-02 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference (Tentative) | 25/06/2020 | 26/06/2020
TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 15 | 11 | 11 | Scheduled | 26/06/2020 | 10/07/2020
TO-20-220 kV A1/A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1-A2 | 47 | 34 | 34 | Scheduled | 29/06/2020 | 14/08/2020
TO-20-CKM GIS-220K4-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 2 | 2 | 2 | Scheduled | 29/06/2020 | 30/06/2020
TO-20-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 1 | 1 | 1 | Scheduled | 29/06/2020 | 29/06/2020
TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 75 | 54 | 54 | Scheduled | 29/06/2020 | 11/09/2020
TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-KLN-TB-1-03 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 24 | 18 | 18 | Scheduled | 29/06/2020 | 22/07/2020
TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Scheduled | 29/06/2020 | 30/06/2020
TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 30/06/2020 | 01/07/2020
TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 4 | 4 | 4 | Scheduled | 30/06/2020 | 03/07/2020
TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 30/06/2020 | 02/07/2020
TO-20-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 02/07/2020 | 03/07/2020
TO-20-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 1 | 1 | 1 | Scheduled | 02/07/2020 | 02/07/2020
TO-20-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 1 | 1 | 1 | Scheduled | 02/07/2020 | 02/07/2020
TO-20-ATY-CLW-1-03 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-110 kV A1 @ CLW-01 | BUSBAR SECTION - CARLOW 110-CARLOW 110-110A1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-CLW-T141-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-CLA-110K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-DMY-1-02 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-MAC-2-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 16 | 12 | 12 | Scheduled | 06/07/2020 | 21/07/2020
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 06/07/2020 | 08/07/2020
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 8 | 6 | 6 | Scheduled | 06/07/2020 | 13/07/2020
TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 2 | 2 | 2 | Scheduled | 06/07/2020 | 07/07/2020
TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 06/07/2020 | 08/07/2020
TO-20-MAY-TH-1-03 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 2 | 2 | 2 | Scheduled | 06/07/2020 | 07/07/2020
TO-20-MUL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 5 | 5 | Reference | 06/07/2020 | 10/07/2020
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 07/07/2020 | 07/07/2020
TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 2 | 2 | 2 | Scheduled | 09/07/2020 | 10/07/2020
TO-20-110 kV A1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV B1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 3 | 3 |  | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Tentative | 13/07/2020 | 15/07/2020
TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 12 | 10 | 10 | Scheduled | 13/07/2020 | 24/07/2020
TO-20-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Tentative | 13/07/2020 | 17/07/2020
TO-20-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference (Tentative) | 13/07/2020 | 15/07/2020
TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 12 | 10 | 10 | Reference | 13/07/2020 | 24/07/2020
TO-20-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 12 | 10 | 10 | Reference | 13/07/2020 | 24/07/2020
TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 2 | 2 | 2 | Scheduled | 13/07/2020 | 14/07/2020
TO-20-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 11 | 9 | 9 | Scheduled | 14/07/2020 | 24/07/2020
TO-20-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 11 | 9 | 9 | Scheduled | 14/07/2020 | 24/07/2020
TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 3 | 3 | 3 | Scheduled | 14/07/2020 | 16/07/2020
TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 4 | 4 | 4 | Scheduled | 14/07/2020 | 17/07/2020
TO-20-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 2 | 2 | 2 | Proposed | 14/07/2020 | 15/07/2020
TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 3 | 3 | 3 | Scheduled | 15/07/2020 | 17/07/2020
TO-20-110 kV A1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Proposed | 16/07/2020 | 17/07/2020
TO-20-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 2 | 2 | 2 | Scheduled | 16/07/2020 | 17/07/2020
TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 7 | 5 | 5 | Scheduled | 19/07/2020 | 25/07/2020
TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 19/07/2020 | 25/07/2020
TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 4 | 4 |  | Scheduled | 20/07/2020 | 23/07/2020
TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 20/07/2020 | 22/07/2020
TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 10 | 8 | 8 | Scheduled | 20/07/2020 | 29/07/2020
TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 4 | 4 | 4 | Scheduled | 20/07/2020 | 23/07/2020
TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 20/07/2020 | 24/07/2020
TO-20-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 20/07/2020 | 24/07/2020
TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Scheduled | 20/07/2020 | 24/07/2020
TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 2 | 2 | 2 | Scheduled | 20/07/2020 | 21/07/2020
TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 8 | 6 | 6 | Scheduled | 20/07/2020 | 27/07/2020
TO-20-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 12 | 10 | 10 | Scheduled | 20/07/2020 | 31/07/2020
TO-20-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 3 | 3 | 3 | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 3 | 3 |  | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 3 | 3 | 3 | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 3 | 3 | 3 | Reference | 22/07/2020 | 24/07/2020
TO-20-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-220 kV B2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-110 kV A1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV B1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 1 | 1 | 1 | Scheduled | 24/07/2020 | 24/07/2020
TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 27/07/2020 | 31/07/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 27/07/2020 | 31/07/2020
TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 9 | 6 | 6 | Scheduled | 27/07/2020 | 04/08/2020
TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 3 | 3 | 3 | Proposed | 27/07/2020 | 29/07/2020
TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 15 | 10 | 10 | Proposed | 27/07/2020 | 10/08/2020
TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 27/07/2020 | 31/07/2020
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 3 | 3 | Proposed | 27/07/2020 | 29/07/2020
TO-20-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 27/07/2020 | 31/07/2020
TO-20-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 3 | 3 | 3 | Reference | 29/07/2020 | 31/07/2020
TO-20-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | 1 | 1 | 1 | Reference | 29/07/2020 | 29/07/2020
TO-20-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 8 | 5 | 5 | Scheduled | 29/07/2020 | 05/08/2020
TO-20-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 2 | 2 | 2 | Proposed | 30/07/2020 | 31/07/2020
TO-20-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV B1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 15 | Planned | July | August
TO-20-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 2 | 2 | Proposed | 30/07/2020 | 31/07/2020
TO-20-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 1 | 1 | 1 | Reference | 31/07/2020 | 31/07/2020
TO-20-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | 5 | 4 | 4 | Reference (Proposed) | 03/08/2020 | 07/08/2020
TO-20-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 5 | 4 | 4 | Reference (Proposed) | 03/08/2020 | 07/08/2020
TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 4 | 4 | Scheduled | 03/08/2020 | 07/08/2020
TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 4 | 4 |  | Proposed | 04/08/2020 | 07/08/2020
TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 |  | Scheduled | 04/08/2020 | 07/08/2020
TO-20-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 04/08/2020 | 06/08/2020
TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 2 | 2 | 2 | Proposed | 04/08/2020 | 05/08/2020
TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 3 | 3 | 3 | Proposed | 04/08/2020 | 06/08/2020
TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 1 | 1 | 1 | Scheduled | 04/08/2020 | 04/08/2020
TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 4 | 4 | 4 | Proposed | 04/08/2020 | 07/08/2020
TO-20-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 4 | 4 | 4 | Proposed | 04/08/2020 | 07/08/2020
TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 3 | 3 | 3 | Proposed | 04/08/2020 | 06/08/2020
TO-20-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 04/08/2020 | 05/08/2020
TO-20-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 2 | 2 | 2 | Proposed | 05/08/2020 | 06/08/2020
TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 3 | 3 | 3 | Proposed | 05/08/2020 | 07/08/2020
TO-20-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 2 | 2 | 2 | Scheduled | 06/08/2020 | 07/08/2020
TO-20-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 12 | 10 |  | Scheduled | 10/08/2020 | 21/08/2020
TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 10/08/2020 | 11/08/2020
TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 10/08/2020 | 14/08/2020
TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 4 | 4 | 4 | Scheduled | 10/08/2020 | 13/08/2020
TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 10/08/2020 | 13/08/2020
TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-BUT-T142-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T142 | 3 | 3 | 3 | Reference | 10/08/2020 | 12/08/2020
TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 |  | Scheduled | 10/08/2020 | 14/08/2020
TO-20-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-220 kV B2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-FIN-T2104-06 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 3 | 3 | 3 | Reference | 10/08/2020 | 12/08/2020
TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 1 | 1 | 1 | Scheduled | 10/08/2020 | 10/08/2020
TO-20-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 10 | 8 | 8 | Scheduled | 10/08/2020 | 19/08/2020
TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 3 | 3 |  | Reference (Proposed) | 10/08/2020 | 12/08/2020
TO-20-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 10/08/2020 | 14/08/2020
TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 2 | 2 | 2 | Proposed | 11/08/2020 | 12/08/2020
TO-20-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 1 | 1 | 1 | Scheduled | 11/08/2020 | 11/08/2020
TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 3 | 3 | 3 | Scheduled | 12/08/2020 | 14/08/2020
TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2020 | 14/08/2020
TO-20-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 3 | 3 | 3 | Reference | 12/08/2020 | 14/08/2020
TO-20-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 12/08/2020 | 12/08/2020
TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 1 | 1 | 1 | Scheduled | 12/08/2020 | 12/08/2020
TO-20-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Proposed | 13/08/2020 | 14/08/2020
TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 1 | 1 | 1 | Scheduled | 13/08/2020 | 13/08/2020
TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 1 | 1 | 1 | Scheduled | 13/08/2020 | 13/08/2020
TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 1 | 1 | 1 | Scheduled | 14/08/2020 | 14/08/2020
TO-20-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | 61 | 45 | 45 | Proposed | 17/08/2020 | 16/10/2020
TO-20-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 61 | 45 | 45 | Proposed | 17/08/2020 | 16/10/2020
TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 1 | 1 |  | Proposed | 17/08/2020 | 17/08/2020
TO-20-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 1 | 1 | 1 | Proposed | 17/08/2020 | 17/08/2020
TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 14 | 10 |  | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 17/08/2020 | 18/08/2020
TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 4 | 4 | 4 | Proposed | 17/08/2020 | 20/08/2020
TO-20-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 9 | 7 | 7 | Proposed | 17/08/2020 | 25/08/2020
TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 4 | 4 | 4 | Scheduled | 17/08/2020 | 20/08/2020
TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 19/08/2020 | 20/08/2020
TO-20-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 19/08/2020 | 20/08/2020
TO-20-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 19/08/2020 | 20/08/2020
TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 21/08/2020 | 21/08/2020
TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 21/08/2020 | 21/08/2020
TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 10 | 8 | 8 | Proposed | 24/08/2020 | 02/09/2020
TO-20-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 12 | 10 | 10 | Scheduled | 24/08/2020 | 04/09/2020
TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 5 | 5 |  | Scheduled | 24/08/2020 | 28/08/2020
TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 8 | 6 | 6 | Proposed | 24/08/2020 | 31/08/2020
TO-20-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 29 | 21 | 21 | Reference (Proposed) | 24/08/2020 | 21/09/2020
TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 29 | 21 | 21 | Scheduled | 24/08/2020 | 21/09/2020
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 29 | 21 | 21 | Scheduled | 24/08/2020 | 21/09/2020
TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 29 | 21 | 21 | Proposed | 24/08/2020 | 21/09/2020
TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 2 | 2 | 2 | Scheduled | 27/08/2020 | 28/08/2020
TO-20-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 64 | 45 | 45 | Proposed | 31/08/2020 | 02/11/2020
TO-20-AD-ST101-02 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 64 | 45 | 45 | Scheduled | 31/08/2020 | 02/11/2020
TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 5 | 5 | 5 | Reference | 31/08/2020 | 04/09/2020
TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 6 | 4 | 4 | Scheduled | 01/09/2020 | 06/09/2020
TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 2 | 2 | 2 | Scheduled | 01/09/2020 | 02/09/2020
TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 10 | 8 |  | Scheduled | 02/09/2020 | 11/09/2020
TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 10 | 8 | 8 | Proposed | 02/09/2020 | 11/09/2020
TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 3 | 3 | 3 | Scheduled | 02/09/2020 | 04/09/2020
TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 2 | 2 |  | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 8 | 6 |  | Proposed | 03/09/2020 | 10/09/2020
TO-20-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2020 | 04/09/2020
TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-MOY-CAP2-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 7 | 5 | 5 | Proposed | 03/09/2020 | 09/09/2020
TO-20-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2020 | 04/09/2020
TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-MOY-TAW-2-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 7 | 5 | 5 | Proposed | 03/09/2020 | 09/09/2020
TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 8 | 6 | 6 | Scheduled | 04/09/2020 | 11/09/2020
TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | Unknown | Unknown | 5 | Planned | September | September
TO-20-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | September | September
TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | September | September
TO-20-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 54 | Planned | September | November
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 14/09/2020 | 18/09/2020
TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-LIS-SKL-1-02 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 15 | Planned | September | October
TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-20-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RRU-SKL-1-02 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SKL-110SA1-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SKL-T141-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 4 | Planned | September | September
TO-20-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 4 | Planned | September | September
TO-20-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 7 | 5 | 5 | Proposed | 16/09/2020 | 22/09/2020
TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 16/09/2020 | 17/09/2020
TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-TBG-T102-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-TBG-T142-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown |  | Planned | September | November
TO-20-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 43 | Planned | September | November
TO-20-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-220 kV A2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-07 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-20-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown |  | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown |  | Planned | September | September
TO-20-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN-T2104-05 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | September | September
TO-20-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | September | September
TO-20-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 5 | Planned | September | October
TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 3 | Planned | September | September
TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 2 | Planned | September | September
TO-20-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | Unknown | 1 | Planned | October | October
TO-20-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 2 | Planned | October | October
TO-20-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 1 | 1 | 1 | Proposed | 16/10/2020 | 16/10/2020
TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | Unknown | Unknown |  | Planned | October | October
TO-20-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 3 | Planned | November | November
TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | November | November
TO-20-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-FIN-HN-1-03 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-HN-T2010/11-03 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 5 | Planned | November | November
TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | Unknown | 1 | Planned | November | November
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 159 | 110 | 110 | Scheduled | 24/02/2020 | 31/07/2020
TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 7 | 5 | 5 | Scheduled | 25/02/2020 | 02/03/2020
TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-CAP1-03 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 2 | 2 | 2 | Reference | 25/02/2020 | 26/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 96 | 64 | 64 | Scheduled | 26/02/2020 | 31/05/2020
TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 16 | 12 | 12 | Scheduled | 26/02/2020 | 12/03/2020
TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/03/2020 | 06/03/2020
TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 7 | 5 | 5 | Scheduled | 04/03/2020 | 10/03/2020
TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/03/2020 | 13/03/2020
TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 4 | 4 |  | Reference | 10/03/2020 | 13/03/2020
TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 26/03/2020 | 26/03/2020
TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 26/03/2020 | 02/04/2020
TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 02/04/2020 | 03/04/2020
TO-20-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 4 | 4 | 4 | Scheduled | 06/04/2020 | 09/04/2020
TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 06/04/2020 | 07/04/2020
TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 3 | 3 | 3 | Scheduled | 06/04/2020 | 08/04/2020
TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 20/04/2020 | 20/04/2020
TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 18 | 14 | 14 | Scheduled | 11/05/2020 | 28/05/2020
TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Scheduled | 19/05/2020 | 19/05/2020
TO-20-KPG-KNR-1-110-03 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Tentative | 21/05/2020 | 22/05/2020
TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 128 | 90 |  | Scheduled | 21/05/2020 | 25/09/2020
TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 25/05/2020 | 29/05/2020
TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 2 | 2 | 2 | Tentative | 26/05/2020 | 27/05/2020
TO-20-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 170 | 120 | 120 | Scheduled | 02/06/2020 | 18/11/2020
TO-20-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 11 | 9 | 9 | Scheduled | 02/06/2020 | 12/06/2020
TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 04/06/2020 | 05/06/2020
TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 10/06/2020 | 11/06/2020
TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 8 | 6 | 6 | Scheduled | 10/06/2020 | 17/06/2020
TO-20-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 1 | 1 | 1 | Scheduled | 12/06/2020 | 12/06/2020
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 15/06/2020 | 19/06/2020
TO-20-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 12 | 10 | 10 | Scheduled | 15/06/2020 | 26/06/2020
TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 1 | 1 | 1 | Scheduled | 16/06/2020 | 16/06/2020
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 9 | 7 | 7 | Scheduled | 18/06/2020 | 26/06/2020
TO-20-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 22/06/2020 | 23/06/2020
TO-20-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/06/2020 | 24/06/2020
TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 2 | 2 | 2 | Scheduled | 23/06/2020 | 24/06/2020
TO-20-KLN-TB-1-03 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 4 | 4 | 4 | Scheduled | 30/06/2020 | 03/07/2020
TO-20-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 02/07/2020 | 03/07/2020
TO-20-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 2 | 2 | 2 | Scheduled | 06/07/2020 | 07/07/2020
TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 3 | 3 |  | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 11 | 9 | 9 | Scheduled | 14/07/2020 | 24/07/2020
TO-20-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 11 | 9 | 9 | Scheduled | 14/07/2020 | 24/07/2020
TO-20-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 4 | 4 |  | Scheduled | 20/07/2020 | 23/07/2020
TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 4 | 4 | 4 | Scheduled | 20/07/2020 | 23/07/2020
TO-20-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 12 | 10 | 10 | Scheduled | 20/07/2020 | 31/07/2020
TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 1 | 1 | 1 | Scheduled | 24/07/2020 | 24/07/2020
TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 27/07/2020 | 31/07/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 27/07/2020 | 31/07/2020
TO-20-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | 5 | 4 | 4 | Reference (Proposed) | 03/08/2020 | 07/08/2020
TO-20-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 5 | 4 | 4 | Proposed | 03/08/2020 | 07/08/2020
TO-20-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 5 | 4 | 4 | Reference (Proposed) | 03/08/2020 | 07/08/2020
TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 04/08/2020 | 06/08/2020
TO-20-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 04/08/2020 | 05/08/2020
TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 10/08/2020 | 11/08/2020
TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 10/08/2020 | 14/08/2020
TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 4 | 4 | 4 | Scheduled | 10/08/2020 | 13/08/2020
TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 |  | Scheduled | 10/08/2020 | 14/08/2020
TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 17/08/2020 | 18/08/2020
TO-20-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 5 | 5 | 5 | Reference | 31/08/2020 | 04/09/2020
TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 6 | 4 | 4 | Scheduled | 01/09/2020 | 06/09/2020
TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 3 | Planned | September | September
TO-20-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 15 | Planned | September | October
TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-20-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | Unknown | 4 | Planned | September | October
TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | November | November
TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 3 | Planned | November | November
TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November
TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 |  | Scheduled | 24/02/2020 | 28/02/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 67 | 46 |  | Scheduled | 24/02/2020 | 30/04/2020
TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 25/02/2020 | 26/02/2020
TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 29 | 20 | 20 | Scheduled | 28/02/2020 | 27/03/2020
TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 19 | 14 | 14 | Scheduled | 02/03/2020 | 20/03/2020
TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 23/03/2020 | 27/03/2020
TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-KKY-110SA1-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 3 | 3 | 3 | Scheduled | 25/05/2020 | 27/05/2020
TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 3 | 3 | 3 | Scheduled | 25/05/2020 | 27/05/2020
TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-KKY-T142-03 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 3 | 3 | 3 | Reference | 25/05/2020 | 27/05/2020
TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 1 | 1 | 1 | Scheduled | 02/06/2020 | 02/06/2020
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 02/06/2020 | 08/06/2020
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 09/06/2020 | 10/06/2020
TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 20 | 14 | 14 | Scheduled | 12/06/2020 | 01/07/2020
TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 8 | 6 | 6 | Scheduled | 17/06/2020 | 24/06/2020
TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 11 | 9 | 9 | Scheduled | 22/06/2020 | 02/07/2020
TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 22/06/2020 | 26/06/2020
TO-20-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 3 | 3 | 3 | Scheduled | 24/06/2020 | 26/06/2020
TO-20-ATY-CLW-1-03 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-110 kV A1 @ CLW-01 | BUSBAR SECTION - CARLOW 110-CARLOW 110-110A1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-CLW-T141-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 8 | 6 | 6 | Scheduled | 06/07/2020 | 13/07/2020
TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 07/07/2020 | 07/07/2020
TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 20/07/2020 | 22/07/2020
TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 10 | 8 | 8 | Scheduled | 20/07/2020 | 29/07/2020
TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 20/07/2020 | 24/07/2020
TO-20-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 20/07/2020 | 24/07/2020
TO-20-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 3 | 3 | 3 | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 3 | 3 |  | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 3 | 3 | 3 | Scheduled | 22/07/2020 | 24/07/2020
TO-20-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 3 | 3 | 3 | Reference | 22/07/2020 | 24/07/2020
TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 3 | 3 | 3 | Proposed | 27/07/2020 | 29/07/2020
TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 5 | 5 | 5 | Proposed | 27/07/2020 | 31/07/2020
TO-20-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV B1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 1 | 1 | 1 | Proposed | 30/07/2020 | 30/07/2020
TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 2 | 2 | 2 | Proposed | 04/08/2020 | 05/08/2020
TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-BUT-T142-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T142 | 3 | 3 | 3 | Reference | 10/08/2020 | 12/08/2020
TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 10/08/2020 | 12/08/2020
TO-20-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 3 | 3 | 3 | Reference | 10/08/2020 | 12/08/2020
TO-20-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 10 | 8 | 8 | Scheduled | 10/08/2020 | 19/08/2020
TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 3 | 3 | 3 | Scheduled | 12/08/2020 | 14/08/2020
TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2020 | 14/08/2020
TO-20-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 3 | 3 | 3 | Reference | 12/08/2020 | 14/08/2020
TO-20-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 1 | 1 |  | Proposed | 17/08/2020 | 17/08/2020
TO-20-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 1 | 1 | 1 | Proposed | 17/08/2020 | 17/08/2020
TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 19/08/2020 | 20/08/2020
TO-20-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 19/08/2020 | 20/08/2020
TO-20-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 19/08/2020 | 20/08/2020
TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 10 | 8 | 8 | Proposed | 24/08/2020 | 02/09/2020
TO-20-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 29 | 21 | 21 | Reference (Proposed) | 24/08/2020 | 21/09/2020
TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 29 | 21 | 21 | Scheduled | 24/08/2020 | 21/09/2020
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 29 | 21 | 21 | Scheduled | 24/08/2020 | 21/09/2020
TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 29 | 21 | 21 | Proposed | 24/08/2020 | 21/09/2020
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | Unknown | 1 | Planned | October | October
TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-20-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 215 | 149 | 149 | Scheduled | 24/02/2020 | 25/09/2020
TO-20-MOY-110SA1-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA1 | 194 | 134 | 134 | Scheduled | 24/02/2020 | 04/09/2020
TO-20-MOY-110SA2-01 | SECTIONALISING DISCONNECT - MOY 110-MOY 110-110SA2 | 194 | 134 | 134 | Scheduled | 24/02/2020 | 04/09/2020
TO-20-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 3 | 3 |  | Reference | 24/02/2020 | 26/02/2020
TO-20-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 |  | Scheduled | 24/02/2020 | 26/02/2020
TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 185 | 127 | 127 | Scheduled | 02/03/2020 | 02/09/2020
TO-20-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 9 | 7 | 7 | Reference | 02/03/2020 | 10/03/2020
TO-20-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 9 | 7 | 7 | Scheduled | 02/03/2020 | 10/03/2020
TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 178 | 122 | 122 | Scheduled | 09/03/2020 | 02/09/2020
TO-20-MOY-T141-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 178 | 122 | 122 | Reference | 09/03/2020 | 02/09/2020
TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 178 | 122 | 122 | Scheduled | 09/03/2020 | 02/09/2020
TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 1 | 1 | 1 | Scheduled | 12/03/2020 | 12/03/2020
TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 2 | 2 |  | Scheduled | 07/04/2020 | 08/04/2020
TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 36 | 25 | 25 | Scheduled | 16/04/2020 | 21/05/2020
TO-20-CSH-GAL-2-06 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 3 | 3 | 3 | Scheduled | 09/06/2020 | 11/06/2020
TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | 2 | 2 | 2 | Reference | 09/06/2020 | 10/06/2020
TO-20-110 kV A1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 11/06/2020 | 11/06/2020
TO-20-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 11/06/2020 | 11/06/2020
TO-20-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 2 | 2 | 2 | Scheduled | 16/06/2020 | 17/06/2020
TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 9 | 7 | 7 | Scheduled | 18/06/2020 | 26/06/2020
TO-20-110 kV A2 @ CLN-01 | BUSBAR SECTION - CLOON 110-CLOON 110-110A2 | 2 | 2 | 2 | Tentative | 25/06/2020 | 26/06/2020
TO-20-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 2 | 2 | 2 | Tentative | 25/06/2020 | 26/06/2020
TO-20-CLN-T142-02 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference (Tentative) | 25/06/2020 | 26/06/2020
TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 15 | 11 | 11 | Scheduled | 26/06/2020 | 10/07/2020
TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-110 kV A1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV B1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 1 | 1 | 1 | Scheduled | 09/07/2020 | 09/07/2020
TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Tentative | 13/07/2020 | 15/07/2020
TO-20-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 3 | 3 | 3 | Scheduled | 13/07/2020 | 15/07/2020
TO-20-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Tentative | 13/07/2020 | 17/07/2020
TO-20-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference (Tentative) | 13/07/2020 | 15/07/2020
TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 13/07/2020 | 17/07/2020
TO-20-110 kV A1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 1 | 1 | 1 | Scheduled | 16/07/2020 | 16/07/2020
TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 27/07/2020 | 31/07/2020
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 3 | 3 | Proposed | 27/07/2020 | 29/07/2020
TO-20-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 27/07/2020 | 31/07/2020
TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 2 | 2 | 2 | Scheduled | 10/08/2020 | 11/08/2020
TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 3 | 3 |  | Reference (Proposed) | 10/08/2020 | 12/08/2020
TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 12/08/2020 | 13/08/2020
TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 12/08/2020 | 12/08/2020
TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 1 | 1 | 1 | Scheduled | 12/08/2020 | 12/08/2020
TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 1 | 1 | 1 | Scheduled | 13/08/2020 | 13/08/2020
TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 1 | 1 | 1 | Scheduled | 13/08/2020 | 13/08/2020
TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 1 | 1 | 1 | Scheduled | 14/08/2020 | 14/08/2020
TO-20-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 14 | 10 |  | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 14 | 10 | 10 | Scheduled | 17/08/2020 | 30/08/2020
TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 21/08/2020 | 21/08/2020
TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 21/08/2020 | 21/08/2020
TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 5 | 5 | 5 | Scheduled | 31/08/2020 | 04/09/2020
TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 10 | 8 |  | Scheduled | 02/09/2020 | 11/09/2020
TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 10 | 8 | 8 | Proposed | 02/09/2020 | 11/09/2020
TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 2 | 2 |  | Proposed | 03/09/2020 | 04/09/2020
TO-20-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 8 | 6 |  | Proposed | 03/09/2020 | 10/09/2020
TO-20-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2020 | 04/09/2020
TO-20-MOY-CAP2-03 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 7 | 5 | 5 | Proposed | 03/09/2020 | 09/09/2020
TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-MOY-T142-02 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2020 | 04/09/2020
TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 2 | 2 | 2 | Proposed | 03/09/2020 | 04/09/2020
TO-20-MOY-TAW-2-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 7 | 5 | 5 | Proposed | 03/09/2020 | 09/09/2020
TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 8 | 6 | 6 | Scheduled | 04/09/2020 | 11/09/2020
TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 14/09/2020 | 18/09/2020
TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 7 | 5 | 5 | Proposed | 16/09/2020 | 22/09/2020
TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 16/09/2020 | 17/09/2020
TO-20-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 16/09/2020 | 17/09/2020
TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 6 | Planned | September | October
TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 5 | Planned | October | October
TO-20-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | Unknown | Unknown | 2 | Planned | October | October
TO-20-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | Unknown | Unknown |  | Planned | October | October

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 12 | 10 | 10 | Scheduled | 24/02/2020 | 06/03/2020
TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/02/2020 | 25/02/2020
TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 3 | 3 | Scheduled | 04/03/2020 | 06/03/2020
TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 9 | 9 | Scheduled | 09/03/2020 | 20/03/2020
TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-RRU-110SA2-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/03/2020 | 10/03/2020
TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 18/03/2020 | 18/03/2020
TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/03/2020 | 19/03/2020
TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2020 | 20/03/2020
TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 24/03/2020 | 25/03/2020
TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 2 | Planned | March | March
TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 2 | 2 | 2 | Scheduled | 30/03/2020 | 31/03/2020
TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 36 | 25 | 25 | Scheduled | 16/04/2020 | 21/05/2020
TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 19 | 14 |  | Scheduled | 20/04/2020 | 08/05/2020
TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 4 | 4 | 4 | Scheduled | 05/05/2020 | 08/05/2020
TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 18 | 14 | 14 | Scheduled | 11/05/2020 | 28/05/2020
TO-20-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 5 | 5 |  | Proposed | 11/05/2020 | 15/05/2020
TO-20-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 11/05/2020 | 15/05/2020
TO-20-RRU-110SA1-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 18/05/2020 | 22/05/2020
TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 3 | 3 | 3 | Scheduled | 18/05/2020 | 20/05/2020
TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 9 | 7 | 7 | Scheduled | 18/05/2020 | 26/05/2020
TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 128 | 90 |  | Scheduled | 21/05/2020 | 25/09/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 26 | 19 |  | Scheduled | 25/05/2020 | 19/06/2020
TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 15 | 10 | 10 | Scheduled | 27/05/2020 | 10/06/2020
TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 09/06/2020 | 10/06/2020
TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 10/06/2020 | 10/06/2020
TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 15/06/2020 | 19/06/2020
TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 22/06/2020 | 26/06/2020
TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 11 | 9 | 9 | Scheduled | 22/06/2020 | 02/07/2020
TO-20-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 2 | 2 | 2 | Tentative | 25/06/2020 | 26/06/2020
TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 29/06/2020 | 03/07/2020
TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 24 | 18 | 18 | Scheduled | 29/06/2020 | 22/07/2020
TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 30/06/2020 | 01/07/2020
TO-20-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 1 | 1 | 1 | Scheduled | 02/07/2020 | 02/07/2020
TO-20-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 1 | 1 | 1 | Scheduled | 02/07/2020 | 02/07/2020
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 06/07/2020 | 08/07/2020
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 06/07/2020 | 08/07/2020
TO-20-MUL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 4 | 4 | 4 | Reference | 06/07/2020 | 09/07/2020
TO-20-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 5 | 5 | Reference | 06/07/2020 | 10/07/2020
TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 2 | 2 | 2 | Scheduled | 16/07/2020 | 17/07/2020
TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 2 | 2 | 2 | Scheduled | 20/07/2020 | 21/07/2020
TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-FLA-LOU-1-05 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 3 | 3 | Proposed | 27/07/2020 | 29/07/2020
TO-20-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | 8 | 5 | 5 | Scheduled | 29/07/2020 | 05/08/2020
TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 15 | Planned | July | August
TO-20-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 2 | 2 | Proposed | 30/07/2020 | 31/07/2020
TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 4 | 4 |  | Proposed | 04/08/2020 | 07/08/2020
TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 1 | 1 | 1 | Scheduled | 04/08/2020 | 04/08/2020
TO-20-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 2 | 2 | 2 | Proposed | 05/08/2020 | 06/08/2020
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 10/08/2020 | 13/08/2020
TO-20-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 1 | 1 | 1 | Scheduled | 10/08/2020 | 10/08/2020
TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 2 | 2 | 2 | Proposed | 11/08/2020 | 12/08/2020
TO-20-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 1 | 1 | 1 | Scheduled | 11/08/2020 | 11/08/2020
TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 2 | 2 | 2 | Scheduled | 01/09/2020 | 02/09/2020
TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-LIS-SKL-1-02 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-20-RRU-SKL-1-02 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SKL-110SA1-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SKL-T141-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | October | October

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 10 | 8 | 8 | Scheduled | 26/02/2020 | 06/03/2020
TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 6 | 4 | 4 | Scheduled | 27/02/2020 | 03/03/2020
TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 78 | 52 |  | Scheduled | 13/03/2020 | 29/05/2020
TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 30 | 20 | 20 | Scheduled | 18/03/2020 | 16/04/2020
TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 5 | 5 | 5 | Scheduled | 20/04/2020 | 24/04/2020
TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 19 | 14 |  | Scheduled | 20/04/2020 | 08/05/2020
TO-20-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Scheduled | 27/04/2020 | 01/05/2020
TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 78 | 55 | 55 | Scheduled | 11/05/2020 | 27/07/2020
TO-20-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 5 | 5 | 5 | Tentative | 25/05/2020 | 29/05/2020
TO-20-FIN-SHL-1-03 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 5 | 5 | 5 | Tentative | 25/05/2020 | 29/05/2020
TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 26 | 19 |  | Scheduled | 25/05/2020 | 19/06/2020
TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 8 | 5 | 5 | Scheduled | 26/05/2020 | 02/06/2020
TO-20-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-SHL-T2016-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 2 | 2 | Tentative | 01/06/2020 | 03/06/2020
TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 59 | 43 |  | Scheduled | 02/06/2020 | 30/07/2020
TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 02/06/2020 | 08/06/2020
TO-20-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 2 | 2 | Tentative | 04/06/2020 | 06/06/2020
TO-20-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 4 | 4 | 4 | Scheduled | 08/06/2020 | 11/06/2020
TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 4 | 4 | 4 | Scheduled | 08/06/2020 | 11/06/2020
TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 4 | 4 | 4 | Proposed | 08/06/2020 | 11/06/2020
TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 3 | 3 | 3 | Scheduled | 10/06/2020 | 12/06/2020
TO-20-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | 2 | Scheduled | 22/06/2020 | 23/06/2020
TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 11 | 9 | 9 | Scheduled | 22/06/2020 | 02/07/2020
TO-20-220 kV A1 @ CKM-02 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 3 | 3 | 3 | Scheduled | 24/06/2020 | 26/06/2020
TO-20-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 24/06/2020 | 24/06/2020
TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 10 | 8 | 8 | Scheduled | 24/06/2020 | 03/07/2020
TO-20-CKM GIS-220K4-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 2 | 2 | 2 | Scheduled | 29/06/2020 | 30/06/2020
TO-20-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 1 | 1 | 1 | Scheduled | 29/06/2020 | 29/06/2020
TO-20-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Scheduled | 29/06/2020 | 30/06/2020
TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 30/06/2020 | 02/07/2020
TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 06/07/2020 | 08/07/2020
TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2020 | 09/07/2020
TO-20-MAY-TH-1-03 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 2 | 2 | 2 | Scheduled | 06/07/2020 | 07/07/2020
TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 12 | 10 | 10 | Scheduled | 13/07/2020 | 24/07/2020
TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 12 | 10 | 10 | Reference | 13/07/2020 | 24/07/2020
TO-20-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 12 | 10 | 10 | Reference | 13/07/2020 | 24/07/2020
TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 2 | 2 | 2 | Scheduled | 13/07/2020 | 14/07/2020
TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 4 | 4 | 4 | Scheduled | 14/07/2020 | 17/07/2020
TO-20-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 2 | 2 | 2 | Proposed | 14/07/2020 | 15/07/2020
TO-20-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Proposed | 16/07/2020 | 17/07/2020
TO-20-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 7 | 5 | 5 | Scheduled | 16/07/2020 | 22/07/2020
TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Scheduled | 20/07/2020 | 24/07/2020
TO-20-CDU-FIN-2-06 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-220 kV B2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 7 | 5 | 5 | Scheduled | 23/07/2020 | 29/07/2020
TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 15 | 10 | 10 | Proposed | 27/07/2020 | 10/08/2020
TO-20-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | 1 | 1 | 1 | Reference | 29/07/2020 | 29/07/2020
TO-20-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 2 | 2 | 2 | Proposed | 30/07/2020 | 31/07/2020
TO-20-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 1 | 1 | 1 | Reference | 31/07/2020 | 31/07/2020
TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 |  | Scheduled | 04/08/2020 | 07/08/2020
TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 3 | 3 | 3 | Proposed | 04/08/2020 | 06/08/2020
TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 4 | 4 | 4 | Proposed | 04/08/2020 | 07/08/2020
TO-20-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 4 | 4 | 4 | Proposed | 04/08/2020 | 07/08/2020
TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 3 | 3 | 3 | Proposed | 04/08/2020 | 06/08/2020
TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 3 | 3 | 3 | Proposed | 05/08/2020 | 07/08/2020
TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 10/08/2020 | 13/08/2020
TO-20-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-220 kV B2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-FIN-T2104-06 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 5 | 5 | 5 | Proposed | 10/08/2020 | 14/08/2020
TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 9 | 7 | 7 | Proposed | 17/08/2020 | 25/08/2020
TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 4 | 4 | 4 | Proposed | 17/08/2020 | 20/08/2020
TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 4 | 4 | 4 | Scheduled | 17/08/2020 | 20/08/2020
TO-20-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 12 | 10 | 10 | Scheduled | 24/08/2020 | 04/09/2020
TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 29 | 21 | 21 | Scheduled | 24/08/2020 | 21/09/2020
TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 2 | 2 | 2 | Scheduled | 27/08/2020 | 28/08/2020
TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | Unknown | Unknown | 5 | Planned | September | September
TO-20-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | September | September
TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-20-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown |  | Planned | September | November
TO-20-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 43 | Planned | September | November
TO-20-220 kV A2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-220 kV B2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 1 | Planned | September | September
TO-20-FIN-T2104-07 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 5 | Planned | September | September
TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-20-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-20-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown |  | Planned | September | September
TO-20-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown |  | Planned | September | September
TO-20-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown |  | Planned | September | September
TO-20-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | September | September
TO-20-FIN-T2104-05 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | September | September
TO-20-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | Unknown | 1 | Planned | September | September
TO-20-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-FIN-HN-1-02 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | September | October
TO-20-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 5 | Planned | September | October
TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 3 | Planned | September | September
TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 3 | Planned | September | September
TO-20-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-FIN-T2104-04 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown | 2 | Planned | September | September
TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-20-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | Unknown | Unknown | 5 | Planned | October | October
TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-FIN-HN-1-03 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-20-HN-T2010/11-03 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 5 | Planned | November | November
TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | Unknown | 1 | Planned | November | November
TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | Unknown | Unknown | 5 | Planned | November | November

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-20-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 4 | 4 | 4 | Scheduled | 24/02/2020 | 27/02/2020
TO-20-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 100 | 67 | 67 | Scheduled | 24/02/2020 | 02/06/2020
TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 67 | 46 |  | Scheduled | 24/02/2020 | 30/04/2020
TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 16 | 12 | 12 | Scheduled | 24/02/2020 | 10/03/2020
TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 90 | 61 | 61 | Scheduled | 24/02/2020 | 23/05/2020
TO-20-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 1 | 1 | 1 | Reference | 25/02/2020 | 25/02/2020
TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 96 | 64 | 64 | Scheduled | 26/02/2020 | 31/05/2020
TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 8 | 6 | 6 | Scheduled | 09/03/2020 | 16/03/2020
TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 9 | 6 | 6 | Scheduled | 16/03/2020 | 24/03/2020
TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Tentative | 14/04/2020 | 21/04/2020
TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 4 | 4 | 4 | Scheduled | 05/05/2020 | 08/05/2020
TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 18/05/2020 | 18/05/2020
TO-20-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 8 | 6 | 6 | Tentative | 22/05/2020 | 29/05/2020
TO-20-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 8 | 6 | 6 | Tentative | 22/05/2020 | 29/05/2020
TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/05/2020 | 29/05/2020
TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 4 | 4 | 4 | Scheduled | 02/06/2020 | 05/06/2020
TO-20-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 1 | 1 | 1 | Scheduled | 03/06/2020 | 03/06/2020
TO-20-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 03/06/2020 | 03/06/2020
TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 3 | 3 | 3 | Scheduled | 03/06/2020 | 05/06/2020
TO-20-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 1 | 1 | Scheduled | 04/06/2020 | 04/06/2020
TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2020 | 12/06/2020
TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 8 | 6 | 6 | Scheduled | 16/06/2020 | 23/06/2020
TO-20-220 kV A1/A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1-A2 | 47 | 34 | 34 | Scheduled | 29/06/2020 | 14/08/2020
TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 75 | 54 | 54 | Scheduled | 29/06/2020 | 11/09/2020
TO-20-CLA-110K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-DMY-1-02 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-MAC-2-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 5 | 5 | 5 | Scheduled | 06/07/2020 | 10/07/2020
TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 16 | 12 | 12 | Scheduled | 06/07/2020 | 21/07/2020
TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 8 | 6 | 6 | Scheduled | 06/07/2020 | 13/07/2020
TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 2 | 2 | 2 | Scheduled | 09/07/2020 | 10/07/2020
TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 3 | 3 | 3 | Scheduled | 14/07/2020 | 16/07/2020
TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 3 | 3 | 3 | Scheduled | 15/07/2020 | 17/07/2020
TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 7 | 5 | 5 | Scheduled | 19/07/2020 | 25/07/2020
TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 19/07/2020 | 25/07/2020
TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | Unknown | Unknown | 2 | Planned | July | July
TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 8 | 6 | 6 | Scheduled | 20/07/2020 | 27/07/2020
TO-20-110 kV A1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV B1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | 1 | 1 | 1 | Scheduled | 23/07/2020 | 23/07/2020
TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 27/07/2020 | 31/07/2020
TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 9 | 6 | 6 | Scheduled | 27/07/2020 | 04/08/2020
TO-20-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 3 | 3 | 3 | Scheduled | 29/07/2020 | 31/07/2020
TO-20-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 3 | 3 | 3 | Reference | 29/07/2020 | 31/07/2020
TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 4 | 4 | Scheduled | 03/08/2020 | 07/08/2020
TO-20-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 3 | 3 | 3 | Scheduled | 04/08/2020 | 06/08/2020
TO-20-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 2 | 2 | 2 | Scheduled | 06/08/2020 | 07/08/2020
TO-20-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 12 | 10 |  | Scheduled | 10/08/2020 | 21/08/2020
TO-20-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 10/08/2020 | 14/08/2020
TO-20-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 2 | 2 | 2 | Proposed | 13/08/2020 | 14/08/2020
TO-20-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | 61 | 45 | 45 | Proposed | 17/08/2020 | 16/10/2020
TO-20-AD-220K1-2-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | 61 | 45 | 45 | Proposed | 17/08/2020 | 16/10/2020
TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 17/08/2020 | 21/08/2020
TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 5 | 5 |  | Scheduled | 24/08/2020 | 28/08/2020
TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 8 | 6 | 6 | Proposed | 24/08/2020 | 31/08/2020
TO-20-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 64 | 45 | 45 | Proposed | 31/08/2020 | 02/11/2020
TO-20-AD-ST101-02 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 64 | 45 | 45 | Scheduled | 31/08/2020 | 02/11/2020
TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Proposed | 31/08/2020 | 04/09/2020
TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 3 | 3 | 3 | Scheduled | 02/09/2020 | 04/09/2020
TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | September | September
TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 54 | Planned | September | November
TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Proposed | 14/09/2020 | 15/09/2020
TO-20-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 4 | Planned | September | September
TO-20-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 4 | Planned | September | September
TO-20-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | Unknown | Unknown | 2 | Planned | September | September
TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-20-TBG-T102-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-TBG-T142-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-20-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 1 | 1 | 1 | Proposed | 16/10/2020 | 16/10/2020