## All Works Summary
Alert Status | Outage ID | Feeder ID | From Bus | To Bus | CKT | Description | Work ID | Start Date | Finish Date | Priority | Status | Project Manager
OD1326 | TO-20-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04000 | TO-20-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109103511101 | TO-20-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA1 | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103511106 | TO-20-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA1 | As a consequence of AGL-110SA2: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1327 | TO-20-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103511102 | TO-20-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA2 | As a consequence of AGL-110SA1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103511107 | TO-20-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | AGANNYGAL 110 | AGANNYGAL 110 | 110SA2 | Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0951 | TO-20-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | AGANNYGAL 110 | DERRYBRIEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 12/09/2020 |  | Scheduled
16CM0038 | TO-20-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | AGANNYGAL 110 | DERRYBRIEN 110 | 1 | CB - Siemens 3AP mod required to prevent spring charging lockout with loss of AC. | 900713712 | 07/09/2020 | 12/09/2020 | 2 | Scheduled
20EG00001 | TO-20-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | AGANNYGAL 110 | DERRYBRIEN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 07/09/2020 | 12/09/2020 | 4 | Scheduled
CAPX20200109103511103 | TO-20-AGL-DYN-1-03 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | AGANNYGAL 110 | DERRYBRIEN 110 | 1 | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210172705 | TO-20-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | AGANNYGAL 110 | DERRYBRIEN 110 | 1 | Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10002 | TO-20-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | AGANNYGAL 110 | ENNIS 110 | 1 | 110kV MO Cubicle Operational Test | 901129481 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00003 | TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | AGANNYGAL 110 | ENNIS 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129954 | 15/06/2020 | 19/06/2020 | 4 | Scheduled
19LN1184 | TO-20-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | AGANNYGAL 110 | ENNIS 110 | 1 | 2018HP-1[124]Off PlumbPlumb insulators | 900982973 | 15/06/2020 | 19/06/2020 | 4 | Scheduled
CAPX2020102214323102 | TO-20-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0381 | TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | EMP AMS: Peplace Fuse Holders on all CTV | 901087473 | 04/08/2020 | 07/08/2020 | 2 | Scheduled
20CM0380 | TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | EMP AMS: Spring charge locking out with | 901087472 | 04/08/2020 | 07/08/2020 | 1 | Scheduled
20CM0296 | TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | Replace faulty isolation block. | 901081611 | 04/08/2020 | 07/08/2020 | 1 | Scheduled
20EG00007 | TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129955 | 04/08/2020 | 07/08/2020 | 4 | Scheduled
20EG20000 | TO-20-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | Cable Insp. 110kV XLPE |  | 04/08/2020 | 07/08/2020 | 4 | Scheduled
CAPX20200109103511104 | TO-20-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210172708 | TO-20-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | AGANNYGAL 110 | SHANNONBRIDGE 110 | 1 | Simultaneous AGL-SH-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133518 | TO-20-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | AGHADA 220 | AGHADA 220 | 220A1 | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133520 | TO-20-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | AGHADA 220 | AGHADA 220 | 220A2 | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133519 | TO-20-220 kV B1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | AGHADA 220 | AGHADA 220 | 220B1 | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191122090451 | TO-20-220 kV B1/B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | AGHADA 220 | AGHADA 220 | 220B1-B2 | Blackstart test |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133521 | TO-20-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | AGHADA 220 | AGHADA 220 | 220B2 | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020055 | TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | AGHADA 220 | AGHADA 220 | 220K1-2 | P2 Protection maintenance of ISM21 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0003 | TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | AGHADA 220 | AGHADA 220 | 220K1-2 | V-string busbar insulator has corrosion | 900891284 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0004 | TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | AGHADA 220 | AGHADA 220 | 220K1-2 | O1-Hotspot Sectionaliser SA | 900912297 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG06002 | TO-20-AD-220K1-2-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1-2 | AGHADA 220 | AGHADA 220 | 220K1-2 | HV Pressure Vessel Inspection | 901045781 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP191114102614 | TO-20-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | AGHADA 220 | GLANAGOW 220 | 1 | Blackstart Test |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0903 | TO-20-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | AGHADA 220 | GLANAGOW 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20107 | TO-20-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | AGHADA 220 | GLANAGOW 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0255 | TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Total Maintenance Outage Duration Requested |  | 19/07/2020 | 25/07/2020 |  | Scheduled
20EG00742 | TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00741 | TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG06000 | TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | HV Pressure Vessel Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00744 | TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17CM0288 | TO-20-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | O1-Surge Counters have moisture inside. | 900719850 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN5198 | TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Hotspot 3 (Lwr 1 Span 28/29) Lower phase midspan joint (Repair by 30th Oct 2020) | 901098961 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
20LN5199 | TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Hotspot 4 (Lwr 2 Span 28/29) Lower phase midspan joint (Repair by 30th Jul 2020) | 901098964 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
20LN5200 | TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Hotspot 1 (C1 Span 61/62) Centre Midspan joint (Repair by 30th Oct 2020) | 901098965 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
CAPX2019101410530307 | TO-20-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530314 | TO-20-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5201 | TO-20-AD-KRA-1-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | AGHADA 220 | KNOCKRAHA 220 | 1 | Hotspot 2 (Upr 1 Span 61 / 62) Upper midspan joint (Measure resistance during next available outage) | 901098966 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
CAPX2020060310121317 | TO-20-AD-KRA-2-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0256 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Total Maintenance Outage Duration Requested |  | 19/07/2020 | 25/07/2020 |  | Scheduled
20LN5205 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Hotspot 2 (C1 Span 61/62) Centre midspan joint (Repair by 30th Oct 2020) | 901098970 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
CAPX2019101409072030 | TO-20-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409072043 | TO-20-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5204 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Hotspot 5 (Upr 2 Span 28/29) Upper Midspan (Repair by 30th Oct 2020) | 901098969 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
20LN5203 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Hotspot 4 (Upr 1 Span 28/29) Upper Midspan (Repair by 30th Oct 2020) | 901098968 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
20LN5202 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Hotspot 3 (C2 Span 28/29) Centre Midspan (Repair by 30th Jul 2020) | 901098967 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
20LN5206 | TO-20-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | Hotspot 1 (C2 Span 61/62) Centre midspan joint (Repair by 30th Jul 2020) | 901098971 | 19/07/2020 | 25/07/2020 | 1 | Scheduled
CAPX2019101411492621 | TO-20-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | AGHADA 220 | KNOCKRAHA 220 | 2 | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020112 | TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | AGHADA 220 | LONG POINT 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 20/07/2020 | 21/07/2020 | 3 | Scheduled
OD0257 | TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | AGHADA 220 | LONG POINT 220 | 1 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 21/07/2020 |  | Scheduled
20EG20124 | TO-20-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | AGHADA 220 | LONG POINT 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 20/07/2020 | 21/07/2020 | 4 | Scheduled
OD0258 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020021212041310 | TO-20-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2) | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0271 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | O1-Aghada 220kv Gantree Glass Insulator | 901028751 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG02171 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN1286 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | 2018HP-1[9]Vib Dampers-Replace | 900983098 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02169 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20661 | TO-20-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100212153007 | TO-20-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | AGHADA 220 | RAFFEEN 220 | 1 | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201022104051 | TO-20-AD-ST101-03 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | AGHADA 110 | AGHADA 10 | ST101 | Proximity outge for civil works | CP0794 | 23/11/2020 | 26/11/2020 |  | Scheduled
20EG06003 | TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | AGHADA 220 | AGHADA G11/12 | T2011/12 | HV Pressure Vessel Inspection |  | 24/02/2020 | 02/06/2020 | 4 | Scheduled
20EG01624 | TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | AGHADA 220 | AGHADA G11/12 | T2011/12 | 220kV SF6 Cubicle Ordinary Service | 901130028 | 24/02/2020 | 02/06/2020 | 4 | Scheduled
20EG01625 | TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | AGHADA 220 | AGHADA G11/12 | T2011/12 | 220kV Cubicle Condition Assessment |  | 24/02/2020 | 02/06/2020 | 4 | Scheduled
20EG20263 | TO-20-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | AGHADA 220 | AGHADA G11/12 | T2011/12 | Annual Insp. 400 & 220 Station OF Cable | 901129053 | 24/02/2020 | 02/06/2020 | 4 | Scheduled
PROT2020144 | TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | AGHADA 220 | AGHADA G14 | T2014 | P3 Protection maintenance of 7SA612, 7UT92 |  | 05/08/2020 | 06/08/2020 | 3 | Scheduled
OD0635 | TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | AGHADA 220 | AGHADA G14 | T2014 | Total Maintenance Outage Duration Requested |  | 05/08/2020 | 06/08/2020 |  | Scheduled
TOP191114165657 | TO-20-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | AGHADA 220 | AGHADA G14 | T2014 | Blackstart Test |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20277 | TO-20-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | AGHADA 220 | AGHADA G14 | T2014 | Annual Insp. 400 & 220 Station OF Cable |  | 05/08/2020 | 06/08/2020 | 4 | Scheduled
OD1356 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201023085100 | TO-20-AD-T2102-04 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | Proximity outage. To facilitate crossing of 110kV cable | CP0794 | 23/11/2020 | 26/11/2020 |  | Scheduled
20EG01769 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01773 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 220/110kV Trafo Tap Changer Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01772 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01770 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01768 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01767 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0007 | TO-20-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | Oil sampling of cable boxes on T2102 Tra | 900908020 | 05/08/2020 | 07/08/2020 | 2 | Scheduled
20EG01771 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20526 | TO-20-AD-T2102-02 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | AGHADA 220 | AGHADA 110 | T2102 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0004 | TO-20-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | AGHADA 110 | WHITEGATE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00011 | TO-20-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | AGHADA 110 | WHITEGATE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10006 | TO-20-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | AGHADA 110 | WHITEGATE 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020152 | TO-20-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | AHANE 110 | KILLONAN 110 | 2 | P3 Protection maintenance of 7SA513 |  | 25/12/2500 | 25/12/2500 | 3 | Reference (Unscheduled)
20CM0417 | TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | ANNER 110 | DOON 110 | 1 | Replacement of Stolen Earths |  | 22/09/2020 | 23/09/2020 | 1 | Scheduled
20EG10008 | TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | ANNER 110 | DOON 110 | 1 | 110kV Sect / Dist Operational Test |  | 22/09/2020 | 23/09/2020 | 4 | Scheduled
19EG10009 | TO-20-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | ANNER 110 | DOON 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 22/09/2020 | 23/09/2020 | 4 | Scheduled
TOP200213084236 | TO-20-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | ANNER 110 | ANNER 10 | T101 | As a consequence of work on Anner-Doon 110 kV |  | 22/09/2020 | 23/09/2020 |  | Reference
TOP200213084201 | TO-20-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | ANNER 110 | ANNER 10 | T103 | As a consequence of work on Anner-Doon 110 kV |  | 22/09/2020 | 23/09/2020 |  | Reference
CAPX2019100316290002 | TO-20-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110A3 | Energisation of T104 from Drumline | CP1065 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200727115445 | TO-20-110 kV B1 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110B1 | Proximity for T103 black start | PROX | 12/08/2020 | 12/08/2020 |  | Scheduled
TOP200717171247 | TO-20-110 kV B3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110B3 | Proximity for T103 black start |  | 12/08/2020 | 12/08/2020 |  | Scheduled
OD1114 | TO-20-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110K3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21055 | TO-20-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110K3 | 110kV GIS Cubicle Operational Test | 901076456 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121716133515 | TO-20-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110K3 | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133514 | TO-20-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110K3 | As a consequence of 110 kV A3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100316290003 | TO-20-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110K3 | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline | CP1065 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100316290004 | TO-20-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SA1-3CB | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline | CP1065 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0993 | TO-20-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0009 | TO-20-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-2CB | OEM Fault Investigation / Repair on SB2. | 901053225 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019121716133504 | TO-20-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133511 | TO-20-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ AA GIS: 110 kV A2/B2 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133517 | TO-20-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-3CB | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121716133505 | TO-20-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS 110 | 110SB1-3CB | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0007 | TO-20-AA GIS-DRU-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | ARDNACRUSHA GIS 110 | DRUMLINE 110 | 1 | Total Maintenance Outage Duration Requested |  | 03/11/2020 | 06/11/2020 |  | Scheduled
20EG00021 | TO-20-AA GIS-DRU-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | ARDNACRUSHA GIS 110 | DRUMLINE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 03/11/2020 | 06/11/2020 | 4 | Scheduled
CAPX2019100316290001 | TO-20-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | ARDNACRUSHA GIS 110 | DRUMLINE 110 | 1 | Energisation of T104 from Drumline | CP1065 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1381 | TO-20-AA GIS-ENN-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0008 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 13/03/2020 |  | Scheduled
TOP201020175534 | TO-20-AA GIS-ENN-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | operator training |  | 10/11/2020 | 10/11/2020 |  | Scheduled
16LN3170 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | 2015CP-1[132]Off Plumb Poles | 900725270 | 09/03/2020 | 13/03/2020 | 1 | Scheduled
16LN3232 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | 2015CP-1[149]Off Plumb Poles | 900725277 | 09/03/2020 | 13/03/2020 | 1 | Scheduled
19EG10012 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | 110kV GIS Cubicle Operational Test | 901045735 | 09/03/2020 | 13/03/2020 | 4 | Scheduled
20EG00025 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | 110kV MO Cubicle Ordinary Service | 901129840 | 09/03/2020 | 13/03/2020 | 4 | Scheduled
20EG20703 | TO-20-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | ARDNACRUSHA GIS 110 | ENNIS 110 | 1 | Cable Insp. 110kV XLPE | 901129157 | 09/03/2020 | 13/03/2020 | 4 | Scheduled
17LN0562 | TO-20-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | ARDNACRUSHA GIS 110 | LIMERICK 110 | 1 | 2016CP-1[72]Off Plumb Insulators | 900816810 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17LN0542 | TO-20-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | ARDNACRUSHA GIS 110 | LIMERICK 110 | 1 | 2016CP-1[32]Off Plumb Poles leaning | 900816798 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG10015 | TO-20-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | ARDNACRUSHA GIS 110 | LIMERICK 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331710 | TO-20-AA GIS-LIM-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | ARDNACRUSHA GIS 110 | LIMERICK 110 | 1 | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201001091843 | TO-20-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | ARDNACRUSHA GIS 110 | SINGLAND 110 | 1 | DSO request for CA on SNG T102 |  | 27/10/2020 | 30/10/2020 |  | Proposed
20EG10017 | TO-20-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | ARDNACRUSHA GIS 110 | SINGLAND 110 | 1 | 110kV GIS Cubicle Operational Test |  | 27/10/2020 | 30/10/2020 | 4 | Proposed
19EG10016 | TO-20-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | ARDNACRUSHA GIS 110 | SINGLAND 110 | 1 | 110kV GIS Cubicle Operational Test | 901018827 | 20/07/2020 | 23/07/2020 | 4 | Scheduled
OD0637 | TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS G1 | T101 | Total Maintenance Outage Duration Requested |  | 16/06/2020 | 16/06/2020 |  | Scheduled
19EG10942 | TO-20-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS G1 | T101 | 110KV MO Cubicle Operational Test | 901050256 | 16/06/2020 | 16/06/2020 | 4 | Scheduled
OD1374 | TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS G3 | T103 | Total Maintenance Outage Duration Requested |  | 20/04/2020 | 20/04/2020 |  | Scheduled
19EG23781 | TO-20-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS G3 | T103 | 110kV GIS Cubicle Operational Test |  | 20/04/2020 | 20/04/2020 | 4 | Scheduled
CAPX2019100316290000 | TO-20-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | ARDNACRUSHA GIS 110 | ARDNACRUSHA GIS G4 | T104 | Outage of transformer to faciliatet trafo replacement (IPP request) | CP1065 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1226 | TO-20-AGP-TIV-1-01 | 110kV FEEDER - ARDNAGAPPARY 110-TIEVEBRACK 110-1 | ARDNAGAPPARY 110 | TIEVEBRACK 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23801 | TO-20-AGP-TIV-1-01 | 110kV FEEDER - ARDNAGAPPARY 110-TIEVEBRACK 110-1 | ARDNAGAPPARY 110 | TIEVEBRACK 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23759 | TO-20-AGP-TIV-1-01 | 110kV FEEDER - ARDNAGAPPARY 110-TIEVEBRACK 110-1 | ARDNAGAPPARY 110 | TIEVEBRACK 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0012 | TO-20-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | ARIGNA tee | CARRICK ON SHANNON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00036 | TO-20-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | ARIGNA tee | CARRICK ON SHANNON 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1111 | TO-20-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | ARIGNA tee | CARRICK ON SHANNON 110 | 1 | 2019HP-1[188]Vib Dampers Loose | 901085136 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1112 | TO-20-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | ARIGNA tee | CARRICK ON SHANNON 110 | 1 | 2019HP-2[182, 183]Replace Pole Bolt | 901086390 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0013 | TO-20-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | ARIGNA tee | CORDERRY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10019 | TO-20-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | ARIGNA tee | CORDERRY 110 | 1 | 110kV SF6 Cubicle Operational Test | 901039100 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121811050026 | TO-20-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | ARKLOW 110 | ARKLOW 110 | 110A1 | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050028 | TO-20-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | ARKLOW 110 | ARKLOW 110 | 110A2 | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050027 | TO-20-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | ARKLOW 110 | ARKLOW 110 | 110B1 | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050029 | TO-20-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | ARKLOW 110 | ARKLOW 110 | 110B2 | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050030 | TO-20-220 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | ARKLOW 220 | ARKLOW 220 | 220A1 | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050032 | TO-20-220 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | ARKLOW 220 | ARKLOW 220 | 220A2 | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050031 | TO-20-220 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | ARKLOW 220 | ARKLOW 220 | 220B1 | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121811050033 | TO-20-220 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | ARKLOW 220 | ARKLOW 220 | 220B2 | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0363 | TO-20-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | ARKLOW 220 | ARKLOW 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00987 | TO-20-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | ARKLOW 220 | ARKLOW 220 | 220K1-2 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0014 | TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | ARKLOW 110 | BALLYBEG 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/02/2020 | 26/02/2020 |  | Scheduled
19EG10021 | TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | ARKLOW 110 | BALLYBEG 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129646 | 25/02/2020 | 26/02/2020 | 4 | Scheduled
20LN0141 | TO-20-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | ARKLOW 110 | BALLYBEG 110 | 1 | 2019HP-1[51]Insulator Broken Lower/ph | 901084881 | 25/02/2020 | 26/02/2020 | 2 | Scheduled
OD0015 | TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | ARKLOW 110 | BANOGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11294 | TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | ARKLOW 110 | BANOGE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0444 | TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | ARKLOW 110 | BANOGE 110 | 1 | R phase Banoge 110kV CubicleDL., R phase connectio hotpot repair due by 17thAugust 2020 | 901134734 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN0170 | TO-20-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | ARKLOW 110 | BANOGE 110 | 1 | 2019HP-1[129]Vib Dampers EW Damper | 901085135 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD0259 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 16/10/2020 |  | Forced Out
PROT2020113 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/05/2020 | 16/10/2020 | 3 | Forced Out
19CM0003 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | Timber HAZCNF_20M (122-123) | 900979480 | 25/05/2020 | 16/10/2020 | 2 | Forced Out
19CM0006 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | Replace SF6 density gauge on GIS to AIS | 900978744 | 25/05/2020 | 16/10/2020 | 2 | Forced Out
18EG10387 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | 220kV GIS Cubicle Operational Test | 901039045 | 25/05/2020 | 16/10/2020 | 3 | Forced Out
20CM0040 | TO-20-ARK-CKM GIS-1-02 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | ESBi Repeat Insulation Tests on VT all p | 900532102 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0445 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | T phase Carrickmines 220kVCubicle. T phase GIS Copper earth strp hotspot DUE : IMMEDIATELY | 901134737 | 25/05/2020 | 16/10/2020 | 1 | Forced Out
20CM0041 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | 01 outage required. Hot Spots | 900596268 | 25/05/2020 | 16/10/2020 | 2 | Forced Out
20CM0451 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GIS Copper earth strap DUE : 17-Jul-20 | 901134736 | 25/05/2020 | 16/10/2020 | 1 | Forced Out
20CM0465 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GISbushing connection DUE : 17-Nov-20 | 901134735 | 25/05/2020 | 16/10/2020 | 1 | Forced Out
19EG00752 | TO-20-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | ARKLOW 220 | CARRICKMINES GIS 220 | 1 | 220kV GIS Cubicle Ordinary Service | 901042325 | 25/05/2020 | 16/10/2020 | 4 | Forced Out
TOP200921110858 | TO-20-ARK-LWD-1-03 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | Proximity outage of the Arklow Lodgewood |  | 05/10/2020 | 09/10/2020 |  | Scheduled
OD0260 | TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | Total Maintenance Outage Duration Requested |  | 30/09/2020 | 16/10/2020 |  | Scheduled
20CM0010 | TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | Wire in low air alarm as per original de | 900908600 | 30/09/2020 | 16/10/2020 | 2 | Scheduled
20CM0454 | TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | T Phase Arklow 220kV Cubicle. T Phase VT connection DUE : 17-Jul-20 | 901134792 | 30/09/2020 | 16/10/2020 | 1 | Scheduled
19EG11183 | TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | 220kV SF6 Cubicle Operational Test |  | 30/09/2020 | 16/10/2020 | 4 | Scheduled
20LN0321 | TO-20-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | ARKLOW 220 | LODGEWOOD 220 | 1 | 2019HP-1[21]Bird Nests remove birds nest | 901084299 | 30/09/2020 | 16/10/2020 | 2 | Scheduled
OD0017 | TO-20-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | ARKLOW 110 | SHELTON ABBEY 110 | 2 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 17/12/2020 |  | Scheduled
TOP201022094630 | TO-20-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | ARKLOW 110 | SHELTON ABBEY 110 | 2 | Proximity to allow ESBN to replace corroded gantry in Shelton Abbey Compound |  | 23/11/2020 | 17/12/2020 |  | Scheduled
PROT2020069 | TO-20-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | ARKLOW 110 | SHELTON ABBEY 110 | 2 | P3 Protection maintenance of 7SA612, GRZ100 |  | 23/11/2020 | 17/12/2020 | 3 | Scheduled
20EG00051 | TO-20-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | ARKLOW 110 | SHELTON ABBEY 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 23/11/2020 | 17/12/2020 | 4 | Scheduled
20EG10026 | TO-20-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | ARKLOW 110 | SHELTON ABBEY 110 | 2 | 110kV Sect / Dist Operational Test |  | 23/11/2020 | 17/12/2020 | 4 | Scheduled
OD0738 | TO-20-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | ARKLOW 220 | ARKLOW 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01774 | TO-20-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | ARKLOW 220 | ARKLOW 110 | T2101 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0019 | TO-20-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00059 | TO-20-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00057 | TO-20-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN5242 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 5 (AT No.11, Span 10-11) Right Deadend Termination (Repair by 6th Aug 2020) | 901148345 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5238 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 1 (ET No.1, Span 1-2) Left Deadend Terminiation (Repair by 6th Nov 2020) | 901148340 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5239 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 2 (AT No.6, Span 6-7) Right Deadend Terminiation (Repair by 6th Nov 2020) | 901148341 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5240 | TO-20-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 3 (AT No.10, Span 9-10) Centre Deadend Terminiation (Repair by 6th Nov 2020) | 901148342 | 16/11/2020 | 19/11/2020 |  | Scheduled
20LN5241 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 4 (AT No.10, Span 10-11) Centre Deadend Terminiation (Repair by 6th June 2020) | 901148343 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5243 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 6 (AT No.154, Span 153-154) Centre Jumper Terminal (Repair by 6th Nov 2020) | 901148346 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5245 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 8 (R2, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020) | 901148349 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5246 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 9 (C1, Span 204-205) Centre Midspan Joint (Repair Immediately) | 901148350 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5247 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 10 (C1, Span 204-205) Right Midspan Joint (Measure resistance by while repairing Hotspot 9)) | 901148351 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5248 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 11 (R2, Span 168-169) Centre Midspan Joints (Measure resistance by 6th Aug 2020) | 901148352 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5244 | TO-20-ARV-COS-1-02 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | ARVA 110 | CARRICK ON SHANNON 110 | 1 | Hotspot 7 (R1, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020) | 901148348 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
TOP200113144955 | TO-20-ARV-GWE-1-01 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | P2 Protection maintenance of 7SA612, REL521 |  | 09/11/2020 | 13/11/2020 |  | Scheduled
OD0020 | TO-20-ARV-GWE-1-01 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 13/11/2020 |  | Scheduled
20EG00061 | TO-20-ARV-GWE-1-01 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 09/11/2020 | 13/11/2020 | 4 | Scheduled
CAPX2020010910460148 | TO-20-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN0462 | TO-20-ARV-GWE-1-01 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | 2019HP-1[157]Earths-Replace LPH e/w | 901084866 | 09/11/2020 | 13/11/2020 | 4 | Scheduled
20LN0464 | TO-20-ARV-GWE-1-01 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | ARVA 110 | GORTAWEE 110 | 1 | 2019HP-1[158]Earths-Replace RPH e/w | 901084867 | 09/11/2020 | 13/11/2020 | 4 | Scheduled
OD0021 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 06/03/2020 |  | Scheduled
20EG00065 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129885 | 24/02/2020 | 06/03/2020 | 4 | Scheduled
20EG00067 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 110kV CUBICLE CONDITION ASSESSMENT | 901129179 | 24/02/2020 | 06/03/2020 | 4 | Scheduled
20LN0484 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[63]Replace Pole only -Rot | 901086417 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0470 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[4]Replace Pole only -Rot | 901086415 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0481 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[58]Replace Pole only -Rot | 901086416 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0501 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[128]Replace Pole only -Rot | 901086418 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0503 | TO-20-ARV-NAV-1-02 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[132]Replace Pole only -Rot | 901086419 | 05/10/2020 | 09/10/2020 | 1 | Scheduled
20LN0509 | TO-20-ARV-NAV-1-02 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[191]Replace Pole only -Rot | 901086420 | 05/10/2020 | 09/10/2020 | 1 | Scheduled
20LN0511 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[199]Replace Pole only -Rot | 901086421 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0531 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[319]Replace Pole only -Rot | 901086424 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0515 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[229]Replace Pole only -Rot | 901086422 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
20LN0472 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[6]Earths-Replace earth lead | 901084868 | 24/02/2020 | 06/03/2020 | 4 | Scheduled
20LN0516 | TO-20-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | ARVA 110 | NAVAN 110 | 1 | 2019HP-1[230]Replace Pole only -Rot | 901086423 | 24/02/2020 | 06/03/2020 | 1 | Scheduled
OD0022 | TO-20-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | ARVA 110 | SHANKILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 29/10/2020 | 30/10/2020 |  | Scheduled
20EG10035 | TO-20-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | ARVA 110 | SHANKILL 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 29/10/2020 | 30/10/2020 | 4 | Scheduled
20LN0544 | TO-20-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | ARVA 110 | SHANKILL 110 | 1 | 2019HP-1[21]Bird Nests | 901084300 | 29/10/2020 | 30/10/2020 | 4 | Scheduled
TOP200429170256 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | Proximity for hot spot work LIS-SKL cubicle | PR0001 | 14/09/2020 | 25/09/2020 |  | Scheduled
OD0023 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 25/09/2020 |  | Scheduled
TOP200114090741 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 14/09/2020 | 25/09/2020 |  | Scheduled
20CM0292 | TO-20-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | O 1 O 1 ARVA 2 C.B. MONITORING TEMI | 901028567 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0388 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | Visual inspection of HIS HV cable sealin | 901068797 | 14/09/2020 | 25/09/2020 | 1 | Scheduled
18EG02392 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 25/09/2020 | 3 | Scheduled
19LN1838 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | 2018HP-1[Am 35]Bird Nests | 900983642 | 14/09/2020 | 25/09/2020 | 4 | Scheduled
20CM0293 | TO-20-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | Investigate CB gas leak & repair if poss | 901045926 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN1839 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | 2018HP-1[Am 29]Bird Nests | 900983641 | 14/09/2020 | 25/09/2020 | 4 | Scheduled
20EG20724 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | Cable Insp. 110kV XLPE |  | 14/09/2020 | 25/09/2020 | 4 | Scheduled
20LN0619 | TO-20-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | ARVA 110 | SHANKILL 110 | 2 | 2019HP-1[143]Bird Nests | 901084301 | 14/09/2020 | 25/09/2020 | 4 | Scheduled
OD0816 | TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | ATHEA 110 | ATHEA 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 25/08/2020 |  | Scheduled
20EG11336 | TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | ATHEA 110 | ATHEA 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 24/08/2020 | 25/08/2020 | 4 | Scheduled
20EG11338 | TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | ATHEA 110 | ATHEA 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 24/08/2020 | 25/08/2020 | 4 | Scheduled
20EG11337 | TO-20-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | ATHEA 110 | ATHEA 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 24/08/2020 | 25/08/2020 | 4 | Scheduled
OD0814 | TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | ATHEA 110 | DROMADA 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 28/08/2020 |  | Scheduled
18EG11330 | TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | ATHEA 110 | DROMADA 110 | 1 | 110kV SF6 Cubicle Operational Test | 901043693 | 24/08/2020 | 28/08/2020 | 3 | Scheduled
20EG20704 | TO-20-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | ATHEA 110 | DROMADA 110 | 1 | Cable Insp. 110kV XLPE |  | 24/08/2020 | 28/08/2020 | 4 | Scheduled
OD0966 | TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | ATHEA 110 | KNOCKANURE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10219 | TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | ATHEA 110 | KNOCKANURE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901043731 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02419 | TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | ATHEA 110 | KNOCKANURE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042193 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20726 | TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | ATHEA 110 | KNOCKANURE 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20705 | TO-20-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | ATHEA 110 | KNOCKANURE 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0895 | TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | ATHEA 110 | ATHEA 20 | T121 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 27/08/2020 |  | Scheduled
18EG11365 | TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | ATHEA 110 | ATHEA 20 | T121 | 110kV SF6 Cubicle Operational Test | 901043038 | 24/08/2020 | 27/08/2020 | 3 | Scheduled
20EG21388 | TO-20-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | ATHEA 110 | ATHEA 20 | T121 | Cable Insp. 110kV XLPE |  | 24/08/2020 | 27/08/2020 | 4 | Scheduled
OD0365 | TO-20-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18EG11253 | TO-20-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 901039205 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG11254 | TO-20-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 901039204 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG11255 | TO-20-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901039013 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020010910331741 | TO-20-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331736 | TO-20-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | ATHLONE 110 | ATHLONE 110 | 110SA1-2CB | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0327 | TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | ATHLONE 110 | ATHLONE 110 | CAP3 | Total Maintenance Outage Duration Requested |  | 22/06/2020 | 26/06/2020 |  | Scheduled
20CM0012 | TO-20-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | ATHLONE 110 | ATHLONE 110 | CAP3 | Contact resistance measurement on the ci | 901078674 | 22/06/2020 | 26/06/2020 | 2 | Scheduled
CAPX2020010910331737 | TO-20-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | ATHLONE 110 | ATHLONE 110 | CAP3 | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN0888 | TO-20-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | ATHLONE 110 | LANESBORO 110 | 1 | Conductor Sampling section 179-199 | 901046063 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351107 | TO-20-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | ATHLONE 110 | LANESBORO 110 | 1 | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331738 | TO-20-ATH-LA-1-03 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | ATHLONE 110 | LANESBORO 110 | 1 | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1271 | TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | ATHLONE 110 | ATHLONE 110 | M/CAP1 | Total Maintenance Outage Duration Requested |  | 30/06/2020 | 01/07/2020 |  | Scheduled
20CM0011 | TO-20-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | ATHLONE 110 | ATHLONE 110 | M/CAP1 | O1- Spray Weeds Cap 1 Cubicle | 901067981 | 30/06/2020 | 01/07/2020 | 2 | Scheduled
CAPX2020010910331739 | TO-20-ATH-M/CAP1-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | ATHLONE 110 | ATHLONE 110 | M/CAP1 | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0025 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN1886 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 2018HP-1[Am 75]Bird Nests | 900983699 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00079 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10038 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00077 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20004 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN0652 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 2019HP-1[23]Check Structure -Check Rot | 901086374 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN0655 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 2019HP-1[43]Check Structure -Check Rot | 901086375 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN0660 | TO-20-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 2019HP-1[75]Bird Nests | 901084302 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331742 | TO-20-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | ATHLONE 110 | SHANNONBRIDGE 110 | 1 | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331740 | TO-20-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | ATHLONE 110 | ATHLONE 38 | T141 | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331743 | TO-20-ATH-T142-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | ATHLONE 110 | ATHLONE 38 | T142 | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1211 | TO-20-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | ATHY 110 | ATHY 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04004 | TO-20-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | ATHY 110 | ATHY 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109103511108 | TO-20-ATY-110SA1-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | ATHY 110 | ATHY 110 | 110SA1 | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103511109 | TO-20-ATY-110SA2-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | ATHY 110 | ATHY 110 | 110SA2 | As a consequence of ATY-110SA1: 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200519091724 | TO-20-ATY-CLW-1-03 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | Proximity for Carlow Kellis 1 110 kV |  | 06/07/2020 | 09/07/2020 |  | Scheduled
TOP191209145820 | TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | 2019HP-1[122]Anti-Cl. Guard -Replace. Wrong type fitted | 901084078 | 24/02/2020 | 28/02/2020 |  | Scheduled
OD0026 | TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 28/02/2020 |  | Scheduled
TOP191209145857 | TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | End Tower 122 - Station Gantry in Carlow Replace insulators. Fit corona rings | 901074611 | 24/02/2020 | 28/02/2020 |  | Scheduled
20EG10041 | TO-20-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | 110kV SF6 Cubicle Operational Test | 901128701 | 24/02/2020 | 28/02/2020 | 4 | Scheduled
CAPX20200109103511110 | TO-20-ATY-CLW-1-02 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | ATHY 110 | CARLOW 110 | 1 | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191118154909 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | H7 cubicle ordinary service |  | 27/04/2020 | 01/05/2020 |  | Scheduled
OD0027 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/04/2020 | 01/05/2020 |  | Scheduled
PROT2020047 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | P2 Protection maintenance of REL521 |  | 27/04/2020 | 01/05/2020 | 2 | Scheduled
19EG00081 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901038563 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
20CM0267 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | lamp in mech box o/o/o , corrision on wa | 901072095 | 27/04/2020 | 01/05/2020 | 2 | Scheduled
19EG00080 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042196 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
20CM0379 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | moisture in surge counters | 901087221 | 27/04/2020 | 01/05/2020 | 1 | Scheduled
14LN3523 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 1[57] Replace pole - wayleave issue | 900606197 | 27/04/2020 | 01/05/2020 | 1 | Scheduled
19LN7122 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 2018HP-1[128]Check Structure-top rot | 900989777 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
19EG00404 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901050572 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
20CM0428 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | Replacement of Stolen Earths | 901146375 | 27/04/2020 | 01/05/2020 | 1 | Scheduled
20LN0701 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 2019HP-1[129]Check Structure -Check Rot | 901086377 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
20LN0702 | TO-20-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | ATHY 110 | PORTLAOISE 110 | 1 | 2019HP-1[130]Check Structure -Check Rot | 901086378 | 27/04/2020 | 01/05/2020 | 4 | Scheduled
CAPX20200109103511111 | TO-20-ATY-T101-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | ATHY 110 | ATHY 10 | T101 | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200113163908 | TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | P1 Protection maintenance of ISM21 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0366 | TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00994 | TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00995 | TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00993 | TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331744 | TO-20-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331750 | TO-20-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | AUGHINISH 110 | AUGHINISH 110 | 110SA1-2CB | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0028 | TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200821140655 | TO-20-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | Customer outage request |  | 09/11/2020 | 20/11/2020 |  | Scheduled
TOP201019174513 | TO-20-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | 1[EM 48] replacement of 110kV strain/duplicate insulator |  | 09/11/2020 | 20/11/2020 |  | Scheduled
TOP200821140640 | TO-20-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | As a consequence of CFM T101 |  | 09/11/2020 | 20/11/2020 |  | Scheduled
20EG00086 | TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129898 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331745 | TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20005 | TO-20-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | AUGHINISH 110 | CASTLEFARM 110 | 1 | Cable Insp. 110kV XLPE | 901129107 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020025 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | P2 Protection maintenance of 7SJ611, RADSB |  | 14/09/2020 | 02/10/2020 | 2 | Scheduled
TOP200804163805 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | Customer outage 14 @ CFM T102 14 Sept - 02 Oct |  | 14/09/2020 | 02/10/2020 |  | Scheduled
OD0029 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 02/10/2020 |  | Scheduled
TOP200821141317 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | Paint 110kV Tower |  | 14/09/2020 | 02/10/2020 |  | Scheduled
TOP200821141230 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | Replacement of Insulators |  | 14/09/2020 | 02/10/2020 |  | Scheduled
TOP200821140850 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | As a consequence of CFM-T102 |  | 14/09/2020 | 02/10/2020 |  | Scheduled
20CM0016 | TO-20-AUG-CFM-2-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | Assist with Relay Testing | 901030139 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00088 | TO-20-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 02/10/2020 | 4 | Scheduled
CAPX2020010910331751 | TO-20-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | AUGHINISH 110 | CASTLEFARM 110 | 2 | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1187 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 22/05/2020 |  | Scheduled
TOP200415112756 | TO-20-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Outstanding issues with the AR Supervisory scheme on the bay including testing and recommissioning of the BCU and testing of new commands and PI back to NCC |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00098 | TO-20-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN5208 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 2 (Transposition Tower No. 58 Span 58/59) Centre Jumper Terminal (Repair by 24th Oct) | 901110456 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5207 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 1 (Transposition Tower No. 58 Span 58/59) Right Jumper Terminal (Repair by 24th Oct) | 901110462 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5214 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 8 (DC Cable Tower No.160 Span 159/160) Lower (DC) Jumper Terminal (Repair by 24th Oct) | 901110437 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5209 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 3 (Transposition Tower No. 58 Span 58/59) Left Jumper Terminal (Repair by 24th Oct) | 901110457 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5210 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 4 (Transposition Tower No. 58 Span 57/58) Left Jumper Terminal (Repair by 24th Jul) | 901110439 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5211 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 5 (Transposition Tower No. 58 Span 57/58) Centre Jumper Terminal (Repair by 24th May) | 901110460 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5212 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 6 (Transposition Tower No. 58 Span 57/58) Right Jumper Terminal (Repair by 24th Oct) | 901110461 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20LN5213 | TO-20-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | AUGHINISH 110 | KILPADDOGE 110 | 1 | Hotspot 7 (DC Cable Tower No.160 Span 159/160) Top (DC) Jumper Terminal (Repair by 24th Oct) | 901110438 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
OD0030 | TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | AUGHINISH 110 | MONETEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10046 | TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | AUGHINISH 110 | MONETEEN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10045 | TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | AUGHINISH 110 | MONETEEN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331746 | TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | AUGHINISH 110 | MONETEEN 110 | 1 | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN0721 | TO-20-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | AUGHINISH 110 | MONETEEN 110 | 1 | 2019HP-1[19]Off Plumb -plumb poles | 901084931 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0031 | TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | AUGHINISH 110 | SEALROCK 110 | 3 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 24/07/2020 |  | Scheduled
20EG10047 | TO-20-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | AUGHINISH 110 | SEALROCK 110 | 3 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20007 | TO-20-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | AUGHINISH 110 | SEALROCK 110 | 3 | Cable Insp. 110kV XLPE | 901129109 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
CAPX2020010910331747 | TO-20-AUG-SK-3-03 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | AUGHINISH 110 | SEALROCK 110 | 3 | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0032 | TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | Total Maintenance Outage Duration Requested |  | 08/09/2020 | 10/09/2020 |  | Scheduled
TOP200821141951 | TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | Outage start @ 06:00 09 Nov 2020, Outage end @ 18:00 12 Nov 2020 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200821141939 | TO-20-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | Customer outage request |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10048 | TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | 110kV SF6 Cubicle Operational Test |  | 08/09/2020 | 10/09/2020 | 4 | Scheduled
CAPX2020010910331752 | TO-20-AUG-SK-4-03 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20008 | TO-20-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | AUGHINISH 110 | SEALROCK 110 | 4 | Cable Insp. 110kV XLPE |  | 08/09/2020 | 10/09/2020 | 4 | Scheduled
OD1328 | TO-20-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | BALLYBEG 110 | BALLYBEG 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04007 | TO-20-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | BALLYBEG 110 | BALLYBEG 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0034 | TO-20-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | BALLYBEG 110 | CARRICKMINES GIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/11/2020 | 13/11/2020 |  | Scheduled
18EG23417 | TO-20-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | BALLYBEG 110 | CARRICKMINES GIS 110 | 1 | Annual Insp. 110kV Feeder XLPE Cable | 900944045 | 10/11/2020 | 13/11/2020 | 3 | Scheduled
19LN0617 | TO-20-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | BALLYBEG 110 | CARRICKMINES GIS 110 | 1 | 2018HP-1[104]Foundation/Site repair | 900979776 | 10/11/2020 | 13/11/2020 | 4 | Scheduled
20EG00102 | TO-20-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | BALLYBEG 110 | CARRICKMINES GIS 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 10/11/2020 | 13/11/2020 | 4 | Scheduled
15EG04008 | TO-20-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | BALLYDINE 110 | BALLYDINE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 900782940 | 22/07/2020 | 24/07/2020 | 1 | Scheduled
20CM0426 | TO-20-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | BALLYDINE 110 | BALLYDINE 110 | 110SA1 | Replacement of Stolen Earths | 901091973 | 22/07/2020 | 24/07/2020 | 1 | Scheduled
CAPX20200109103511112 | TO-20-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | BALLYDINE 110 | BALLYDINE 110 | 110SA1 | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 22/07/2020 | 24/07/2020 |  | Scheduled
CAPX20200109103511113 | TO-20-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | BALLYDINE 110 | BALLYDINE 110 | 110SA2 | As a consequence of BDN-110SA1: 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 24/06/2020 | 26/06/2020 |  | Scheduled
OD0035 | TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | BALLYDINE 110 | CULLENAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 22/07/2020 | 24/07/2020 |  | Scheduled
16LN0392 | TO-20-BDN-CUL-1-03 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | BALLYDINE 110 | CULLENAGH 110 | 1 | 2015HP-3[26,35,40]Off Plumb Poles | 900727019 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
15LN0546 | TO-20-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | BALLYDINE 110 | CULLENAGH 110 | 1 | 2014HP-[58,59,60,77,97,99,107]Off Plumb | 900649539 | 09/09/2020 | 11/09/2020 | 1 | Scheduled
15LN0545 | TO-20-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | BALLYDINE 110 | CULLENAGH 110 | 1 | 2014HP-[27,35,40,48,55,56]Off Plumb | 900649538 | 09/09/2020 | 11/09/2020 | 1 | Scheduled
CAPX20200109103511114 | TO-20-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | BALLYDINE 110 | CULLENAGH 110 | 1 | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 22/07/2020 | 24/07/2020 |  | Scheduled
OD0036 | TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | BALLYDINE 110 | DOON 110 | 1 | Total Maintenance Outage Duration Requested |  | 30/07/2020 | 06/08/2020 |  | Scheduled
20EG10055 | TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | BALLYDINE 110 | DOON 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129614 | 30/07/2020 | 06/08/2020 | 4 | Scheduled
20EG00108 | TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | BALLYDINE 110 | DOON 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901151576 | 30/07/2020 | 06/08/2020 | 4 | Scheduled
19LN2097 | TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | BALLYDINE 110 | DOON 110 | 1 | 2018HP-1[2]Replace Pole only-Rot | 900983907 | 30/07/2020 | 06/08/2020 | 1 | Scheduled
20CM0419 | TO-20-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | BALLYDINE 110 | DOON 110 | 1 | Replacement of Stolen Earths | 901091975 | 30/07/2020 | 06/08/2020 | 1 | Scheduled
TOP200210153146 | TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | BALLYDINE 110 | BALLYDINE 10 | MRK1 | Replace Stolen Earths |  | 22/07/2020 | 24/07/2020 |  | Scheduled
OD0456 | TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | BALLYDINE 110 | BALLYDINE 10 | MRK1 | Total Maintenance Outage Duration Requested |  | 22/07/2020 | 24/07/2020 |  | Scheduled
20EG10056 | TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | BALLYDINE 110 | BALLYDINE 10 | MRK1 | 110kV MO Cubicle Operational Test |  | 22/07/2020 | 24/07/2020 | 4 | Scheduled
CAPX20200109103511115 | TO-20-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | BALLYDINE 110 | BALLYDINE 10 | MRK1 | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 22/07/2020 | 24/07/2020 |  | Scheduled
OD0457 | TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | BALLYDINE 110 | BALLYDINE 10 | MRK3 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 20/07/2020 |  | Scheduled
20CM0422 | TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | BALLYDINE 110 | BALLYDINE 10 | MRK3 | Replace Stolen Earths | 901091974 | 13/07/2020 | 20/07/2020 | 1 | Scheduled
18EG00114 | TO-20-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | BALLYDINE 110 | BALLYDINE 10 | MRK3 | 110kV SF6 Cubicle Ordinary Service | 901042188 | 13/07/2020 | 20/07/2020 | 3 | Scheduled
CAPX20200109103511116 | TO-20-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | BALLYDINE 110 | BALLYDINE 38 | T141 | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 22/07/2020 | 24/07/2020 |  | Reference
CAPX2020102710021217 | TO-20-BLI-DMY-1-06 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | BALLYLICKEY 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020083111380711 | TO-20-BLI-DMY-1-04 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | BALLYLICKEY 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Reference
CAPX2020072209525805 | TO-20-BLI-DMY-1-01 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | BALLYLICKEY 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2020102710021223 | TO-20-BLI-DMY-1-07 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | BALLYLICKEY 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331762 | TO-20-BLI-DMY-1-01 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | BALLYLICKEY 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2020083111380712 | TO-20-BLI-T142-04 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | BALLYLICKEY 110 | BALLYLICKEY 38 | T142 | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Reference
CAPX2020102710021218 | TO-20-BLI-T142-06 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | BALLYLICKEY 110 | BALLYLICKEY 38 | T142 | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020102710021224 | TO-20-BLI-T142-07 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | BALLYLICKEY 110 | BALLYLICKEY 38 | T142 | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020072209525806 | TO-20-BLI-T142-01 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | BALLYLICKEY 110 | BALLYLICKEY 38 | T142 | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2020010910331763 | TO-20-BLI-T142-01 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | BALLYLICKEY 110 | BALLYLICKEY 38 | T142 | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2019121810393238 | TO-20-110 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110A1 | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 20/02/2020 | 20/02/2020 |  | Scheduled
CAPX2019121810393244 | TO-20-110 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110A2 | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 20/02/2020 | 20/02/2020 |  | Scheduled
CAPX2019121810393239 | TO-20-110 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110B1 | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 20/02/2020 | 20/02/2020 |  | Scheduled
CAPX2019121810393245 | TO-20-110 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110B2 | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 20/02/2020 | 20/02/2020 |  | Scheduled
OD1115 | TO-20-BYH-110K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23459 | TO-20-BYH-110K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K1 | 110kV GIS Cubicle Operational Test | 901050244 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121810393240 | TO-20-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K1 | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393241 | TO-20-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K1 | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393246 | TO-20-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K2 | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393247 | TO-20-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110K2 | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1117 | TO-20-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23466 | TO-20-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test | 901043737 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121810393242 | TO-20-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393248 | TO-20-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1118 | TO-20-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SB1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23469 | TO-20-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SB1-2CB | 110kV GIS Cubicle Operational Test | 901043738 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121810393243 | TO-20-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393249 | TO-20-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | BALLYNAHULLA 110 | BALLYNAHULLA 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0995 | TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K1 | Total Maintenance Outage Duration Requested |  | 27/02/2020 | 03/03/2020 |  | Scheduled
20CM0019 | TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K1 | PI from DEM1 & DEM2 not working followin | 901078169 | 27/02/2020 | 03/03/2020 | 1 | Scheduled
20EG21076 | TO-20-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K1 | 220kV GIS Cubicle Ordinary Service | 901129779 | 27/02/2020 | 03/03/2020 | 4 | Scheduled
OD0996 | TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K2 | Total Maintenance Outage Duration Requested |  | 04/03/2020 | 10/03/2020 |  | Scheduled
20CM0021 | TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K2 | PI from DEM1 & DEM2 not working followin | 901078168 | 04/03/2020 | 10/03/2020 | 1 | Scheduled
20EG21080 | TO-20-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220K2 | 220kV GIS Cubicle Ordinary Service | 901129804 | 04/03/2020 | 10/03/2020 | 4 | Scheduled
OD0997 | TO-20-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21084 | TO-20-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220SA1-2CB | 220kV GIS Cubicle Operational Test | 901043813 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0998 | TO-20-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220SB1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21089 | TO-20-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | BALLYNAHULLA 220 | BALLYNAHULLA 220 | 220SB1-2CB | 220kV GIS Cubicle Operational Test | 901043800 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP201013123139 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Maintenance |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0985 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0401 | TO-20-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Aux Relay - replace contactors |  | 12/11/2020 | 20/11/2020 | 2 | Scheduled
20CM0404 | TO-20-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Aux Relay - replace contactors |  | 12/11/2020 | 20/11/2020 | 2 | Scheduled
20EG21031 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21027 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21033 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21026 | TO-20-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | BALLYNAHULLA 220 | BALLYVOUSKILL 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1189 | TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | BALLYNAHULLA 110 | CORDAL 110 | 1 | Total Maintenance Outage Duration Requested |  | 11/08/2020 | 13/08/2020 |  | Scheduled
18EG23573 | TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | BALLYNAHULLA 110 | CORDAL 110 | 1 | Insp. 110kV Feeder XLPE Cable | 901128997 | 11/08/2020 | 13/08/2020 | 3 | Scheduled
20EG23574 | TO-20-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | BALLYNAHULLA 110 | CORDAL 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129678 | 11/08/2020 | 13/08/2020 | 4 | Scheduled
OD1225 | TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | BALLYNAHULLA 110 | GLENLARA 110 | 1 | Total Maintenance Outage Duration Requested |  | 26/03/2020 | 26/03/2020 |  | Scheduled
20EG23662 | TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | BALLYNAHULLA 110 | GLENLARA 110 | 1 | 110kV GIS Cubicle Operational Test | 901129526 | 26/03/2020 | 26/03/2020 | 4 | Scheduled
20EG23369 | TO-20-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | BALLYNAHULLA 110 | GLENLARA 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129703 | 26/03/2020 | 26/03/2020 | 4 | Scheduled
OD0986 | TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | SF6 repairs in Knockanure |  | 27/10/2020 | 11/11/2020 |  | Scheduled
17EG21041 | TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Annual Insp. 400 & 220 Statn. XLPE Cable | 901051726 | 27/10/2020 | 11/11/2020 | 3 | Scheduled
18LN1761 | TO-20-BYH-KNR-1-05 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | 2017HP-1[37]Susp/Dup 220kV replacement | 900897561 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17EG21034 | TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Annual Insp. 400 & 220 Statn. XLPE Cable | 901051722 | 27/10/2020 | 11/11/2020 | 3 | Scheduled
20CM0395 | TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Aux Relay - replace contactors |  | 27/10/2020 | 11/11/2020 | 2 | Scheduled
20CM0394 | TO-20-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Aux Relay - replace contactors |  | 27/10/2020 | 11/11/2020 | 1 | Scheduled
20EG21037 | TO-20-BYH-KNR-1-05 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019112814362501 | TO-20-BYH-KNR-1-02 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder | CP0883 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21038 | TO-20-BYH-KNR-1-05 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100215315709 | TO-20-BYH-KNR-1-03 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Proximity outage to remove scaffolding | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN0804 | TO-20-BYH-KNR-1-05 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | 2019HP-1[80]Insulator Broken disc | 901084882 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100214461800 | TO-20-BYH-KNR-1-04 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Line uprate works - restringing, foundation reinforcement, hardware etc | CP0883 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100215315701 | TO-20-BYH-KNR-1-03 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | BALLYNAHULLA 220 | KNOCKANURE 220 | 1 | Proximity outage to move link box | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1139 | TO-20-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23333 | TO-20-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2101 | 110kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23330 | TO-20-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2101 | 220kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23445 | TO-20-BYH-T2101-02 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2101 | Cable Insp. 400 & 220kV Feeder XLPE | 901129028 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1140 | TO-20-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2102 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 03/09/2020 |  | Scheduled
20CM0025 | TO-20-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2102 | Following the malfunction fault on oil m | 901079981 | 01/09/2020 | 03/09/2020 | 2 | Scheduled
20CM0024 | TO-20-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2102 | False low oil alarm & DC earth fault com | 901075872 | 01/09/2020 | 03/09/2020 | 2 | Scheduled
20EG23324 | TO-20-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2102 | 110kV GIS Cubicle Operational Test |  | 01/09/2020 | 03/09/2020 | 4 | Scheduled
20EG23321 | TO-20-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | BALLYNAHULLA 220 | BALLYNAHULLA 110 | T2102 | 220kV GIS Cubicle Operational Test |  | 01/09/2020 | 03/09/2020 | 4 | Scheduled
CAPX2019121810393226 | TO-20-110 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110A1 | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 18/02/2020 | 18/02/2020 |  | Scheduled
CAPX2019121810393232 | TO-20-110 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110A2 | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 18/02/2020 | 18/02/2020 |  | Scheduled
CAPX2019121810393227 | TO-20-110 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110B1 | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 18/02/2020 | 18/02/2020 |  | Scheduled
CAPX2019121810393233 | TO-20-110 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110B2 | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 18/02/2020 | 18/02/2020 |  | Scheduled
CAPX2019121810393228 | TO-20-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110K1 | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393229 | TO-20-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110K1 | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393234 | TO-20-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110K2 | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393235 | TO-20-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110K2 | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1001 | TO-20-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21099 | TO-20-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test | 901043740 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019121810393236 | TO-20-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393230 | TO-20-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393231 | TO-20-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393237 | TO-20-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | BALLYVOUSKILL 110 | BALLYVOUSKILL 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1003 | TO-20-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | BALLYVOUSKILL 220 | BALLYVOUSKILL 220 | 220K1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21110 | TO-20-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | BALLYVOUSKILL 220 | BALLYVOUSKILL 220 | 220K1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1004 | TO-20-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | BALLYVOUSKILL 220 | BALLYVOUSKILL 220 | 220K2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21111 | TO-20-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | BALLYVOUSKILL 220 | BALLYVOUSKILL 220 | 220K2 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0268 | TO-20-BVK-CLA-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0407 | TO-20-BVK-CLA-1-02 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | Aux Relay - replace contactors |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00788 | TO-20-BVK-CLA-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00790 | TO-20-BVK-CLA-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG21043 | TO-20-BVK-CLA-1-03 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | 220kV GIS Cubicle Ordinary Service | 901050433 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100210345745 | TO-20-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | BALLYVOUSKILL 220 | CLASHAVOON 220 | 1 | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23803 | TO-20-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | BALLYVOUSKILL 110 | COOMATAGGART 110 | 1 | Cable Insp. 110kV XLPE | 901132973 | 28/09/2020 | 02/10/2020 | 4 | Scheduled
OD1190 | TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | BALLYVOUSKILL 110 | GARROW 110 | 1 | Total Maintenance Outage Duration Requested |  | 30/06/2020 | 03/07/2020 |  | Scheduled
20CM0389 | TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | BALLYVOUSKILL 110 | GARROW 110 | 1 | Water ingress into JB01 Link Box – Raise | 901056104 | 30/06/2020 | 03/07/2020 | 1 | Scheduled
20CM0390 | TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | BALLYVOUSKILL 110 | GARROW 110 | 1 | Visual inspection of HIS HV cable sealin | 901068796 | 30/06/2020 | 03/07/2020 | 2 | Scheduled
20EG21005 | TO-20-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | BALLYVOUSKILL 110 | GARROW 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129712 | 30/06/2020 | 03/07/2020 | 4 | Scheduled
OD1043 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21229 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21236 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21232 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21231 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21230 | TO-20-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2101 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1044 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21243 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21245 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21298 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21248 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21249 | TO-20-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | BALLYVOUSKILL 220 | BALLYVOUSKILL 110 | T2102 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020048 | TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | BALLYWATER 110 | CRANE 110 | 1 | P2 Protection maintenance of 7SA513 |  | 02/06/2020 | 02/06/2020 | 2 | Scheduled
OD0038 | TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | BALLYWATER 110 | CRANE 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/06/2020 | 02/06/2020 |  | Scheduled
20EG10059 | TO-20-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | BALLYWATER 110 | CRANE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129684 | 02/06/2020 | 02/06/2020 | 4 | Scheduled
OD0039 | TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | BALTRASNA 110 | CORDUFF 110 | 1 | Total Maintenance Outage Duration Requested |  | 05/08/2020 | 05/08/2020 |  | Scheduled
20EG10060 | TO-20-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | BALTRASNA 110 | CORDUFF 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129589 | 05/08/2020 | 05/08/2020 | 4 | Scheduled
OD0040 | TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | BALTRASNA 110 | DRYBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 13/08/2020 |  | Scheduled
19LN2158 | TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | BALTRASNA 110 | DRYBRIDGE 110 | 1 | 2018HP-1[98]Insul&HW Replace check | 900983998 | 10/08/2020 | 13/08/2020 | 4 | Scheduled
20EG10062 | TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | BALTRASNA 110 | DRYBRIDGE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129588 | 10/08/2020 | 13/08/2020 | 4 | Scheduled
20EG10063 | TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | BALTRASNA 110 | DRYBRIDGE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 10/08/2020 | 13/08/2020 | 4 | Scheduled
20LN0843 | TO-20-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | BALTRASNA 110 | DRYBRIDGE 110 | 1 | 2019HP-1[56]Replace Pole only -Rot | 901086425 | 10/08/2020 | 13/08/2020 | 1 | Scheduled
OD1308 | TO-20-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | BANDON 110 | BANDON 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 28/09/2020 | 30/09/2020 |  | Scheduled
20EG04010 | TO-20-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | BANDON 110 | BANDON 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 28/09/2020 | 30/09/2020 | 4 | Scheduled
CAPX20200109103511117 | TO-20-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | BANDON 110 | BANDON 110 | 110SA1 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 28/09/2020 | 30/09/2020 |  | Scheduled
CAPX20200109103511118 | TO-20-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | BANDON 110 | BANDON 110 | 110SA2 | As a consequence of BAN-110SA1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 28/09/2020 | 30/09/2020 |  | Scheduled
OD0041 | TO-20-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | BANDON 110 | BRINNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 28/09/2020 | 30/09/2020 |  | Scheduled
20EG10064 | TO-20-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | BANDON 110 | BRINNY 110 | 1 | 110kV MO Cubicle Operational Test |  | 28/09/2020 | 30/09/2020 | 4 | Scheduled
CAPX20200109103511119 | TO-20-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | BANDON 110 | BRINNY 110 | 1 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 28/09/2020 | 30/09/2020 |  | Scheduled
OD1371 | TO-20-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | BANDON 110 | BRINNY 110 | 2 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 14/08/2020 |  | Scheduled
20EG10065 | TO-20-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | BANDON 110 | BRINNY 110 | 2 | 110kV MO Cubicle Operational Test |  | 10/08/2020 | 14/08/2020 | 4 | Scheduled
OD1272 | TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | BANDON 110 | BANDON 110 | CAP1 | Total Maintenance Outage Duration Requested |  | 02/06/2020 | 05/06/2020 |  | Scheduled
20CM0029 | TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | BANDON 110 | BANDON 110 | CAP1 | O1- R Phase Manual Handle Limit Switch n | 901079629 | 02/06/2020 | 05/06/2020 | 1 | Scheduled
20EG05006 | TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | BANDON 110 | BANDON 110 | CAP1 | 110kV SF6 Cubicle Ordinary Service |  | 02/06/2020 | 05/06/2020 | 4 | Scheduled
20CM0001 | TO-20-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | BANDON 110 | BANDON 110 | CAP1 | Resolve the issue regarding the isolator switch to the motor circuit for manual charging of closing coil. |  | 02/06/2020 | 05/06/2020 | 2 | Scheduled
CAPX20200109103511120 | TO-20-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | BANDON 110 | BANDON 110 | CAP1 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 28/09/2020 | 30/09/2020 |  | Scheduled
TOP200908145230 | TO-20-BAN-DMY-1-04 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | BANDON 110 | DUNMANWAY 110 | 1 | As consequence of Bandon-Brinny 110kV outage |  | 28/09/2020 | 30/09/2020 |  | Scheduled
CAPX2020062516112800 | TO-20-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | BANDON 110 | DUNMANWAY 110 | 1 | 110 kV A2 @ DMY: Isolate M21BBP Cabinet | CP0930 | 13/07/2020 | 17/07/2020 |  | Scheduled
OD0043 | TO-20-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | BANDON 110 | DUNMANWAY 110 | 1 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 17/07/2020 |  | Scheduled
20EG10067 | TO-20-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | BANDON 110 | DUNMANWAY 110 | 1 | 110kV MO Cubicle Operational Test | 901129476 | 13/07/2020 | 17/07/2020 | 4 | Scheduled
CAPX20200109103511121 | TO-20-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | BANDON 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 02/09/2020 | 04/09/2020 |  | Scheduled
OD0044 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/09/2020 | 15/09/2020 |  | Scheduled
20EG00137 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 09/09/2020 | 15/09/2020 | 4 | Scheduled
20EG10068 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 09/09/2020 | 15/09/2020 | 4 | Scheduled
19LN2203 | TO-20-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 2018HP-1[MP141]Arcing horns-Replace | 900984137 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00139 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 09/09/2020 | 15/09/2020 | 4 | Scheduled
20CM0273 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | O1-Bandon 110kv Cubicle Moss Build Up | 901028752 | 09/09/2020 | 15/09/2020 | 1 | Scheduled
19LN2208 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 2018HP-1[77]Off PlumbPlumb poles | 900984142 | 09/09/2020 | 15/09/2020 | 4 | Scheduled
20CM0274 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | O1-Bandon 110kv CB SF6 Indicator corrode | 901028753 | 09/09/2020 | 15/09/2020 | 1 | Scheduled
20LN5236 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | Hotspot 1 (Strain Pole No.114, Span 114/115) Centre Jumper Terminal (Repair by 6th Nov) | 901147760 | 09/09/2020 | 15/09/2020 | 1 | Scheduled
20EG20009 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | Cable Insp. 110kV XLPE |  | 09/09/2020 | 15/09/2020 | 4 | Scheduled
20LN0903 | TO-20-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 2019HP-1[141]Arching Horns -Missing | 900995455 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN0897 | TO-20-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | BANDON 110 | RAFFEEN 110 | 1 | 2019HP-1[151]Insulator broken aux insul | 901084834 | 09/09/2020 | 15/09/2020 | 2 | Scheduled
CAPX20200109103511122 | TO-20-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | BANDON 110 | BANDON 10 | T101 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX20200109103511123 | TO-20-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | BANDON 110 | BANDON 38 | T141 | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 28/09/2020 | 30/09/2020 |  | Reference
OD1370 | TO-20-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | BANOGE 110 | CRANE 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/11/2020 | 27/11/2020 |  | Scheduled
19EG10023 | TO-20-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | BANOGE 110 | CRANE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 27/11/2020 | 27/11/2020 | 4 | Scheduled
19EG11295 | TO-20-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | BANOGE 110 | CRANE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 27/11/2020 | 27/11/2020 | 4 | Scheduled
PROT2020104 | TO-20-BRY-RAF-1-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-1 | BARNAHELY 110 | RAFFEEN 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/12/2500 | 25/12/2500 | 3 | Reference (Unscheduled)
PROT2020105 | TO-20-BRY-RAF-2-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-2 | BARNAHELY 110 | RAFFEEN 110 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/12/2500 | 25/12/2500 | 3 | Reference (Unscheduled)
PROT2020163 | TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | BARODA 110 | BARODA 110 | 110SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 20/07/2020 | 22/07/2020 | 3 | Scheduled
OD0367 | TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | BARODA 110 | BARODA 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 22/07/2020 |  | Scheduled
20EG00997 | TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | BARODA 110 | BARODA 110 | 110SA1-2CB | 110kV GIS Cubicle Ordinary Service |  | 20/07/2020 | 22/07/2020 | 4 | Scheduled
20CM0353 | TO-20-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | BARODA 110 | BARODA 110 | 110SA1-2CB | Arrange outage to complete testing of Ci | 901087481 | 20/07/2020 | 22/07/2020 | 1 | Scheduled
OD0048 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | Total Maintenance Outage Duration Requested |  | 23/03/2020 | 27/03/2020 |  | Scheduled
20EG00146 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901129183 | 23/03/2020 | 27/03/2020 | 4 | Scheduled
20CM0416 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | Repair Mid-Point Link Box | 900567665 | 23/03/2020 | 27/03/2020 | 4 | Scheduled
20EG00145 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129932 | 23/03/2020 | 27/03/2020 | 4 | Scheduled
19EG20010 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | Cable Insp. 110kV XLPE |  | 23/03/2020 | 27/03/2020 | 4 | Scheduled
20CM0031 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | Reclosing sw protection panel : while tu | 901076771 | 23/03/2020 | 27/03/2020 | 1 | Scheduled
20EG00144 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129957 | 23/03/2020 | 27/03/2020 | 4 | Scheduled
20CM0409 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | Inspect Phisterer CSE's (check serial number) | 900567665 | 23/03/2020 | 27/03/2020 | 1 | Scheduled
20CM0250 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | CT T-phase insulator damaged | 901076765 | 23/03/2020 | 27/03/2020 | 1 | Scheduled
20CM0249 | TO-20-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | BARODA 110 | MONREAD 110 | 1 | PI on DL/DE o/o/o | 901076757 | 23/03/2020 | 27/03/2020 | 1 | Scheduled
OD0049 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00151 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00150 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0255 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | surge counter illigable | 901078182 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0410 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | Inspect Phisterer CSE's (check serial number) |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG00148 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00149 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20011 | TO-20-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460194 | TO-20-BDA-NEW-1-02 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | BARODA 110 | NEWBRIDGE 110 | 1 | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0464 | TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | BARODA 110 | BARODA 10 | T101 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 02/09/2020 |  | Scheduled
20EG01333 | TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | BARODA 110 | BARODA 10 | T101 | 110KV CUBICLE CONDITION ASSESSMENT |  | 24/08/2020 | 02/09/2020 | 4 | Scheduled
20CM0032 | TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | BARODA 110 | BARODA 10 | T101 | Fire alarm to be certafied | 900796245 | 24/08/2020 | 02/09/2020 | 1 | Scheduled
20EG01332 | TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | BARODA 110 | BARODA 10 | T101 | 110kV SF6 Cubicle Ordinary Service |  | 24/08/2020 | 02/09/2020 | 4 | Scheduled
20EG20249 | TO-20-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | BARODA 110 | BARODA 10 | T101 | Cable Insp. 110kV XLPE |  | 24/08/2020 | 02/09/2020 | 4 | Scheduled
OD0465 | TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | BARODA 110 | BARODA 10 | T102 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 29/07/2020 |  | Scheduled
20EG01334 | TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | BARODA 110 | BARODA 10 | T102 | 110kV SF6 Cubicle Ordinary Service |  | 20/07/2020 | 29/07/2020 | 4 | Scheduled
20EG01335 | TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | BARODA 110 | BARODA 10 | T102 | 110KV CUBICLE CONDITION ASSESSMENT | 901129202 | 20/07/2020 | 29/07/2020 | 4 | Scheduled
20EG20250 | TO-20-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | BARODA 110 | BARODA 10 | T102 | Cable Insp. 110kV XLPE | 901129127 | 20/07/2020 | 29/07/2020 | 4 | Scheduled
19LN7198 | TO-20-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | BARRYMORE tee | KNOCKRAHA 110 | 1 | Hotspot 4 (Angle Tower No. 278, span 277/278) Right Deadend (repair by October 2019) | 901046847 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN7199 | TO-20-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | BARRYMORE tee | KNOCKRAHA 110 | 1 | Hotspot 5 (Angle Tower No.278, span 278/279) Left Deadend (repair by October 2019) | 901046848 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020101315173401 | TO-20-110 kV A1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1 | BELCAMP 110 | BELCAMP 110 | 110A1 | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2020101315173409 | TO-20-110 kV A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | BELCAMP 110 | BELCAMP 110 | 110A3 | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173402 | TO-20-110 kV B1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1 | BELCAMP 110 | BELCAMP 110 | 110B1 | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2020101315173410 | TO-20-110 kV B3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B3 | BELCAMP 110 | BELCAMP 110 | 110B3 | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173400 | TO-20-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | BELCAMP 110 | BELCAMP 110 | 110K1 | EI: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2020101315173405 | TO-20-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | BELCAMP 110 | BELCAMP 110 | 110K1 | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2020101315173404 | TO-20-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | BELCAMP 110 | BELCAMP 110 | 110K1 | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2020101315173403 | TO-20-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | BELCAMP 110 | BELCAMP 110 | 110K1 | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2019112611152900 | TO-20-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | BELCAMP 110 | BELCAMP 110 | 110K1 | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
CAPX2020101315173411 | TO-20-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | BELCAMP 110 | BELCAMP 110 | 110K3 | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173413 | TO-20-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | BELCAMP 110 | BELCAMP 110 | 110K3 | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173412 | TO-20-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | BELCAMP 110 | BELCAMP 110 | 110K3 | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173408 | TO-20-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | BELCAMP 110 | BELCAMP 110 | 110K3 | EI: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2019112611152901 | TO-20-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | BELCAMP 110 | BELCAMP 110 | 110K3 | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
CAPX2020101315173414 | TO-20-BLC-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | BELCAMP 110 | BELCAMP 110 | 110SA1-3CB | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173406 | TO-20-BLC-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | BELCAMP 110 | BELCAMP 110 | 110SA1-3CB | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2019112611152902 | TO-20-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | BELCAMP 110 | BELCAMP 110 | 110SA1-3CB | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
CAPX2020101315173415 | TO-20-BLC-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | BELCAMP 110 | BELCAMP 110 | 110SB1-3CB | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3 | CP1013 | 11/11/2020 | 12/11/2020 |  | Scheduled
CAPX2020101315173407 | TO-20-BLC-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | BELCAMP 110 | BELCAMP 110 | 110SB1-3CB | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station | CP1013 | 09/11/2020 | 10/11/2020 |  | Scheduled
CAPX2019112611152903 | TO-20-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | BELCAMP 110 | BELCAMP 110 | 110SB1-3CB | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
CAPX2020101315173422 | TO-20-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | BELCAMP 110 | DARNDALE 110 | 1 | EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590735 | TO-20-BLC-DND-3-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | BELCAMP 110 | DARNDALE 110 | 3 | EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020102311352506 | TO-20-BLC-DND-3-03 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | BELCAMP 110 | DARNDALE 110 | 3 | EI: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019112611152904 | TO-20-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | BELCAMP 220 | FINGLAS 220 | 1 | Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
CAPX2019112611152905 | TO-20-BLC-T2103-01 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | BELCAMP 220 | BELCAMP 110 | T2103 | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages. | CP0437 | 04/09/2020 | 09/09/2020 |  | Scheduled
OD0695 | TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | BELLACORICK 110 | BELLACORICK 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 03/09/2020 | 04/09/2020 |  | Proposed
17EG11204 | TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | BELLACORICK 110 | BELLACORICK 110 | 110SA1 | 110kV Sect / Dist Operational Test | 900942127 | 03/09/2020 | 04/09/2020 | 2 | Proposed
CAPX20200109103511129 | TO-20-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | BELLACORICK 110 | BELLACORICK 110 | 110SA1 | As a consequence of BK-110SA2: 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103511125 | TO-20-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | BELLACORICK 110 | BELLACORICK 110 | 110SA1 | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 03/09/2020 | 04/09/2020 |  | Proposed
OD0696 | TO-20-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | BELLACORICK 110 | BELLACORICK 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11203 | TO-20-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | BELLACORICK 110 | BELLACORICK 110 | 110SA2 | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109103511126 | TO-20-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | BELLACORICK 110 | BELLACORICK 110 | 110SA2 | As a consequence of BK-110SA1: 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 03/09/2020 | 04/09/2020 |  | Proposed
OD0809 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/11/2020 | 19/11/2020 |  | Scheduled
19LN0478 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | 2018HP-40m[59-60]TimCut 110kV(Rural) | 900979811 | 12/11/2020 | 19/11/2020 | 1 | Scheduled
19EG00157 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | 110kV MO Cubicle Ordinary Service | 901050314 | 12/11/2020 | 19/11/2020 | 4 | Scheduled
19EG10078 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | 110kV MO Cubicle Operational Test | 901050277 | 12/11/2020 | 19/11/2020 | 4 | Scheduled
CAPX20200109103511131 | TO-20-BK-CBR-1-04 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN0965 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | 2019HP-30m[168-169]TimCut 110kV(Rural) | 901088171 | 12/11/2020 | 19/11/2020 | 1 | Scheduled
20LN5256 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | HAZ CNF 80m[101-102] 8-9m High Timber U | 901060073 | 12/11/2020 | 19/11/2020 | 1 | Scheduled
20EG20012 | TO-20-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | BELLACORICK 110 | CASTLEBAR 110 | 1 | Cable Insp. 110kV XLPE |  | 12/11/2020 | 19/11/2020 | 4 | Scheduled
OD0054 | TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | BELLACORICK 110 | MOY 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
20EG23786 | TO-20-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | BELLACORICK 110 | MOY 110 | 1 | Cable Inspection XLPE |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
CAPX20200109103511127 | TO-20-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | BELLACORICK 110 | MOY 110 | 1 | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1227 | TO-20-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0488 | TO-20-BK-SKY-1-03 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | NCC CANNOT OPERATE CB | 901137803 | 14/07/2020 | 15/07/2020 | 1 | Scheduled
20EG23747 | TO-20-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23745 | TO-20-BK-SKY-1-03 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129688 | 14/07/2020 | 15/07/2020 | 4 | Scheduled
20EG23742 | TO-20-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109103511132 | TO-20-BK-SKY-1-02 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | BELLACORICK 110 | SRAHNAKILLY 110 | 1 | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191210160751 | TO-20-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | BELLACORICK 110 | BELLACORICK 20 | T122 | Bay Outage for BZP | CP0850 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX20200109103511133 | TO-20-BK-T122-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | BELLACORICK 110 | BELLACORICK 20 | T122 | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX20200109103511128 | TO-20-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | BELLACORICK 110 | BELLACORICK 38 | T141 | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 03/09/2020 | 04/09/2020 |  | Reference (Proposed)
CAPX2019101112164641 | TO-20-BIN-110SA1-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164640 | TO-20-BIN-110SA1-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164631 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164623 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164620 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164617 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164614 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164613 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164609 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164627 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164604 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164600 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164635 | TO-20-BIN-110SA1-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164610 | TO-20-BIN-110SA1-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA1 | BINBANE 110 | BINBANE 110 | 110SA1 | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164612 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164601 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164611 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164643 | TO-20-BIN-110SA2-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164615 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164616 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164618 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164621 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164642 | TO-20-BIN-110SA2-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164628 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164632 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164636 | TO-20-BIN-110SA2-02 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164624 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164605 | TO-20-BIN-110SA2-01 | SECTIONALISING DISCONNECT - BINBANE 110-BINBANE 110-110SA2 | BINBANE 110 | BINBANE 110 | 110SA2 | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0064 | TO-20-BIN-CF-1-05 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
PROT2020071 | TO-20-BIN-CF-1-05 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | P3 Protection maintenance of 7SA511, GRZ100 |  | 27/10/2020 | 30/10/2020 | 3 | Scheduled
20EG00164 | TO-20-BIN-CF-1-05 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
20LN5257 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 1 (AM No.110, Span 109-110) Centre Deadend Termination (Repair by 5th Sep 2020) | 901153752 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5258 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 2 (AM No.110, Span 109-110) Right Deadend Termination (Repair by 5th Sep 2020) | 901153753 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5259 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 3 (AM No.110, Span 110-111) Centre Deadend Termination (Repair by 5th Dec 2020) | 901153754 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5260 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 4 (AM No.110, Span 110-111) Right Deadend Termination (Repair by 5th Dec 2020) | 901153755 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5261 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 5 (AM No.116, Span 116-117) Left Deadend Termination (Repair by 5th Jul 2020) | 901153756 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5262 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 6 (AM No.116, Span 116-117) Centre Deadend Termination (Repair by 5th Sep 2020) | 901153757 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5263 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 7 (AM No.116, Span 116-117) Right Deadend Termination (Repair immediately) | 901153758 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5265 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 9 (AM No.116, Span 115-116) Right Deadend Termination (Repair by 5th Dec 2020) | 901153940 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019101112164602 | TO-20-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164625 | TO-20-BIN-CF-1-02 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164633 | TO-20-BIN-CF-1-04 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101112164629 | TO-20-BIN-CF-1-03 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5264 | TO-20-BIN-CF-1-06 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | BINBANE 110 | CATHALEENS FALL 110 | 1 | Hotspot 8 (AM No.116, Span 115-116) Centre Deadend Termination (Repair by 5th Dec 2020) | 901153759 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019101112164607 | TO-20-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | BINBANE 110 | BINBANE 38 | T141 | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164647 | TO-20-BIN-T141-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | BINBANE 110 | BINBANE 38 | T141 | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164646 | TO-20-BIN-T141-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | BINBANE 110 | BINBANE 38 | T141 | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164638 | TO-20-BIN-T141-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | BINBANE 110 | BINBANE 38 | T141 | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164630 | TO-20-BIN-T142-03 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164626 | TO-20-BIN-T142-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142 | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164622 | TO-20-BIN-T142-05 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164619 | TO-20-BIN-T142-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164634 | TO-20-BIN-T142-04 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164603 | TO-20-BIN-T142-06 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | BINBANE 110 | BINBANE 38 | T142 | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164649 | TO-20-BIN-T143-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | BINBANE 110 | BINBANE 38 | T143 | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164648 | TO-20-BIN-T143-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | BINBANE 110 | BINBANE 38 | T143 | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164639 | TO-20-BIN-T143-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | BINBANE 110 | BINBANE 38 | T143 | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101112164608 | TO-20-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | BINBANE 110 | BINBANE 38 | T143 | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019110812345649 | TO-20-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | BINBANE 110 | TIEVEBRACK 110 | 1 | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110812345648 | TO-20-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | BINBANE 110 | TIEVEBRACK 110 | 1 | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141 | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110812345639 | TO-20-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | BINBANE 110 | TIEVEBRACK 110 | 1 | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110812345608 | TO-20-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | BINBANE 110 | TIEVEBRACK 110 | 1 | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle | CP0878 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200907153550 | TO-20-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | BLAKE 110 | BLAKE 38 | T142 | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200907152653 | TO-20-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | BLAKE 110 | BLAKE 38 | T142 | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200907152846 | TO-20-BLK,T-BLK-1-02 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | BLAKE tee | BLAKE 110 | 1 | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200907153925 | TO-20-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | BLAKE tee | BLAKE 110 | 1 | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0057 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19CM0322 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | Copper earths stolen from 110kV CTs to be reinstalled | 901076412 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
12LN0528 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | 7[3,8,11,14,23,24,28]Replace damaged mem | 900400277 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16CM0144 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | Step bolts required [2,3,4,5,6,8,10,13,14,17,19,20,21,23,24,25,26,27,28,29,31,33,34,35,37] | 900691700 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19LN6053 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | 2018HP-1[31]Check Struct/Found/etc-Base | 900988632 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00168 | TO-20-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | BLAKE tee | MAYNOOTH 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200907153419 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | Remake jumpers following maintenance on Blake Tee Maynooth & Blake Tee Newbridge |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200907153329 | TO-20-BLK,T-NEW-1-03 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | Break jumpers for maintenance on Blake Tee Maynooth |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200630100642 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | surge counter illigable | 901078182 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD0058 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN6441 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018HP-1[171]Earths-Replace-E/W broken | 900989019 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN6440 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018HP-1[181]Off Plumbplumb poles | 900989021 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN6442 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018HP-1[180]Off Plumbplumb poles | 900989020 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0667 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018CP-1[171]Stays - Replace | 901038283 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02160 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0668 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018CP-1[171]Earths - Replace (E strap) | 901038284 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02166 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0674 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018CP-1[168]Earths - Replace (HW Rusty) | 901038290 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0665 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018CP-1[171]Vibration Dampers -rusty | 901038281 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN6438 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2018HP-1[171]Off Plumbplumb poles | 900989018 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN4786 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2019HP-1[171]Earths-Replace broken x2 | 901084874 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460195 | TO-20-BLK,T-NEW-1-02 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN4785 | TO-20-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | BLAKE tee | NEWBRIDGE 110 | 1 | 2019HP-1[170]Earths-Replace broken x2 | 901084873 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200324151714 | TO-20-BGH-110SA1-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | BOGGERAGH 110 | BOGGERAGH 110 | 110SA1 | As a consequence of work on Boggeragh-Clashavoon 110 kV |  | 29/07/2020 | 31/07/2020 |  | Scheduled
CAPX2019100210345737 | TO-20-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | BOGGERAGH 110 | BOGGERAGH 110 | 110SA1 | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0698 | TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | BOGGERAGH 110 | BOGGERAGH 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 29/07/2020 | 31/07/2020 |  | Scheduled
20EG11263 | TO-20-BGH-110SA2-02 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | BOGGERAGH 110 | BOGGERAGH 110 | 110SA2 | 110kV Sect / Dist Operational Test | 901130115 | 29/07/2020 | 31/07/2020 | 4 | Scheduled
CAPX2019100210345738 | TO-20-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | BOGGERAGH 110 | BOGGERAGH 110 | 110SA2 | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0059 | TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | BOGGERAGH 110 | CLASHAVOON 110 | 1 | Total Maintenance Outage Duration Requested |  | 29/07/2020 | 31/07/2020 |  | Scheduled
20CM0066 | TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | BOGGERAGH 110 | CLASHAVOON 110 | 1 | O1-Main ON sign in c.b. chassis is very | 900973236 | 29/07/2020 | 31/07/2020 | 1 | Scheduled
20CM0068 | TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | BOGGERAGH 110 | CLASHAVOON 110 | 1 | O1- Hotspot Boggeragh CT T Phase. | 900989872 | 29/07/2020 | 31/07/2020 | 1 | Scheduled
CAPX2019100210345739 | TO-20-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | BOGGERAGH 110 | CLASHAVOON 110 | 1 | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20013 | TO-20-BGH-CLA-1-02 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | BOGGERAGH 110 | CLASHAVOON 110 | 1 | Cable Insp. 110kV XLPE | 901129114 | 29/07/2020 | 31/07/2020 | 4 | Scheduled
TOP200324152623 | TO-20-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | BOGGERAGH 110 | BOGGERAGH 20 | T121 | As a consequence of work on Boggeragh-Clashavoon 110 kV |  | 29/07/2020 | 31/07/2020 |  | Scheduled
CAPX2019100210345740 | TO-20-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | BOGGERAGH 110 | BOGGERAGH 20 | T121 | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200324153656 | TO-20-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | BOGGERAGH 110 | BOGGERAGH 33 | T132 | As a consequence of work on Boggeragh-Clashavoon 110 kV |  | 29/07/2020 | 31/07/2020 |  | Scheduled
CAPX2019100211193841 | TO-20-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | BOGGERAGH 110 | BOGGERAGH 33 | T132 | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200324154034 | TO-20-BGH-T142-02 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | BOGGERAGH 110 | BOGGERAGH 38 | T142 | As a consequence of work on Boggeragh-Clashavoon 110 kV |  | 29/07/2020 | 31/07/2020 |  | Reference
CAPX2019100210345741 | TO-20-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | BOGGERAGH 110 | BOGGERAGH 38 | T142 | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0060 | TO-20-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | BOOLTIAGH 110 | ENNIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10087 | TO-20-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | BOOLTIAGH 110 | ENNIS 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00175 | TO-20-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | BOOLTIAGH 110 | ENNIS 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0471 | TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | BOOLTIAGH 110 | BOOLTIAGH 20 | T121 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 23/07/2020 |  | Scheduled
20EG01344 | TO-20-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | BOOLTIAGH 110 | BOOLTIAGH 20 | T121 | 110kV SF6 Cubicle Ordinary Service |  | 20/07/2020 | 23/07/2020 | 4 | Scheduled
OD1364 | TO-20-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | BRINNY 110 | BRINNY 10 | T101 | Total Maintenance Outage Duration Requested |  | 02/09/2020 | 04/09/2020 |  | Scheduled
20EG23717 | TO-20-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | BRINNY 110 | BRINNY 10 | T101 | 110kV SF6 Cubicle Ordinary Service |  | 02/09/2020 | 04/09/2020 | 4 | Scheduled
CAPX20200109103511124 | TO-20-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | BRINNY 110 | BRINNY 10 | T101 | As a consequence of BAN-BRI-1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 02/09/2020 | 03/09/2020 |  | Scheduled
OD1309 | TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 20/08/2020 |  | Scheduled
20EG04014 | TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 17/08/2020 | 20/08/2020 | 4 | Scheduled
CAPX2020010910460100 | TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA1 | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 17/08/2020 | 20/08/2020 |  | Scheduled
CAPX2020010910460104 | TO-20-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA1 | As a consequence of BUT-110SA2: 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 17/08/2020 | 20/08/2020 |  | Scheduled
OD1310 | TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 13/08/2020 |  | Scheduled
20EG04015 | TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901146318 | 10/08/2020 | 13/08/2020 | 4 | Scheduled
CAPX2020010910460101 | TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA2 | As a consequence of BUT-110SA1: 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 10/08/2020 | 13/08/2020 |  | Scheduled
CAPX2020010910460105 | TO-20-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | BUTLERSTOWN 110 | BUTLERSTOWN 110 | 110SA2 | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 10/08/2020 | 13/08/2020 |  | Scheduled
OD0061 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 20/08/2020 |  | Scheduled
19CM0144 | TO-20-BUT-CUL-1-02 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | Copper earths stolen from DL, DE, all 110kV CT’s, VT’s and surge arrestors to be reinstalled | 901080692 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG10089 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 17/08/2020 | 20/08/2020 | 4 | Scheduled
20EG20014 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | Cable Insp. 110kV XLPE |  | 17/08/2020 | 20/08/2020 | 4 | Scheduled
20LN0979 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 2019HP-1[23]Check (General) -LPh weight | 901084678 | 17/08/2020 | 20/08/2020 | 2 | Scheduled
CAPX2020010910460102 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 17/08/2020 | 20/08/2020 |  | Scheduled
20LN0983 | TO-20-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 2019HP-2[49,50]Off Plumb -plumb poles | 901084937 | 17/08/2020 | 20/08/2020 | 4 | Scheduled
PROT2020072 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | P3 Protection maintenance of 7SA612, REL551 |  | 10/08/2020 | 12/08/2020 | 3 | Scheduled
OD0062 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 12/08/2020 |  | Scheduled
20EG10092 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129696 | 10/08/2020 | 12/08/2020 | 4 | Scheduled
20EG10091 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129602 | 10/08/2020 | 12/08/2020 | 4 | Scheduled
CAPX2020010910460106 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 10/08/2020 | 12/08/2020 |  | Scheduled
CAPX2020010910460158 | TO-20-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | BUTLERSTOWN 110 | KILLOTERAN 110 | 1 | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 10/08/2020 | 12/08/2020 |  | Scheduled
CAPX2020010910460103 | TO-20-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | BUTLERSTOWN 110 | BUTLERSTOWN 38 | T141 | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 12/08/2020 | 14/08/2020 |  | Reference
CAPX2020010910460107 | TO-20-BUT-T142-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T142 | BUTLERSTOWN 110 | BUTLERSTOWN 38 | T142 | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 17/08/2020 | 20/08/2020 |  | Reference
20CM0452 | TO-20-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | CAHIR 110 | CAHIR 110 | 110K1-2 | T Phase Bus coupler 110kV Cubicle. T Phase Bus coupler DB DUE : 17-Jul-20 | 901134763 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0459 | TO-20-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | CAHIR 110 | CAHIR 110 | 110K1-2 | R Phase Bus coupler 110kV Cubicle. R Phase CT.DUE : 17-Aug-20 | 901134760 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0461 | TO-20-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | CAHIR 110 | CAHIR 110 | 110K1-2 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA & T Phase CT connection DUE : 17-Aug-20 | 901134762 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0460 | TO-20-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | CAHIR 110 | CAHIR 110 | 110K1-2 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA. DUE : 17-Aug-20 | 901134761 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
TOP200529152644 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | Poles currently in crop, good chance it will be cut by 13th of July KK | 901132793 | 13/07/2020 | 17/07/2020 |  | Scheduled
18LN1836 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 2017HP-4[47,56,72,75]Off Plumb | 900897598 | 13/07/2020 | 17/07/2020 | 2 | Scheduled
18LN1835 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 2017HP-5[5,12,13,33,37]Off Plumb | 900897597 | 13/07/2020 | 17/07/2020 | 2 | Scheduled
19EG10094 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129615 | 13/07/2020 | 17/07/2020 | 4 | Scheduled
20CM0466 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | T Phase Doon 110kV Cubicle. TPhase CB connection DUE : 17-Nov-2 hotspot | 901134764 | 13/07/2020 | 17/07/2020 | 1 | Scheduled
20EG10093 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129607 | 13/07/2020 | 17/07/2020 | 4 | Scheduled
20LN0993 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 2019HP-5[14,29,30,37,38]Off Plumb | 901084938 | 13/07/2020 | 17/07/2020 | 2 | Scheduled
20LN0994 | TO-20-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | CAHIR 110 | DOON 110 | 1 | 2019HP-3[53,56,72]Off Plumb -plumb poles | 901084939 | 13/07/2020 | 17/07/2020 | 2 | Scheduled
OD0859 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | CAHIR 110 | KILL HILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
PROT2020073 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-Kill Hill 110-1 | CAHIR 110 | KILL HILL 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 27/10/2020 | 30/10/2020 | 3 | Scheduled
PROT2020074 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-Kill Hill 110-1 | CAHIR 110 | KILL HILL 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 27/10/2020 | 30/10/2020 | 3 | Scheduled
19LN2412 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | CAHIR 110 | KILL HILL 110 | 1 | 2018HP-1[47]Off Plumb | 900984365 | 27/10/2020 | 30/10/2020 | 4 | Scheduled
20EG02545 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | CAHIR 110 | KILL HILL 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
20EG11395 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | CAHIR 110 | KILL HILL 110 | 1 | 110kV MO Cubicle Operational Test |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
20LN1043 | TO-20-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | CAHIR 110 | KILL HILL 110 | 1 | 2019HP-1[47]Off Plumb -plumb poles | 901084942 | 27/10/2020 | 30/10/2020 | 4 | Scheduled
OD0065 | TO-20-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | CAHIR 110 | TIPPERARY 110 | 1 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 27/11/2020 |  | Scheduled
19LN2413 | TO-20-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | CAHIR 110 | TIPPERARY 110 | 1 | 2018HP-1[2]Earths-Replace-Broken | 900984378 | 23/11/2020 | 27/11/2020 | 4 | Scheduled
19LN2417 | TO-20-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | CAHIR 110 | TIPPERARY 110 | 1 | "2018HP-5[36,55,84,90,91]Off Plumb-Poles | 900984369 | 23/11/2020 | 27/11/2020 | 4 | Scheduled
19LN2416 | TO-20-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | CAHIR 110 | TIPPERARY 110 | 1 | "2018HP-5[25,26,29,34,35]Off Plumb-Poles | 900984368 | 23/11/2020 | 27/11/2020 | 4 | Scheduled
TOP200520085039 | TO-20-110 kV A1 @ CLW-01 | BUSBAR SECTION - CARLOW 110-CARLOW 110-110A1 | CARLOW 110 | CARLOW 110 | 110A1 | Proximity for Carlow Kellis 1 110 kV | PROX | 06/07/2020 | 09/07/2020 |  | Scheduled
OD0067 | TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | CARLOW 110 | KELLIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 09/07/2020 |  | Scheduled
20CM0036 | TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | CARLOW 110 | KELLIS 110 | 1 | busbar disconnect seized at top , bird c | 901075041 | 06/07/2020 | 09/07/2020 | 1 | Scheduled
19EG10101 | TO-20-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | CARLOW 110 | KELLIS 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038904 | 06/07/2020 | 09/07/2020 | 4 | Scheduled
OD0068 | TO-20-CLW-KLS-2-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113163612 | TO-20-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | P1 Protection maintenance of 7SA511 |  | 24/03/2020 | 02/04/2020 |  | Forced Out
20EG00205 | TO-20-CLW-KLS-2-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00204 | TO-20-CLW-KLS-2-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0431 | TO-20-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | Replacement of Stolen Earths |  | 24/03/2020 | 02/04/2020 | 1 | Forced Out
20LN1092 | TO-20-CLW-KLS-2-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | 2019HP-1[16]Off Plumb -plumb poles | 901084945 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1093 | TO-20-CLW-KLS-2-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | CARLOW 110 | KELLIS 110 | 2 | 2019HP-1[17]Off Plumb -plumb poles | 901084946 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200519083557 | TO-20-CLW-T141-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | CARLOW 110 | CARLOW 38 | T141 | Proximity for Carlow Kellis 1 110 kV |  | 06/07/2020 | 09/07/2020 |  | Reference
PROT2020164 | TO-20-COS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | CARRICK ON SHANNON 110 | CARRICK ON SHANNON 110 | 110SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0932 | TO-20-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | CARRICK ON SHANNON 110 | CARRICK ON SHANNON 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG02537 | TO-20-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | CARRICK ON SHANNON 110 | CARRICK ON SHANNON 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0069 | TO-20-COS-FLA-1-05 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | Total Maintenance Outage Duration Requested |  | 26/11/2020 | 01/12/2020 |  | Scheduled
20CM0132 | TO-20-COS-FLA-1-05 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | O1 Investigate control circuit including | 901053362 | 26/11/2020 | 01/12/2020 | 1 | Scheduled
20EG10104 | TO-20-COS-FLA-1-05 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 26/11/2020 | 01/12/2020 | 4 | Scheduled
20CM0131 | TO-20-COS-FLA-1-05 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | O1 Replacement coupling required on H3 d | 901053361 | 26/11/2020 | 01/12/2020 | 1 | Scheduled
CAPX2019101715390453 | TO-20-COS-FLA-1-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390456 | TO-20-COS-FLA-1-04 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100414120540 | TO-20-COS-FLA-1-02 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390452 | TO-20-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 1 | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 1 110 kV bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200507122559 | TO-20-COS-FLA-2-04 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | Studied outage for potential extension of CP1031 due to CV-19 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0070 | TO-20-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00212 | TO-20-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | 110kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101715390449 | TO-20-COS-FLA-2-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390446 | TO-20-COS-FLA-2-02 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390445 | TO-20-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | CARRICK ON SHANNON 110 | FLAGFORD 110 | 2 | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 2 110 kV Bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393258 | TO-20-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | CARRICKMINES 220 | CARRICKMINES 220 | 220A1 | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393260 | TO-20-220 kV A2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A2 | CARRICKMINES 220 | CARRICKMINES 220 | 220A2 | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393259 | TO-20-220 kV B1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B1 | CARRICKMINES 220 | CARRICKMINES 220 | 220B1 | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393261 | TO-20-220 kV B2 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B2 | CARRICKMINES 220 | CARRICKMINES 220 | 220B2 | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
OD0369 | TO-20-CKM-220K1-2-01 | COUPLER/SECTIONALISING CB - CARRICKMINES 220-CARRICKMINES 220-220K1-2 | CARRICKMINES 220 | CARRICKMINES 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0042 | TO-20-CKM-220K1-2-01 | COUPLER/SECTIONALISING CB - CARRICKMINES 220-CARRICKMINES 220-220K1-2 | CARRICKMINES 220 | CARRICKMINES 220 | 220K1-2 | O/1 Missing 220kV coupler on Indicator R | 900959119 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019121810393262 | TO-20-220 kV A1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220A1 | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393268 | TO-20-220 kV A2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220A2 | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393274 | TO-20-220 kV A3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220A3 | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393280 | TO-20-220 kV A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220A4 | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393263 | TO-20-220 kV B1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220B1 | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393269 | TO-20-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220B2 | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393275 | TO-20-220 kV B3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220B3 | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393281 | TO-20-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220B4 | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 05/03/2020 | 05/03/2020 |  | Tentative
CAPX2019121810393277 | TO-20-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220K3 | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393276 | TO-20-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220K3 | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200617144615 | TO-20-CKM GIS-220K4-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220K4 | Outage for EI of T2101 |  | 29/06/2020 | 30/06/2020 |  | Scheduled
CAPX2019121810393282 | TO-20-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220K4 | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393283 | TO-20-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220K4 | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393264 | TO-20-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA1-2 | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393270 | TO-20-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA1-2 | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393265 | TO-20-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA1-3 | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393278 | TO-20-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA1-3 | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393271 | TO-20-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA2-4 | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393284 | TO-20-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SA2-4 | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393272 | TO-20-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB1-2 | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393266 | TO-20-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB1-2 | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393279 | TO-20-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB1-3 | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393267 | TO-20-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB1-3 | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393273 | TO-20-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB2-4 | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393285 | TO-20-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | 220SB2-4 | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1102 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | Total Maintenance Outage Duration Requested |  | 20/04/2020 | 24/04/2020 |  | Scheduled
17EG10391 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 220kV MO Cubicle Operational Test | 901038749 | 20/04/2020 | 24/04/2020 | 1 | Scheduled
19LN2460 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 2018HP-1[131]Check Struct/Found/etc-Base | 900984617 | 20/04/2020 | 24/04/2020 | 4 | Scheduled
19LN2464 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 2018HP-1[123]Check Struct/Found/etc-Base | 900984613 | 20/04/2020 | 24/04/2020 | 4 | Scheduled
19LN2496 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 2018HP-1[34]Check Struct/Found/etc-Base | 900984585 | 20/04/2020 | 24/04/2020 | 4 | Scheduled
20EG06005 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | HV Pressure Vessel Inspection |  | 20/04/2020 | 24/04/2020 | 4 | Scheduled
19LN2489 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 2018HP-1[48]Check Struct/Found/etc-Base | 900984592 | 20/04/2020 | 24/04/2020 | 4 | Scheduled
19LN2477 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | 2018HP-1[8]Check Struct/Found/etc-Base | 900984573 | 20/04/2020 | 24/04/2020 | 4 | Scheduled
20CM0101 | TO-20-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | CARRICKMINES GIS 220 | DUNSTOWN 220 | 1 | O. ESBI Inspect and test all the cylinde | 900444584 | 20/04/2020 | 24/04/2020 | 2 | Scheduled
TOP191014144204 | TO-20-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | CARRICKMINES GIS 220 | IRISHTOWN 220 | 1 | placeholder for maintenance |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020130 | TO-20-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | CARRICKMINES GIS 220 | CARRICKMINES GIS 220 | R2001 | P3 Protection maintenance of 7SJ611, RET670, POW-RPH3 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020010910465526 | TO-20-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | Proximity outage for work on Poolbeg 220kV K1-3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0263 | TO-20-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 27/11/2020 |  | Scheduled
20CM0442 | TO-20-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | Detection and repair of fluid leak |  | 16/11/2020 | 27/11/2020 | 1 | Scheduled
20EG00767 | TO-20-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | 220kV MO Cubicle Ordinary Service |  | 16/11/2020 | 27/11/2020 | 4 | Scheduled
20EG00769 | TO-20-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | 220kV Cubicle Condition Assessment |  | 16/11/2020 | 27/11/2020 | 4 | Scheduled
18EG20115 | TO-20-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | CARRICKMINES 220 | POOLBEG 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 900925587 | 16/11/2020 | 27/11/2020 | 3 | Scheduled
CAPX2020010910465527 | TO-20-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | CARRICKMINES 220 | CARRICKMINES 220 | PST2201 | As a consequence of CKM-PB-1: Proximity outage for work on Poolbeg 220kV K1-3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0049 | TO-20-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | CARRICKMINES 220 | CARRICKMINES 220 | R2001 | N 0 1 non outage(important) | 900525391 | 21/10/2020 | 22/10/2020 | 2 | Scheduled
20EG10505 | TO-20-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | CARRICKMINES 220 | CARRICKMINES 220 | R2001 | HV Reactor Operational Test |  | 21/10/2020 | 22/10/2020 | 4 | Scheduled
19CM0115 | TO-20-CKM-R2001-02 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | CARRICKMINES 220 | CARRICKMINES 220 | R2001 | Carrickmines R2001 Shunt Reactor: Fit bushing monitor (HV and LV) | 901038711 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
PROT2020023 | TO-20-CKM-T2102-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2102 | CARRICKMINES 220 | CARRICKMINES 110 | T2102 | P1 Protection maintenance of 7SA612 |  | 29/07/2020 | 29/07/2020 | 1 | Reference
OD0071 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 27/11/2020 |  | Scheduled
PROT2020049 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | P2 Protection maintenance of REL521 |  | 14/09/2020 | 27/11/2020 | 2 | Scheduled
PROT2020026 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | P2 Protection maintenance of 7SA511, REL521 |  | 14/09/2020 | 27/11/2020 | 2 | Scheduled
CAPX2020070716145301 | TO-20-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | Proximity outage due to proximity of the bays within the station. | CP1037 | 20/07/2020 | 28/08/2020 |  | Scheduled
20EG00216 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 27/11/2020 | 4 | Scheduled
18CM1209 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | O1-Cb,CT & DA slight algae growth. | 900973233 | 14/09/2020 | 27/11/2020 | 1 | Scheduled
20EG00217 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 14/09/2020 | 27/11/2020 | 4 | Scheduled
20CM0163 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | O1-DA not showing open position indicati | 900894946 | 14/09/2020 | 27/11/2020 | 1 | Scheduled
20LN1214 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | 2019HP-1[120]Off Plumb -plumb poles | 901084947 | 14/09/2020 | 27/11/2020 | 2 | Scheduled
CAPX2019100309413401 | TO-20-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | CARRIGADROHID 110 | KILBARRY 110 | 1 | Terminating 110 kV cable at station bay and end masts | CP1037 | 14/09/2020 | 27/11/2020 |  | Scheduled
OD0072 | TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 16/03/2020 |  | Scheduled
PROT2020076 | TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | P3 Protection maintenance of REL521, REL551 |  | 09/03/2020 | 16/03/2020 | 3 | Scheduled
20EG00221 | TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 09/03/2020 | 16/03/2020 | 4 | Scheduled
20EG10110 | TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 09/03/2020 | 16/03/2020 | 4 | Scheduled
CAPX2019100210345729 | TO-20-CD-MAC-1-04 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345705 | TO-20-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay. | CP0829 | 09/03/2020 | 16/03/2020 |  | Scheduled
CAPX2019100210345720 | TO-20-CD-MAC-1-03 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345708 | TO-20-CD-MAC-1-02 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | CARRIGADROHID 110 | MACROOM 110 | 1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0641 | TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | CARRIGADROHID 110 | CARRIGADROHID G3 | T103 | Total Maintenance Outage Duration Requested |  | 16/06/2020 | 23/06/2020 | 2 | Scheduled
20EG10946 | TO-20-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | CARRIGADROHID 110 | CARRIGADROHID G3 | T103 | 110KV SF6 Cubicle Operational Test | 901129579 | 16/06/2020 | 23/06/2020 | 4 | Scheduled
CAPX2020072209525807 | TO-20-CDN-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | CARRIGDANGAN 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2020083111380713 | TO-20-CDN-DMY-1-04 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | CARRIGDANGAN 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Scheduled
CAPX2020102710021219 | TO-20-CDN-DMY-1-06 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | CARRIGDANGAN 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102710021225 | TO-20-CDN-DMY-1-07 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | CARRIGDANGAN 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331764 | TO-20-CDN-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | CARRIGDANGAN 110 | DUNMANWAY 110 | 1 | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Tentative
TOP200923123325 | TO-20-CBG-CBR-1-01 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | CARROWBEG 110 | CASTLEBAR 110 | 1 | XLPE inspection |  | 09/10/2020 | 09/10/2020 |  | Reference
PROT2020016 | TO-20-CBG-CBR-1-01 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | CARROWBEG 110 | CASTLEBAR 110 | 1 | P1 Protection maintenance of 7SA513 |  | 09/10/2020 | 09/10/2020 | 1 | Reference
TOP200923123227 | TO-20-CBG-T142-01 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | CARROWBEG 110 | CARROWBEG 38 | T142 | DSO maintenance |  | 05/10/2020 | 16/10/2020 |  | Reference
TOP200110113345 | TO-20-CBG-T142-01 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | CARROWBEG 110 | CARROWBEG 38 | T142 | As a consequence of work on Carrowbeg-Castlebar 110 kV |  | 05/10/2020 | 16/10/2020 |  | Reference
CAPX2019101714263864 | TO-20-110 kV A1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403415 | TO-20-110 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101714263816 | TO-20-110 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393286 | TO-20-110 kV A1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover | BB0001 | 12/03/2020 | 12/03/2020 |  | Scheduled
CAPX2019101713403456 | TO-20-110 kV A1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331756 | TO-20-110 kV A1 @ CSH-08 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071425 | TO-20-110 kV A1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071422 | TO-20-110 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | CASHLA 110 | CASHLA 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071439 | TO-20-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071436 | TO-20-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393288 | TO-20-110 kV A2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover | BB0001 | 12/03/2020 | 12/03/2020 |  | Scheduled
CAPX2020010910331757 | TO-20-110 kV A2 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403445 | TO-20-110 kV A2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403442 | TO-20-110 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | CASHLA 110 | CASHLA 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403457 | TO-20-110 kV B1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393287 | TO-20-110 kV B1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover | BB0001 | 12/03/2020 | 12/03/2020 |  | Scheduled
CAPX2019101012071423 | TO-20-110 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403416 | TO-20-110 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071426 | TO-20-110 kV B1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071467 | TO-20-110 kV B1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071414 | TO-20-110 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | CASHLA 110 | CASHLA 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334428 | TO-20-110 kV B1/B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1-B2 | CASHLA 110 | CASHLA 110 | 110B1-B2 | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV) | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071440 | TO-20-110 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | CASHLA 110 | CASHLA 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393289 | TO-20-110 kV B2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | CASHLA 110 | CASHLA 110 | 110B2 | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover | BB0001 | 12/03/2020 | 12/03/2020 |  | Scheduled
CAPX2019101012071437 | TO-20-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | CASHLA 110 | CASHLA 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403443 | TO-20-110 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | CASHLA 110 | CASHLA 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403446 | TO-20-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | CASHLA 110 | CASHLA 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0370 | TO-20-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 26/11/2020 |  | Scheduled
20CM0058 | TO-20-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | O1 SA failed to open intermittently | 901058830 | 23/11/2020 | 26/11/2020 | 1 | Scheduled
20CM0059 | TO-20-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | O1 DA2 seems to be operating slower than | 901058832 | 23/11/2020 | 26/11/2020 | 1 | Scheduled
20CM0471 | TO-20-CSH-110K1-2-04 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | DB 110kV Coupler R Phse Disconnect DUE : next available opportunity. | 901133361 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019101009334427 | TO-20-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla 110 kV Coupler bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334429 | TO-20-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV) | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071433 | TO-20-CSH-110K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | CASHLA 110 | CASHLA 110 | 110K1-2 | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393290 | TO-20-220 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | CASHLA 220 | CASHLA 220 | 220A1 | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071406 | TO-20-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | CASHLA 220 | CASHLA 220 | 220A1 | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393292 | TO-20-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | CASHLA 220 | CASHLA 220 | 220A2 | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393294 | TO-20-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | CASHLA 220 | CASHLA 220 | 220A4 | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334410 | TO-20-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | CASHLA 220 | CASHLA 220 | 220B1 | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393291 | TO-20-220 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | CASHLA 220 | CASHLA 220 | 220B1 | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334401 | TO-20-220 kV B1/B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1-B2 | CASHLA 220 | CASHLA 220 | 220B1-B2 | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV) | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393293 | TO-20-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | CASHLA 220 | CASHLA 220 | 220B2 | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121810393295 | TO-20-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | CASHLA 220 | CASHLA 220 | 220B4 | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0917 | TO-20-CSH-220K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0474 | TO-20-CSH-220K1-2-05 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | 220 kV Coupler SB 2-4 S and T Phse Disconnect DUE : next available opportunity. | 901133644 | 07/10/2020 | 23/10/2020 | 1 | Scheduled
19EG01017 | TO-20-CSH-220K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | 220kV MO Cubicle Ordinary Service | 901041551 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0473 | TO-20-CSH-220K1-2-05 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | 220 kV Coupler k1-2 R Phase DB2 Pantograph. DUE : next available opportunity. | 901133364 | 07/10/2020 | 23/10/2020 | 1 | Scheduled
20CM0472 | TO-20-CSH-220K1-2-05 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | 220 kV Coupler k1-2 R Phas DA Pantograph DUE : next available opportunity. | 901133643 | 07/10/2020 | 23/10/2020 | 1 | Scheduled
CAPX2019101009334403 | TO-20-CSH-220K1-2-04 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100311344011 | TO-20-CSH-220K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | Commission new Sync Scheme - all bays in turn | MC0237 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334402 | TO-20-CSH-220K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV) | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110711421600 | TO-20-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334400 | TO-20-CSH-220K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | CASHLA 220 | CASHLA 220 | 220K1-2 | Install Sprecher & Schuh type HPF-511 220 kV Circuit breaker replacement in the Cashla 220 kV Coupler bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0372 | TO-20-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | CASHLA 220 | CASHLA 220 | 220K2-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020054 | TO-20-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | CASHLA 220 | CASHLA 220 | 220K2-4 | P2 Protection maintenance of 7SJ511 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01021 | TO-20-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | CASHLA 220 | CASHLA 220 | 220K2-4 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100311344013 | TO-20-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | CASHLA 220 | CASHLA 220 | 220K2-4 | Commission new Sync Scheme - all bays in turn | MC0237 | 16/03/2020 | 18/03/2020 |  | Scheduled
PROT2020131 | TO-20-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | CASHLA 110 | CASHLA 110 | CAP1 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
PROT2020132 | TO-20-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | CASHLA 110 | CASHLA 110 | CAP2 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0074 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18LN1029 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[68]Vib Damp Replace-Left & Mid | 900876667 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1025 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[64]Vib Damp Replace-Mid Phase | 900876663 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1042 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[91]Vib Damp Replace | 900876680 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1016 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[18]Off Plumb Poles | 900876654 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1015 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[16]Off Plumb Poles | 900876653 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1014 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[12]Vib Damp Replace-Left Phase | 900876652 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1013 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[8]Vib Damp Replace-Right Phase | 900876651 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1017 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[22]Off Plumb Poles | 900876655 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1026 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[65]Vib Damp Replace-Left & Mid | 900876664 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1018 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[22]Vib Damp Replace-Mid Phase | 900876656 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1043 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[93]Vib Damp Replace | 900876681 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1049 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-3[108]Vib Damp Replace | 900876687 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1047 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-6[105]Vib Damp Replace | 900876685 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1024 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[63]Vib Damp Replace-Left Phase | 900876662 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1051 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[111]Vib Damp Replace | 900876689 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1052 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[116]Vib Damp Replace | 900876690 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1012 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-4[5]Vib Damp Replace | 900876650 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1022 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[55]Vib Damp Replace-Left Phase | 900876660 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1034 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[79]Vib Damp Replace-Right Phase | 900876672 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1033 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[76]Vib Damp Replace-Left Phase | 900876671 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1032 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[75]Vib Damp Replace-Left Phase | 900876670 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1031 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[72]Vib Damp Replace-Left & Mid | 900876669 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1030 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-3[71]Vib Damp Replace-All Phases | 900876668 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1044 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[94]Vib Damp Replace | 900876682 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1035 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[81]Vib Damp Replace-Mid & Right | 900876673 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1050 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[110]Vib Damp Replace | 900876688 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1046 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[100]Vib Damp Replace-Right Phas | 900876684 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1045 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[95]Vib Damp Replace | 900876683 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1021 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[53]Vib Damp Replace-Right Phase | 900876659 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1020 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[31]Vib Damp Replace-Mid Phase | 900876658 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1019 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-6[23]Vib Damp Replace-All Phases | 900876657 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1027 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[66]Vib Damp Replace-Mid Phase | 900876665 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1028 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[67]Vib Damp Replace-Mid Phase | 900876666 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1040 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[89]Vib Damp Replace | 900876678 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1048 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[106]Vib Damp Replace | 900876686 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1210 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017HP-1[103]Off Plumb -Poles | 900897288 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18LN1023 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[61]Vib Damp Replace-Left & Mid | 900876661 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1058 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[124]Vib Damp Replace | 900876696 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1011 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[2]Vib Damp Replace-Right Phase | 900876649 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1036 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[83]Vib Damp Replace-Right Phase | 900876674 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1056 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-4[124]Stays New stays to be dug | 900876694 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1038 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[86]Vib Damp Replace-Mid Phase | 900876676 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1037 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[84]Vib Damp Replace-Mid Phase | 900876675 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1059 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[127]Earths - Replace Lead | 900876697 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1041 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[90]Vib Damp Replace | 900876679 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1057 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[124]Off Plumb Insulators | 900876695 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1053 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[121]Vib Damp Replace | 900876691 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1054 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[122]Off Plumb Insulators | 900876692 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN1055 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-2[123]Vib Damp Replace | 900876693 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG00225 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18LN1039 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2017CP-1[87]Vib Damp Replace-Mid Phase | 900876677 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2019101713403452 | TO-20-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | EI: Install Sprecher & Schuh type HPF-511 1110 kV Circuit breaker replacement in the 110 kV Cloon bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403458 | TO-20-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071468 | TO-20-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1237 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2019HP-1[Stn]Insulator Broken | 901084835 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN1236 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2019HP-1[128]Earths-Replace Broken R/ph | 901084869 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20LN1233 | TO-20-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | CASHLA 110 | CLOON 110 | 1 | 2019HP-1[106]Replace Pole only -Rot | 901086427 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0075 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | Total Maintenance Outage Duration Requested |  | 20/11/2020 | 27/11/2020 |  | Scheduled
19LN2631 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | 2018HP-1[212]Insulator-Off Plumb | 900984733 | 20/11/2020 | 27/11/2020 | 4 | Scheduled
14LN2627 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | 2[166,167 ]Ins / H/D repl chk-Fi | 900564546 | 20/11/2020 | 27/11/2020 | 1 | Scheduled
14LN1321 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | 1[221]Ins & H/D repl chk-Fit Dup | 900563143 | 20/11/2020 | 27/11/2020 | 1 | Scheduled
19LN2638 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | 2018HP-1[9]Vib Dampers-Fatigue replace | 900984695 | 20/11/2020 | 27/11/2020 | 4 | Scheduled
18EG02313 | TO-20-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | CASHLA 110 | DALTON 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 900943159 | 20/11/2020 | 27/11/2020 | 3 | Scheduled
OD0076 | TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | CASHLA 110 | ENNIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 18/06/2020 | 26/06/2020 |  | Scheduled
20EG00229 | TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | CASHLA 110 | ENNIS 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 18/06/2020 | 26/06/2020 | 4 | Scheduled
20EG00231 | TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | CASHLA 110 | ENNIS 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 18/06/2020 | 26/06/2020 | 4 | Scheduled
20EG00230 | TO-20-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | CASHLA 110 | ENNIS 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 18/06/2020 | 26/06/2020 | 4 | Scheduled
CAPX2019100210172703 | TO-20-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | CASHLA 110 | ENNIS 110 | 1 | Simultaneous CSH-ENN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0264 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020033 | TO-20-CSH-FLA-1-09 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | P2 Protection maintenance of 7SA513., REL521 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
PROT2020114 | TO-20-CSH-FLA-1-09 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | P3 Protection maintenance of 7SA513, REL521 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19LN2730 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2018HP-1[am 247]Insulatorfit duplicates | 900984858 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18EG00772 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 220kV MO Cubicle Ordinary Service | 900943176 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG00771 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 220kV MO Cubicle Ordinary Service | 900943133 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20LN1303 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[215]Bird Nests | 901084309 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019102513581712 | TO-20-CSH-FLA-1-04 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071407 | TO-20-CSH-FLA-1-03 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1288 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[134]Bird Nests | 901084304 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1297 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[203]Bird Nests | 901084305 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1299 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[210]Bird Nests | 901084306 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019110711421601 | TO-20-CSH-FLA-1-07 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1301 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[212]Bird Nests | 901084308 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101009334405 | TO-20-CSH-FLA-1-03 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at Cashla station in the Flagford 220 kV bay (CB also to be replaced at remote end) | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1309 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[240]Bird Nests | 901084310 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1312 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[247]Insulator Fit Duplicate | 901084836 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1324 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[73]Bird Nests | 901084311 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1325 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[78]Bird Nests | 901084312 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1327 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[80]Bird Nests | 901084313 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100311344008 | TO-20-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Commission new Sync Scheme - all bays in turn | MC0237 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110711421604 | TO-20-CSH-FLA-1-08 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100411043106 | TO-20-CSH-FLA-1-03 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at flagford station in the Cashla 220 kV bay (CB also to be replaced at remote end) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094610 | TO-20-CSH-FLA-1-06 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334407 | TO-20-CSH-FLA-1-04 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1300 | TO-20-CSH-FLA-1-10 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | CASHLA 220 | FLAGFORD 220 | 1 | 2019HP-1[211]Bird Nests | 901084307 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0077 | TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00233 | TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042209 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00232 | TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | 110kV MO Cubicle Ordinary Service | 901042382 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101713403420 | TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 1 bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071424 | TO-20-CSH-GAL-1-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331778 | TO-20-CSH-GAL-1-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1336 | TO-20-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | 2019HP-1[12]Insulator Broken Insul | 901084837 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331768 | TO-20-CSH-GAL-1-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071427 | TO-20-CSH-GAL-1-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | CASHLA 110 | GALWAY 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0078 | TO-20-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00237 | TO-20-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | 110kV SF6 Cubicle Ordinary Service | 901042210 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101012071438 | TO-20-CSH-GAL-2-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071434 | TO-20-CSH-GAL-2-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5227 | TO-20-CSH-GAL-2-06 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | Hotspot 1 (L1 Span 9/10) Left Midspan Joint (Repair by 27th Jul) | 901139264 | 09/06/2020 | 11/06/2020 | 1 | Scheduled
CAPX2019101012071441 | TO-20-CSH-GAL-2-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331773 | TO-20-CSH-GAL-2-05 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331789 | TO-20-CSH-GAL-2-05 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403432 | TO-20-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | CASHLA 110 | GALWAY 110 | 2 | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 2 bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0079 | TO-20-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | CASHLA 110 | GALWAY 110 | 3 | Total Maintenance Outage Duration Requested |  | 04/11/2020 | 04/11/2020 |  | Scheduled
20EG10122 | TO-20-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | CASHLA 110 | GALWAY 110 | 3 | 110kV MO Cubicle Operational Test |  | 04/11/2020 | 04/11/2020 | 4 | Scheduled
CAPX2020010910331783 | TO-20-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | CASHLA 110 | GALWAY 110 | 3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331794 | TO-20-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | CASHLA 110 | GALWAY 110 | 3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210172701 | TO-20-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | CASHLA 220 | PROSPECT 220 | 1 | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 13/07/2020 | 17/07/2020 |  | Scheduled
TOP200807094843 | TO-20-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | CASHLA 110 | SALTHILL 110 | 1 | Proximity for Salthil SA2 maintenance |  | 01/09/2020 | 04/09/2020 |  | Scheduled
OD0080 | TO-20-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | CASHLA 110 | SALTHILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 04/09/2020 |  | Scheduled
20EG11283 | TO-20-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | CASHLA 110 | SALTHILL 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
20EG20688 | TO-20-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | CASHLA 110 | SALTHILL 110 | 1 | Cable Insp. 110kV XLPE |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
20LN1429 | TO-20-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | CASHLA 110 | SALTHILL 110 | 1 | 2019HP-1[85]Off Plumb -plumb poles | 901084949 | 01/09/2020 | 04/09/2020 | 4 | Scheduled
OD0744 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | Total Maintenance Outage Duration Requested |  | 26/06/2020 | 10/07/2020 |  | Scheduled
19CM0114 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | Cashla T2101: Corrosion on Fan Box. Replace | 901038716 | 26/06/2020 | 10/07/2020 | 2 | Scheduled
20EG01798 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 26/06/2020 | 10/07/2020 | 4 | Scheduled
20EG01797 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | 220kV SF6 Cubicle Ordinary Service | 901129992 | 26/06/2020 | 10/07/2020 | 4 | Scheduled
18EG01802 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | 220/110 & 275/220 TRAFO COND. ASSESSMENT | 900944214 | 26/06/2020 | 10/07/2020 | 1 | Scheduled
18EG01803 | TO-20-CSH-T2101-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | 220/110kV Trafo Tap Changer Inspection | 900944679 | 26/06/2020 | 10/07/2020 | 1 | Scheduled
CAPX2019100311344009 | TO-20-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | Commission new Sync Scheme - all bays in turn | MC0237 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110711421602 | TO-20-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | CASHLA 220 | CASHLA 110 | T2101 | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0745 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG11043 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | 220kV MO Cubicle Operational Test | 901038879 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG11044 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | 220/110 & 275/220 Trafo Operational Test | 901045361 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG11045 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | 110kV MO Cubicle Operational Test | 901038883 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19CM0112 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Cashla T2102 Transformer: Drycol Replacement | 901039321 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19CM0113 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Cashla T2102: Corrosion on Fan Box. Replace | 901038717 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019101009334411 | TO-20-CSH-T2102-04 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100311344012 | TO-20-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Commission new Sync Scheme - all bays in turn | MC0237 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334409 | TO-20-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Install Sprecher & Schuh type HPF-514 220 kV Circuit breaker replacement in the T2102 220 kV Bay at Cashla station | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101714334219 | TO-20-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403417 | TO-20-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071415 | TO-20-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | CASHLA 220 | CASHLA 110 | T2102 | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0746 | TO-20-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | CASHLA 220 | CASHLA 110 | T2104 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01811 | TO-20-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | CASHLA 220 | CASHLA 110 | T2104 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01813 | TO-20-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | CASHLA 220 | CASHLA 110 | T2104 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01812 | TO-20-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | CASHLA 220 | CASHLA 110 | T2104 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0266 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | Total Maintenance Outage Duration Requested |  | 16/04/2020 | 21/05/2020 |  | Scheduled
19EG10402 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 220kV SF6 Cubicle Operational Test | 901038878 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
20CM0481 | TO-20-CSH-TY-1-09 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 01 Tynagh DL Fault | 901148822 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN2983 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 2018HP-1[104]Vib DampersR/Ph | 900985040 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
19EG10403 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 220kV SF6 Cubicle Operational Test | 901039106 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
19LN0061 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | DISC CONTACTS DAMAGED | 900979523 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
20LN1441 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 2019HP-1[57]Bird Nests | 901084267 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
CAPX2019100311344010 | TO-20-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | Commission new Sync Scheme - all bays in turn | MC0237 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601115 | TO-20-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110711440503 | TO-20-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102513581713 | TO-20-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101009334408 | TO-20-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101012071420 | TO-20-CSH-TY-1-06 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1444 | TO-20-CSH-TY-1-03 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | 2019HP-1[107]Bird Nests | 901084268 | 16/04/2020 | 21/05/2020 | 4 | Scheduled
CAPX2019101012071404 | TO-20-CSH-TY-1-04 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100715321600 | TO-20-CSH-TY-1-07 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | CASHLA 220 | TYNAGH 220 | 1 | Fibre wrapping of the line - to be installed on OPGW earthwire | CP1019 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101412303805 | TO-20-CBT-INC-1-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | CASTLEBAGOT 220 | INCHICORE 220 | 1 | Proximity outage to allow for erection of HV equipment in interface compound. | CP0872 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010713331506 | TO-20-CBT-INC-2-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-2 | CASTLEBAGOT 220 | INCHICORE 220 | 2 | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required | CP0872 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101412303804 | TO-20-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | CASTLEBAGOT 220 | MAYNOOTH 220 | 1 | Proximity outage to allow for erection of HV equipment in interface compound. | CP0872 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1280 | TO-20-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | CASTLEBAR 110 | CASTLEBAR 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23658 | TO-20-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | CASTLEBAR 110 | CASTLEBAR 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901039130 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0081 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN3006 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018HP-1[165]Vib Dampers-Fatigue replace | 900985122 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0720 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[72]Crossarm -Replace | 901038334 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0719 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[73]Anti Split Bolts | 901038333 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0716 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[75]Anti Split Bolts | 901038330 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0715 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[75]Insulator -Broken Disk | 901038329 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00244 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0722 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[101]Off Plumb -Poles | 901038336 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0723 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[103]Off Plumb -Poles | 901038337 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0724 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[105]Off Plumb -Poles | 901038338 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0721 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[100]Off Plumb -Poles | 901038335 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0725 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[106]Off Plumb -Poles | 901038339 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0726 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[106]Found/Site repair | 901038340 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0727 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[106]Insulator -Off Plumb | 901038341 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0729 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[109]Off Plumb -Poles | 901038343 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3005 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018HP-1[164]Vib Dampers-Fatigue replace | 900985121 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0731 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[111]Anti Split Bolts | 901038345 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0732 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[114]Off Plumb -Poles | 901038346 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0733 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[114]Insulator -Off Plumb | 901038347 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0736 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[118]Off Plumb -Poles | 901038350 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0737 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[119]Off Plumb -Poles | 901038351 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0739 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[121]Crossarm -Replace Bolt | 901038353 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0782 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[214]Insulator -Off Plumb | 901038394 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0697 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[30]Found/Site repair | 901038312 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0681 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[3]Off Plumb -Poles | 901038297 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0682 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[12]Off Plumb -Poles | 901038298 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0683 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[15]Off Plumb -Poles | 901038299 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0684 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[15]Insulator -Off Plumb | 901038300 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0685 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[17]Off Plumb -Poles | 901038301 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0686 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[18]Off Plumb -Poles | 901038302 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0687 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[19]Off Plumb -Poles | 901038303 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0688 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[20]Off Plumb -Poles | 901038304 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0689 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[21]Off Plumb -Poles | 901038305 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0690 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[21]Insulator -Off Plumb | 901038306 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0710 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[66]Pole Bolt -Tighten | 901038324 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0696 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[30]Vibration Dampers | 901038311 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0714 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[77]Ubolts -Level | 901038328 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0698 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[31]Vibration Dampers | 901038313 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0703 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[36]Anti Split Bolts | 901038317 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0705 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[43]Pole Bolt -Tighten | 901038319 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0706 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[49]Off Plumb -Poles | 901038320 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0708 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[63]Pole Bolt -Tighten | 901038322 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00245 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0730 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[111]Off Plumb -Poles | 901038344 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0709 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[65]Pole Bolt -Tighten | 901038323 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0740 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[122]Crossarm -Tighten Bolt | 901038354 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0713 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[82]Insulator -Off Plumb | 901038327 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0694 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[28]Vibration Dampers | 901038310 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0766 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[43]Pole Bolt -Bent | 901038378 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0833 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[277]Pole Bolt -Bent | 901038443 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0827 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[288]Off Plumb -Poles | 901038437 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0826 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[287]Off Plumb -Poles | 901038436 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0807 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[260]Vibration Dampers -Replace | 901038418 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0794 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[246]Conductor Check | 901038405 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0755 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[150]Vibration Dampers -Required | 901038367 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0756 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[156]Stepbolts -Remove | 901038368 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0757 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[157]Pole Bolt -Tighten | 901038369 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0758 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[157]Insulator -Off Plumb | 901038370 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0792 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[246]Anti-Cl. Guard | 901038403 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0765 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[11]Earths - Replace -Bolt bent | 901038377 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0834 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[279]Pole Bolt -Bent | 901038444 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0771 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[165]Found/Site repair | 901038383 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0773 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[178]Insulator -Off Plumb | 901038385 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0776 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[187]Anti-Cl. Guard | 901038388 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0728 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[108]Crossarm | 901038342 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0781 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[214]Off Plumb -Poles | 901038393 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0741 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[123]Off Plumb -Poles | 901038355 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0789 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[233]Insulator -Off Plumb | 901038400 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0784 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[218]Insulator -Off Plumb | 901038396 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0783 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[218]Off Plumb -Poles | 901038395 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0764 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[4]Pole Bolt -Bent | 901038376 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0747 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[137]Pole Bolt -Replace | 901038360 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0743 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[127]Off Plumb -Poles | 901038357 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0744 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[127]Found/Site repair -Sleepers | 901038358 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0745 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[128]Off Plumb -Poles | 901038359 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0748 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[139]Off Plumb -Poles | 901038361 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0749 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[139]Crossarm | 901038362 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0750 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[140]Off Plumb -Poles | 901038363 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0753 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[147]Pole Bolt -Tighten | 901038366 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN0751 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2018CP-1[140]Crossarm | 901038364 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1564 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2019HP-1[53]Insulator Broken Aux Insul | 901084839 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1565 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2019HP-2[59, 60]Vib Dampers -Replace | 901085137 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1573 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | 2019HP-3[279,280,282]Vib Dampers -EW V/D | 901085138 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20015 | TO-20-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | CASTLEBAR 110 | CLOON 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0082 | TO-20-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | CASTLEBAR 110 | DALTON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00248 | TO-20-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | CASTLEBAR 110 | DALTON 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00249 | TO-20-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | CASTLEBAR 110 | DALTON 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020133 | TO-20-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | P3 Protection maintenance of 7SJ511, CPR097 |  | 02/11/2020 | 10/11/2020 | 3 | Scheduled
OD0336 | TO-20-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | Total Maintenance Outage Duration Requested |  | 02/11/2020 | 10/11/2020 |  | Scheduled
19EG05027 | TO-20-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | Capacitor: measurement of can values, detailed checks & HV bay condition assessment | 901050222 | 02/11/2020 | 10/11/2020 | 4 | Scheduled
19EG05026 | TO-20-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | 110kV SF6 Cubicle Ordinary Service | 901042289 | 02/11/2020 | 10/11/2020 | 4 | Scheduled
19EG05029 | TO-20-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | Capacitor/SVC Ordinary Service | 901042362 | 02/11/2020 | 10/11/2020 | 4 | Scheduled
CAPX2019100313390200 | TO-20-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | SVC Refurbishment | MC0331 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020053 | TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | CASTLEDOCKRELL 110 | LODGEWOOD 110 | 1 | P2 Protection maintenance of 7SA612 |  | 20/07/2020 | 24/07/2020 | 2 | Scheduled
OD0083 | TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | CASTLEDOCKRELL 110 | LODGEWOOD 110 | 1 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 24/07/2020 |  | Scheduled
20EG02273 | TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | CASTLEDOCKRELL 110 | LODGEWOOD 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129863 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
20EG02262 | TO-20-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | CASTLEDOCKRELL 110 | LODGEWOOD 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901129181 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
CAPX2020010910351122 | TO-20-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | CASTLEDOCKRELL 110 | LODGEWOOD 110 | 1 | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351123 | TO-20-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | CASTLEDOCKRELL 110 | CASTLEDOCKRELL 20 | T121 | As a consequence of CDK-LWD-1: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 20/07/2020 | 24/07/2020 |  | Reference
TOP200813102344 | TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | CASTLEFARM 110 | CASTLEFARM 10 | T101 | Customer works |  | 09/11/2020 | 20/11/2020 |  | Reference
CAPX2020010910331748 | TO-20-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | CASTLEFARM 110 | CASTLEFARM 10 | T101 | As a consequence of AUG-CFM-1 | PR0001 | 09/11/2020 | 20/11/2020 |  | Reference
TOP200813102643 | TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | CASTLEFARM 110 | CASTLEFARM 10 | T102 | Customer works |  | 14/09/2020 | 02/10/2020 |  | Reference
CAPX2020010910331754 | TO-20-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | CASTLEFARM 110 | CASTLEFARM 10 | T102 | As a consequence of AUG-CFM-2 | PR0001 | 14/09/2020 | 02/10/2020 |  | Reference
OD1329 | TO-20-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | CASTLEVIEW 110 | CASTLEVIEW 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04022 | TO-20-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | CASTLEVIEW 110 | CASTLEVIEW 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1330 | TO-20-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | CASTLEVIEW 110 | CASTLEVIEW 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04023 | TO-20-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | CASTLEVIEW 110 | CASTLEVIEW 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901038579 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0084 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | Total Maintenance Outage Duration Requested |  | 05/05/2020 | 08/05/2020 |  | Scheduled
PROT2020077 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | P3 Protection maintenance of 7SA511, R1Z23b |  | 05/05/2020 | 08/05/2020 | 3 | Scheduled
20CM0061 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | O1-Cowcross 7SA5111 Relay faulty display | 901023280 | 05/05/2020 | 08/05/2020 | 1 | Scheduled
20EG10127 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 05/05/2020 | 08/05/2020 | 4 | Scheduled
20EG10128 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | 110kV MO Cubicle Operational Test |  | 05/05/2020 | 08/05/2020 | 4 | Scheduled
20CM0062 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | O1-Scada not commissioned on this bay. | 901052222 | 05/05/2020 | 08/05/2020 | 1 | Scheduled
20EG20016 | TO-20-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | CASTLEVIEW 110 | COW CROSS 110 | 1 | Cable Insp. 110kV XLPE |  | 05/05/2020 | 08/05/2020 | 4 | Scheduled
OD0086 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 28/08/2020 |  | Scheduled
TOP200113142825 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | P1 Protection maintenance of 7SA511, REL521 |  | 24/08/2020 | 28/08/2020 |  | Scheduled
TOP200113142933 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | P2 Protection maintenance of 7SA511 |  | 24/08/2020 | 28/08/2020 |  | Scheduled
19EG00259 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042300 | 24/08/2020 | 28/08/2020 | 4 | Scheduled
19EG00258 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042211 | 24/08/2020 | 28/08/2020 | 4 | Scheduled
20EG20017 | TO-20-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | CASTLEVIEW 110 | KNOCKRAHA 110 | 1 | Cable Insp. 110kV XLPE |  | 24/08/2020 | 28/08/2020 | 4 | Scheduled
CAPX2019121810393296 | TO-20-110 kV A1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | 110A1 | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover | BB0001 | 16/07/2020 | 16/07/2020 |  | Scheduled
CAPX2019121810393298 | TO-20-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | 110A2 | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover | BB0001 | 16/07/2020 | 16/07/2020 |  | Scheduled
CAPX2019121810393297 | TO-20-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | 110B1 | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover | BB0001 | 16/07/2020 | 16/07/2020 |  | Scheduled
CAPX2019121810393299 | TO-20-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | 110B2 | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover | BB0001 | 16/07/2020 | 16/07/2020 |  | Scheduled
OD0960 | TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 04/09/2020 | 11/09/2020 |  | Scheduled
17CM0401 | TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | CAP2 | FI-011-11 Oil Sampling of Instrument tra | 900616524 | 04/09/2020 | 11/09/2020 | 2 | Scheduled
19EG05031 | TO-20-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | CATHALEENS FALL 110 | CATHALEENS FALL 110 | CAP2 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment | 901050223 | 04/09/2020 | 11/09/2020 | 4 | Scheduled
PROT2020154 | TO-20-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | CATHALEENS FALL 110 | CLIFF 110 | 1 | P3 Protection maintenance of 7SA511 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
TOP200903135822 | TO-20-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | CATHALEENS FALL 110 | CLOGHER 110 | 1 | Telecoms- fibre works |  | 02/11/2020 | 06/11/2020 |  | Scheduled
CAPX2020100715442301 | TO-20-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | CATHALEENS FALL 110 | CLOGHER 110 | 1 | Slit trenching and ducting in close proximity to C-Fall 1 circuit in Clogher station compound for new windfarm connection | CP1011 | 02/11/2020 | 06/11/2020 |  | Scheduled
CAPX2020100715442300 | TO-20-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | Slit trenching and ducting in close proximity to C-Fall 2 circuit in Clogher station compound for new windfarm connection | CP1011 | 19/10/2020 | 23/10/2020 |  | Scheduled
OD0167 | TO-20-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | Total Maintenance Outage Duration Requested |  | 19/10/2020 | 23/10/2020 |  | Scheduled
15LN1367 | TO-20-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | 2014HP-2[20,21]Insulator Fit Dups. Proximity Outag of Cath Falls-Clogher 110kV. Wayleave Issue | 900649885 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
17LN1657 | TO-20-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | 2016HP-1[21]Insulator Fit Dups | 900819398 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17LN1656 | TO-20-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | 2016HP-1[20]Insulator Fit Dups | 900819397 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00501 | TO-20-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 19/10/2020 | 23/10/2020 | 4 | Scheduled
19EG23426 | TO-20-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | CATHALEENS FALL 110 | CLOGHER 110 | 2 | 110kV GIS Cubicle Operational Test | 901043763 | 19/10/2020 | 23/10/2020 | 4 | Scheduled
OD0088 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
15LN0871 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2014HP-1[295]Off Plumb | 900649868 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
15LN0873 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2014HP-1[298]Off Plumb | 900649866 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG00264 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17LN1613 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2016HP-1[14]Off Plumb | 900819396 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN3144 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[287]Check(General)-rusty Xarm | 900985204 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3146 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[281]Check(General)-rusty Xarm | 900985206 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3145 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[282]Check(General)-rusty Xarm | 900985205 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3148 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[228]Check(General)-rusty Xarm | 900985208 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3149 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[169]Check(General)-rusty Xarm | 900985209 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3147 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2018HP-1[278]Check(General)-rusty Xarm | 900985207 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
15LN0872 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2014HP-1[296]Off Plumb | 900649867 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
18LN3903 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2017HP-1[4]Vib Damps Dampers fatigue (Landowner access available May-July) | 900898249 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
15LN0874 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2014HP-1[299]Off Plumb | 900649865 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN1624 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2019HP-1[13]Earths-Replace Left pole e/w | 901084870 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN1759 | TO-20-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | CATHALEENS FALL 110 | CORRACLASSY 110 | 1 | 2019HP-1[277]Off Plumb -plumb poles | 901084950 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0090 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020027 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | P2 Protection maintenance of 7SA511, REL521 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
18LN3457 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | 2017HP-1[30]Anti-Cl. Guard -Fit | 900898210 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG00276 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00274 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG11301 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901068533 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17LN1672 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | 2016HP-1[194]Check-General Ground works | 900819401 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG20694 | TO-20-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | CATHALEENS FALL 110 | SRANANAGH 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0091 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | Total Maintenance Outage Duration Requested |  | 02/09/2020 | 11/09/2020 |  | Scheduled
TOP200113152722 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | P2 Protection maintenance of 7SA511, REL521 |  | 02/09/2020 | 11/09/2020 |  | Scheduled
20EG00278 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 02/09/2020 | 11/09/2020 | 4 | Scheduled
18LN3513 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2017HP-3[74,75,76]Off Plumb Poles | 900898213 | 02/09/2020 | 11/09/2020 | 3 | Scheduled
19LN3257 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2018HP-1[44]Check(General)-old Xarm | 900985321 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
19LN3219 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2018HP-1[93]Check(General)rusty crossarm | 900985335 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20EG00280 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 110KV CUBICLE CONDITION ASSESSMENT |  | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20EG00277 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20LN1881 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2019HP-1[77]Off Plumb -plumb poles | 901084951 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20LN1907 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2019HP-1[185]Off Plumb -plumb poles | 901084952 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20LN1920 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2019HP-1[247]Bird Nests | 901084269 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
20LN1908 | TO-20-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | CATHALEENS FALL 110 | SRANANAGH 110 | 2 | 2019HP-1[186]Off Plumb -plumb poles | 901084953 | 02/09/2020 | 11/09/2020 | 4 | Scheduled
TOP200617094118 | TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | CATHALEENS FALL 110 | CATHALEENS FALL G3 | T103 | Extra work day for IPP works on |  | 29/06/2020 | 03/07/2020 |  | Scheduled
20EG01640 | TO-20-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | CATHALEENS FALL 110 | CATHALEENS FALL G3 | T103 | 110KV SF6 Cubicle Ordinary Service | 901129790 | 29/06/2020 | 03/07/2020 | 4 | Scheduled
CAPX2020010910460112 | TO-20-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | CAUTEEN 110 | CAUTEEN 110 | 110SA1 | As a consequence of CTN-110SA2: 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0703 | TO-20-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | CAUTEEN 110 | CAUTEEN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11234 | TO-20-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | CAUTEEN 110 | CAUTEEN 110 | 110SA2 | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460113 | TO-20-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | CAUTEEN 110 | CAUTEEN 110 | 110SA2 | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0092 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN5261 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | "2018HP-4[122,123,127,128]Off Plumb" | 900987743 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN5262 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | "2018HP-5[72,85,102,105,121]Off Plumb" | 900987742 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN5260 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | "2018HP-4[134,135,136,137]Off Plumb" | 900987744 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN5256 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | 2018HP-1[AT11]Bird NestsCentre phase | 900987748 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN5263 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | "2018HP-6[5,15,47,48,51,64]Off Plumb" | 900987741 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG11229 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038731 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10302 | TO-20-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | CAUTEEN 110 | KILLONAN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020062 | TO-20-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | CAUTEEN 110 | CAUTEEN 38 | T142 | P2 Protection maintenance of 7SA612 |  | 25/12/2500 | 25/12/2500 | 2 | Reference (Unscheduled)
CAPX2020010910460114 | TO-20-CTN-T142-02 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | CAUTEEN 110 | CAUTEEN 38 | T142 | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910460115 | TO-20-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | CAUTEEN 110 | CAUTEEN 38 | T144 | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0093 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/10/2020 | 15/10/2020 |  | Scheduled
20CM0467 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | R,S & T Phases Tipperary 110kV Cubicle.R,S & T Phase Dlconnections DUE : 17-Nov-20 | 901134773 | 06/10/2020 | 15/10/2020 | 1 | Scheduled
19LN3296 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | "2018HP-2[3,19]Off PlumbPlumb poles" | 900985386 | 06/10/2020 | 15/10/2020 | 4 | Scheduled
20EG00586 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 06/10/2020 | 15/10/2020 | 4 | Scheduled
20EG02201 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 06/10/2020 | 15/10/2020 | 4 | Scheduled
20LN1922 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | 2019HP-1[3]Off Plumb -plumb poles | 901084954 | 06/10/2020 | 15/10/2020 | 4 | Scheduled
20LN1923 | TO-20-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | 2019HP-1[4]Bird Nests Over Right phase | 901084270 | 06/10/2020 | 15/10/2020 | 4 | Scheduled
CAPX2020010910460116 | TO-20-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | CAUTEEN 110 | TIPPERARY 110 | 1 | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1193 | TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | CHARLEVILLE 110 | GLENLARA 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/03/2020 | 13/03/2020 |  | Reference
20EG00281 | TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | CHARLEVILLE 110 | GLENLARA 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129798 | 10/03/2020 | 13/03/2020 | 4 | Reference
20EG23797 | TO-20-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | CHARLEVILLE 110 | GLENLARA 110 | 1 | 110kV SF6 Cubicle Operational Test | 901116384 | 10/03/2020 | 13/03/2020 | 4 | Reference
OD0095 | TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/11/2020 | 16/11/2020 |  | Scheduled
19LN3326 | TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | 2018HP-1[68]Bird NestsRight phase | 900985430 | 10/11/2020 | 16/11/2020 | 4 | Scheduled
20EG10143 | TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 10/11/2020 | 16/11/2020 | 4 | Scheduled
20CM0462 | TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | T Phase Killonan 110kV cubicle. Tphase DL/DE connection DUE : 17-Aug-20 | 901134774 | 10/11/2020 | 16/11/2020 | 1 | Scheduled
20LN1957 | TO-20-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | 2019HP-1[13]Off Plumb -plumb poles | 901084958 | 10/11/2020 | 16/11/2020 | 4 | Scheduled
CAPX2019100209112202 | TO-20-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | CHARLEVILLE 110 | KILLONAN 110 | 1 | EI: Line diversion work to enable construction of GIS building | CP0624 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020078 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 27/07/2020 | 31/07/2020 | 3 | Scheduled
OD0096 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 31/07/2020 |  | Scheduled
19EG10145 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 27/07/2020 | 31/07/2020 | 4 | Scheduled
19LN3330 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | "2018HP-6[16,19,62,72,81,92]Off Plumb" | 900985441 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
19EG10146 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | 110kV SF6 Cubicle Operational Test | 901076481 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
20LN1966 | TO-20-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | 2019HP-2[61,62]Off Plumb -plumb poles | 901084959 | 27/07/2020 | 31/07/2020 | 2 | Scheduled
TOP200416101117 | TO-20-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | CLAHANE 110 | CLAHANE 20 | T122 | Customer work |  | 19/05/2020 | 19/05/2020 |  | Scheduled
OD0097 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 19/10/2020 |  | Scheduled
19LN0880 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[64]Replace Pole only -Rotten | 901045854 | 12/10/2020 | 19/10/2020 | 1 | Scheduled
19LN0879 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[63]Ubolts -Replace (rust) | 901038484 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0885 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[69]Off Plumb -Poleset | 901038488 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0884 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[68]Off Plumb -Poleset | 901038487 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0847 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[50]Found/Site repair -Sleepers | 901038455 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
20EG11250 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 12/10/2020 | 19/10/2020 | 4 | Scheduled
20CM0413 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | Inspect Phisterer CSE & record serial number |  | 12/10/2020 | 19/10/2020 | 2 | Scheduled
19LN0849 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[50]Crossarm -Repair Grid Gain | 901038457 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0857 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[54]Crossarm -Repair Grid Gain | 901038464 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0875 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[62]Crossarm -Repair Grid Gain | 901038480 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0878 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[63]Insulator -Replace (rust) | 901038483 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
19LN0846 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | 2018CP-1[49]Replace/Retire pole butts | 901038454 | 12/10/2020 | 19/10/2020 | 4 | Scheduled
20EG20018 | TO-20-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | CLAHANE 110 | TRALEE 110 | 1 | Cable Insp. 110kV XLPE |  | 12/10/2020 | 19/10/2020 | 4 | Scheduled
OD0098 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/02/2020 | 02/03/2020 |  | Scheduled
TOP200113164938 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | P2 Protection maintenance of REL521, GRL100 |  | 25/02/2020 | 02/03/2020 |  | Scheduled
20CM0065 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | Water in Tech. Box in H2 Trien CB-SS. | 901080639 | 25/02/2020 | 02/03/2020 | 1 | Scheduled
19LN3353 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 2018HP-1[57]Insul&HW Replace check | 900985522 | 25/02/2020 | 02/03/2020 | 4 | Scheduled
16LN3417 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 2015CP-1[26]Off Plumb | 900773923 | 25/02/2020 | 02/03/2020 | 3 | Scheduled
17LN1729 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 2016HP-1[29]Insul&H-ware check | 900819428 | 25/02/2020 | 02/03/2020 | 3 | Scheduled
19LN3355 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 2018HP-1[44]Insul&HW Replace check | 900985520 | 25/02/2020 | 02/03/2020 | 4 | Scheduled
20EG06068 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | HV Pressure Vessel Inspection | 901114178 | 25/02/2020 | 02/03/2020 | 4 | Scheduled
19LN3357 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 2018HP-1[42]Insul&HW Replace check | 900985518 | 25/02/2020 | 02/03/2020 | 4 | Scheduled
CAPX2020010910351162 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 02/03/2020 |  | Scheduled
CAPX2020010910351176 | TO-20-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | CLAHANE 110 | TRIEN 110 | 1 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 02/03/2020 |  | Scheduled
CAPX2019100210345733 | TO-20-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | CLASHAVOON 110 | CLASHAVOON 110 | 110A1 | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932100 | TO-20-110 kV A1 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | CLASHAVOON 110 | CLASHAVOON 110 | 110A1 | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover | BB0001 | 10/09/2020 | 10/09/2020 |  | Scheduled
CAPX2020010910331758 | TO-20-110 kV A1 @ CLA-03 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | CLASHAVOON 110 | CLASHAVOON 110 | 110A1 | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932102 | TO-20-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | CLASHAVOON 110 | CLASHAVOON 110 | 110A2 | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover | BB0001 | 10/09/2020 | 10/09/2020 |  | Scheduled
CAPX2020010910331760 | TO-20-110 kV A2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | CLASHAVOON 110 | CLASHAVOON 110 | 110A2 | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932101 | TO-20-110 kV B1 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | CLASHAVOON 110 | CLASHAVOON 110 | 110B1 | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover | BB0001 | 10/09/2020 | 10/09/2020 |  | Scheduled
CAPX2020010910331759 | TO-20-110 kV B1 @ CLA-03 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | CLASHAVOON 110 | CLASHAVOON 110 | 110B1 | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345735 | TO-20-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | CLASHAVOON 110 | CLASHAVOON 110 | 110B1 | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331761 | TO-20-110 kV B2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | CLASHAVOON 110 | CLASHAVOON 110 | 110B2 | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932103 | TO-20-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | CLASHAVOON 110 | CLASHAVOON 110 | 110B2 | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover | BB0001 | 10/09/2020 | 10/09/2020 |  | Scheduled
CAPX2019100210345742 | TO-20-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | CLASHAVOON 110 | CLASHAVOON 110 | 110K1-2 | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0375 | TO-20-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | CLASHAVOON 220 | CLASHAVOON 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01035 | TO-20-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | CLASHAVOON 220 | CLASHAVOON 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01034 | TO-20-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | CLASHAVOON 220 | CLASHAVOON 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01036 | TO-20-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | CLASHAVOON 220 | CLASHAVOON 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01033 | TO-20-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | CLASHAVOON 220 | CLASHAVOON 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0099 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 26/02/2020 | 31/05/2020 |  | Scheduled
20EG10155 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129659 | 26/02/2020 | 31/05/2020 | 4 | Scheduled
20EG20706 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | Cable Insp. 110kV XLPE |  | 26/02/2020 | 31/05/2020 | 4 | Scheduled
CAPX2019100308542500 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | EI: Realingment of the line to allow for the construction of the new N22 bypass. A number of new towers are being constructed and polesets moved | CP0996 | 26/02/2020 | 31/05/2020 |  | Scheduled
20LN2065 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | 2019HP-2[19,20]Off Plumb -plumb poles | 901084964 | 26/02/2020 | 31/05/2020 | 2 | Scheduled
20LN2057 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | 2019HP-2[76,77]Off Plumb -plumb poles | 901084963 | 26/02/2020 | 31/05/2020 | 2 | Scheduled
20LN2007 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | 2019HP-2[91,92]Off Plumb -plumb poles | 901084962 | 26/02/2020 | 31/05/2020 | 2 | Scheduled
20LN2003 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | 2019HP-1[131]Off Plumb -plumb poles | 901084961 | 26/02/2020 | 31/05/2020 | 2 | Scheduled
20EG20728 | TO-20-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | CLASHAVOON 110 | CLONKEEN 110 | 1 | Cable Insp. 110kV XLPE |  | 26/02/2020 | 31/05/2020 | 4 | Scheduled
CAPX2020062516112801 | TO-20-CLA-DMY-1-03 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | CLASHAVOON 110 | DUNMANWAY 110 | 1 | 110 kV A2 @ DMY: Isolate M21BBP Cabinet | CP0930 | 13/07/2020 | 17/07/2020 |  | Scheduled
PROT2020034 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | P2 Protection maintenance of 7SA513, GRL100 |  | 23/11/2020 | 27/11/2020 | 2 | Scheduled
CAPX2020091508195808 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | Proximity outage to allow for A1/B1 busbar section to be retired | CP0796 + CP0973 | 23/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020060310121318 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 23/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020102914341808 | TO-20-CLA-KRA-1-05 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | Proximity outage to allow for A1B1 busbar section to be retired | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020115 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | P3 Protection maintenance of 7SA513, GRL100 |  | 23/11/2020 | 27/11/2020 | 3 | Scheduled
OD0267 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 27/11/2020 |  | Scheduled
19CM0332 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | Replace stolen earths | 901091471 | 23/11/2020 | 27/11/2020 | 1 | Scheduled
19EG10405 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | 220kV SF6 Cubicle Operational Test | 901038860 | 23/11/2020 | 27/11/2020 | 4 | Scheduled
18EG10404 | TO-20-CLA-KRA-1-04 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | 220kV SF6 Cubicle Operational Test | 901050471 | 23/11/2020 | 27/11/2020 | 3 | Scheduled
CAPX2019101409072033 | TO-20-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101411492622 | TO-20-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409072044 | TO-20-CLA-KRA-1-03 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | CLASHAVOON 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1369 | TO-20-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200302104759 | TO-20-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | Offline PD test on new cable |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG223720 | TO-20-CLA-MAC-1-05 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100210345712 | TO-20-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102112121223 | TO-20-CLA-MAC-1-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345743 | TO-20-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345700 | TO-20-CLA-MAC-1-04 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | CLASHAVOON 110 | MACROOM 110 | 1 | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0100 | TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 16/03/2020 |  | Scheduled
20EG10154 | TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | 110kV MO Cubicle Operational Test |  | 09/03/2020 | 16/03/2020 | 4 | Scheduled
CAPX2019100210345706 | TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay. | CP0829 | 09/03/2020 | 16/03/2020 |  | Scheduled
20EG223720 | TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 09/03/2020 | 16/03/2020 | 4 | Scheduled
CAPX2019100210345721 | TO-20-CLA-MAC-2-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345709 | TO-20-CLA-MAC-2-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN2092 | TO-20-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | 2019HP-1[12]Off Plumb -plumb poles | 901084965 | 09/03/2020 | 16/03/2020 | 2 | Scheduled
CAPX2019100210345730 | TO-20-CLA-MAC-2-04 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | CLASHAVOON 110 | MACROOM 110 | 2 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0747 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01822 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01819 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18CM1265 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | O1- S phase bushing low in oil. | 900973237 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01821 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01818 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0071 | TO-20-CLA-T2101-04 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Replace timber supports on T2101 Transfo | 900908038 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100210345732 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Remove old 125 MVA trafo and bund, constuct new bund, install and commission new 250 MVA trafo. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345736 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345744 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345734 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345746 | TO-20-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | CLASHAVOON 220 | CLASHAVOON 110 | T2101 | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0748 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 21/07/2020 |  | Scheduled
20EG02388 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 220kV CUBICLE CONDITION ASSESSMENT |  | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20EG02389 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 220/110 & 275/220 TRAFO COND. ASSESSMENT | 901130541 | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20EG02387 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20EG02386 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20EG02385 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 220kV SF6 Cubicle Ordinary Service |  | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20EG02384 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 110kV SF6 Cubicle Ordinary Service |  | 06/07/2020 | 21/07/2020 | 4 | Scheduled
20CM0074 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | O1-OLTC Tap position not corresponding w | 900879219 | 06/07/2020 | 21/07/2020 | 2 | Scheduled
20CM0073 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | O1- Moss on all equipment in Cubicle | 900909472 | 06/07/2020 | 21/07/2020 | 2 | Scheduled
20EG02390 | TO-20-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | CLASHAVOON 220 | CLASHAVOON 110 | T2102 | 220/110kV Trafo Tap Changer Inspection | 901130545 | 06/07/2020 | 21/07/2020 | 4 | Scheduled
OD0644 | TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | CLIFF 110 | CLIFF G1 | T101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG10949 | TO-20-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | CLIFF 110 | CLIFF G1 | T101 | 110KV SF6 Cubicle Operational Test | 901129648 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020065 | TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | CLIFF 110 | CLIFF G2 | T102 | P2 Protection maintenance of 7SJ511 |  | 25/08/2020 | 25/08/2020 | 2 | Scheduled
20EG10950 | TO-20-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | CLIFF 110 | CLIFF G2 | T102 | 110KV SF6 Cubicle Operational Test |  | 25/08/2020 | 25/08/2020 | 4 | Scheduled
OD0942 | TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG11408 | TO-20-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | 110kV SF6 Cubicle Operational Test | 900938714 | 22/06/2020 | 23/06/2020 | 4 | Scheduled
CAPX2020010910351187 | TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351177 | TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351188 | TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351163 | TO-20-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA1 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1218 | TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18EG11407 | TO-20-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | 110kV SF6 Cubicle Operational Test |  | 22/06/2020 | 23/06/2020 | 3 | Scheduled
CAPX2020010910351178 | TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351164 | TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351190 | TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351189 | TO-20-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | CLOGHBOOLA 110 | CLOGHBOOLA 110 | 110SA2 | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351179 | TO-20-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | CLOGHBOOLA 110 | CLOGHBOOLA 20 | T122 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351165 | TO-20-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | CLOGHBOOLA 110 | CLOGHBOOLA 20 | T122 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351192 | TO-20-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | CLOGHBOOLA 110 | CLOGHBOOLA 20 | T122 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351191 | TO-20-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | CLOGHBOOLA 110 | CLOGHBOOLA 20 | T122 | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 22/06/2020 | 23/06/2020 |  | Reference
OD0904 | TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG11410 | TO-20-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | 110kV SF6 Cubicle Operational Test | 901068541 | 22/06/2020 | 23/06/2020 | 4 | Scheduled
CAPX2020010910351180 | TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351166 | TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351193 | TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351194 | TO-20-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | CLOGHBOOLA 110 | CLOGHBOOLA 33 | T131 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0912 | TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 22/06/2020 | 23/06/2020 |  | Scheduled
19EG11409 | TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901043718 | 22/06/2020 | 23/06/2020 | 4 | Scheduled
18EG23639 | TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901050357 | 22/06/2020 | 23/06/2020 | 3 | Scheduled
CAPX2020010910351196 | TO-20-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20755 | TO-20-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | Cable Insp. 110kV XLPE |  | 22/06/2020 | 23/06/2020 | 4 | Scheduled
CAPX2020010910351195 | TO-20-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351167 | TO-20-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351181 | TO-20-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | CLOGHBOOLA 110 | TRIEN 110 | 1 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932104 | TO-20-110 kV A1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | CLOGHER 110 | CLOGHER 110 | 110A1 | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 17/09/2020 | 17/09/2020 |  | Scheduled
CAPX20191218103932106 | TO-20-110 kV A2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | CLOGHER 110 | CLOGHER 110 | 110A2 | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 17/09/2020 | 17/09/2020 |  | Scheduled
CAPX20191218103932105 | TO-20-110 kV B1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | CLOGHER 110 | CLOGHER 110 | 110B1 | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 17/09/2020 | 17/09/2020 |  | Scheduled
CAPX20191218103932107 | TO-20-110 kV B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | CLOGHER 110 | CLOGHER 110 | 110B2 | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 17/09/2020 | 17/09/2020 |  | Scheduled
OD1007 | TO-20-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | CLOGHER 110 | CLOGHER 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21127 | TO-20-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | CLOGHER 110 | CLOGHER 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901050343 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG21126 | TO-20-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | CLOGHER 110 | CLOGHER 110 | 110K1-2 | 110kV GIS Cubicle Operational Test | 901043754 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0970 | TO-20-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | CLOGHER 110 | DRUMKEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 27/11/2020 |  | Scheduled
20EG00270 | TO-20-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | CLOGHER 110 | DRUMKEEN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 23/11/2020 | 27/11/2020 | 4 | Scheduled
20LN2097 | TO-20-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | CLOGHER 110 | DRUMKEEN 110 | 1 | 2019HP-1[47]Earths-Replace | 901084871 | 23/11/2020 | 27/11/2020 | 4 | Scheduled
20EG21012 | TO-20-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | CLOGHER 110 | DRUMKEEN 110 | 1 | Cable Insp. 110kV XLPE |  | 23/11/2020 | 27/11/2020 | 4 | Scheduled
OD0971 | TO-20-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | CLOGHER 110 | MULREAVY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21299 | TO-20-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | CLOGHER 110 | MULREAVY 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20191218103932108 | TO-20-110 kV A1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | CLOGHRAN 110 | CLOGHRAN 110 | 110A1 | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932114 | TO-20-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | CLOGHRAN 110 | CLOGHRAN 110 | 110A2 | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932109 | TO-20-110 kV B1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | CLOGHRAN 110 | CLOGHRAN 110 | 110B1 | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932115 | TO-20-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | CLOGHRAN 110 | CLOGHRAN 110 | 110B2 | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932111 | TO-20-CLG-110K1-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | CLOGHRAN 110 | CLOGHRAN 110 | 110K1 | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932110 | TO-20-CLG-110K1-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | CLOGHRAN 110 | CLOGHRAN 110 | 110K1 | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932117 | TO-20-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | CLOGHRAN 110 | CLOGHRAN 110 | 110K2 | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932116 | TO-20-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | CLOGHRAN 110 | CLOGHRAN 110 | 110K2 | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932112 | TO-20-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | CLOGHRAN 110 | CLOGHRAN 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932118 | TO-20-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | CLOGHRAN 110 | CLOGHRAN 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932119 | TO-20-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | CLOGHRAN 110 | CLOGHRAN 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932113 | TO-20-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | CLOGHRAN 110 | CLOGHRAN 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1151 | TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | CLOGHRAN 110 | CORDUFF 110 | 1 | Total Maintenance Outage Duration Requested |  | 30/06/2020 | 02/07/2020 |  | Scheduled
20CM0077 | TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | CLOGHRAN 110 | CORDUFF 110 | 1 | O/1 SURGE ARRESTOR BROKEN | 900637313 | 30/06/2020 | 02/07/2020 | 2 | Scheduled
20EG23222 | TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | CLOGHRAN 110 | CORDUFF 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 30/06/2020 | 02/07/2020 | 4 | Scheduled
20EG23219 | TO-20-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | CLOGHRAN 110 | CORDUFF 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 30/06/2020 | 02/07/2020 | 4 | Scheduled
OD0817 | TO-20-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | CLOGHRAN 110 | FINGLAS GIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/11/2020 | 27/11/2020 |  | Scheduled
19EG20708 | TO-20-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | CLOGHRAN 110 | FINGLAS GIS 110 | 1 | Cable Insp. 110kV XLPE | 901115062 | 25/11/2020 | 27/11/2020 | 4 | Scheduled
17EG20707 | TO-20-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | CLOGHRAN 110 | FINGLAS GIS 110 | 1 | Annual Insp. 110kV Feeder XLPE Cable | 900840443 | 25/11/2020 | 27/11/2020 | 3 | Scheduled
PROT2020181 | TO-20-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | CLOGHRAN 110 | CLOGHRAN 20 | T121 | P3 Protection maintenance of 7SA612 |  | 19/10/2020 | 23/10/2020 | 3 | Scheduled
TOP200527114111 | TO-20-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | CLOGHRAN 110 | CLOGHRAN 20 | T121 | 5 Day Customer Outage |  | 19/10/2020 | 23/10/2020 |  | Scheduled
TOP200527114214 | TO-20-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | CLOGHRAN 110 | CLOGHRAN 20 | T122 | 5 day customer outage |  | 28/09/2020 | 02/10/2020 |  | Scheduled
PROT2020182 | TO-20-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | CLOGHRAN 110 | CLOGHRAN 20 | T123 | P3 Protection maintenance of 7SA612 |  | 27/10/2020 | 30/10/2020 | 3 | Scheduled
TOP200527113643 | TO-20-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | CLOGHRAN 110 | CLOGHRAN 20 | T123 | 5 Day Customer outage |  | 27/10/2020 | 30/10/2020 |  | Scheduled
OD0842 | TO-20-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | CLOGHRAN 110 | CLOGHRAN 20 | T123 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
18EG11355 | TO-20-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | CLOGHRAN 110 | CLOGHRAN 20 | T123 | 110kV SF6 Cubicle Operational Test | 901030848 | 27/10/2020 | 30/10/2020 | 3 | Scheduled
TOP200527114343 | TO-20-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | CLOGHRAN 110 | CLOGHRAN 20 | T124 | 4 day customer outage |  | 09/11/2020 | 13/11/2020 |  | Scheduled
OD1144 | TO-20-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | CLOGHRAN 110 | CLOGHRAN 20 | T124 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 13/11/2020 |  | Scheduled
18EG23510 | TO-20-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | CLOGHRAN 110 | CLOGHRAN 20 | T124 | Annual Insp. 110kV Feeder XLPE Cable | 901006517 | 09/11/2020 | 13/11/2020 | 3 | Scheduled
TOP200527114437 | TO-20-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | CLOGHRAN 110 | CLOGHRAN 20 | T126 | 5 day customer outage |  | 02/11/2020 | 06/11/2020 |  | Scheduled
CAPX2020100615524000 | TO-20-220 kV A1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | CLONEE 220 | CLONEE 220 | 220A1 | Civil and Electrical Installation Works associated with new F1 bay | CP1049 | 28/10/2020 | 18/11/2020 |  | Scheduled
CAPX20191218103932124 | TO-20-220 kV A1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | CLONEE 220 | CLONEE 220 | 220A1 | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932120 | TO-20-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | CLONEE 220 | CLONEE 220 | 220A2 | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020100615524002 | TO-20-220 kV B1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | CLONEE 220 | CLONEE 220 | 220B1 | Civil and Electrical Installation Works associated with new F1 bay | CP1049 | 19/11/2020 | 27/11/2020 |  | Scheduled
CAPX20191218103932125 | TO-20-220 kV B1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | CLONEE 220 | CLONEE 220 | 220B1 | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932121 | TO-20-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | CLONEE 220 | CLONEE 220 | 220B2 | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020100615524001 | TO-20-CLE-220K1-05 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | CLONEE 220 | CLONEE 220 | 220K1 | As a consequence of 220 kV A1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay | CP1049 | 28/10/2020 | 18/11/2020 |  | Scheduled
CAPX2020100615524003 | TO-20-CLE-220K1-06 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | CLONEE 220 | CLONEE 220 | 220K1 | As a consequence of 220 kV B1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay | CP1049 | 19/11/2020 | 27/11/2020 |  | Scheduled
CAPX20191218103932127 | TO-20-CLE-220K1-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | CLONEE 220 | CLONEE 220 | 220K1 | As a consequence of 220 kV B1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932126 | TO-20-CLE-220K1-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | CLONEE 220 | CLONEE 220 | 220K1 | As a consequence of 220 kV A1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932123 | TO-20-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | CLONEE 220 | CLONEE 220 | 220K2 | As a consequence of 220 kV B2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932122 | TO-20-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | CLONEE 220 | CLONEE 220 | 220K2 | As a consequence of 220 kV A2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1103 | TO-20-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | CLONEE 220 | CORDUFF 220 | 1 | Total Maintenance Outage Duration Requested |  | 19/11/2020 | 02/12/2020 |  | Scheduled
19EG23363 | TO-20-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | CLONEE 220 | CORDUFF 220 | 1 | 220kV SF6 Cubicle Operational Test | 901045472 | 19/11/2020 | 02/12/2020 | 4 | Scheduled
20EG00802 | TO-20-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | CLONEE 220 | CORDUFF 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 19/11/2020 | 02/12/2020 | 4 | Scheduled
TOP200824171041 | TO-20-CLE-T221-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | CLONEE 220 | CLONEE 20 | T221 | Customer outage request |  | 21/09/2020 | 05/10/2020 |  | Scheduled
TOP200818161745 | TO-20-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | CLONEE 220 | CLONEE 20 | T224 | Customer outage |  | 09/09/2020 | 17/09/2020 |  | Scheduled
OD1147 | TO-20-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | CLONEE 220 | CLONEE 20 | T224 | Total Maintenance Outage Duration Requested |  | 09/09/2020 | 17/09/2020 |  | Scheduled
20EG23342 | TO-20-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | CLONEE 220 | CLONEE 20 | T224 | 220kV SF6 Cubicle Operational Test |  | 09/09/2020 | 17/09/2020 | 4 | Scheduled
OD1104 | TO-20-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | CLONEE 220 | WOODLAND 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG06038 | TO-20-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | CLONEE 220 | WOODLAND 220 | 1 | HV Pressure Vessel Inspection | 901046058 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN3479 | TO-20-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | CLONEE 220 | WOODLAND 220 | 1 | 2018HP-1[3]Check Struct/Found/etc-base | 900985608 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00803 | TO-20-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | CLONEE 220 | WOODLAND 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020165 | TO-20-CKN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | CLONKEEN 110 | CLONKEEN 110 | 110SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0823 | TO-20-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | CLONKEEN 110 | CLONKEEN 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11342 | TO-20-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | CLONKEEN 110 | CLONKEEN 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11340 | TO-20-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | CLONKEEN 110 | CLONKEEN 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11341 | TO-20-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | CLONKEEN 110 | CLONKEEN 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0101 | TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | CLONKEEN 110 | COOMAGEARLAHY 110 | 1 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
20EG10156 | TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | CLONKEEN 110 | COOMAGEARLAHY 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129698 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
20EG10152 | TO-20-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | CLONKEEN 110 | COOMAGEARLAHY 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129658 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
PROT2020030 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | P2 Protection maintenance of REL521, GRL100 |  | 08/06/2020 | 12/06/2020 | 2 | Scheduled
OD0102 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | Total Maintenance Outage Duration Requested |  | 08/06/2020 | 12/06/2020 |  | Scheduled
20EG02490 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129956 | 08/06/2020 | 12/06/2020 | 4 | Scheduled
20EG00312 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 08/06/2020 | 12/06/2020 | 4 | Scheduled
20CM0391 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | Visual inspection of HIS HV cable sealin | 901068795 | 08/06/2020 | 12/06/2020 | 1 | Scheduled
20EG02491 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 08/06/2020 | 12/06/2020 | 4 | Scheduled
19EG00311 | TO-20-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | CLONKEEN 110 | GARROW 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 08/06/2020 | 12/06/2020 | 4 | Scheduled
PROT2020156 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | P3 Protection maintenance of 7SA612 |  | 04/06/2020 | 05/06/2020 | 3 | Scheduled
PROT2020079 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | P3 Protection maintenance of 7SA612, 7SA511 |  | 04/06/2020 | 05/06/2020 | 3 | Scheduled
OD0103 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 04/06/2020 | 05/06/2020 |  | Scheduled
19LN3516 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | 2018HP-1[33]Off PlumbPlumb poles | 900985669 | 04/06/2020 | 05/06/2020 | 4 | Scheduled
20EG10158 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129657 | 04/06/2020 | 05/06/2020 | 4 | Scheduled
20CM0463 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | R Phase Knockearagh 110kV Cubicle. R Phase DL contact. DUE : 17-Aug-20 hotspot | 901134777 | 04/06/2020 | 05/06/2020 | 1 | Scheduled
20LN2131 | TO-20-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | CLONKEEN 110 | KNOCKEARAGH 110 | 1 | 2019HP-1[32]Off Plumb -plumb poles | 901084966 | 04/06/2020 | 05/06/2020 | 2 | Scheduled
TOP200610173403 | TO-20-110 kV A2 @ CLN-01 | BUSBAR SECTION - CLOON 110-CLOON 110-110A2 | CLOON 110 | CLOON 110 | 110A2 | Proximity for EI of CLN T142 | PR0001 | 25/06/2020 | 26/06/2020 |  | Tentative
CAPX2020010910460117 | TO-20-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | CLOON 110 | CLOON 110 | 110SA1 | As a consequence of CLN-110SA2: 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1331 | TO-20-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | CLOON 110 | CLOON 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04027 | TO-20-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | CLOON 110 | CLOON 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039700 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460118 | TO-20-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | CLOON 110 | CLOON 110 | 110SA2 | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0104 | TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 16/10/2020 |  | Scheduled
TOP200610173259 | TO-20-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | Proximity for EI of CLN T142 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113143128 | TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | P1 Protection maintenance of 7SA511, REL521 |  | 12/10/2020 | 16/10/2020 |  | Scheduled
17LN1826 | TO-20-CLN-LA-1-05 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 2016HP-1[97]Stays - Check Check stays | 900819454 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG00317 | TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042219 | 12/10/2020 | 16/10/2020 | 4 | Scheduled
19EG00318 | TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042220 | 12/10/2020 | 16/10/2020 | 4 | Scheduled
18CM0280 | TO-20-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | Repair fault busbar disconnect | 900957961 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910351112 | TO-20-CLN-LA-1-02 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN2173 | TO-20-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 2019HP-1[97]Stays-Replace Broken | 901085132 | 12/10/2020 | 16/10/2020 | 4 | Scheduled
CAPX2020010910460119 | TO-20-CLN-LA-1-02 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | CLOON 110 | LANESBORO 110 | 1 | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200610173538 | TO-20-CLN-T142-02 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | CLOON 110 | CLOON 38 | T142 | EI of CLN T142 request from RC | PR0001 | 25/06/2020 | 26/06/2020 |  | Reference (Tentative)
CAPX2020010910460120 | TO-20-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | CLOON 110 | CLOON 38 | T142 | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0376 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10562 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 900859226 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17EG10563 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 900859195 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
16EG01037 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 900744240 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17EG10564 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 900859196 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17EG10565 | TO-20-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test | 900839239 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020010910465505 | TO-20-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465500 | TO-20-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-2CB | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0377 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113164037 | TO-20-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | P1 Protection maintenance of 7SJ511 | PROT | 25/12/2500 | 25/12/2500 |  | Unscheduled
16EG01044 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV Sect / Dist Ordinary Service | 900744242 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16EG02410 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV Sect / Dist Ordinary Service | 900745182 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16EG02195 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV Sect / Dist Ordinary Service | 900778168 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16EG01045 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV GIS Cubicle Ordinary Service | 900777933 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG10567 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV Sect / Dist Operational Test | 901076464 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
16EG01043 | TO-20-COL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110kV Sect / Dist Ordinary Service | 900778172 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910465501 | TO-20-COL-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465506 | TO-20-COL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | COLLEGE PARK 110 | COLLEGE PARK 110 | 110SA1-3CB | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0111 | TO-20-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0479 | TO-20-COL-CDU-1-04 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | R Phase Hotspot found on R Phase CT HV Connection DUE IMMEDIATELY0 | 900981227 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG10172 | TO-20-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | 110kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465507 | TO-20-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465502 | TO-20-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20023 | TO-20-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | COLLEGE PARK 110 | CORDUFF 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1230 | TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | COLLEGE PARK 110 | FINGLAS GIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/02/2020 | 03/03/2020 |  | Scheduled
OD0973 | TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | COLLEGE PARK 110 | FINGLAS GIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/02/2020 | 03/03/2020 |  | Scheduled
20EG00321 | TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | COLLEGE PARK 110 | FINGLAS GIS 110 | 1 | 110kV GIS Cubicle Ordinary Service | 901128698 | 27/02/2020 | 03/03/2020 | 4 | Scheduled
20LN3083 | TO-20-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | COLLEGE PARK 110 | FINGLAS GIS 110 | 1 | 2019HP-1[14]Replace Pole only -Rot | 901086432 | 27/02/2020 | 03/03/2020 | 2 | Scheduled
CAPX2020010910465503 | TO-20-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | COLLEGE PARK 110 | COLLEGE PARK 10 | T101 | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0004 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910465508 | TO-20-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | COLLEGE PARK 110 | COLLEGE PARK 10 | T101 | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910465504 | TO-20-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | COLLEGE PARK 110 | COLLEGE PARK 10 | T103 | As a consequence of COL-110SA1-3CB: 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0004 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910465510 | TO-20-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | COLLEGE PARK 110 | COLLEGE PARK 10 | T103 | As a consequence of COL-110SA1-3CB: 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910465509 | TO-20-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | COLLEGE PARK 110 | COLLEGE PARK 10 | T103 | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service | PR0004 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP201001151839 | TO-20-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | COOLNANOONAGH 110 | KILPADDOGE 110 | 1 | Outage to facilitate customer's work |  | 28/10/2020 | 02/11/2020 |  | Scheduled
TOP200923112834 | TO-20-CNO-T131-02 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | COOLNANOONAGH 110 | COOLNANOONAGH 33 | T131 | Outage to facilitate customer's work |  | 20/11/2020 | 24/11/2020 |  | Tentative
TOP200819171407 | TO-20-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | COOLNANOONAGH 110 | COOLNANOONAGH 33 | T131 | Black start testing |  | 31/08/2020 | 31/08/2020 |  | Scheduled
OD0106 | TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | COOLROE 110 | INNISCARRA 110 | 1 | Total Maintenance Outage Duration Requested |  | 03/06/2020 | 05/06/2020 |  | Scheduled
20EG10165 | TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | COOLROE 110 | INNISCARRA 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 03/06/2020 | 05/06/2020 | 4 | Scheduled
20LN2189 | TO-20-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | COOLROE 110 | INNISCARRA 110 | 1 | 2019HP-2[8,9]Off Plumb -plumb poles | 901084967 | 03/06/2020 | 05/06/2020 | 2 | Scheduled
TOP200114102207 | TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | P3 Protection maintenance of 7SA511, REL521 |  | 29/06/2020 | 11/09/2020 |  | Scheduled
TOP200114102048 | TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | P2 Protection maintenance of 7SA511, REL521 |  | 29/06/2020 | 11/09/2020 |  | Scheduled
OD0107 | TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 11/09/2020 |  | Scheduled
CAPX2020090813472503 | TO-20-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | Proximity outage to facilitate the civil works and installation of the commercial fibre, cable pull, scaffolding erection and calbe termination | CP1037 | 21/09/2020 | 09/10/2020 |  | Scheduled
20EG20698 | TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | Cable Insp. 110kV XLPE |  | 29/06/2020 | 11/09/2020 | 4 | Scheduled
CAPX2019100309413400 | TO-20-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | COOLROE 110 | KILBARRY 110 | 1 | Terminating 110 kV cable at station bay and end masts | CP1037 | 29/06/2020 | 11/09/2020 |  | Scheduled
OD0914 | TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | COOMAGEARLAHY 110 | COOMAGEARLAHY 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
17CM0210 | TO-20-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | COOMAGEARLAHY 110 | COOMAGEARLAHY 110 | 110SA1 | O2.Sectionaliser not working from Mimic. | 900801826 | 13/07/2020 | 15/07/2020 | 2 | Scheduled
TOP200114170005 | TO-20-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | COOMAGEARLAHY 110 | COOMAGEARLAHY 110 | 110SA2 | Prox for SA1 |  | 13/07/2020 | 15/07/2020 |  | Scheduled
OD0108 | TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | COOMAGEARLAHY 110 | GLANLEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
20EG10168 | TO-20-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | COOMAGEARLAHY 110 | GLANLEE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129700 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
OD0495 | TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | COOMAGEARLAHY 110 | COOMAGEARLAHY 20 | T121 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 16/07/2020 |  | Scheduled
20EG10817 | TO-20-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | COOMAGEARLAHY 110 | COOMAGEARLAHY 20 | T121 | 110kV SF6 Cubicle Operational Test | 901129701 | 13/07/2020 | 16/07/2020 | 4 | Scheduled
OD0496 | TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | COOMAGEARLAHY 110 | COOMAGEARLAHY 20 | T122 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
20EG10818 | TO-20-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | COOMAGEARLAHY 110 | COOMAGEARLAHY 20 | T122 | 110kV SF6 Cubicle Operational Test | 901129699 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
TOP200911112719 | TO-20-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | COOMATAGGART 110 | COOMATAGGART 110 | 110SA1 | As consequence of Ballyvouskill - Coomataggart 110kV outage |  | 28/09/2020 | 02/10/2020 |  | Scheduled
TOP200911112808 | TO-20-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | COOMATAGGART 110 | COOMATAGGART 110 | 110SA2 | As consequence of Ballyvouskill - Coomataggart 110kV outage |  | 28/09/2020 | 02/10/2020 |  | Scheduled
TOP200908154438 | TO-20-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | COOMATAGGART 110 | COOMATAGGART 33 | T132 | As consequence of Ballyvouskill - Coomataggart 110kV outage |  | 28/09/2020 | 02/10/2020 |  | Scheduled
TOP200908154206 | TO-20-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | COOMATAGGART 110 | COOMATAGGART 38 | T141 | As consequence of Ballyvouskill - Coomataggart 110kV outage |  | 28/09/2020 | 02/10/2020 |  | Reference
OD1332 | TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | CORDAL 110 | CORDAL 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 11/08/2020 | 13/08/2020 |  | Scheduled
20EG23708 | TO-20-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | CORDAL 110 | CORDAL 110 | 110SA1 | 110kV Sect / Dist Operational Test | 901130105 | 11/08/2020 | 13/08/2020 | 4 | Scheduled
OD1333 | TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | CORDAL 110 | CORDAL 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 11/08/2020 | 13/08/2020 |  | Scheduled
20EG23709 | TO-20-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | CORDAL 110 | CORDAL 110 | 110SA2 | 110kV Sect / Dist Operational Test | 901146308 | 11/08/2020 | 13/08/2020 | 4 | Scheduled
OD1224 | TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | CORDAL 110 | CORDAL 33 | T132 | Total Maintenance Outage Duration Requested |  | 11/08/2020 | 14/08/2020 |  | Scheduled
20CM0392 | TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | CORDAL 110 | CORDAL 33 | T132 | Replair replace bonding leads (damaged) | 901074069 | 11/08/2020 | 14/08/2020 | 1 | Scheduled
20EG23705 | TO-20-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | CORDAL 110 | CORDAL 33 | T132 | 110kV SF6 Cubicle Operational Test | 901118391 | 11/08/2020 | 14/08/2020 | 4 | Scheduled
TOP200324125534 | TO-20-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | CORDAL 38 | CORDAL 38 | T141 | As a consequence of work on Ballynahulla-Cordal 110 kV circuit |  | 11/08/2020 | 13/08/2020 |  | Reference
CAPX2020021009203403 | TO-20-CDY-110SA1-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | CORDERRY 110 | CORDERRY 110 | 110SA1 | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Remove BB dropper | CP0942 | 24/02/2020 | 25/02/2020 |  | Scheduled
CAPX2020021009203411 | TO-20-CDY-110SA1-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | CORDERRY 110 | CORDERRY 110 | 110SA1 | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper | CP0942 | 19/10/2020 | 23/10/2020 |  | Scheduled
CAPX2020021009203412 | TO-20-CDY-110SA2-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | CORDERRY 110 | CORDERRY 110 | 110SA2 | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper | CP0942 | 19/10/2020 | 23/10/2020 |  | Scheduled
CAPX2020021009203404 | TO-20-CDY-110SA2-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | CORDERRY 110 | CORDERRY 110 | 110SA2 | 110 kV A2 @ CDY: Remove BB dropper | CP0942 | 24/02/2020 | 25/02/2020 |  | Scheduled
OD0109 | TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | CORDERRY 110 | GARVAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
19CM0036 | TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | CORDERRY 110 | GARVAGH 110 | 1 | Leak detection on CB & repair if required | 901129384 | 13/07/2020 | 15/07/2020 | 1 | Scheduled
19LN3601 | TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | CORDERRY 110 | GARVAGH 110 | 1 | 2018HP-1[Am11]Bird Nests | 900985802 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
20EG10169 | TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | CORDERRY 110 | GARVAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129706 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
20EG20665 | TO-20-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | CORDERRY 110 | GARVAGH 110 | 1 | Cable Insp. 110kV XLPE |  | 13/07/2020 | 15/07/2020 | 4 | Scheduled
CAPX2020021009203413 | TO-20-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper | CP0942 | 19/10/2020 | 23/10/2020 |  | Scheduled
CAPX2020021009203405 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110 kV A2 @ CDY: Remove BB dropper | CP0942 | 24/02/2020 | 23/10/2020 |  | Scheduled
TOP200117151947 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | P1 Protection maintenance of REL521, REL551 |  | 24/02/2020 | 23/10/2020 |  | Scheduled
19EG10170 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901039099 | 24/02/2020 | 23/10/2020 | 4 | Scheduled
20EG00336 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 24/02/2020 | 23/10/2020 | 4 | Scheduled
16LN3353 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 2015CP-1[28]Check Structure Worm Holes | 900725308 | 24/02/2020 | 23/10/2020 | 1 | Scheduled
20EG00338 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 24/02/2020 | 23/10/2020 | 4 | Scheduled
16LN3114 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 2015CP-3[16,19,30]Replace Pole only | 900725307 | 24/02/2020 | 23/10/2020 | 1 | Scheduled
CAPX2019100308102513 | TO-20-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends | CP0942 | 19/10/2020 | 23/10/2020 |  | Scheduled
CAPX2019100715473300 | TO-20-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | CORDERRY 110 | SRANANAGH 110 | 1 | 110 kV OHL outage | CP0942 | 24/02/2020 | 23/10/2020 |  | Scheduled
CAPX2020021009203406 | TO-20-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | CORDERRY 110 | CORDERRY 20 | T122 | 110 kV A2 @ CDY: Remove BB dropper | CP0942 | 24/02/2020 | 25/02/2020 |  | Reference
CAPX2020021009203414 | TO-20-CDY-T122-02 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | CORDERRY 110 | CORDERRY 20 | T122 | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper | CP0942 | 19/10/2020 | 23/10/2020 |  | Reference
CAPX2019121810393250 | TO-20-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | CORDUFF 110 | CORDUFF 110 | 110A1 | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2019100410000313 | TO-20-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | CORDUFF 110 | CORDUFF 110 | 110A2 | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2 | CP1025 | 13/07/2020 | 24/07/2020 |  | Scheduled
CAPX2019100410000312 | TO-20-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | CORDUFF 110 | CORDUFF 110 | 110A2 | Install DA bases on H2 | CP1025 | 02/06/2020 | 17/06/2020 |  | Scheduled
CAPX2019121810393252 | TO-20-110 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | CORDUFF 110 | CORDUFF 110 | 110A2 | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2020083114080012 | TO-20-110 kV A3 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | CORDUFF 110 | CORDUFF 110 | 110A3 | To facilitate CB connection works associated with DN0241/CP1025 Corduff | CP1025 | 15/09/2020 | 17/09/2020 |  | Scheduled
CAPX2020103012130602 | TO-20-110 kV A3 @ CDU-06 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | CORDUFF 110 | CORDUFF 110 | 110A3 | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay | CP1009_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100410000304 | TO-20-110 kV A3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | CORDUFF 110 | CORDUFF 110 | 110A3 | 110 kV A3/B3 IN TURN @ CDU: Test interlocking | CP1025 | 18/11/2020 | 20/11/2020 |  | Scheduled
CAPX2019100410000302 | TO-20-110 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | CORDUFF 110 | CORDUFF 110 | 110A3 | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11 | CP1025 | 02/06/2020 | 12/06/2020 |  | Scheduled
CAPX2019121810393254 | TO-20-110 kV A3 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | CORDUFF 110 | CORDUFF 110 | 110A3 | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2019121810393256 | TO-20-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | CORDUFF 110 | CORDUFF 110 | 110A4 | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2019121810393251 | TO-20-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | CORDUFF 110 | CORDUFF 110 | 110B1 | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2019100410000314 | TO-20-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | CORDUFF 110 | CORDUFF 110 | 110B2 | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2 | CP1025 | 13/07/2020 | 24/07/2020 |  | Scheduled
CAPX2019121810393253 | TO-20-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | CORDUFF 110 | CORDUFF 110 | 110B2 | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover | BB0001 | 24/02/2020 | 10/03/2020 |  | Scheduled
CAPX2019100410000311 | TO-20-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | CORDUFF 110 | CORDUFF 110 | 110B2 | Install DB bases on H2 | CP1025 | 24/02/2020 | 10/03/2020 |  | Scheduled
CAPX2020103012130603 | TO-20-110 kV B3 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | CORDUFF 110 | CORDUFF 110 | 110B3 | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay | CP1009_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100410000303 | TO-20-110 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | CORDUFF 110 | CORDUFF 110 | 110B3 | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11 | CP1025 | 02/06/2020 | 12/06/2020 |  | Scheduled
CAPX2019121810393255 | TO-20-110 kV B3 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | CORDUFF 110 | CORDUFF 110 | 110B3 | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2019100410000305 | TO-20-110 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | CORDUFF 110 | CORDUFF 110 | 110B3 | 110 kV A3/B3 IN TURN @ CDU: Test interlocking | CP1025 | 18/11/2020 | 20/11/2020 |  | Scheduled
CAPX2019121810393257 | TO-20-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | CORDUFF 110 | CORDUFF 110 | 110B4 | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover | BB0001 | 27/02/2020 | 27/02/2020 |  | Tentative
CAPX2020102810300013 | TO-20-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | CORDUFF 110 | CORDUFF 110 | 110K1-2 | Test interlocking | CP1025 | 18/11/2020 | 20/11/2020 |  | Scheduled
CAPX2019101009093206 | TO-20-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | CORDUFF 110 | CORDUFF 110 | 110K1-3 | Test interlocking | CP1025 | 18/11/2020 | 20/11/2020 |  | Scheduled
OD1334 | TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | CORDUFF 110 | CORDUFF 110 | 110SA2-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0710 | TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | CORDUFF 110 | CORDUFF 110 | 110SA2-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11010 | TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | CORDUFF 110 | CORDUFF 110 | 110SA2-4 | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0356 | TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | CORDUFF 110 | CORDUFF 110 | 110SA2-4 | Misc- earthing required | 901087518 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG11012 | TO-20-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | CORDUFF 110 | CORDUFF 110 | 110SA2-4 | 220kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465512 | TO-20-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | CORDUFF 220 | CORDUFF 220 | 220A1 | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465514 | TO-20-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | CORDUFF 220 | CORDUFF 220 | 220A2 | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010916102000 | TO-20-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | CORDUFF 220 | CORDUFF 220 | 220A3 | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3 | PR0005 | 13/10/2020 | 13/10/2020 |  | Scheduled
CAPX2020010910465513 | TO-20-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | CORDUFF 220 | CORDUFF 220 | 220B1 | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465515 | TO-20-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | CORDUFF 220 | CORDUFF 220 | 220B2 | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010916102001 | TO-20-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | CORDUFF 220 | CORDUFF 220 | 220B3 | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3 | PR0005 | 13/10/2020 | 13/10/2020 |  | Scheduled
TOP200818180156 | TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | CORDUFF 220 | CORDUFF 220 | 220K1-2 | Proximity outage of Corduff 220 kV A1/B1 IN TURN required for this outage |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0380 | TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | CORDUFF 220 | CORDUFF 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0079 | TO-20-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | CORDUFF 220 | CORDUFF 220 | 220K1-2 | O/1 FIT EARTHING STIRRUPS TO CUBICLE | 900909533 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG10578 | TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | CORDUFF 220 | CORDUFF 220 | 220K1-3 | 220kV Sect / Dist Operational Test | 901076476 | 13/10/2020 | 13/10/2020 | 4 | Scheduled
19EG10579 | TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | CORDUFF 220 | CORDUFF 220 | 220K1-3 | 220kV Sect / Dist Operational Test | 901076475 | 13/10/2020 | 13/10/2020 | 4 | Scheduled
20CM0080 | TO-20-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | CORDUFF 220 | CORDUFF 220 | 220K1-3 | o/1 FIT EARTHING STIRRUPS TO CUBICLE | 900909532 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17CM3771 | TO-20-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | CORDUFF 220 | CORDUFF 220 | 220K1-3 | Repair PI fault on DA3 | 900889827 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG10580 | TO-20-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | CORDUFF 220 | CORDUFF 220 | 220K1-3 | 220kV SF6 Cubicle Operational Test | 901076486 | 13/10/2020 | 13/10/2020 | 4 | Scheduled
OD0269 | TO-20-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | CORDUFF 220 | FINGLAS 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020008 | TO-20-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | CORDUFF 220 | FINGLAS 220 | 1 | P1 Protection maintenance of 7SA513, REL551 |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG10409 | TO-20-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | CORDUFF 220 | FINGLAS 220 | 1 | 220kV SF6 Cubicle Operational Test | 901038698 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10408 | TO-20-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | CORDUFF 220 | FINGLAS 220 | 1 | 220kV SF6 Cubicle Operational Test | 901039067 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465517 | TO-20-CDU-FIN-1-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | CORDUFF 220 | FINGLAS 220 | 1 | 220 kV A3/B3 @ CDU: Proximity outage for work on Corduff 220kV K1-3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200826173921 | TO-20-CDU-FIN-2-07 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | Switching to start from 18:00 11 Sept |  | 11/09/2020 | 13/09/2020 |  | Scheduled
OD0270 | TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | Total Maintenance Outage Duration Requested |  | 10/06/2020 | 10/08/2020 |  | Scheduled
CAPX2020083115412209 | TO-20-CDU-FIN-2-08 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | Proximity outage required to remove scaffolding at the new Belcamp bay. | CP0437 | 21/09/2020 | 22/09/2020 |  | Scheduled
CAPX2020072010415108 | TO-20-CDU-FIN-2-07 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay | CP0437 | 11/09/2020 | 13/09/2020 |  | Scheduled
18EG10411 | TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | 220kV SF6 Cubicle Operational Test | 901031837 | 10/06/2020 | 10/08/2020 | 3 | Scheduled
19EG00796 | TO-20-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | 220kV SF6 Cubicle Ordinary Service | 901042328 | 10/06/2020 | 10/08/2020 | 4 | Scheduled
CAPX2019112611152906 | TO-20-CDU-FIN-2-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | CORDUFF 220 | FINGLAS 220 | 2 | EI: Energise Belcamp-Finglas cable, Belcamp-T2103 and Belcamp 110 kV station | CP0437 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0271 | TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | CORDUFF 220 | HUNTSTOWN 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20125 | TO-20-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | CORDUFF 220 | HUNTSTOWN 220 | 1 | Cable Insp. 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0112 | TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | CORDUFF 110 | MACETOWN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10175 | TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | CORDUFF 110 | MACETOWN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129598 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0219 | TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | CORDUFF 110 | MACETOWN 110 | 1 | CORDUFF SCADA SWITCH FAULTY | 901072034 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00343 | TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | CORDUFF 110 | MACETOWN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20024 | TO-20-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | CORDUFF 110 | MACETOWN 110 | 1 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0113 | TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | CORDUFF 110 | MULLINGAR 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 08/07/2020 |  | Scheduled
18LN0412 | TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | CORDUFF 110 | MULLINGAR 110 | 1 | 2017CP-1[285]Off Plumb pole | 900902317 | 06/07/2020 | 08/07/2020 | 3 | Scheduled
20EG20025 | TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | CORDUFF 110 | MULLINGAR 110 | 1 | Cable Insp. 110kV XLPE |  | 06/07/2020 | 08/07/2020 | 4 | Scheduled
CAPX2020010910331731 | TO-20-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | CORDUFF 110 | MULLINGAR 110 | 1 | 110 kV A2 @ MUL: Proximity outage for work on CAP2 | PR0001 | 06/07/2020 | 09/07/2020 |  | Scheduled
20LN2272 | TO-20-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | CORDUFF 110 | MULLINGAR 110 | 1 | 2019HP-1[48]Arching Horns check | 901084099 | 06/07/2020 | 08/07/2020 | 2 | Scheduled
OD0114 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/09/2020 | 28/09/2020 |  | Scheduled
19LN3680 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | 2018HP-1[39]Check Struct/Found/etc-Base | 900985861 | 25/09/2020 | 28/09/2020 | 4 | Scheduled
19LN3679 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | 2018HP-1[41]Check Struct/Found/etc-Base | 900985862 | 25/09/2020 | 28/09/2020 | 4 | Scheduled
20EG10179 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/09/2020 | 28/09/2020 | 4 | Scheduled
20CM0078 | TO-20-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | O/1 Change R Phase surge counter | 900891899 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN3677 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | 2018HP-1[50]Check Struct/Found/etc-Base | 900985864 | 25/09/2020 | 28/09/2020 | 4 | Scheduled
19LN3678 | TO-20-CDU-PLA-1-03 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | CORDUFF 110 | PLATIN 110 | 1 | 2018HP-1[46]Check Struct/Found/etc-Base | 900985863 | 25/09/2020 | 28/09/2020 | 4 | Scheduled
CAPX2020101511561306 | TO-20-CDU-RYB GIS-1-01 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | CORDUFF 110 | RYEBROOK GIS 110 | 1 | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133 | CP1056 | 26/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020101511561310 | TO-20-CDU-RYB GIS-1-01 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | CORDUFF 110 | RYEBROOK GIS 110 | 1 | EI: Energise T133 | CP1056 | 26/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020032817553000 | TO-20-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | CORDUFF 110 | RYEBROOK GIS 110 | 1 | EI: Replacement of tower 29 on Corduff Ryebrook OHL. | CP0668 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201013145842 | TO-20-CDU-SNU-1-03 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | CORDUFF 110 | SNUGBOROUGH 110 | 1 | De-gas 110kV Cubicles for repair |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100309273705 | TO-20-CDU-SNU-1-02 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | CORDUFF 110 | SNUGBOROUGH 110 | 1 | EI: Energise T103 | CP1014 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100309273704 | TO-20-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | CORDUFF 110 | SNUGBOROUGH 110 | 1 | EI: Energise T101 and Coupler K1 | CP1014 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020083114080011 | TO-20-CDU-T2101-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | Outage on T2101 F3/H5 to facilitate excavation works for project CP1025 required under transformer flyover | CP1025 | 29/07/2020 | 05/08/2020 |  | Scheduled
OD0749 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0359 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | Misc- Silica gel needs replacing | 901090021 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG01826 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | 220kV SF6 Cubicle Ordinary Service | 901042339 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19CM0109 | TO-20-CDU-T2101-03 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | Corduff T2101 Transformer: Drycol Replacment | 901039324 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0084 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | Repair faulty gas connections | 900776813 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01825 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01827 | TO-20-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | CORDUFF 220 | CORDUFF 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service | 901042113 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0750 | TO-20-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | CORDUFF 220 | CORDUFF 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01834 | TO-20-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | CORDUFF 220 | CORDUFF 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19CM0108 | TO-20-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | CORDUFF 220 | CORDUFF 110 | T2102 | Corduff T2102 Transformer: Drycol Replacment | 901039325 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01832 | TO-20-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | CORDUFF 220 | CORDUFF 110 | T2102 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01833 | TO-20-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | CORDUFF 220 | CORDUFF 110 | T2102 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200728164548 | TO-20-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | SF6 leak repairs |  | 19/08/2020 | 25/08/2020 |  | Scheduled
CAPX2020022812180700 | TO-20-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | Uprate bay conductor on Corduff - Woodland circuit | MC0333 | 19/08/2020 | 25/08/2020 |  | Scheduled
OD0273 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200124163802 | TO-20-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | P2 Prot Maintenance |  | 19/08/2020 | 25/08/2020 |  | Scheduled
17LN0684 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 2016CP-1[33]Replace Member Stub-bars | 900816871 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0328 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | Inspect and test all the cylinders, pist | 900532138 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0329 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | SF6 Cublicle Ordinary Serice DA, DB and | 901038603 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17LN1948 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 2016HP-1[1-11]Check Structure -Painting | 900819486 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0327 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | O. ESBI Inspect and test all the cylind | 900444597 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG00807 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 901042329 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17LN0675 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 2016CP-1[18]Replace Member Raker | 900816866 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG10415 | TO-20-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 220kV SF6 Cubicle Operational Test | 901039068 | 19/08/2020 | 25/08/2020 | 4 | Scheduled
19EG00809 | TO-20-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 220kV Cubicle Condition Assessment | 901129132 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23805 | TO-20-CDU-WOO-1-04 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | 0/1 Invetigate and Repair SF6 leak | 901125085 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
TOP200513171931 | TO-20-110 kV A1 @ COR-01 | BUSBAR SECTION - CORRACLASSY 110-CORRACLASSY 110-110A1 | CORRACLASSY 110 | CORRACLASSY 110 | 110A1 | Busbar outage for cubicle assessment on COR-ENS PST |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0116 | TO-20-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | CORRACLASSY 110 | ENNISKILLEN 110 | PST | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00365 | TO-20-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | CORRACLASSY 110 | ENNISKILLEN 110 | PST | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00364 | TO-20-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | CORRACLASSY 110 | ENNISKILLEN 110 | PST | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0117 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 30/09/2020 | 02/10/2020 |  | Scheduled
20EG00369 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20EG00368 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20EG00367 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 110kV Sect / Dist Ordinary Service |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20EG00366 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20LN2405 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 2019HP-1[69]Earths-Replace L/pole e/w | 901084872 | 30/09/2020 | 02/10/2020 | 4 | Scheduled
CAPX2020010910460143 | TO-20-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | CORRACLASSY 110 | GORTAWEE 110 | 1 | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/09/2020 | 02/10/2020 |  | Scheduled
OD1335 | TO-20-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | COW CROSS 110 | COW CROSS 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04033 | TO-20-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | COW CROSS 110 | COW CROSS 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020017 | TO-20-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | COW CROSS 110 | OLDCOURT 110 | 2 | P1 Protection maintenance of 7SA612 |  | 25/02/2020 | 25/02/2020 | 1 | Reference
PROT2020083 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 27/07/2020 | 04/08/2020 | 3 | Scheduled
OD0120 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 04/08/2020 |  | Scheduled
20CM0090 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | O1-Top up with oil pole of CB as glass w | 901068560 | 27/07/2020 | 04/08/2020 | 1 | Scheduled
20CM0089 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | O1-Maintenance reqd on Raffeen 110 KV su | 900934544 | 27/07/2020 | 04/08/2020 | 1 | Scheduled
20CM0424 | TO-20-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | Replacement of Stolen Earths | 901065864 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG06063 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | HV Pressure Vessel Inspection |  | 27/07/2020 | 04/08/2020 | 4 | Scheduled
20EG00375 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | 110kV MO Cubicle Ordinary Service | 901129844 | 27/07/2020 | 04/08/2020 | 4 | Scheduled
20EG20027 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | Cable Insp. 110kV XLPE | 901129143 | 27/07/2020 | 04/08/2020 | 4 | Scheduled
20LN2413 | TO-20-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | COW CROSS 110 | RAFFEEN 110 | 1 | 2019HP-2[13,14]Insul&HW Replac check | 901085552 | 27/07/2020 | 04/08/2020 | 2 | Scheduled
OD0121 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG10194 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
20EG10193 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 110kV MO Cubicle Operational Test |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
20CM0321 | TO-20-COW-WHI-1-02 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | O1- Disconnects heavily corroded. | 901059047 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN3761 | TO-20-COW-WHI-1-02 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | "2018HP-2[50,73]Off PlumbPlumb poles" | 900985959 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN2429 | TO-20-COW-WHI-1-02 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 2019HP-2[71,72]Off Plumb -plumb poles | 901084968 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN2437 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 2019HP-1[36]Arching Horns -Replace | 901084142 | 16/11/2020 | 20/11/2020 | 2 | Scheduled
20LN2436 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 2019HP-1[38]Arching Horns -Replace | 901084141 | 16/11/2020 | 20/11/2020 | 2 | Scheduled
20LN2435 | TO-20-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | COW CROSS 110 | WHITEGATE 110 | 1 | 2019HP-1[40]Arching Horns -Replace | 901084140 | 16/11/2020 | 20/11/2020 | 2 | Scheduled
TOP200713120910 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | Final confirmaton on 25th of July regarding land access |  | 27/07/2020 | 29/07/2020 |  | Scheduled
OD0122 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 29/07/2020 |  | Scheduled
17LN1975 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2016HP-1[14]Off Plumb Straighten P-set | 900819497 | 27/07/2020 | 29/07/2020 | 3 | Scheduled
20EG11215 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129686 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
19LN3765 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2018HP-1[25]Off Plumb | 900985979 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
20EG11214 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129595 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
19LN3766 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2018HP-1[26]Off Plumb | 900985980 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
19LN3768 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2018HP-1[14]Off Plumb | 900985977 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
20CM0414 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | Inspect Pfisterer CSE and record serial number | 901132793 | 27/07/2020 | 29/07/2020 | 2 | Scheduled
14LN1216 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 1[14]Off Plumb | 900563038 | 27/07/2020 | 29/07/2020 | 3 | Scheduled
18LN2709 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2017HP-1[14]Off Plumb -Poles | 900898042 | 27/07/2020 | 29/07/2020 | 3 | Scheduled
20LN2446 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 2019HP-1[14]Off Plumb -plumb poles | 901090924 | 27/07/2020 | 29/07/2020 | 2 | Scheduled
CAPX2020010910351117 | TO-20-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20664 | TO-20-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | CRANE 110 | LODGEWOOD 110 | 1 | Cable Insp. 110kV XLPE | 901113582 | 27/07/2020 | 29/07/2020 | 4 | Scheduled
OD0123 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/06/2020 | 24/06/2020 |  | Scheduled
18LN0641 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 2017CP-1[106]Off Plumb -Poles | 900902506 | 17/06/2020 | 24/06/2020 | 2 | Scheduled
20EG00384 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 17/06/2020 | 24/06/2020 | 4 | Scheduled
20EG00386 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 17/06/2020 | 24/06/2020 | 4 | Scheduled
18LN0630 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 2017CP-3[13, 24, 25]Off Plumb -Poles | 900902495 | 17/06/2020 | 24/06/2020 | 2 | Scheduled
18LN0608 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 2017CP-1[38]Shear Block - Repair | 900902473 | 17/06/2020 | 24/06/2020 | 2 | Scheduled
18LN0609 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 2017CP-1[38]Replace Member -Bar 225 | 900902474 | 17/06/2020 | 24/06/2020 | 2 | Scheduled
18LN0586 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 2017CP-1[106]Off Plumb Insulator | 900902451 | 17/06/2020 | 24/06/2020 | 2 | Scheduled
20EG10195 | TO-20-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129685 | 17/06/2020 | 24/06/2020 | 4 | Scheduled
CAPX2019100208021800 | TO-20-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100207582400 | TO-20-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | CRANE 110 | WEXFORD 110 | 1 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200114095450 | TO-20-CRY-LWD-1-01 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | CRORY 110 | LODGEWOOD 110 | 1 | P3 Protection maintenance of 7SA611, 7SJ804 |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
20EG23795 | TO-20-CRY-LWD-1-01 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | CRORY 110 | LODGEWOOD 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Reference (Unscheduled)
CAPX2020010910351118 | TO-20-CRY-LWD-1-01 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | CRORY 110 | LODGEWOOD 110 | 1 | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351119 | TO-20-CRY-T121-01 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | CRORY 110 | CRORY 20 | T121 | As a consequence of CRY-LWD-1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910465518 | TO-20-110 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | CULLENAGH 110 | CULLENAGH 110 | 110A1 | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932128 | TO-20-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | CULLENAGH 110 | CULLENAGH 110 | 110A1 | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465520 | TO-20-110 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | CULLENAGH 110 | CULLENAGH 110 | 110A2 | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932130 | TO-20-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | CULLENAGH 110 | CULLENAGH 110 | 110A2 | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465519 | TO-20-110 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | CULLENAGH 110 | CULLENAGH 110 | 110B1 | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932129 | TO-20-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | CULLENAGH 110 | CULLENAGH 110 | 110B1 | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932131 | TO-20-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | CULLENAGH 110 | CULLENAGH 110 | 110B2 | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465521 | TO-20-110 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | CULLENAGH 110 | CULLENAGH 110 | 110B2 | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020166 | TO-20-CUL-110K1-2-03 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | P3 Protection maintenance of 7SJ511 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0382 | TO-20-CUL-110K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191118143933 | TO-20-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01065 | TO-20-CUL-110K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01064 | TO-20-CUL-110K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01063 | TO-20-CUL-110K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | CULLENAGH 110 | CULLENAGH 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465522 | TO-20-220 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | CULLENAGH 220 | CULLENAGH 220 | 220A1 | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932132 | TO-20-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | CULLENAGH 220 | CULLENAGH 220 | 220A1 | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465524 | TO-20-220 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | CULLENAGH 220 | CULLENAGH 220 | 220A2 | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932134 | TO-20-220 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | CULLENAGH 220 | CULLENAGH 220 | 220A2 | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465523 | TO-20-220 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | CULLENAGH 220 | CULLENAGH 220 | 220B1 | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932133 | TO-20-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | CULLENAGH 220 | CULLENAGH 220 | 220B1 | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465525 | TO-20-220 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | CULLENAGH 220 | CULLENAGH 220 | 220B2 | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932135 | TO-20-220 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | CULLENAGH 220 | CULLENAGH 220 | 220B2 | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020056 | TO-20-CUL-220K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | P2 Protection maintenance of 7SJ511 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD0383 | TO-20-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01068 | TO-20-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01069 | TO-20-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01067 | TO-20-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01070 | TO-20-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | CULLENAGH 220 | CULLENAGH 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0125 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 31/08/2020 | 02/09/2020 |  | Scheduled
20EG10198 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | 110kV MO Cubicle Operational Test |  | 31/08/2020 | 02/09/2020 | 4 | Scheduled
20EG10197 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 31/08/2020 | 02/09/2020 | 4 | Scheduled
19LN3780 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | "2018HP-4[6,25,26,77]Off Plumb-Poles" | 900985985 | 31/08/2020 | 02/09/2020 | 4 | Scheduled
20LN2460 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | 2019HP-2[5,6]Off Plumb -plumb poles | 901084969 | 31/08/2020 | 02/09/2020 | 2 | Scheduled
20EG20028 | TO-20-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | CULLENAGH 110 | DUNGARVAN 110 | 1 | Cable Insp. 110kV XLPE |  | 31/08/2020 | 02/09/2020 | 4 | Scheduled
OD1256 | TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 31/07/2020 |  | Proposed
PROT2020116 | TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | P3 Protection maintenance of 7SA513, REL521 |  | 27/07/2020 | 31/07/2020 | 3 | Proposed
18EG00812 | TO-20-CUL-GI GIS-1-06 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | 220kV Cubicle Condition Assessment | 900943872 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG10418 | TO-20-CUL-GI GIS-1-06 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | 220kV MO Cubicle Operational Test | 900840902 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG00810 | TO-20-CUL-GI GIS-1-06 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 900943447 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17LN3489 | TO-20-CUL-GI GIS-1-06 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Line Towers 35 - Replace angle insulator | 900855588 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17LN3488 | TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Line Towers 35 & 36 (Angle & Intermediate) - Replace intermediate insulators and measurement of existing strain insulator chain length | 900855589 | 27/07/2020 | 31/07/2020 | 2 | Proposed
17EG20227 | TO-20-CUL-GI GIS-1-06 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Cable Insp. 110kV XLPE | 901006385 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100809402301 | TO-20-CUL-GI GIS-1-02 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN2474 | TO-20-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | 2019HP-3[27,28,29]Clean Insulators | 901086391 | 27/07/2020 | 31/07/2020 | 2 | Proposed
CAPX2019100809402305 | TO-20-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | CULLENAGH 220 | GREAT ISLAND GIS 220 | 1 | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0275 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2020021410064804 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 30/04/2020 |  | Scheduled
20CM0182 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Ordinary service required on DB followin | 901081935 | 24/02/2020 | 30/04/2020 | 2 | Scheduled
CAPX2019101410530308 | TO-20-CUL-KRA-1-02 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409163503 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2019100212153005 | TO-20-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331726 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Proximity outage for work on Knockraha-Raffeen 220 kV | PR0001 | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2019101409072004 | TO-20-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | CULLENAGH 220 | KNOCKRAHA 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 30/04/2020 |  | Scheduled
TOP200117144842 | TO-20-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | P1 Protection maintenance of 7SA511, 7SA511, 7UT512 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0751 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0091 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | Replace main cover gasket | 900706946 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01839 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01840 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01841 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 220/110 & 275/220 - Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01842 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01843 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0092 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | Power Diagnostix are to carry out PD mea | 900794262 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01845 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 220/110kV Trafo Tap Changer Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0093 | TO-20-CUL-T2101-04 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | Refurbish main cover using Megalift devi | 900908056 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
18CM0009 | TO-20-CUL-T2101-04 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | Repair oil leak on tertiary bushings | 900807712 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG01844 | TO-20-CUL-T2101-02 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | CULLENAGH 220 | CULLENAGH 110 | T2101 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0126 | TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | CULLENAGH 110 | WATERFORD 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/11/2020 | 03/11/2020 |  | Scheduled
20EG10200 | TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | CULLENAGH 110 | WATERFORD 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 02/11/2020 | 03/11/2020 | 4 | Scheduled
20EG20029 | TO-20-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | CULLENAGH 110 | WATERFORD 110 | 1 | Cable Insp. 110kV XLPE |  | 02/11/2020 | 03/11/2020 | 4 | Scheduled
CAPX2020010910460121 | TO-20-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | CUNGHILL 110 | CUNGHILL 110 | 110SA1 | As a consequence of CUN-110SA2: 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1336 | TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | CUNGHILL 110 | CUNGHILL 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04037 | TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | CUNGHILL 110 | CUNGHILL 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039702 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460122 | TO-20-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | CUNGHILL 110 | CUNGHILL 110 | 110SA2 | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0127 | TO-20-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | CUNGHILL 110 | GLENREE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG11230 | TO-20-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | CUNGHILL 110 | GLENREE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901068536 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00395 | TO-20-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | CUNGHILL 110 | GLENREE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042223 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109103317102 | TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | CUNGHILL 110 | GLENREE 110 | 1 | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460123 | TO-20-CUN-GLR-1-02 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | CUNGHILL 110 | GLENREE 110 | 1 | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0128 | TO-20-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | CUNGHILL 110 | SLIGO 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00399 | TO-20-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | CUNGHILL 110 | SLIGO 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042227 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10204 | TO-20-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | CUNGHILL 110 | SLIGO 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038824 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020022 | TO-20-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | CUNGHILL 110 | CUNGHILL 20 | T121 | P1 Protection maintenance of 7SA513 |  | 16/06/2020 | 17/06/2020 | 1 | Scheduled
OD0384 | TO-20-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | CUSHALING 110 | CUSHALING 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020057 | TO-20-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | CUSHALING 110 | CUSHALING 110 | 110SA1-2CB | P2 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG11401 | TO-20-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | CUSHALING 110 | CUSHALING 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10587 | TO-20-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | CUSHALING 110 | CUSHALING 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901038992 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG11400 | TO-20-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | CUSHALING 110 | CUSHALING 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0837 | TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | CUSHALING 110 | MOUNTLUCAS 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/06/2020 | 10/06/2020 |  | Scheduled
20EG11367 | TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | CUSHALING 110 | MOUNTLUCAS 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 09/06/2020 | 10/06/2020 | 4 | Scheduled
20EG11366 | TO-20-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | CUSHALING 110 | MOUNTLUCAS 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 09/06/2020 | 10/06/2020 | 4 | Scheduled
TOP200624151726 | TO-20-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | CUSHALING 110 | NEWBRIDGE 110 | 1 | Timber Cutting |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0129 | TO-20-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | CUSHALING 110 | NEWBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10205 | TO-20-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | CUSHALING 110 | NEWBRIDGE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460189 | TO-20-CUS-NEW-1-02 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | CUSHALING 110 | NEWBRIDGE 110 | 1 | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0130 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/06/2020 | 01/07/2020 |  | Scheduled
18LN0809 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[71]Off Plumb Poles | 900876727 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0792 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[28]Found/Site repair Fill base | 900876709 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0839 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-2[102,103]Off Plumb Poles | 900876757 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1002 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[181]Stepbolts Missing-Fit | 900876943 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0988 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[103]Pole Bolt Loose-Tighten | 900876929 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0812 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[73]Replace Member -Bent | 900876730 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1154 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017HP-2[200]Check Structure Top Rot | 900898064 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0997 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[110]Stepbolts Missing-Fit | 900876938 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0998 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[111]Stepbolts Missing-Fit | 900876939 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0999 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[130]Stepbolts Missing-Fit | 900876940 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN2771 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017HP-2[92]Check Structure Top Rot | 900898062 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1001 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[167]Stepbolts Missing-Fit | 900876942 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0985 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[4]Pole Bolt Loose-Tighten | 900876926 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1005 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[4]Earths Repair attach. point | 900876947 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1006 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[7]Off Plumb -Earth attach point | 900876948 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1007 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[4]Earths Repair earth straps | 900876949 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1008 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[6]Earths Reclip oxlip | 900876950 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN1009 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[7]Earths Reclip oxlip | 900876951 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
20EG00405 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 12/06/2020 | 01/07/2020 | 4 | Scheduled
20EG00403 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 12/06/2020 | 01/07/2020 | 4 | Scheduled
18LN1000 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[147]Stepbolts Missing-Fit | 900876941 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0872 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[134]Off Plumb Poles | 900876791 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0810 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[71]Found/Site repair Fill base | 900876728 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0811 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[73]Shear Block Repair all | 900876729 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0823 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[89]Found/Site repair Sleepers | 900876741 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0841 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[103]Off Plumb Insulator | 900876759 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0842 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[104]Replace/Retire pole butts | 900876760 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0996 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[105]Stepbolts Missing-Fit | 900876937 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0843 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[105]Shear Block Repair all | 900876761 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0951 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[204]Shear Block Clear base | 900876891 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0885 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[147]Shear Block Repair | 900876804 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0890 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[150]Replace/Retire pole butts | 900876809 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0914 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[167]Shear Block Repair all | 900876833 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0925 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[181]Shear Block Clear base | 900876864 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0929 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[185]Off Plumb Pole & Insulator | 900876869 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0931 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[185]Found/Site repair Fill base | 900876871 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0937 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[190]Off Plumb Pole & Insulator | 900876877 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
18LN0941 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2017CP-1[194]Found/Site repair Fill base | 900876881 | 12/06/2020 | 01/07/2020 | 3 | Scheduled
20LN2600 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2019HP-1[200]Replace Pole only -Rot | 900898064 | 12/06/2020 | 01/07/2020 | 1 | Scheduled
20LN2599 | TO-20-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | CUSHALING 110 | PORTLAOISE 110 | 1 | 2019HP-1[199]Insul&HW Replac check | 901085553 | 12/06/2020 | 01/07/2020 | 4 | Scheduled
OD0646 | TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | CUSHALING 110 | CUSHALING G1 | T101 | Total Maintenance Outage Duration Requested |  | 07/07/2020 | 07/07/2020 |  | Scheduled
20EG10951 | TO-20-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | CUSHALING 110 | CUSHALING G1 | T101 | 110kV SF6 Cubicle Operational Test |  | 07/07/2020 | 07/07/2020 | 4 | Scheduled
OD0647 | TO-20-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | CUSHALING 110 | CUSHALING G3/5 | T103/5 | Total Maintenance Outage Duration Requested |  | 19/11/2020 | 19/11/2020 |  | Scheduled
19EG10952 | TO-20-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | CUSHALING 110 | CUSHALING G3/5 | T103/5 | 110kV SF6 Cubicle Operational Test |  | 19/11/2020 | 19/11/2020 | 4 | Scheduled
CAPX2020102816182609 | TO-20-DAL-T141-09 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121 | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020081409432500 | TO-20-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage | CP1057 | 10/08/2020 | 14/08/2020 |  | Reference
CAPX2020081409432516 | TO-20-DAL-T141-05 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage | CP1057 | 05/10/2020 | 06/10/2020 |  | Reference
CAPX2020081409432520 | TO-20-DAL-T141-06 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020081409432508 | TO-20-DAL-T141-03 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage | CP1057 | 15/09/2020 | 21/09/2020 |  | Reference
CAPX2020081409432504 | TO-20-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020081409432512 | TO-20-DAL-T141-04 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge | CP1057 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020102816182614 | TO-20-DAL-T141-09 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020102816182604 | TO-20-DAL-T141-09 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121 | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020110214131728 | TO-20-DAL-T141-11 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | DALLOW 110 | DALLOW 38 | T141 | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage | CP1057 | 16/11/2020 | 30/11/2020 |  | Reference
CAPX2020081409432513 | TO-20-DAL,T-DAL-1-04 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432517 | TO-20-DAL,T-DAL-1-05 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage | CP1057 | 05/10/2020 | 06/10/2020 |  | Scheduled
CAPX2020081409432521 | TO-20-DAL,T-DAL-1-06 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102816182605 | TO-20-DAL,T-DAL-1-09 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121 | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102816182615 | TO-20-DAL,T-DAL-1-09 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432509 | TO-20-DAL,T-DAL-1-03 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage | CP1057 | 15/09/2020 | 21/09/2020 |  | Scheduled
CAPX2020102816182610 | TO-20-DAL,T-DAL-1-09 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121 | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020110214131729 | TO-20-DAL,T-DAL-1-11 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage | CP1057 | 16/11/2020 | 30/11/2020 |  | Scheduled
CAPX2020081409432505 | TO-20-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432501 | TO-20-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | DALLOW tee | DALLOW 110 | 1 | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage | CP1057 | 10/08/2020 | 14/08/2020 |  | Scheduled
CAPX2020081409432510 | TO-20-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage | CP1057 | 15/09/2020 | 21/09/2020 |  | Scheduled
CAPX2020081409432518 | TO-20-DAL,T-PLS-1-05 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage | CP1057 | 05/10/2020 | 06/10/2020 |  | Scheduled
CAPX2020081409432506 | TO-20-DAL,T-PLS-1-02 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432514 | TO-20-DAL,T-PLS-1-04 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge | CP1057 | 22/09/2020 | 05/10/2020 |  | Scheduled
CAPX2020081409432522 | TO-20-DAL,T-PLS-1-06 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020110214131730 | TO-20-DAL,T-PLS-1-13 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage | CP1057 | 16/11/2020 | 30/11/2020 |  | Scheduled
OD0132 | TO-20-DAL,T-PLS-1-08 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432502 | TO-20-DAL,T-PLS-1-03 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage | CP1057 | 10/08/2020 | 14/08/2020 |  | Scheduled
20EG00407 | TO-20-DAL,T-PLS-1-08 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0268 | TO-20-DAL,T-PLS-1-08 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | Moisture in LAs | 900965558 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0269 | TO-20-DAL,T-PLS-1-08 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | DALLOW tee | PORTLAOISE 110 | 1 | H6 , loose stripped cores in mech box , | 901072096 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020102816182617 | TO-20-DAL,T-SH-1-11 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise | CP1057_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102214323103 | TO-20-DAL,T-SH-1-08 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432507 | TO-20-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise | CP1057 | 17/08/2020 | 14/09/2020 |  | Scheduled
CAPX2020081409432519 | TO-20-DAL,T-SH-1-05 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage | CP1057 | 05/10/2020 | 06/10/2020 |  | Scheduled
CAPX2020081409432515 | TO-20-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0133 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 07/10/2020 | 27/11/2020 |  | Scheduled
CAPX2020110214131731 | TO-20-DAL,T-SH-1-12 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage | CP1057 | 16/11/2020 | 30/11/2020 |  | Scheduled
CAPX2020081409432523 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise | CP1057 | 07/10/2020 | 27/11/2020 |  | Scheduled
CAPX2020081409432511 | TO-20-DAL,T-SH-1-04 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage | CP1057 | 15/09/2020 | 21/09/2020 |  | Scheduled
CAPX2020081409432503 | TO-20-DAL,T-SH-1-02 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage | CP1057 | 10/08/2020 | 14/08/2020 |  | Scheduled
20EG00409 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 07/10/2020 | 27/11/2020 | 4 | Scheduled
20EG00410 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 07/10/2020 | 27/11/2020 | 4 | Scheduled
20CM0456 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | T Phase DA Disconnect DUE: 17-Jul-20 | 901133675 | 07/10/2020 | 27/11/2020 | 1 | Scheduled
20LN5082 | TO-20-DAL,T-SH-1-06 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | DALLOW tee | SHANNONBRIDGE 110 | 1 | 2019HP-1[252]Bird Nests -Remove | 901084339 | 07/10/2020 | 27/11/2020 | 4 | Scheduled
PROT2020134 | TO-20-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | DALTON 110 | DALTON 110 | CAP1 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20CM0094 | TO-20-DLT-CAP1-02 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | DALTON 110 | DALTON 110 | CAP1 | Hot Spots Hot spot detected please refer | 900945902 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020101513062223 | TO-20-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | DARNDALE 110 | DARNDALE 110 | 110A1 | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315173416 | TO-20-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | DARNDALE 110 | DARNDALE 110 | 110A1 | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590736 | TO-20-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | DARNDALE 110 | DARNDALE 110 | 110A2 | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590729 | TO-20-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | DARNDALE 110 | DARNDALE 110 | 110A2 | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315173424 | TO-20-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | DARNDALE 110 | DARNDALE 110 | 110B1 | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315173417 | TO-20-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | DARNDALE 110 | DARNDALE 110 | 110B1 | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590737 | TO-20-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | DARNDALE 110 | DARNDALE 110 | 110B2 | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590730 | TO-20-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | DARNDALE 110 | DARNDALE 110 | 110B2 | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2019121610100618 | TO-20-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | DARNDALE 110 | DARNDALE 110 | 110B2 | 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101315173425 | TO-20-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | DARNDALE 110 | DARNDALE 110 | 110K1 | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315173418 | TO-20-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | DARNDALE 110 | DARNDALE 110 | 110K1 | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315173419 | TO-20-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | DARNDALE 110 | DARNDALE 110 | 110K1 | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315173426 | TO-20-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | DARNDALE 110 | DARNDALE 110 | 110K1 | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590731 | TO-20-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590739 | TO-20-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590738 | TO-20-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590732 | TO-20-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2019121610100620 | TO-20-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121610100619 | TO-20-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | DARNDALE 110 | DARNDALE 110 | 110K2 | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101315590727 | TO-20-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590720 | TO-20-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590733 | TO-20-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590740 | TO-20-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2019121610100622 | TO-20-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121610100621 | TO-20-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | DARNDALE 110 | DARNDALE 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101315522928 | TO-20-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | DARNDALE 110 | DARNDALE 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020101315590734 | TO-20-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | DARNDALE 110 | DARNDALE 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315590741 | TO-20-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | DARNDALE 110 | DARNDALE 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122 | CP1013 | 18/11/2020 | 19/11/2020 |  | Tentative
CAPX2020101315522921 | TO-20-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | DARNDALE 110 | DARNDALE 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123 | CP1013 | 16/11/2020 | 17/11/2020 |  | Tentative
CAPX2020102311352505 | TO-20-DND-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | DARNDALE 110 | DARNDALE 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: EI for T124 also requires outage of Belcamp 3 cubicle | CP1013_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200821174213 | TO-20-DYN-T121-03 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | DERRYBRIEN 110 | DERRYBRIEN 20 | T121 | As a consequence of AGL-DYN-110kV |  | 07/09/2020 | 12/09/2020 |  | Reference
CAPX20200109103511105 | TO-20-DYN-T121-02 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | DERRYBRIEN 110 | DERRYBRIEN 20 | T121 | As a consequence of AGL-DYN-1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100210172706 | TO-20-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | DERRYBRIEN 110 | DERRYBRIEN 20 | T121 | As a consequence of AGL-DYN-1: Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1337 | TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | DERRYIRON 110 | DERRYIRON 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 25/02/2020 |  | Scheduled
19EG04042 | TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | DERRYIRON 110 | DERRYIRON 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039703 | 24/02/2020 | 25/02/2020 | 4 | Scheduled
CAPX2020010910460124 | TO-20-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | DERRYIRON 110 | DERRYIRON 110 | 110SA1 | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 24/02/2020 | 25/02/2020 |  | Scheduled
CAPX2020010910460127 | TO-20-DER-110SA1-02 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | DERRYIRON 110 | DERRYIRON 110 | 110SA1 | As a consequence of DER-110SA2: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0897 | TO-20-DER-110SA2-02 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | DERRYIRON 110 | DERRYIRON 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
14EG04043 | TO-20-DER-110SA2-02 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | DERRYIRON 110 | DERRYIRON 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 900666902 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910460128 | TO-20-DER-110SA2-02 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | DERRYIRON 110 | DERRYIRON 110 | 110SA2 | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460125 | TO-20-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | DERRYIRON 110 | DERRYIRON 110 | 110SA2 | As a consequence of DER-110SA1: 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 24/02/2020 | 25/02/2020 |  | Scheduled
OD0136 | TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 25/02/2020 |  | Scheduled
20CM0368 | TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | Measurement of copper conductor diameter | 901087474 | 24/02/2020 | 25/02/2020 | 2 | Scheduled
20CM0096 | TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | ESBI N01 non outage (important) Misc- wo | 900623151 | 24/02/2020 | 25/02/2020 | 1 | Scheduled
20LN2646 | TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | 2019HP-1[71]Bird Nests | 901084275 | 24/02/2020 | 25/02/2020 | 4 | Scheduled
CAPX2020010910460126 | TO-20-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 24/02/2020 | 25/02/2020 |  | Scheduled
CAPX2020010910351100 | TO-20-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | DERRYIRON 110 | KINNEGAD 110 | 1 | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191014144349 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | proximity needed of Derryiron - Maynooth for maintenance on Dunstown - Maynooth 2 |  | 21/09/2020 | 16/10/2020 |  | Scheduled
OD0137 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 21/09/2020 | 16/10/2020 |  | Scheduled
19CM0052 | TO-20-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | Investigate CB gas leak & repair if possible | 901045929 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
18EG20034 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | Annual Insp. 110 Feeder OF Cable | 900944029 | 21/09/2020 | 16/10/2020 | 3 | Scheduled
20EG10216 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20CM0225 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | Missing Earths on Earths on CB | 901080694 | 21/09/2020 | 16/10/2020 | 2 | Scheduled
20LN5255 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 118 need to be replaced by the autumn 2020 before winter storms commence. | 901150825 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
20LN5254 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 117 need to be replaced by the autumn 2020 before winter storms commence. | 901150824 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
20LN5253 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 116 need to be replaced by the autumn 2020 before winter storms commence. | 901150823 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
CAPX2020010910331724 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | Proximity outage for work on Dunstown-Maynooth-2 220 kV | PR0001 | 21/09/2020 | 16/10/2020 |  | Scheduled
20LN2698 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[183]Off Plumb -plumb poles | 901084978 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
CAPX2020010910460129 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 21/09/2020 | 16/10/2020 |  | Scheduled
20LN2663 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[75]Replace Pole only -Rot | 901086429 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
20LN2697 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[182]Off Plumb -plumb poles | 901084977 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2648 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[4]Off Plumb -plumb poles | 901084970 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2652 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[28]Off Plumb -plumb poles | 901084971 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2653 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[29]Off Plumb -plumb poles | 901084972 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2673 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[106]Replace Pole only -Rot | 901086430 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
20LN2680 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[124]Replace Pole only -Rot | 901086431 | 21/09/2020 | 16/10/2020 | 1 | Scheduled
20LN2692 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[160]Off Plumb -plumb poles | 901084973 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2694 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[164]Off Plumb -plumb poles | 901084975 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2696 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[181]Off Plumb -plumb poles | 901084976 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
20LN2693 | TO-20-DER-MAY-1-01 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | DERRYIRON 110 | MAYNOOTH 110 | 1 | 2019HP-1[161]Off Plumb -plumb poles | 901084974 | 21/09/2020 | 16/10/2020 | 4 | Scheduled
OD0648 | TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | DERRYIRON 110 | RHODE 110 | T1/T2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200128135330 | TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | DERRYIRON 110 | RHODE 110 | T1/T2 | P2 Protection maintenance of 7SA513 | PROT | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10953 | TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | DERRYIRON 110 | RHODE 110 | T1/T2 | 110KV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460130 | TO-20-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | DERRYIRON 110 | RHODE 110 | T1/T2 | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200110084334 | TO-20-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | P3 Protection maintenance of REL521 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200110084326 | TO-20-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | P1 Protection maintenance of 7SA511, REL521 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1222 | TO-20-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
14EG00426 | TO-20-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 900775914 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16EG00425 | TO-20-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 900775276 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910460131 | TO-20-DER-TSB-1-02 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | DERRYIRON 110 | THORNSBERRY 110 | 1 | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0506 | TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | DROMADA 110 | DROMADA 20 | T121 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 28/08/2020 |  | Scheduled
19EG01405 | TO-20-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | DROMADA 110 | DROMADA 20 | T121 | 110KV CUBICLE CONDITION ASSESSMENT | 901038511 | 24/08/2020 | 28/08/2020 | 4 | Scheduled
PROT2020088 | TO-20-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | DRUMKEEN 110 | LETTERKENNY 110 | 1 | P3 Protection maintenance of 7SA511, REL551 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
PROT2020089 | TO-20-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | DRUMKEEN 110 | LETTERKENNY 110 | 1 | P3 Protection maintenance of 7SA511, REL551 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0140 | TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | DRUMKEEN 110 | LETTERKENNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 29/09/2020 | 29/09/2020 |  | Scheduled
19EG10220 | TO-20-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | DRUMKEEN 110 | LETTERKENNY 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 29/09/2020 | 29/09/2020 | 4 | Scheduled
CAPX2019100209481101 | TO-20-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | DRUMKEEN 110 | LETTERKENNY 110 | 1 | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020018 | TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | DRUMKEEN 110 | MEENTYCAT 110 | 1 | P1 Protection maintenance of 7SA513 |  | 14/09/2020 | 18/09/2020 | 1 | Scheduled
OD0141 | TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | DRUMKEEN 110 | MEENTYCAT 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
20EG00433 | TO-20-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | DRUMKEEN 110 | MEENTYCAT 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 18/09/2020 | 4 | Scheduled
PROT2020158 | TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | P3 Protection maintenance of 7SA511 |  | 25/05/2020 | 29/05/2020 | 3 | Scheduled
OD0142 | TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 29/05/2020 |  | Scheduled
TOP201020174107 | TO-20-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | Operator training |  | 10/11/2020 | 10/11/2020 |  | Scheduled
PROT2020019 | TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | P1 Protection maintenance of 7SA511 |  | 25/05/2020 | 29/05/2020 | 1 | Scheduled
19LN4140 | TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | 2018HP-1[18]Off PlumbPlumb poleset | 900986381 | 25/05/2020 | 29/05/2020 | 4 | Scheduled
19LN4144 | TO-20-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | DRUMLINE 110 | ENNIS 110 | 1 | 2018HP-1[75]Off PlumbPlumb poleset | 900986388 | 25/05/2020 | 29/05/2020 | 4 | Scheduled
OD1314 | TO-20-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | DRYBRIDGE 110 | DRYBRIDGE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04050 | TO-20-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | DRYBRIDGE 110 | DRYBRIDGE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460134 | TO-20-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | DRYBRIDGE 110 | DRYBRIDGE 110 | 110SA1 | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460135 | TO-20-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | DRYBRIDGE 110 | DRYBRIDGE 110 | 110SA2 | As a consequence of DRY-110SA1: 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0143 | TO-20-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | DRYBRIDGE 110 | GORMAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG00441 | TO-20-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | DRYBRIDGE 110 | GORMAN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
20EG00442 | TO-20-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | DRYBRIDGE 110 | GORMAN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
20LN2751 | TO-20-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | DRYBRIDGE 110 | GORMAN 110 | 1 | 2019HP-2[105]Vib Dampers -Replace | 901085139 | 16/11/2020 | 20/11/2020 | 4 | Scheduled
OD0144 | TO-20-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | DRYBRIDGE 110 | LOUTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 13/11/2020 |  | Scheduled
20EG00445 | TO-20-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | DRYBRIDGE 110 | LOUTH 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 09/11/2020 | 13/11/2020 | 4 | Scheduled
CAPX2020010910460136 | TO-20-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | DRYBRIDGE 110 | LOUTH 110 | 1 | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0145 | TO-20-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | DRYBRIDGE 110 | PLATIN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10231 | TO-20-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | DRYBRIDGE 110 | PLATIN 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460137 | TO-20-DRY-PLA-1-02 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | DRYBRIDGE 110 | PLATIN 110 | 1 | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460138 | TO-20-DRY-T141-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | DRYBRIDGE 110 | DRYBRIDGE 38 | T141 | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0146 | TO-20-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | DUNDALK 110 | LOUTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/08/2020 | 06/08/2020 |  | Scheduled
20CM0098 | TO-20-DDK-LOU-1-03 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | DUNDALK 110 | LOUTH 110 | 1 | N O 1 Louth H4 (Mal)Louth DL Fault | 901082258 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG10232 | TO-20-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | DUNDALK 110 | LOUTH 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 06/08/2020 | 06/08/2020 | 4 | Scheduled
20CM0371 | TO-20-DDK-LOU-1-02 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | DUNDALK 110 | LOUTH 110 | 1 | EMP AMS Replace CB Counter | 901087469 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020081315093100 | TO-20-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | DUNDALK 110 | MULLAGHARLIN 110 | 1 | 110 kV A1 @ MLN: Civil works on bay H1 and H0 | CP1101 | 13/08/2020 | 18/09/2020 |  | Scheduled
TOP200113103214 | TO-20-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | DUNFIRTH 110 | DUNFIRTH 20 | T122 | Full tee outage |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200115095848 | TO-20-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | DUNFIRTH 110 | DUNFIRTH 20 | T122 | Remake jumpers following maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200115095603 | TO-20-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | DUNFIRTH 110 | DUNFIRTH 20 | T122 | Break jumpers for maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200115095641 | TO-20-DFR,T-DFR-1-01 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | DUNFIRTH tee | DUNFIRTH 110 | 1 | Break jumpers for maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113103102 | TO-20-DFR,T-DFR-1-01 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | DUNFIRTH tee | DUNFIRTH 110 | 1 | Full tee outage |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200220113930 | TO-20-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | DUNFIRTH tee | DUNFIRTH 110 | 1 | Remake jumpers following maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200115095459 | TO-20-DFR,T-KIN-1-01 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | DUNFIRTH tee | KINNEGAD 110 | 1 | Break jumpers for maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0149 | TO-20-DFR,T-KIN-1-01 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | DUNFIRTH tee | KINNEGAD 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200115095936 | TO-20-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | DUNFIRTH tee | KINNEGAD 110 | 1 | Remake jumpers following maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00461 | TO-20-DFR,T-KIN-1-01 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | DUNFIRTH tee | KINNEGAD 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042225 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351104 | TO-20-DFR,T-KIN-1-02 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | DUNFIRTH tee | KINNEGAD 110 | 1 | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200115095731 | TO-20-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | DUNFIRTH tee | RINAWADE 110 | 1 | Remake jumpers following maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200115095713 | TO-20-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | DUNFIRTH tee | RINAWADE 110 | 1 | Break jumpers for maintenance on Dunfirth tee Rinawade |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0150 | TO-20-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | DUNFIRTH tee | RINAWADE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00463 | TO-20-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | DUNFIRTH tee | RINAWADE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601111 | TO-20-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | DUNFIRTH tee | RINAWADE 110 | 1 | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1339 | TO-20-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | DUNGARVAN 110 | DUNGARVAN 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04054 | TO-20-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | DUNGARVAN 110 | DUNGARVAN 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0151 | TO-20-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | DUNGARVAN 110 | WOODHOUSE 110 | 1 | Total Maintenance Outage Duration Requested |  | 19/11/2020 | 26/11/2020 |  | Scheduled
20EG00465 | TO-20-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | DUNGARVAN 110 | WOODHOUSE 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 19/11/2020 | 26/11/2020 | 4 | Scheduled
20EG05113 | TO-20-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | DUNGARVAN 110 | WOODHOUSE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 19/11/2020 | 26/11/2020 | 4 | Scheduled
CAPX2020102710021226 | TO-20-DMY-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020062516112802 | TO-20-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A2 @ DMY: Isolate M21BBP Cabinet | CP0930 | 13/07/2020 | 17/07/2020 |  | Scheduled
OD0857 | TO-20-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 17/07/2020 |  | Scheduled
OD1278 | TO-20-DMY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2020102710021220 | TO-20-DMY-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020072209525808 | TO-20-DMY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2020083111380714 | TO-20-DMY-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Scheduled
20EG02505 | TO-20-DMY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service |  | 04/08/2020 | 17/08/2020 | 4 | Tentative
CAPX2020010910331765 | TO-20-DMY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Tentative
20EG11397 | TO-20-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | DUNMANWAY 110 | DUNMANWAY 110 | 110SA1-2CB | 220kV SF6 Cubicle Operational Test |  | 13/07/2020 | 17/07/2020 | 4 | Scheduled
OD1273 | TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | DUNMANWAY 110 | DUNMANWAY 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 29/05/2020 |  | Scheduled
CAPX2020062516112803 | TO-20-DMY-CAP2-02 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | DUNMANWAY 110 | DUNMANWAY 110 | CAP2 | 110 kV A2 @ DMY: Isolate M21BBP Cabinet | CP0930 | 13/07/2020 | 17/07/2020 |  | Scheduled
20EG05041 | TO-20-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | DUNMANWAY 110 | DUNMANWAY 110 | CAP2 | 110kV SF6 Cubicle Ordinary Service |  | 25/05/2020 | 29/05/2020 | 4 | Scheduled
CAPX2020072209525809 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2020102710021227 | TO-20-DMY-MAC-1-10 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200529153550 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | Work on Location 124 to stop tripping |  | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2020083111380715 | TO-20-DMY-MAC-1-07 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Scheduled
CAPX2020102710021221 | TO-20-DMY-MAC-1-09 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0152 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | Total Maintenance Outage Duration Requested |  | 04/08/2020 | 17/08/2020 |  | Tentative
19EG00470 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901050325 | 04/08/2020 | 17/08/2020 | 4 | Tentative
19EG10240 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110kV MO Cubicle Operational Test | 901058948 | 04/08/2020 | 17/08/2020 | 4 | Tentative
19LN4226 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 2018HP-1[84]Off PlumbPlumb poles | 900986469 | 04/08/2020 | 17/08/2020 | 4 | Tentative
CAPX2019100210345701 | TO-20-DMY-MAC-1-01 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102112121224 | TO-20-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5249 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | Oxlip earth position movement | 901148535 | 04/08/2020 | 17/08/2020 | 1 | Tentative
CAPX2020010910331766 | TO-20-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Tentative
CAPX2019100210345713 | TO-20-DMY-MAC-1-02 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | DUNMANWAY 110 | MACROOM 110 | 1 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020072209525810 | TO-20-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | DUNMANWAY 110 | DUNMANWAY 38 | T141 | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay | CP0930 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2020102710021228 | TO-20-DMY-T141-07 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | DUNMANWAY 110 | DUNMANWAY 38 | T141 | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020102710021222 | TO-20-DMY-T141-06 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | DUNMANWAY 110 | DUNMANWAY 38 | T141 | 110 kV A1 @ DMY: Installation of busbar dropper. | CP0930 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020083111380716 | TO-20-DMY-T141-04 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | DUNMANWAY 110 | DUNMANWAY 38 | T141 | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay | CP0930 | 16/09/2020 | 25/09/2020 |  | Reference
CAPX2020010910331767 | TO-20-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | DUNMANWAY 110 | DUNMANWAY 38 | T141 | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1) | PR0001 | 04/08/2020 | 17/08/2020 |  | Reference (Tentative)
CAPX2020062516112804 | TO-20-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | DUNMANWAY 110 | DUNMANWAY 38 | T142 | 110 kV A2 @ DMY: Isolate M21BBP Cabinet | CP0930 | 13/07/2020 | 17/07/2020 |  | Reference
CAPX20191218103932136 | TO-20-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | DUNSTOWN 220 | DUNSTOWN 220 | 220A1 | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932138 | TO-20-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | DUNSTOWN 220 | DUNSTOWN 220 | 220A2 | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932137 | TO-20-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | DUNSTOWN 220 | DUNSTOWN 220 | 220B1 | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932139 | TO-20-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | DUNSTOWN 220 | DUNSTOWN 220 | 220B2 | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0385 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 10/11/2020 | 19/11/2020 |  | Scheduled
19CM0327 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | Replace stolen earths | 901080785 | 10/11/2020 | 19/11/2020 | 1 | Scheduled
20EG06008 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | HV Pressure Vessel Inspection |  | 10/11/2020 | 19/11/2020 | 4 | Scheduled
19EG10588 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039168 | 10/11/2020 | 19/11/2020 | 4 | Scheduled
19EG10589 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039169 | 10/11/2020 | 19/11/2020 | 4 | Scheduled
19EG10590 | TO-20-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | DUNSTOWN 220 | DUNSTOWN 220 | 220K1-2 | 220kV SF6 Cubicle Operational Test | 901038890 | 10/11/2020 | 19/11/2020 | 4 | Scheduled
CAPX20191218103932140 | TO-20-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | DUNSTOWN 400 | DUNSTOWN 400 | 400A1 | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932142 | TO-20-400 kV A2 @ DSN-03 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | DUNSTOWN 400 | DUNSTOWN 400 | 400A2 | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100313243702 | TO-20-400 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | DUNSTOWN 400 | DUNSTOWN 400 | 400A2 | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI). | MC0316 | 16/09/2020 | 18/09/2020 |  | Scheduled
CAPX2019100313243700 | TO-20-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | DUNSTOWN 400 | DUNSTOWN 400 | 400A2 | Civil works to dig and pour bases for post insulators on 400 kV side of T4202. | MC0316 | 04/08/2020 | 17/08/2020 |  | Scheduled
CAPX20191218103932141 | TO-20-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | DUNSTOWN 400 | DUNSTOWN 400 | 400B1 | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20191218103932143 | TO-20-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | DUNSTOWN 400 | DUNSTOWN 400 | 400B2 | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020072016272500 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202. | MC0316 | 10/08/2020 | 28/08/2020 |  | Scheduled
OD0386 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 28/08/2020 |  | Scheduled
20EG00950 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01076 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20CM0102 | TO-20-DSN-400K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | O. ESBI Inspect and test all the cylind | 900444678 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0103 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | Inspect and test all the cylinders, pist | 900531917 | 10/08/2020 | 28/08/2020 | 2 | Scheduled
20EG01075 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG00952 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG00951 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG00949 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG06052 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | HV Pressure Vessel Inspection |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01077 | TO-20-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | DUNSTOWN 400 | DUNSTOWN 400 | 400K1-2 | 400kV SF6 Cubicle Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
TOP191202091704 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | Replace stolen earths |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191107133220 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2016HP-3[157]Strain/Dup 220kV replace |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191107133108 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2017HP-1[103]Anti-Cl. Guard fit |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0276 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18LN1177 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2017HP-1[103]Anti-Cl. Guard fit | 900898068 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19LN4246 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2018HP-1[178-179]Vib Dampers-EW damper | 900986539 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0430 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | Replacement of Stolen Earths |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
16CM0093 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2[140,143] Replace bent/damaged steel member | 900719181 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN4251 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2018HP-1[39]Insulatorbroken insulator | 900986534 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN4249 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2018HP-1[173]Earths-Replace-Earth Strap | 900986536 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN4247 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2018HP-1[176-177]Vib Dampers-EW damper | 900986538 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG06006 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | HV Pressure Vessel Inspection | 901045782 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18EG10422 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 220kV SF6 Cubicle Operational Test | 900955894 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG10421 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 220kV SF6 Cubicle Operational Test | 900955895 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17LN2228 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2016HP-3[157]Strain/Dup 220kV replace | 900819574 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN4248 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2018HP-1[174]Earths-Replace-Earth Strap | 900986537 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0105 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | ESBI 01. VT Insulation retest Important | 900566652 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0104 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | O. ESBI Inspect and test all the cylind | 900444600 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100309341600 | TO-20-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | Proximity outage for stringing of Donard Test Line | CP1017 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN2851 | TO-20-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | 2019HP-1[39]Insulator Strain insul | 901084901 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331725 | TO-20-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | DUNSTOWN 220 | KELLIS 220 | 1 | Proximity outage for work on Great Island-Kellis 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113165247 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | P2 Protection maintenance of 7SA513, 7SL32 |  | 20/07/2020 | 24/07/2020 |  | Scheduled
OD0277 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 24/07/2020 |  | Scheduled
20CM0226 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | Oil Gauges To Be Cleaned | 901080649 | 20/07/2020 | 24/07/2020 | 2 | Scheduled
19EG06009 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | HV Pressure Vessel Inspection | 901043824 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
19LN4299 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | 2018HP-1[1]Insulatorfit dups on lead ins | 900986540 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
19CM0321 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | Copper earths stolen from 220kV DE and CTs to be reinstalled | 901076413 | 20/07/2020 | 24/07/2020 | 1 | Scheduled
19CM0324 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | Replace stolen earths | 901080780 | 20/07/2020 | 24/07/2020 | 1 | Scheduled
20LN2917 | TO-20-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | DUNSTOWN 220 | MAYNOOTH 220 | 1 | 2019HP-1[Stn]Insulator BB in Maynooth | 901084902 | 20/07/2020 | 24/07/2020 | 2 | Scheduled
OD0278 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | Total Maintenance Outage Duration Requested |  | 05/10/2020 | 23/10/2020 |  | Scheduled
19EG00826 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 220kV SF6 Cubicle Ordinary Service | 901042331 | 05/10/2020 | 23/10/2020 | 1 | Scheduled
19EG00827 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 220kV SF6 Cubicle Ordinary Service | 901042332 | 05/10/2020 | 23/10/2020 | 1 | Scheduled
19EG00828 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 220kV Cubicle Condition Assessment | 901038532 | 05/10/2020 | 23/10/2020 | 1 | Scheduled
16CM0302 | TO-20-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | Replace Cylinders | 900943761 | 25/12/2500 | 25/12/2500 |  | Unscheduled
19CM0325 | TO-20-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | Replace stolen earths | 901080781 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN4346 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[40]Insulatorfit duplicates | 900986551 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
19LN4332 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[39]Insulatorfit duplicates | 900986550 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
19LN4324 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[14]Insulatorbroken | 900986545 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
19LN4311 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[77]Insulatorfit duplicates | 900986554 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
19LN4310 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[78]Insulatorfit duplicates | 900986555 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
13LN0650 | TO-20-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2[77&am 78]Insulator fit duplicate. Proximity outage of Derryiron-Maynooth 110kV required | 900483534 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN4353 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2018HP-1[57-57A]Conflicts-fit guard wire | 900986552 | 05/10/2020 | 23/10/2020 | 4 | Scheduled
20LN2984 | TO-20-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | DUNSTOWN 220 | MAYNOOTH 220 | 2 | 2019HP-1[14]Insulator Broken C/ph | 901084903 | 05/10/2020 | 23/10/2020 | 2 | Scheduled
OD1267 | TO-20-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 11/11/2020 |  | Tentative
20CM0106 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | O. ESBI Inspect and test all the cylinde | 900444627 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0107 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | O. ESBI Inspect and test all the cylind | 900489556 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0108 | TO-20-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | Inspect and test all the cylinders, pist | 900531814 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
16CM0184 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | O/1 R4001 DRYCOL INTERNAL FAULT | 900690047 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN4536 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2018HP-1[214]ACGFit ACG | 900986826 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN4452 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2018HP-1[371]Bird Nestsremove asap | 900986733 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN4545 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2018HP-1[238]Bird Nestsremove asap | 900986835 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG06051 | TO-20-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | HV Pressure Vessel Inspection |  | 09/11/2020 | 11/11/2020 | 4 | Tentative
19CM0104 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | Dunstown R4001 Reactor: Refurbush Reactor, regasket & paint | 901038719 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG06054 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | HV Pressure Vessel Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3024 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[564]Insulator Broken | 901084911 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3023 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[563]Insulator Broken | 901084910 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3025 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[567]Bird Nests | 901084408 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3015 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[410]Insulator Broken | 901084908 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3014 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[402]Insulator Broken | 901084907 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3013 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[396]Insulator Broken | 901084906 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3010 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[371]Insulator Broken | 901084905 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3002 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[361]Insulator Broken | 901084904 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN2998 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[331]Bird Nests | 901084407 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100213211100 | TO-20-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | EI: Line refurb works | CP0873 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3020 | TO-20-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | DUNSTOWN 400 | MONEYPOINT GIS 400 | 1 | 2019HP-1[486]Insulator Broken | 901084909 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020147 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | P3 Protection maintenance of 7SL24, 7SL24, 7UT22 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0752 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Total Maintenance Outage Duration Requested |  | 18/03/2020 | 16/04/2020 |  | Scheduled
20EG01847 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 400/220kV Transformer Ordinary Service | 901130061 | 18/03/2020 | 16/04/2020 | 4 | Scheduled
19CM0027 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Oil Sampling - VT's UTF245 ESBI | 901045943 | 18/03/2020 | 16/04/2020 | 4 | Scheduled
20EG06012 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | HV Pressure Vessel Inspection |  | 18/03/2020 | 16/04/2020 | 4 | Scheduled
19EG01852 | TO-20-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 220KV CUBICLE CONDITION ASSESSMENT - Use OD1385 | 901038531 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0110 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Earth Winding externally to facilitate t | 900543177 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG01848 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 220kV SF6 Cubicle Ordinary Service | 901042340 | 18/03/2020 | 16/04/2020 | 4 | Scheduled
20EG06053 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | HV Pressure Vessel Inspection |  | 18/03/2020 | 16/04/2020 | 4 | Scheduled
19CM0103 | TO-20-DSN-T4201-04 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Dunstown T4201: Refurb work on OLTC diverters and remove elemental sulphur Look at long term plan for this trafo with Eirgrid Install on line IDD/Camlin bushing monitor Long outage required in refurb is being done. Fit bushing monitor (HV and LV) | 901038718 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01846 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 400kV SF6 Cubicle Ordinary Service | 901130035 | 18/03/2020 | 16/04/2020 | 4 | Scheduled
17CM0023 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Replace contacts in the trafo | 900546841 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG01848 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 220kV SF6 Cubicle Ordinary Service |  | 18/03/2020 | 16/04/2020 | 4 | Scheduled
20EG01849 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 400KV CUBICLE CONDITION ASSESSMENT Use OD1385 | 901129262 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01850 | TO-20-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 400/220kV Trafo Tap Changer Inspection. Use OD1385. | 901146361 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG01851 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1385. | 901146154 | 18/03/2020 | 16/04/2020 | 1 | Scheduled
17CM0417 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | ESBI 01 outage required (important)Misc- | 900606811 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17CM0422 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | ESBI 01 outage required. A Siemens senio | 900534083 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
17CM0425 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | ESBI 0 1 - A Siemens transformer test sp | 900533460 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
17CM0495 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | ESBI01 GE are to repair and recommission | 900781800 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0438 | TO-20-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Partial Discharge Test on T4201. Use OD1385. | 901133926 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19CM0054 | TO-20-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Investigate CB gas leak & repair if possible | 901045931 | 18/03/2020 | 16/04/2020 | 1 | Scheduled
20CM0111 | TO-20-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | DUNSTOWN 400 | DUNSTOWN 220 | T4201 | Online Oil Regen required due to high le | 900543178 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD1150 | TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | Total Maintenance Outage Duration Requested |  | 31/08/2020 | 04/09/2020 |  | Scheduled
CAPX2020072016272501 | TO-20-DSN-T4202-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202. | MC0316 | 04/08/2020 | 17/08/2020 |  | Scheduled
19CM0323 | TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | Replace stolen earths | 901080786 | 31/08/2020 | 04/09/2020 | 1 | Scheduled
18EG11375 | TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | 400/220kV Transformer Operational Test | 901045409 | 31/08/2020 | 04/09/2020 | 3 | Scheduled
18EG11374 | TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | 400kV SF6 Cubicle Operational Test | 901045732 | 31/08/2020 | 04/09/2020 | 3 | Scheduled
18EG11376 | TO-20-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | 220kV SF6 Cubicle Operational Test | 901038892 | 31/08/2020 | 04/09/2020 | 3 | Scheduled
CAPX2019100313243701 | TO-20-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | Stand new equipment, install new post insulators and string new T4202 bay conductor as far as the 400 kV CB. | MC0316 | 31/08/2020 | 04/09/2020 |  | Scheduled
CAPX2019100313243703 | TO-20-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | DUNSTOWN 400 | DUNSTOWN 220 | T4202 | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI). | MC0316 | 31/08/2020 | 04/09/2020 |  | Scheduled
OD0279 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | Total Maintenance Outage Duration Requested |  | 26/02/2020 | 06/03/2020 |  | Scheduled
TOP200715110230 | TO-20-DSN-TH-1-02 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | Relay Replacement at TH |  | 12/11/2020 | 12/11/2020 |  | Scheduled
PROT2020119 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 26/02/2020 | 06/03/2020 | 3 | Scheduled
PROT2020118 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 26/02/2020 | 06/03/2020 | 3 | Scheduled
19LN4612 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | 2018HP-1[39]Insulatorbroken | 900986853 | 26/02/2020 | 06/03/2020 | 4 | Scheduled
19CM0328 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | Replace stolen earths | 901080783 | 26/02/2020 | 06/03/2020 | 1 | Scheduled
18EG20130 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 900913182 | 26/02/2020 | 06/03/2020 | 3 | Scheduled
18EG10427 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | 220kV SF6 Cubicle Operational Test | 901038891 | 26/02/2020 | 06/03/2020 | 3 | Scheduled
18EG10428 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | 220kV MO Cubicle Operational Test | 901038978 | 26/02/2020 | 06/03/2020 | 3 | Scheduled
19LN4616 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | 2018HP-1[82]Insulatorbroken | 900986859 | 26/02/2020 | 06/03/2020 | 4 | Scheduled
20CM0383 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | Misc- CT R-Phase cover to be refitted du | 901083956 | 26/02/2020 | 06/03/2020 | 2 | Scheduled
20LN3070 | TO-20-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | DUNSTOWN 220 | TURLOUGH HILL 220 | 1 | 2019HP-1[45]Insulator Broken L/ph | 901084913 | 26/02/2020 | 06/03/2020 | 2 | Scheduled
OD0387 | TO-20-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | ENNIS 110 | ENNIS 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19CM0043 | TO-20-ENN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | ENNIS 110 | ENNIS 110 | 110SA1-2CB | Investigate CB gas leak & repair if possible | 901045923 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG11302 | TO-20-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | ENNIS 110 | ENNIS 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11303 | TO-20-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | ENNIS 110 | ENNIS 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11304 | TO-20-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | ENNIS 110 | ENNIS 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0457 | TO-20-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | ENNIS 110 | SLIEVECALLAN 110 | 1 | S Phase Ennis 110kv Cubicle. S Phase cable end bushing connectio hotspot DUE : 17-Jul-20 hotspot | 901134796 | 13/07/2020 | 17/07/2020 | 1 | Scheduled
20CM0447 | TO-20-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | ENNIS 110 | SLIEVECALLAN 110 | 1 | S Phase Slievecallan 110kv Cubicle. S phase se connectio hotspot n DUE : IMMEDIATELY | 901134782 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG23673 | TO-20-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | ENNIS 110 | SLIEVECALLAN 110 | 1 | Cable Insp. 110kV XLPE | 901076133 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0464 | TO-20-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | ENNIS 110 | SLIEVECALLAN 110 | 1 | R & S Phases Ennis 110kV cubicle. R & S Phase DL/DE DUE : 17-Aug-20hotspot | 901134797 | 13/07/2020 | 17/07/2020 | 1 | Scheduled
TOP201007080113 | TO-20-ENN-T142-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T142 | ENNIS 110 | ENNIS 38 | T142 | Outage requested by ESBN. DOF required following CA on T142 110kV cubicle |  | 19/10/2020 | 23/10/2020 |  | Reference
CAPX2020010812200008 | TO-20-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | FINGLAS 110 | FINGLAS 110 | 110A1 | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200010 | TO-20-110 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | FINGLAS 110 | FINGLAS 110 | 110A2 | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200012 | TO-20-110 kV A3 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A3 | FINGLAS 110 | FINGLAS 110 | 110A3 | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200009 | TO-20-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | FINGLAS 110 | FINGLAS 110 | 110B1 | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200011 | TO-20-110 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | FINGLAS 110 | FINGLAS 110 | 110B2 | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200013 | TO-20-110 kV B3 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B3 | FINGLAS 110 | FINGLAS 110 | 110B3 | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0388 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
17EG10598 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | 110kV MO Cubicle Operational Test | 901038699 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG10595 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901039139 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10594 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901039140 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10597 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901039137 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10596 | TO-20-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | FINGLAS 110 | FINGLAS 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901039138 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0389 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01085 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01086 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01088 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01089 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01087 | TO-20-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | FINGLAS 110 | FINGLAS 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010812200014 | TO-20-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | FINGLAS 220 | FINGLAS 220 | 220A1 | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200016 | TO-20-220 kV A2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | FINGLAS 220 | FINGLAS 220 | 220A2 | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200015 | TO-20-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | FINGLAS 220 | FINGLAS 220 | 220B1 | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200017 | TO-20-220 kV B2 @ FIN-11 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | FINGLAS 220 | FINGLAS 220 | 220B2 | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0390 | TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | FINGLAS 220 | FINGLAS 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10606 | TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | FINGLAS 220 | FINGLAS 220 | 220K1-2 | 220kV SF6 Cubicle Operational Test | 901038696 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18CM0230 | TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | FINGLAS 220 | FINGLAS 220 | 220K1-2 | Investigate sync close of 220 kV couple K1 CB. CB Direct Closed. Angle difference <1 deg and voltage difference <0.5 kV. | 901046377 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG10604 | TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | FINGLAS 220 | FINGLAS 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039135 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10605 | TO-20-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | FINGLAS 220 | FINGLAS 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039136 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010812200018 | TO-20-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A1 | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200026 | TO-20-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A2 | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200034 | TO-20-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A3 | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200040 | TO-20-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A4 | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200046 | TO-20-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A5 | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200052 | TO-20-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110A6 | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200019 | TO-20-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B1 | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200027 | TO-20-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B2 | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200035 | TO-20-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B3 | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200041 | TO-20-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B4 | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200047 | TO-20-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B5 | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200053 | TO-20-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110B6 | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1154 | TO-20-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23515 | TO-20-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K1 | 110kV GIS Cubicle Operational Test | 901043767 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010812200020 | TO-20-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K1 | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200021 | TO-20-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K1 | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200029 | TO-20-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K2 | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200028 | TO-20-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K2 | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200048 | TO-20-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K5 | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200049 | TO-20-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K5 | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200055 | TO-20-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K6 | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200054 | TO-20-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | FINGLAS GIS 110 | FINGLAS GIS 110 | 110K6 | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200030 | TO-20-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA1-2CB | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200022 | TO-20-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200036 | TO-20-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA1-3CB | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200023 | TO-20-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA1-3CB | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200042 | TO-20-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA2-4CB | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200031 | TO-20-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA2-4CB | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200050 | TO-20-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA3-5CB | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200037 | TO-20-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA3-5CB | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200056 | TO-20-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA4-6CB | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200043 | TO-20-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SA4-6CB | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200032 | TO-20-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB1-2CB | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200024 | TO-20-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200038 | TO-20-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB1-3CB | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200025 | TO-20-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB1-3CB | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200033 | TO-20-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB2-4CB | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200044 | TO-20-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB2-4CB | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200039 | TO-20-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB35CB | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200051 | TO-20-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB35CB | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200045 | TO-20-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB4-6CB | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200057 | TO-20-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | FINGLAS GIS 110 | FINGLAS GIS 110 | 110SB4-6CB | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1236 | TO-20-FIN GIS-GLA-1-01 | 110kV FEEDER - FINGLAS GIS 110-GLASMORE 110-1 | FINGLAS GIS 110 | GLASMORE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
20EG10243 | TO-20-FIN GIS-GLA-1-01 | 110kV FEEDER - FINGLAS GIS 110-GLASMORE 110-1 | FINGLAS GIS 110 | GLASMORE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Reference (Unscheduled)
OD0753 | TO-20-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | FINGLAS 220 | FINGLAS GIS 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0116 | TO-20-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | FINGLAS 220 | FINGLAS GIS 110 | T2101 | T2101 220KV CB Over Pressure | 901080725 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG01856 | TO-20-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | FINGLAS 220 | FINGLAS GIS 110 | T2101 | 220KV CUBICLE CONDITION ASSESSMENT | 901038497 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01855 | TO-20-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | FINGLAS 220 | FINGLAS GIS 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service | 901042114 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0125 | TO-20-FIN GIS-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2104 | FINGLAS 220 | FINGLAS GIS 110 | T2104 | Hotspot repair S phase 220KV VT connecti | 900852318 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD1047 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | Total Maintenance Outage Duration Requested |  | 11/05/2020 | 27/07/2020 |  | Scheduled
20EG02144 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | 110kV GIS Cubicle Ordinary Service | 901129786 | 11/05/2020 | 27/07/2020 | 4 | Scheduled
18EG11076 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | 220kV SF6 Cubicle Operational Test | 901129542 | 11/05/2020 | 27/07/2020 | 3 | Scheduled
18CM1182 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | ESBI Replace faulty isolation valve on S | 900973442 | 11/05/2020 | 27/07/2020 | 2 | Scheduled
18EG11078 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | 220/110 & 275/220 Trafo Operational Test | 901045418 | 11/05/2020 | 27/07/2020 | 3 | Scheduled
20CM0129 | TO-20-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | FINGLAS 220 | FINGLAS GIS 110 | T2106 | Investigate Hydran alarms not working | 901059907 | 11/05/2020 | 27/07/2020 | 2 | Scheduled
OD0280 | TO-20-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | FINGLAS 220 | HUNTSTOWN 220 | 1 | Total Maintenance Outage Duration Requested |  | 17/09/2020 | 17/11/2020 |  | Scheduled
19CM0330 | TO-20-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | FINGLAS 220 | HUNTSTOWN 220 | 1 | Replace CB counter/ complete CA on VT's & SA's | 901076401 | 17/09/2020 | 17/11/2020 | 1 | Scheduled
17CM0078 | TO-20-FIN-HN-1-04 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | FINGLAS 220 | HUNTSTOWN 220 | 1 | HUNTSTOWN 220KV DL PI IN EIRGRID WHEN DL | 900479248 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0453 | TO-20-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | FINGLAS 220 | HUNTSTOWN 220 | 1 | T Phase Hotspot on T phase DL/DE disconnect DUE : 17-Jul-20 | 901128554 | 17/09/2020 | 17/11/2020 | 1 | Scheduled
OD0281 | TO-20-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | FINGLAS 220 | NORTH WALL 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00836 | TO-20-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | FINGLAS 220 | NORTH WALL 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 901042333 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10431 | TO-20-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | FINGLAS 220 | NORTH WALL 220 | 1 | 220kV GIS Cubicle Operational Test | 901039120 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00839 | TO-20-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | FINGLAS 220 | NORTH WALL 220 | 1 | 220kV Cubicle Condition Assessment | 901038498 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331728 | TO-20-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | FINGLAS 220 | NORTH WALL 220 | 1 | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020072010415107 | TO-20-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | FINGLAS 220 | SHELLYBANKS 220 | 1 | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay | CP0437 | 11/09/2020 | 13/09/2020 |  | Scheduled
OD0282 | TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | FINGLAS 220 | SHELLYBANKS 220 | 1 | Total Maintenance Outage Duration Requested |  | 13/03/2020 | 29/05/2020 |  | Scheduled
TOP200826174014 | TO-20-FIN-SHL-1-04 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | FINGLAS 220 | SHELLYBANKS 220 | 1 | Switching to start at 18:00 11 Sept |  | 11/09/2020 | 13/09/2020 |  | Scheduled
CAPX2020083115412210 | TO-20-FIN-SHL-1-05 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | FINGLAS 220 | SHELLYBANKS 220 | 1 | Proximity outage required to remove scaffolding at the new Belcamp bay. | CP0437 | 23/09/2020 | 25/09/2020 |  | Scheduled
20EG20153 | TO-20-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | FINGLAS 220 | SHELLYBANKS 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 13/03/2020 | 29/05/2020 | 4 | Scheduled
19CM0101 | TO-20-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | FINGLAS 220 | FINGLAS 110 | T2103 | Finglas T2103 Transformer: Drycol Replacement | 901039279 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG01877 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 110KV CUBICLE CONDITION ASSESSMENT |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
20EG01875 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 220kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
20EG01879 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
20CM0122 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 0. 1. ESBI CB - Abnormal timing results | 900474794 | 14/09/2020 | 04/12/2020 | 2 | Scheduled
20EG01876 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 220/110 & 275/220 Trafo Ordinary Service |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
20EG01878 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | 220KV CUBICLE CONDITION ASSESSMENT |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
20EG20554 | TO-20-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | FINGLAS 220 | FINGLAS 110 | T2104 | Cable Insp. 110kV XLPE |  | 14/09/2020 | 04/12/2020 | 4 | Scheduled
CAPX2019101715390460 | TO-20-110 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | FLAGFORD 110 | FLAGFORD 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390457 | TO-20-110 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | FLAGFORD 110 | FLAGFORD 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390454 | TO-20-110 kV A1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | FLAGFORD 110 | FLAGFORD 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200058 | TO-20-110 kV A1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | FLAGFORD 110 | FLAGFORD 110 | 110A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390463 | TO-20-110 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | FLAGFORD 110 | FLAGFORD 110 | 110A1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390447 | TO-20-110 kV A2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | FLAGFORD 110 | FLAGFORD 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390450 | TO-20-110 kV A2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | FLAGFORD 110 | FLAGFORD 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390404 | TO-20-110 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | FLAGFORD 110 | FLAGFORD 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390401 | TO-20-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | FLAGFORD 110 | FLAGFORD 110 | 110A2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200059 | TO-20-110 kV A2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | FLAGFORD 110 | FLAGFORD 110 | 110A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390461 | TO-20-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | FLAGFORD 110 | FLAGFORD 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390458 | TO-20-110 kV B1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | FLAGFORD 110 | FLAGFORD 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390455 | TO-20-110 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | FLAGFORD 110 | FLAGFORD 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200060 | TO-20-110 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | FLAGFORD 110 | FLAGFORD 110 | 110B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390464 | TO-20-110 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | FLAGFORD 110 | FLAGFORD 110 | 110B1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094646 | TO-20-110 kV B1/B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1-B2 | FLAGFORD 110 | FLAGFORD 110 | 110B1-B2 | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390448 | TO-20-110 kV B2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | FLAGFORD 110 | FLAGFORD 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200061 | TO-20-110 kV B2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | FLAGFORD 110 | FLAGFORD 110 | 110B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390402 | TO-20-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | FLAGFORD 110 | FLAGFORD 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390405 | TO-20-110 kV B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | FLAGFORD 110 | FLAGFORD 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390451 | TO-20-110 kV B2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | FLAGFORD 110 | FLAGFORD 110 | 110B2 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0391 | TO-20-FLA-110K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01098 | TO-20-FLA-110K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01095 | TO-20-FLA-110K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01096 | TO-20-FLA-110K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01097 | TO-20-FLA-110K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | 110kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100414120541 | TO-20-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094647 | TO-20-FLA-110K1-2-02 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100411043132 | TO-20-FLA-110K1-2-02 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | FLAGFORD 110 | FLAGFORD 110 | 110K1-2 | Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV coupler bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094611 | TO-20-220 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | FLAGFORD 220 | FLAGFORD 220 | 220A1 | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390429 | TO-20-220 kV A1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | FLAGFORD 220 | FLAGFORD 220 | 220A1 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200062 | TO-20-220 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | FLAGFORD 220 | FLAGFORD 220 | 220A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390426 | TO-20-220 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | FLAGFORD 220 | FLAGFORD 220 | 220A1 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200063 | TO-20-220 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | FLAGFORD 220 | FLAGFORD 220 | 220A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094638 | TO-20-220 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | FLAGFORD 220 | FLAGFORD 220 | 220A2 | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200064 | TO-20-220 kV B1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | FLAGFORD 220 | FLAGFORD 220 | 220B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390430 | TO-20-220 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | FLAGFORD 220 | FLAGFORD 220 | 220B1 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390427 | TO-20-220 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | FLAGFORD 220 | FLAGFORD 220 | 220B1 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094623 | TO-20-220 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | FLAGFORD 220 | FLAGFORD 220 | 220B1 | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094618 | TO-20-220 kV B1/B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1-B2 | FLAGFORD 220 | FLAGFORD 220 | 220B1-B2 | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200065 | TO-20-220 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | FLAGFORD 220 | FLAGFORD 220 | 220B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0392 | TO-20-FLA-220K1-2-04 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0130 | TO-20-FLA-220K1-2-04 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | O1 R phase pantograph on 220kV coupler s | 901068587 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019100411043112 | TO-20-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the 220 kV coupler bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110709503605 | TO-20-FLA-220K1-2-03 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094619 | TO-20-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100414120516 | TO-20-FLA-220K1-2-02 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | FLAGFORD 220 | FLAGFORD 220 | 220K1-2 | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0161 | TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | FLAGFORD 110 | GILRA 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 31/07/2020 |  | Scheduled
TOP200529154003 | TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | FLAGFORD 110 | GILRA 110 | 1 | Extra day required for covid restrictions |  | 27/07/2020 | 31/07/2020 |  | Scheduled
20EG00489 | TO-20-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | FLAGFORD 110 | GILRA 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129904 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
TOP200527093605 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | Outage for timber cutting. RC 3 days request |  | 14/09/2020 | 09/10/2020 |  | Scheduled
OD0283 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 09/10/2020 |  | Scheduled
CAPX2020012316593927 | TO-20-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG00847 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 220kV Cubicle Condition Assessment | 901038537 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
15CM0308 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | Install Game Guards | 900566631 | 14/09/2020 | 09/10/2020 | 1 | Scheduled
19EG00845 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 220kV MO Cubicle Ordinary Service | 901042380 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
20LN3120 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[25]Bird Nests | 901084410 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
CAPX2019101715390437 | TO-20-FLA-LOU-1-04 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | EI: Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the Louth 220 kV bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094639 | TO-20-FLA-LOU-1-04 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3110 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[4]Bird Nests | 901084409 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
20LN3155 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[192]Bird Nests | 901084412 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
20LN3126 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[38]Bird Nests | 901084411 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
20LN3134 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[65]Insulator Broken R/ph | 901084915 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
CAPX2019100212071500 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | Outage to enable refurbishment of OHL, Remove ground proximity clearances and tower reinforcements | CP0867 | 14/09/2020 | 09/10/2020 |  | Scheduled
CAPX2019100414120517 | TO-20-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3149 | TO-20-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | FLAGFORD 220 | LOUTH 220 | 1 | 2019HP-1[156]Insulator Broken C/ph | 901084916 | 14/09/2020 | 09/10/2020 | 4 | Scheduled
OD0974 | TO-20-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | Total Maintenance Outage Duration Requested |  | 04/08/2020 | 28/08/2020 |  | Scheduled
19LN4679 | TO-20-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | 2018HP-1[Am 64]Bird Nests | 900987019 | 04/08/2020 | 28/08/2020 | 4 | Scheduled
19EG00491 | TO-20-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | 110kV MO Cubicle Ordinary Service | 901050316 | 04/08/2020 | 28/08/2020 | 4 | Scheduled
20LN5280 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 19-20 of 3.69m, LV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160394 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5279 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 19-20 of 2.75m, LV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160386 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5278 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 16-17 of 2.58m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160393 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5277 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 16-17 of 1.99m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160385 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5276 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 15-16 of 0.91m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160392 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5274 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 1-2 of 0.98m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160383 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5251 | TO-20-FLA-SLB-1-06 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | Clearance Infringment Spans 43-44 |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG21374 | TO-20-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 04/08/2020 | 28/08/2020 | 4 | Scheduled
20LN5252 | TO-20-FLA-SLB-1-06 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | Clearance Infringment Spans 44-45 |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5281 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 31-32 of 0.92m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160387 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5275 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 15-16 of 0.76m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160384 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN3195 | TO-20-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | 2019HP-1[64]Bird Nests | 901084413 | 04/08/2020 | 28/08/2020 | 4 | Scheduled
20LN5273 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 1-2 of 0.43m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160391 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5283 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 46-47 of 2.52m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160388 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5284 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 46-47 of 3.89m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160396 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5285 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 60-61 of 0.10m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160397 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5286 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 76-77 of 2.23m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160389 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019101715390459 | TO-20-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | EI: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV flagford Sliabh Bawn bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390465 | TO-20-FLA-SLB-1-03 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390462 | TO-20-FLA-SLB-1-02 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5287 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 76-77 of 2.48m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160398 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5289 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 95-96 of 0.90m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160399 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5288 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 95-96 of 0.34m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160390 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5282 | TO-20-FLA-SLB-1-05 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | FLAGFORD 110 | SLIABH BAWN 110 | 1 | SPAN 31-32 of 1.63m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT | 901160395 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG10255 | TO-20-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | FLAGFORD 110 | SLIGO 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101715390403 | TO-20-FLA-SLI-1-05 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | FLAGFORD 110 | SLIGO 110 | 1 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390406 | TO-20-FLA-SLI-1-06 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | FLAGFORD 110 | SLIGO 110 | 1 | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019112211380900 | TO-20-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | FLAGFORD 110 | SLIGO 110 | 1 | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford sligo 110 kV bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0284 | TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | FLAGFORD 220 | SRANANAGH 220 | 1 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 25/11/2020 |  | Scheduled
20CM0133 | TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | FLAGFORD 220 | SRANANAGH 220 | 1 | O1 Srananagh 220kV DE (R phase) earthing | 900891647 | 23/11/2020 | 25/11/2020 | 1 | Scheduled
17EG11306 | TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | FLAGFORD 220 | SRANANAGH 220 | 1 | 220kV SF6 Cubicle Operational Test | 900942726 | 23/11/2020 | 25/11/2020 | 2 | Scheduled
17EG11305 | TO-20-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | FLAGFORD 220 | SRANANAGH 220 | 1 | 220kV SF6 Cubicle Operational Test | 900942345 | 23/11/2020 | 25/11/2020 | 2 | Scheduled
CAPX2019111916535006 | TO-20-FLA-SRA-1-01 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | FLAGFORD 220 | SRANANAGH 220 | 1 | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0758 | TO-20-FLA-T2101-06 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 11/11/2020 |  | Scheduled
CAPX2020012316593928 | TO-20-FLA-T2101-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11080 | TO-20-FLA-T2101-06 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | 220/110 & 275/220 Trafo Operational Test |  | 09/11/2020 | 11/11/2020 | 4 | Scheduled
20EG11081 | TO-20-FLA-T2101-06 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | 110kV MO Cubicle Operational Test |  | 09/11/2020 | 11/11/2020 | 4 | Scheduled
20CM0135 | TO-20-FLA-T2101-07 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Allow 1 additional week for detailed mai | 900907922 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG11079 | TO-20-FLA-T2101-06 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | 220kV MO Cubicle Operational Test |  | 09/11/2020 | 11/11/2020 | 4 | Scheduled
20CM0134 | TO-20-FLA-T2101-06 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Camlin Power are to supply & install a n | 900909437 | 09/11/2020 | 11/11/2020 | 2 | Scheduled
CAPX2019101011094624 | TO-20-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011094625 | TO-20-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Simultaneous FLA-T2101 + FLA-T2101: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV T2101 bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390431 | TO-20-FLA-T2101-04 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715390428 | TO-20-FLA-T2101-03 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101) | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011335622 | TO-20-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the T2101 220 kV bay at flagford station | CP1031 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019110709503607 | TO-20-FLA-T2101-05 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | FLAGFORD 220 | FLAGFORD 110 | T2101 | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0759 | TO-20-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | FLAGFORD 220 | FLAGFORD 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11084 | TO-20-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | FLAGFORD 220 | FLAGFORD 110 | T2102 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11083 | TO-20-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | FLAGFORD 220 | FLAGFORD 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17CM0360 | TO-20-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | FLAGFORD 220 | FLAGFORD 110 | T2102 | O 1 ESBI Replace three 220kV and 110kV b | 900463619 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG11082 | TO-20-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | FLAGFORD 220 | FLAGFORD 110 | T2102 | 220kV SF6 Cubicle Operational Test | 901080658 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0393 | TO-20-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01105 | TO-20-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01104 | TO-20-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01103 | TO-20-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331774 | TO-20-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331769 | TO-20-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331779 | TO-20-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331790 | TO-20-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | GALWAY 110 | GALWAY 110 | 110K1-2 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0395 | TO-20-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01111 | TO-20-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01113 | TO-20-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01112 | TO-20-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331795 | TO-20-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331784 | TO-20-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331770 | TO-20-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331780 | TO-20-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | GALWAY 110 | GALWAY 110 | 110K1-3 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0394 | TO-20-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01107 | TO-20-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01109 | TO-20-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01108 | TO-20-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331791 | TO-20-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331775 | TO-20-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331796 | TO-20-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331785 | TO-20-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | GALWAY 110 | GALWAY 110 | 110K2-3 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1098 | TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | GALWAY 110 | KNOCKRANNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/03/2020 | 12/03/2020 |  | Scheduled
20CM0137 | TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | GALWAY 110 | KNOCKRANNY 110 | 1 | O1 Knockranny CB low gas | 901080915 | 12/03/2020 | 12/03/2020 | 1 | Scheduled
CAPX2020010910331771 | TO-20-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | GALWAY 110 | KNOCKRANNY 110 | 1 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23249 | TO-20-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | GALWAY 110 | KNOCKRANNY 110 | 1 | 110kV GIS Cubicle Operational Test |  | 12/03/2020 | 12/03/2020 | 4 | Scheduled
CAPX2020010910331781 | TO-20-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | GALWAY 110 | KNOCKRANNY 110 | 1 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200114100727 | TO-20-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 02/11/2020 | 03/11/2020 |  | Scheduled
OD0165 | TO-20-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/11/2020 | 03/11/2020 |  | Scheduled
20EG10257 | TO-20-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 02/11/2020 | 03/11/2020 | 4 | Scheduled
20EG11185 | TO-20-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 02/11/2020 | 03/11/2020 | 4 | Scheduled
CAPX2020010910331786 | TO-20-GAL-SAL-1-02 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331797 | TO-20-GAL-SAL-1-02 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | GALWAY 110 | SALTHILL 110 | 1 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331787 | TO-20-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | GALWAY 110 | GALWAY 10 | T101 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331798 | TO-20-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | GALWAY 110 | GALWAY 10 | T101 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331792 | TO-20-GAL-T102-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T102 | GALWAY 110 | GALWAY 10 | T102 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331776 | TO-20-GAL-T102-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T102 | GALWAY 110 | GALWAY 10 | T102 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331772 | TO-20-GAL-T141-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | GALWAY 110 | GALWAY 38 | T141 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331782 | TO-20-GAL-T141-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | GALWAY 110 | GALWAY 38 | T141 | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331777 | TO-20-GAL-T142-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T142 | GALWAY 110 | GALWAY 38 | T142 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331793 | TO-20-GAL-T142-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T142 | GALWAY 110 | GALWAY 38 | T142 | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331788 | TO-20-GAL-T143-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T143 | GALWAY 110 | GALWAY 38 | T143 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331799 | TO-20-GAL-T143-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T143 | GALWAY 110 | GALWAY 38 | T143 | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0396 | TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | GARROW 110 | GARROW 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 23/06/2020 | 24/06/2020 |  | Scheduled
20EG11290 | TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | GARROW 110 | GARROW 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901129711 | 23/06/2020 | 24/06/2020 | 4 | Scheduled
20EG11291 | TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | GARROW 110 | GARROW 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 901130111 | 23/06/2020 | 24/06/2020 | 4 | Scheduled
20EG11292 | TO-20-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | GARROW 110 | GARROW 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 901130110 | 23/06/2020 | 24/06/2020 | 4 | Scheduled
OD0531 | TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | GARROW 110 | GARROW 20 | T122 | Total Maintenance Outage Duration Requested |  | 23/06/2020 | 24/06/2020 |  | Scheduled
20EG10849 | TO-20-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | GARROW 110 | GARROW 20 | T122 | 110kV SF6 Cubicle Operational Test | 901129713 | 23/06/2020 | 24/06/2020 | 4 | Scheduled
CAPX2020010812200066 | TO-20-110 kV A1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110A1 | GARVAGH 110 | GARVAGH 110 | 110A1 | Busbar Changeover | BB0002 | 11/06/2020 | 11/06/2020 |  | Scheduled
CAPX2020010812200068 | TO-20-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | GARVAGH 110 | GARVAGH 110 | 110B1 | Busbar Changeover | BB0002 | 11/06/2020 | 11/06/2020 |  | Scheduled
TOP200109152830 | TO-20-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | GARVAGH 110 | GARVAGH 110 | 110K1 | As a consequence of work on Corderry-Garvagh 110 kV |  | 13/07/2020 | 15/07/2020 |  | Scheduled
CAPX2020010812200067 | TO-20-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | GARVAGH 110 | GARVAGH 110 | 110K1 | As a consequence of 110 kV A1 @ GRV: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200069 | TO-20-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | GARVAGH 110 | GARVAGH 110 | 110K1 | As a consequence of 110 kV B1 @ GRV: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200109152643 | TO-20-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | GARVAGH 110 | GARVAGH 20 | T141 | As a consequence of work on Corderry-Garvagh 110 kV |  | 13/07/2020 | 15/07/2020 |  | Reference
TOP200205090306 | TO-20-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | GILRA 110 | GILRA 20 | T121 | As a consequence of work on Flagford-Gilra 110 kV |  | 27/07/2020 | 31/07/2020 |  | Reference
OD0397 | TO-20-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02231 | TO-20-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02227 | TO-20-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02230 | TO-20-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02232 | TO-20-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0285 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 31/08/2020 |  | Scheduled
20EG02226 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | 220kV Cubicle Condition Assessment |  | 24/08/2020 | 31/08/2020 | 4 | Scheduled
20EG02224 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | 220kV Cubicle Condition Assessment |  | 24/08/2020 | 31/08/2020 | 4 | Scheduled
20EG02223 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 24/08/2020 | 31/08/2020 | 4 | Scheduled
20EG02225 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 24/08/2020 | 31/08/2020 | 4 | Scheduled
20CM0276 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | O1-220kv Cable sealing ends moss build u | 901028746 | 24/08/2020 | 31/08/2020 | 2 | Scheduled
20EG20671 | TO-20-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | GLANAGOW 220 | RAFFEEN 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 24/08/2020 | 31/08/2020 | 4 | Scheduled
OD0649 | TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | GLANAGOW 220 | GLANAGOW G1 | T2001 | Total Maintenance Outage Duration Requested |  | 26/08/2020 | 26/08/2020 |  | Scheduled
TOP191114102659 | TO-20-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | GLANAGOW 220 | GLANAGOW G1 | T2001 | Blackstart Test |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0138 | TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | GLANAGOW 220 | GLANAGOW G1 | T2001 | O1- T2001 Protection Maintenance | 900951244 | 26/08/2020 | 26/08/2020 | 2 | Scheduled
20EG20303 | TO-20-GGO-T2001-02 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | GLANAGOW 220 | GLANAGOW G1 | T2001 | Cable Insp. 400 & 220kV Feeder XLPE |  | 26/08/2020 | 26/08/2020 | 4 | Scheduled
OD0533 | TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | GLANLEE 110 | GLANLEE 20 | T121 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 15/07/2020 |  | Scheduled
18CM1195 | TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | GLANLEE 110 | GLANLEE 20 | T121 | AC and DC Supplies: | 900973585 | 13/07/2020 | 15/07/2020 | 2 | Scheduled
20EG10851 | TO-20-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | GLANLEE 110 | GLANLEE 20 | T121 | 110kV SF6 Cubicle Operational Test | 901129611 | 13/07/2020 | 15/07/2020 | 4 | Scheduled
OD1368 | TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | GLENLARA 110 | KNOCKACUMMER 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 21/08/2020 |  | Scheduled
19EG23777 | TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | GLENLARA 110 | KNOCKACUMMER 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 17/08/2020 | 21/08/2020 | 4 | Scheduled
19EG23776 | TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | GLENLARA 110 | KNOCKACUMMER 110 | 1 | Cable Insp. 110kV XLPE |  | 17/08/2020 | 21/08/2020 | 4 | Scheduled
20EG23780 | TO-20-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | GLENLARA 110 | KNOCKACUMMER 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 17/08/2020 | 21/08/2020 | 4 | Scheduled
OD0398 | TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | GLENREE 110 | GLENREE 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
17EG02440 | TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | GLENREE 110 | GLENREE 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 901130245 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17EG02439 | TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | GLENREE 110 | GLENREE 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 901130243 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX20200109103317100 | TO-20-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | GLENREE 110 | GLENREE 110 | 110SA1-2CB | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109103317103 | TO-20-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | GLENREE 110 | GLENREE 110 | 110SA1-2CB | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0166 | TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | GLENREE 110 | MOY 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/03/2020 | 22/10/2020 |  | Scheduled
19CM0062 | TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | GLENREE 110 | MOY 110 | 1 | Repair SF6 leak on CB (ref. FO Mar 2019) | 901129078 | 02/03/2020 | 22/10/2020 | 1 | Scheduled
19EG11218 | TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | GLENREE 110 | MOY 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 02/03/2020 | 22/10/2020 | 4 | Scheduled
20CM0139 | TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | GLENREE 110 | MOY 110 | 1 | ESB EMP MO raised for PO. Stephen West. | 901058978 | 02/03/2020 | 22/10/2020 | 2 | Scheduled
CAPX20200109103317101 | TO-20-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | GLENREE 110 | MOY 110 | 1 | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0001 | 02/03/2020 | 22/10/2020 |  | Scheduled
CAPX20200109103317104 | TO-20-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | GLENREE 110 | GLENREE 38 | T142 | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200108155811 | TO-20-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | GOLAGH 110 | GOLAGH 10 | T101 | Full tee outage for work on Golagh tee Letterkenny |  | 17/08/2020 | 30/08/2020 |  | Scheduled
OD0975 | TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | GOLAGH tee | CLOGHER 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 30/08/2020 |  | Scheduled
19EG21311 | TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | GOLAGH tee | CLOGHER 110 | 1 | 110kV GIS Cubicle Operational Test | 901045434 | 17/08/2020 | 30/08/2020 | 4 | Scheduled
20EG21313 | TO-20-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | GOLAGH tee | CLOGHER 110 | 1 | Cable Insp. 110kV XLPE |  | 17/08/2020 | 30/08/2020 | 4 | Scheduled
OD0168 | TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | GOLAGH tee | GOLAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 30/08/2020 |  | Scheduled
20EG00503 | TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | GOLAGH tee | GOLAGH 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 17/08/2020 | 30/08/2020 | 4 | Scheduled
18CM0160 | TO-20-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | GOLAGH tee | GOLAGH 110 | 1 | flicker light on SMD o/o/o | 900955641 | 17/08/2020 | 30/08/2020 | 1 | Scheduled
OD0169 | TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | GOLAGH tee | LETTERKENNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 30/08/2020 |  | Scheduled
16CM0092 | TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | GOLAGH tee | LETTERKENNY 110 | 1 | 1[142] Carry out ancillary works at Mast | 900720114 | 17/08/2020 | 30/08/2020 | 2 | Scheduled
20EG00506 | TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | GOLAGH tee | LETTERKENNY 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 17/08/2020 | 30/08/2020 | 4 | Scheduled
20CM0193 | TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | GOLAGH tee | LETTERKENNY 110 | 1 | moisture in H8 surge arrestors | 900952946 | 17/08/2020 | 30/08/2020 | 1 | Scheduled
20EG00505 | TO-20-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | GOLAGH tee | LETTERKENNY 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 17/08/2020 | 30/08/2020 | 4 | Scheduled
CAPX2020010812200074 | TO-20-110 kV A1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | GORMAN 110 | GORMAN 110 | 110A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200079 | TO-20-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | GORMAN 110 | GORMAN 110 | 110A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200075 | TO-20-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | GORMAN 110 | GORMAN 110 | 110A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200076 | TO-20-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | GORMAN 110 | GORMAN 110 | 110B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200077 | TO-20-110 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B2 | GORMAN 110 | GORMAN 110 | 110B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0399 | TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | GORMAN 110 | GORMAN 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 03/07/2020 |  | Scheduled
17CM0397 | TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | GORMAN 110 | GORMAN 110 | 110K1-2 | Install interlocking coils. | 900693010 | 29/06/2020 | 03/07/2020 | 2 | Scheduled
16CM0043 | TO-20-GOR-110K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | GORMAN 110 | GORMAN 110 | 110K1-2 | Complete Siemens CB mod | 900776802 | 29/06/2020 | 03/07/2020 | 2 | Scheduled
CAPX2020010812200078 | TO-20-220 kV A1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | GORMAN 220 | GORMAN 220 | 220A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200080 | TO-20-220 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B1 | GORMAN 220 | GORMAN 220 | 220B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200081 | TO-20-220 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | GORMAN 220 | GORMAN 220 | 220B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0286 | TO-20-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | GORMAN 220 | LOUTH 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10437 | TO-20-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | GORMAN 220 | LOUTH 220 | 1 | 220kV SF6 Cubicle Operational Test | 901068548 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00849 | TO-20-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | GORMAN 220 | LOUTH 220 | 1 | 220kV MO Cubicle Ordinary Service | 901050444 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3266 | TO-20-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | GORMAN 220 | LOUTH 220 | 1 | 2019HP-1[75]Bird Nests | 901084278 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0287 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | Total Maintenance Outage Duration Requested |  | 20/04/2020 | 08/05/2020 |  | Scheduled
20CM0227 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | Low Oil / Leak- T Phase Oil Looks Low | 901080652 | 20/04/2020 | 08/05/2020 | 1 | Scheduled
19CM0317 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | Copper earths stolen from 220kV CT, VT and chokes to be reinstalled | 901076414 | 20/04/2020 | 08/05/2020 | 1 | Scheduled
18EG00852 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 900943466 | 20/04/2020 | 08/05/2020 | 3 | Scheduled
19LN4865 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | 2018HP-1[136]Check Struct/Found/etc-Base | 900987259 | 20/04/2020 | 08/05/2020 | 4 | Scheduled
17LN2427 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | 2016HP-1[141]Insulator Check on gantry | 900819639 | 20/04/2020 | 08/05/2020 | 3 | Scheduled
18EG00853 | TO-20-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | GORMAN 220 | MAYNOOTH 220 | 1 | 220kV MO Cubicle Ordinary Service | 900943354 | 20/04/2020 | 08/05/2020 | 1 | Scheduled
OD0804 | TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | GORMAN 110 | MEATH HILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 19/03/2020 | 19/03/2020 |  | Scheduled
20EG11324 | TO-20-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | GORMAN 110 | MEATH HILL 110 | 1 | 110kV SF6 Cubicle Operational Test | 901117748 | 19/03/2020 | 19/03/2020 | 4 | Scheduled
OD0170 | TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | GORMAN 110 | NAVAN 110 | 1 | Total Maintenance Outage Duration Requested |  | 18/03/2020 | 18/03/2020 |  | Scheduled
20EG10262 | TO-20-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | GORMAN 110 | NAVAN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129624 | 18/03/2020 | 18/03/2020 | 4 | Scheduled
OD0171 | TO-20-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | GORMAN 110 | NAVAN 110 | 2 | Total Maintenance Outage Duration Requested |  | 02/11/2020 | 06/11/2020 |  | Scheduled
20EG10264 | TO-20-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | GORMAN 110 | NAVAN 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 02/11/2020 | 06/11/2020 | 4 | Scheduled
20EG00511 | TO-20-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | GORMAN 110 | NAVAN 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 02/11/2020 | 06/11/2020 | 4 | Scheduled
OD0172 | TO-20-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | GORMAN 110 | NAVAN 110 | 3 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 13/11/2020 |  | Scheduled
20EG20686 | TO-20-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | GORMAN 110 | NAVAN 110 | 3 | Cable Insp. 110kV XLPE |  | 09/11/2020 | 13/11/2020 | 4 | Scheduled
20EG20727 | TO-20-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | GORMAN 110 | NAVAN 110 | 3 | Cable Insp. 110kV XLPE |  | 09/11/2020 | 13/11/2020 | 4 | Scheduled
OD0173 | TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | GORMAN 110 | PLATIN 110 | 1 | Total Maintenance Outage Duration Requested |  | 20/03/2020 | 20/03/2020 |  | Scheduled
20EG10266 | TO-20-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | GORMAN 110 | PLATIN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129660 | 20/03/2020 | 20/03/2020 | 4 | Scheduled
OD0760 | TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | GORMAN 220 | GORMAN 110 | T2101 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 10/07/2020 |  | Scheduled
20CM0141 | TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | GORMAN 220 | GORMAN 110 | T2101 | Following up the faulty sensor alarm on | 900934390 | 06/07/2020 | 10/07/2020 | 1 | Scheduled
20CM0140 | TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | GORMAN 220 | GORMAN 110 | T2101 | ESBIN01 GE are to supply replacement hyd | 900867380 | 06/07/2020 | 10/07/2020 | 1 | Scheduled
20CM0142 | TO-20-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | GORMAN 220 | GORMAN 110 | T2101 | Replace hydran Sensor | 901059815 | 06/07/2020 | 10/07/2020 | 1 | Scheduled
OD1316 | TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | GORTAWEE 110 | GORTAWEE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 30/09/2020 | 02/10/2020 |  | Scheduled
20EG04060 | TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | GORTAWEE 110 | GORTAWEE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20CM0143 | TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | GORTAWEE 110 | GORTAWEE 110 | 110SA1 | Replace disconnect spindles | 900788599 | 30/09/2020 | 02/10/2020 | 1 | Scheduled
CAPX2020010910460144 | TO-20-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | GORTAWEE 110 | GORTAWEE 110 | 110SA1 | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/09/2020 | 02/10/2020 |  | Scheduled
CAPX2020010910460149 | TO-20-GWE-110SA1-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | GORTAWEE 110 | GORTAWEE 110 | 110SA1 | As a consequence of GWE-110SA2: 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1340 | TO-20-GWE-110SA2-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | GORTAWEE 110 | GORTAWEE 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04061 | TO-20-GWE-110SA2-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | GORTAWEE 110 | GORTAWEE 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460150 | TO-20-GWE-110SA2-02 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | GORTAWEE 110 | GORTAWEE 110 | 110SA2 | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460145 | TO-20-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | GORTAWEE 110 | GORTAWEE 110 | 110SA2 | As a consequence of GWE-110SA1: 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/09/2020 | 02/10/2020 |  | Scheduled
CAPX2020010910460146 | TO-20-GWE-CAP1-01 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | GORTAWEE 110 | GORTAWEE 110 | CAP1 | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/09/2020 | 02/10/2020 |  | Scheduled
OD1375 | TO-20-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | GORTAWEE 110 | GORTAWEE 10 | T101 | Total Maintenance Outage Duration Requested |  | 30/09/2020 | 02/10/2020 |  | Scheduled
19EG10852 | TO-20-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | GORTAWEE 110 | GORTAWEE 10 | T101 | 110kV SF6 Cubicle Operational Test |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
CAPX2020010910460147 | TO-20-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | GORTAWEE 110 | GORTAWEE 10 | T101 | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/09/2020 | 02/10/2020 |  | Scheduled
OD0536 | TO-20-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | Total Maintenance Outage Duration Requested |  | 30/09/2020 | 02/10/2020 |  | Scheduled
19EG10853 | TO-20-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | 110kV SF6 Cubicle Operational Test |  | 30/09/2020 | 02/10/2020 | 4 | Scheduled
20CM0144 | TO-20-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | T102 110kV CB: SF6 Gauge corroded and ne | 901073971 | 30/09/2020 | 02/10/2020 | 1 | Scheduled
CAPX2020010910460151 | TO-20-GWE-T102-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460152 | TO-20-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | GORTAWEE 110 | GORTAWEE 38 | T142 | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010812200082 | TO-20-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200083 | TO-20-110 kV A2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100214515400 | TO-20-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110A2 | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200084 | TO-20-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200085 | TO-20-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100214515401 | TO-20-110 kV B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110B2 | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0830 | TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 28/02/2020 | 27/03/2020 |  | Scheduled
20EG10629 | TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110K1-2 | 110kV Sect / Dist Operational Test |  | 28/02/2020 | 27/03/2020 | 4 | Scheduled
CAPX2019100214515402 | TO-20-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110K1-2 | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019120914343500 | TO-20-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | GREAT ISLAND 110 | GREAT ISLAND 110 | 110K1-2 | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo | CP0894 | 28/02/2020 | 27/03/2020 |  | Scheduled
CAPX2020010812200086 | TO-20-220 kV A1 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220A1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200089 | TO-20-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220A2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200092 | TO-20-220 kV B1 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220B1 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200095 | TO-20-220 kV B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220B2 | Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200093 | TO-20-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220K1 | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200087 | TO-20-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220K1 | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200096 | TO-20-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220K2 | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200090 | TO-20-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220K2 | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020167 | TO-20-GI GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020010812200088 | TO-20-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SA1-2CB | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200091 | TO-20-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SA1-2CB | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200097 | TO-20-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SB1-2CB | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010812200094 | TO-20-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SB1-2CB | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover | BB0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0288 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN4949 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2018HP-1[216]Insulatorbroken insulator | 900987496 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN4950 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2018HP-1[117]Insulatorbroken insulator | 900987495 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18LN2848 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2017HP-1[207]Earths-Check earth bond top | 900898108 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18LN2845 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2017HP-1[196]Earths-Check earth bond top | 900898107 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20CM0429 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | Replacement of Stolen Earths |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG00857 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 901042334 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN7134 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | Repair earth on 24 DC towers | 901050728 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18LN2850 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2017HP-1[214]Vib Damps EW damper fatigue | 900898109 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG05111 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 901042324 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18EG05118 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | Annual Insp. 110kV Feeder XLPE Cable | 901006258 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20LN3499 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2019HP-1[212]Vib Dampers EW VD fatigued | 901085221 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN3498 | TO-20-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | GREAT ISLAND GIS 220 | KELLIS 220 | 1 | 2019HP-1[211]Vib Dampers EW VD fatigued | 901085220 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD0289 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18LN3054 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2017HP-3[73/76]Insul & HW replace check | 900898158 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3534 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[5]Check Structure -Contact E&MP | 901086410 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3533 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[4]Check Structure -Contact E&MP | 901086409 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3678 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[39]Bird Nests remove birds nest | 901084416 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3532 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[3]Check Structure -Contact E&MP | 901086408 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3531 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[2]Check Structure -Contact E&MP | 901086407 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3530 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[1]Check Structure -Contact E&MP | 901086406 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3691 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[68]Bird Nests remove birds nest | 901084418 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN3690 | TO-20-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | GREAT ISLAND GIS 220 | LODGEWOOD 220 | 1 | 2019HP-1[67]Bird Nests remove birds nest | 901084417 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
PROT2020175 | TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS G4 | T2004 | P3 Protection maintenance of 7SA612 |  | 01/10/2020 | 09/10/2020 | 3 | Scheduled
TOP200902160059 | TO-20-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | GREAT ISLAND GIS 220 | GREAT ISLAND GIS G4 | T2004 | Customer outage request for Telemess 01/10-09/10 |  | 01/10/2020 | 09/10/2020 |  | Scheduled
OD0177 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 29/05/2020 |  | Scheduled
20CM0365 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | manometer needs replacing | 901090669 | 25/05/2020 | 29/05/2020 | 1 | Scheduled
20CM0492 | TO-20-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Follow on work to replace stolen earths after copper theft | 901160926 | 07/10/2020 | 15/10/2020 | 1 | Scheduled
20CM0147 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 110kV CTVTs Restest: Sphase .96% PF, TPh | 901068754 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
20EG00526 | TO-20-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 07/10/2020 | 15/10/2020 | 4 | Scheduled
20CM0168 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | surge counter unreadable , gas gauge rot | 901072125 | 25/05/2020 | 29/05/2020 | 1 | Scheduled
19LN5045 | TO-20-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2018HP-1[113]Off Plumb | 900987503 | 07/10/2020 | 15/10/2020 | 4 | Scheduled
19LN5044 | TO-20-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2018HP-1[10]Off Plumb | 900987497 | 07/10/2020 | 15/10/2020 | 4 | Scheduled
19LN5043 | TO-20-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2018HP-1[112]Off Plumb | 900987502 | 07/10/2020 | 15/10/2020 | 4 | Scheduled
20CM0437 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Replacement of Stolen Earths | 901133697 | 25/05/2020 | 29/05/2020 | 1 | Scheduled
CAPX2019100809402300 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Circuit and Bay works at Kilkenny & Great Island | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402309 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1 | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402302 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402306 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402303 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402307 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402311 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1 | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402313 | TO-20-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402315 | TO-20-GI-KKY-1-04 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | EI: Simultaneous GI-KKY-1 + GI-KKY-1: Energisation of circuit | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3515 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[116]Off Plumb -plumb poles | 901084981 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
20LN3514 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[112]Off Plumb -plumb poles | 901084980 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
20LN3511 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[89]Bird Nests remove birds nest | 901084415 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
20LN3503 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[16]Check Structure struct & HW | 901086404 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
CAPX2020010910460153 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/05/2020 | 29/05/2020 |  | Scheduled
20LN3502 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[15]Check Structure struct & HW | 901086403 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
20LN3517 | TO-20-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | GREAT ISLAND 110 | KILKENNY 110 | 1 | 2019HP-1[129]Check Structure -Check Rot | 901086405 | 25/05/2020 | 29/05/2020 | 2 | Scheduled
CAPX2019100809402314 | TO-20-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor | CP0945 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100809402312 | TO-20-GI-T141-02 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1 | CP0945 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100809402310 | TO-20-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1 | CP0945 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019120914343501 | TO-20-GI-T142-02 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T142 | GREAT ISLAND 110 | GREAT ISLAND 38 | T142 | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo | CP0894 | 28/02/2020 | 27/03/2020 |  | Reference
CAPX2019112810154803 | TO-20-GI-T142-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T142 | GREAT ISLAND 110 | GREAT ISLAND 38 | T142 | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section. | CP0894 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0762 | TO-20-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | Total Maintenance Outage Duration Requested |  | 09/11/2020 | 10/11/2020 |  | Scheduled
19CM0117 | TO-20-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | Camlin is to replace faulty transformer online oil DGA monitor on T2101 in Gt Island station. | 901038643 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
18EG11088 | TO-20-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | 220/110 & 275/220 Trafo Operational Test |  | 09/11/2020 | 10/11/2020 | 3 | Scheduled
19CM0106 | TO-20-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | CREST Analysis of Paint Samples on T2101 220kV Station. | 901028698 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG11090 | TO-20-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | 110kV SF6 Cubicle Operational Test |  | 09/11/2020 | 10/11/2020 | 4 | Scheduled
20CM0146 | TO-20-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | LOWER FAN BOX FIXING BROKEN....FIX | 900943754 | 09/11/2020 | 10/11/2020 | 2 | Scheduled
20EG20729 | TO-20-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2101 | Cable Insp. 220kV Feeder XLPE |  | 09/11/2020 | 10/11/2020 | 4 | Scheduled
OD0763 | TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2102 | Total Maintenance Outage Duration Requested |  | 28/02/2020 | 27/03/2020 |  | Scheduled
19CM0098 | TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2102 | Great Island T2102:Replace faulty oil level gauge Replace all fans Retest overall tan deltas Treat corrosion | 901039261 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
19EG01911 | TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 28/02/2020 | 27/03/2020 | 4 | Scheduled
CAPX2019100214515403 | TO-20-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2102 | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019120914343502 | TO-20-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | GREAT ISLAND GIS 220 | GREAT ISLAND 110 | T2102 | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo | CP0894 | 28/02/2020 | 27/03/2020 |  | Scheduled
17LN3684 | TO-20-GI-WAT-1-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | GREAT ISLAND 110 | WATERFORD 110 | 1 | Check (General)-Painting Req. Tower 50 & 51 | 900853147 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
16LN2050 | TO-20-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | GREAT ISLAND 110 | WATERFORD 110 | 1 | 2015HP-1[37]Off Plumb Pole | 900727280 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD0179 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | Total Maintenance Outage Duration Requested |  | 28/02/2020 | 27/03/2020 |  | Scheduled
OD1242 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | Total Maintenance Outage Duration Requested |  | 28/02/2020 | 27/03/2020 |  | Scheduled
15LN1487 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[11]Off Plumb | 900650531 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
19EG10274 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 110kV SF6 Cubicle Operational Test | 901038787 | 28/02/2020 | 27/03/2020 | 4 | Scheduled
15LN1492 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[26]Check Structure split in RHP | 900650536 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
15LN1490 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[16]Off Plumb | 900650534 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
15LN1489 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[15]Off Plumb | 900650533 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
15LN1488 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[14]Off Plumb | 900650532 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
19EG10275 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 110kV SF6 Cubicle Operational Test | 901038982 | 28/02/2020 | 27/03/2020 | 4 | Scheduled
15LN1493 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[27]Check Structure split in RHP | 900650537 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
15LN1500 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2014HP-1[8]Off Plumb | 900650529 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
15LN3980 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 1[50] Insulators Off Plumb | 900683451 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
CAPX2019100214515404 | TO-20-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100809402308 | TO-20-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3721 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2019HP-1[11]Off Plumb -plumb poles | 901084982 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
CAPX20200109104601127 | TO-20-GI-WAT-2-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3722 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2019HP-1[18]Insul&HW Replac check | 901085556 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
CAPX2019100809402304 | TO-20-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point | CP0945 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3723 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 2019HP-1[19]Insul&HW Replac check | 901085557 | 28/02/2020 | 27/03/2020 | 2 | Scheduled
CAPX2019120914343503 | TO-20-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | GREAT ISLAND 110 | WATERFORD 110 | 2 | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo | CP0894 | 28/02/2020 | 27/03/2020 |  | Scheduled
OD1239 | TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | GREAT ISLAND 110 | WEXFORD 110 | 1 | Total Maintenance Outage Duration Requested |  | 28/02/2020 | 27/03/2020 |  | Scheduled
20EG10276 | TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | GREAT ISLAND 110 | WEXFORD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129619 | 28/02/2020 | 27/03/2020 | 4 | Scheduled
20EG10277 | TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | GREAT ISLAND 110 | WEXFORD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129640 | 28/02/2020 | 27/03/2020 | 4 | Scheduled
CAPX2019120914343504 | TO-20-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | GREAT ISLAND 110 | WEXFORD 110 | 1 | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo | CP0894 | 28/02/2020 | 27/03/2020 |  | Scheduled
CAPX2019100214515405 | TO-20-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | GREAT ISLAND 110 | WEXFORD 110 | 1 | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section. | CP0894 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113155637 | TO-20-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | GRIFFINRATH 110 | GRIFFINRATH 38 | T141 | Full tee out for GRIFFINRATH tee-GRANGE CASTLE out |  | 27/10/2020 | 28/10/2020 |  | Reference (Tentative)
CAPX2020010910351127 | TO-20-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | GRIFFINRATH 110 | GRIFFINRATH 38 | T141 | As a consequence of GRI,T-GRI-1: GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0175 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 28/10/2020 |  | Tentative
19LN4930 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | 2018HP-1[41]Check Struct/Found/etc-Base | 900987375 | 27/10/2020 | 28/10/2020 | 4 | Tentative
19LN4929 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | 2018HP-1[32]Check Struct/Found/etc-Base | 900987374 | 27/10/2020 | 28/10/2020 | 4 | Tentative
19LN4928 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | 2018HP-1[1]Check Struct/Found/etc-Base | 900987373 | 27/10/2020 | 28/10/2020 | 4 | Tentative
17LN2473 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | 2016HP-39[1-39]Check-General Tower paint | 900819656 | 27/10/2020 | 28/10/2020 | 2 | Tentative
11LN1245 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | 4[6,23,27,34]Repair damaged member | 900331371 | 27/10/2020 | 28/10/2020 | 1 | Tentative
20EG20046 | TO-20-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | Cable Insp. 110kV XLPE |  | 27/10/2020 | 28/10/2020 | 4 | Tentative
CAPX2020010910351128 | TO-20-GRI,T-GCA-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | GRIFFINRATH tee | GRANGE CASTLE 110 | 1 | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201001164930 | TO-20-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | GRIFFINRATH tee | GRIFFINRATH 110 | 1 | as a consequence of: Full tee out for GRIFFINRATH tee-GRANGE CASTLE out |  | 27/10/2020 | 28/10/2020 |  | Tentative
CAPX2020010910351129 | TO-20-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | GRIFFINRATH tee | GRIFFINRATH 110 | 1 | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113155514 | TO-20-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | GRIFFINRATH tee | MAYNOOTH 110 | 1 | Full tee out for GRIFFINRATH tee-GRANGE CASTLE out |  | 27/10/2020 | 28/10/2020 |  | Tentative
OD0902 | TO-20-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | GRIFFINRATH tee | MAYNOOTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 28/10/2020 |  | Tentative
19EG10269 | TO-20-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | GRIFFINRATH tee | MAYNOOTH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901039026 | 27/10/2020 | 28/10/2020 | 4 | Tentative
CAPX2020010910351130 | TO-20-GRI,T-MAY-1-02 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | GRIFFINRATH tee | MAYNOOTH 110 | 1 | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0656 | TO-20-HN-T2002-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | HUNTSTOWN 220 | HUNTSTOWN G2 | T2002 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01666 | TO-20-HN-T2002-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | HUNTSTOWN 220 | HUNTSTOWN G2 | T2002 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20357 | TO-20-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | HUNTSTOWN 220 | HUNTSTOWN G2 | T2002 | Cable Insp. 400 & 220kV Feeder XLPE |  | 03/09/2020 | 04/09/2020 | 4 | Tentative
OD0655 | TO-20-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | HUNTSTOWN 220 | HUNTSTOWN G10/11 | T2010/11 | Total Maintenance Outage Duration Requested |  | 17/09/2020 | 17/11/2020 |  | Scheduled
20EG10960 | TO-20-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | HUNTSTOWN 220 | HUNTSTOWN G10/11 | T2010/11 | 220kV SF6 Cubicle Operational Test |  | 17/09/2020 | 17/11/2020 | 4 | Scheduled
20EG20356 | TO-20-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | HUNTSTOWN 220 | HUNTSTOWN G10/11 | T2010/11 | Cable Insp. 400 & 220kV Feeder XLPE |  | 17/09/2020 | 17/11/2020 | 4 | Scheduled
TOP200303104926 | TO-20-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | IKERRIN 110 | IKERRIN 38 | T141 | Proximity outage for IKE-THU |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020090910010616 | TO-20-IKE-T141-02 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | IKERRIN 110 | IKERRIN 38 | T141 | As a consequence of IKE,T-IKE-1: IKE-SH-THU-1: Proximity outage to cross OHL | CP1057 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200303104834 | TO-20-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | IKERRIN tee | IKERRIN 110 | 1 | Proximity outage for IKE-THU |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020090910010617 | TO-20-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | IKERRIN tee | IKERRIN 110 | 1 | IKE-SH-THU-1: Proximity outage to cross OHL | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020090910010618 | TO-20-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | IKERRIN tee | SHANNONBRIDGE 110 | 1 | IKE-SH-THU-1: Proximity outage to cross OHL | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200303104654 | TO-20-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | IKERRIN tee | SHANNONBRIDGE 110 | 1 | Proximity outage for IKE-THU |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020093 | TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | IKERRIN tee | THURLES 110 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020090910010619 | TO-20-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | IKERRIN tee | THURLES 110 | 1 | IKE-SH-THU-1: Proximity outage to cross OHL | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0183 | TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | IKERRIN tee | THURLES 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10279 | TO-20-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | IKERRIN tee | THURLES 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351153 | TO-20-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | IKERRIN tee | THURLES 110 | 1 | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200716170222 | TO-20-220 kV A6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | INCHICORE 220 | INCHICORE 220 | 220A6 | A6/B6 busbars in turn |  | 17/08/2020 | 11/09/2020 |  | Scheduled
TOP200716170350 | TO-20-220 kV B6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | INCHICORE 220 | INCHICORE 220 | 220B6 | A6/B6 busbars in turn |  | 17/08/2020 | 11/09/2020 |  | Scheduled
PROT2020058 | TO-20-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | INCHICORE 220 | INCHICORE 220 | 220K1-2 | P2 Protection maintenance of ISM21 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD0404 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | Total Maintenance Outage Duration Requested |  | 20/10/2020 | 22/10/2020 |  | Scheduled
PROT2020059 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | P2 Protection maintenance of 7SJ511 |  | 20/10/2020 | 22/10/2020 | 2 | Scheduled
19CM0019 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | CB counter needs replacing | 900977717 | 20/10/2020 | 22/10/2020 | 2 | Scheduled
19EG10647 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | 220kV Sect / Dist Operational Test |  | 20/10/2020 | 22/10/2020 | 4 | Scheduled
19EG10646 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | 220kV Sect / Dist Operational Test | 901076478 | 20/10/2020 | 22/10/2020 | 4 | Scheduled
19EG10645 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | 220kV GIS Cubicle Operational Test | 901076460 | 20/10/2020 | 22/10/2020 | 4 | Scheduled
19EG10644 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | 220kV Sect / Dist Operational Test | 901076479 | 20/10/2020 | 22/10/2020 | 4 | Scheduled
19EG10643 | TO-20-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | INCHICORE 220 | INCHICORE 220 | 220K2-4 | 220kV Sect / Dist Operational Test | 901076477 | 20/10/2020 | 22/10/2020 | 4 | Scheduled
OD0405 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02235 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02236 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02279 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02280 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02281 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02283 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02278 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02282 | TO-20-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | INCHICORE 220 | INCHICORE 220 | 220K4-6 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020009 | TO-20-INC-ISH-1-02 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | P1 Protection maintenance of 7SA513, REL551 |  | 27/10/2020 | 30/10/2020 | 1 | Tentative
PROT2020010 | TO-20-INC-ISH-1-02 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | P1 Protection maintenance of 7SA513, REL551 |  | 27/10/2020 | 30/10/2020 | 1 | Tentative
OD0290 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00861 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0150 | TO-20-INC-ISH-1-02 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | Inchicore Eirgrid RTU: MW, MVAr on the | 900390350 | 27/10/2020 | 30/10/2020 | 2 | Tentative
20CM0443 | TO-20-INC-ISH-1-02 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | Repair Sf6 leak |  | 27/10/2020 | 30/10/2020 | 1 | Tentative
20EG00860 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00862 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00863 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100408430700 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | Installation of ducting | CP0692 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20154 | TO-20-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | INCHICORE 220 | IRISHTOWN 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0292 | TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | INCHICORE 220 | MAYNOOTH 220 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02334 | TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | INCHICORE 220 | MAYNOOTH 220 | 2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02333 | TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | INCHICORE 220 | MAYNOOTH 220 | 2 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101412303803 | TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | INCHICORE 220 | MAYNOOTH 220 | 2 | Erect cable sealing ends, complete remote end works, loop-in Castlebagot Station to Inchicore-Maynooth 2 (EI will be required) - This will re-energise as CBT - May 2 and CBT - Inch 2 | CP0872 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010713331507 | TO-20-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | INCHICORE 220 | MAYNOOTH 220 | 2 | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required | CP0872 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0293 | TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | INCHICORE 220 | POOLBEG 220 | 1 | Total Maintenance Outage Duration Requested |  | 28/09/2020 | 09/10/2020 |  | Scheduled
PROT2020124 | TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | INCHICORE 220 | POOLBEG 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 28/09/2020 | 09/10/2020 | 3 | Scheduled
20EG20159 | TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | INCHICORE 220 | POOLBEG 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 901129050 | 28/09/2020 | 09/10/2020 | 4 | Scheduled
CAPX2019100408430701 | TO-20-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | INCHICORE 220 | POOLBEG 220 | 1 | Installation of ducting | CP0692 | 28/09/2020 | 09/10/2020 |  | Scheduled
OD0294 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 23/10/2020 |  | Scheduled
PROT2020123 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 12/10/2020 | 23/10/2020 | 3 | Scheduled
19EG10451 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | 220kV SF6 Cubicle Operational Test | 901068550 | 12/10/2020 | 23/10/2020 | 4 | Scheduled
19EG10452 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | 220kV GIS Cubicle Operational Test | 901039093 | 12/10/2020 | 23/10/2020 | 4 | Scheduled
CAPX2019100408430702 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | Installation of ducting | CP0692 | 12/10/2020 | 23/10/2020 |  | Scheduled
20EG20172 | TO-20-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | INCHICORE 220 | POOLBEG 220 | 2 | Annual Insp. 400 & 220 Feeder OF Cable |  | 12/10/2020 | 23/10/2020 | 4 | Scheduled
PROT2020014 | TO-20-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | INCHICORE 220 | INCHICORE 110 | T2102 | P1 Protection maintenance of 7SA511, R1Z23b, ISM21 |  | 31/07/2020 | 31/07/2020 | 1 | Reference
PROT2020149 | TO-20-INC-T2104-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2104 | INCHICORE 220 | INCHICORE 110 | T2104 | P3 Protection maintenance of 7SA511, 7SA511, 7UT512 |  | 25/12/2500 | 25/12/2500 | 3 | Reference (Unscheduled)
PROT2020180 | TO-20-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | INCHICORE 220 | INCHICORE 110 | T2106 | P3 Protection maintenance of 7SA612 |  | 13/07/2020 | 24/07/2020 | 3 | Reference
OD1361 | TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | INCHICORE 220 | INCHICORE 110 | T2106 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 24/07/2020 |  | Reference
20EG02349 | TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | INCHICORE 220 | INCHICORE 110 | T2106 | 220kV GIS Cubicle Ordinary Service |  | 13/07/2020 | 24/07/2020 | 4 | Reference
20EG02348 | TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | INCHICORE 220 | INCHICORE 110 | T2106 | 220KV CUBICLE CONDITION ASSESSMENT |  | 13/07/2020 | 24/07/2020 | 4 | Reference
20CM0363 | TO-20-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | INCHICORE 220 | INCHICORE 110 | T2106 | Low Gas / Leak- REPAIR SF6 LEAK | 901084736 | 13/07/2020 | 24/07/2020 | 1 | Reference
PROT2020051 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | P2 Protection maintenance of REL521 |  | 08/06/2020 | 12/06/2020 | 2 | Scheduled
OD0184 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | Total Maintenance Outage Duration Requested |  | 08/06/2020 | 12/06/2020 |  | Scheduled
19LN5168 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | "2018HP-4[22,24,52,58]Off Plumb-Poles" | 900987656 | 08/06/2020 | 12/06/2020 | 4 | Scheduled
20EG00545 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 08/06/2020 | 12/06/2020 | 4 | Scheduled
20EG10281 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 08/06/2020 | 12/06/2020 | 4 | Scheduled
19LN5169 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | "2018HP-3[59,60,64]Off PlumbPlumb poles" | 900987657 | 08/06/2020 | 12/06/2020 | 4 | Scheduled
20CM0222 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | O1-Moisture in Inniscarra 110kv Lighteni | 901059059 | 08/06/2020 | 12/06/2020 | 2 | Scheduled
20CM0221 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 01-Surge Counter Covers Needs replacing | 901028589 | 08/06/2020 | 12/06/2020 | 2 | Scheduled
CAPX2019102112121225 | TO-20-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN3754 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 2019HP-5[22,46,47,57,59]Off Plumb | 901084983 | 08/06/2020 | 12/06/2020 | 2 | Scheduled
20LN3752 | TO-20-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 2019HP-1[91]Vib Dampers Replace EW VD | 901085222 | 08/06/2020 | 12/06/2020 | 2019 - Urgent | Scheduled
CAPX2019100210345714 | TO-20-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345702 | TO-20-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | INNISCARRA 110 | MACROOM 110 | 1 | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0657 | TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | INNISCARRA 110 | INNISCARRA G1 | T101 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 18/05/2020 | 2 | Scheduled
20EG10962 | TO-20-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | INNISCARRA 110 | INNISCARRA G1 | T101 | 110KV SF6 Cubicle Operational Test |  | 18/05/2020 | 18/05/2020 | 4 | Scheduled
OD0406 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02530 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02284 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01151 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02531 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02175 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02174 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG23787 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV GIS Busbar Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01150 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01152 | TO-20-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | IRISHTOWN 220 | IRISHTOWN 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465532 | TO-20-ISH-SHL-1-02 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | Proximity outage for work on Shellybanks 220kV D2/CB1 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0295 | TO-20-ISH-SHL-1-03 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465536 | TO-20-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | Proximity outage for work on Shellybanks 220kV D2/CB2 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00881 | TO-20-ISH-SHL-1-03 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0158 | TO-20-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | Circuit Breaker to be timed | 900977047 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG20181 | TO-20-ISH-SHL-1-03 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | IRISHTOWN 220 | SHELLYBANKS 220 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200525140418 | TO-20-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | KELLIS 110 | KELLIS 110 | 110A1 | Busbar Changeover | BB0000 | 30/07/2020 | 30/07/2020 |  | Scheduled
TOP200525140513 | TO-20-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | KELLIS 110 | KELLIS 110 | 110A2 | Busbar Changeover | BB0000 | 30/07/2020 | 30/07/2020 |  | Scheduled
TOP200525140602 | TO-20-110 kV B1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | KELLIS 110 | KELLIS 110 | 110B1 | Busbar Changeover | BB0000 | 30/07/2020 | 30/07/2020 |  | Scheduled
TOP200525140656 | TO-20-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | KELLIS 110 | KELLIS 110 | 110B2 | Busbar Changeover | BB0000 | 30/07/2020 | 30/07/2020 |  | Scheduled
OD0408 | TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | KELLIS 220 | KELLIS 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 22/06/2020 | 23/06/2020 |  | Scheduled
20EG10657 | TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | KELLIS 220 | KELLIS 220 | 220K1-2 | 220kV SF6 Cubicle Operational Test | 901129547 | 22/06/2020 | 23/06/2020 | 4 | Scheduled
20CM0159 | TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | KELLIS 220 | KELLIS 220 | 220K1-2 | CB door broken | 901076101 | 22/06/2020 | 23/06/2020 | 1 | Scheduled
20EG10656 | TO-20-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | KELLIS 220 | KELLIS 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901130124 | 22/06/2020 | 23/06/2020 | 4 | Scheduled
PROT2020094 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 18/05/2020 | 22/05/2020 | 3 | Scheduled
PROT2020099 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 18/05/2020 | 22/05/2020 | 3 | Scheduled
TOP191118154341 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | H3/H4 cubicle ordinary service |  | 18/05/2020 | 22/05/2020 |  | Scheduled
OD0185 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 22/05/2020 |  | Scheduled
20CM0169 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | surge counters wet inside , cables not s | 901072127 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
20CM0160 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | H4 moisture in surge counters | 901076103 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
19EG00550 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042232 | 18/05/2020 | 22/05/2020 | 1 | Scheduled
19EG00549 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042231 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
19LN5180 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | 2018HP-1[144]Off Plumb | 900987666 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20LN3767 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | 2019HP-1[51]Off Plumb -plumb poles | 901084984 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20LN3777 | TO-20-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | KELLIS 110 | KILKENNY 110 | 1 | 2019HP-1[125]Off Plumb -plumb poles | 901084985 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
OD1388 | TO-20-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0768 | TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | Total Maintenance Outage Duration Requested |  | 23/03/2020 | 27/03/2020 |  | Scheduled
19CM0159 | TO-20-KLS-T2101-04 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | ABB required to overhaul CB poles for gas leak repair work | 901068451 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0161 | TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | Bund Leaking | 901036845 | 23/03/2020 | 27/03/2020 | 1 | Scheduled
18EG11098 | TO-20-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | 220/110 & 275/220 Trafo Operational Test | 901045352 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG11099 | TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | 110kV SF6 Cubicle Operational Test | 901038905 | 23/03/2020 | 27/03/2020 | 3 | Scheduled
20CM0469 | TO-20-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | R,S & T Phases T2101 220kV Cubicle. R, S & T Phase CT internal links, heating appearing internally, possible corrosion/poor connection. DUE : 17-Nov-20 | 901134788 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0449 | TO-20-KLS-T2101-03 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | R & S Phase T2101 110kV Bushing. R & S Phase connection hotspot DUE : IMMEDIATELY | 901134787 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
18EG11097 | TO-20-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | KELLIS 220 | KELLIS 110 | T2101 | 220kV SF6 Cubicle Operational Test | 901038901 | 23/03/2020 | 27/03/2020 | 3 | Scheduled
OD0769 | TO-20-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | KELLIS 220 | KELLIS 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11100 | TO-20-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | KELLIS 220 | KELLIS 110 | T2102 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11101 | TO-20-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | KELLIS 220 | KELLIS 110 | T2102 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11102 | TO-20-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | KELLIS 220 | KELLIS 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200525135658 | TO-20-110 kV A1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | KILBARRY 110 | KILBARRY 110 | 110A1 | Busbar Changeover | BB0000 | 22/10/2020 | 22/10/2020 |  | Scheduled
CAPX2019102114125104 | TO-20-110 kV A1 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | KILBARRY 110 | KILBARRY 110 | 110A1 | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning | CP1037 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102114125102 | TO-20-110 kV A1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | KILBARRY 110 | KILBARRY 110 | 110A1 | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning | CP1037 | 17/08/2020 | 11/09/2020 |  | Scheduled
TOP200525135816 | TO-20-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | KILBARRY 110 | KILBARRY 110 | 110A2 | Busbar Changeover | BB0000 | 22/10/2020 | 22/10/2020 |  | Scheduled
TOP200525135910 | TO-20-110 kV B1 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | KILBARRY 110 | KILBARRY 110 | 110B1 | Busbar Changeover | BB0000 | 22/10/2020 | 22/10/2020 |  | Scheduled
CAPX2019102114125103 | TO-20-110 kV B1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | KILBARRY 110 | KILBARRY 110 | 110B1 | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning | CP1037 | 17/08/2020 | 11/09/2020 |  | Scheduled
CAPX2019102114125105 | TO-20-110 kV B1 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | KILBARRY 110 | KILBARRY 110 | 110B1 | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning | CP1037 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200525140016 | TO-20-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | KILBARRY 110 | KILBARRY 110 | 110B2 | Busbar Changeover | BB0000 | 22/10/2020 | 22/10/2020 |  | Scheduled
TOP200713155142 | TO-20-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | KILBARRY 110 | KILBARRY 110 | 110K1-2 | Proiximity for placement of 38kV cables (HI2192_Kilbarry_38kV Asset Replacement) | PROX | 17/08/2020 | 28/08/2020 |  | Scheduled
PROT2020096 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | P3 Protection maintenance of 7SA511, REL521 |  | 14/04/2020 | 21/04/2020 | 3 | Scheduled
OD0186 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/04/2020 | 21/04/2020 |  | Scheduled
PROT2020095 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | P3 Protection maintenance of 7SA511, REL521 |  | 14/04/2020 | 21/04/2020 | 3 | Scheduled
19EG00553 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | 110kV MO Cubicle Ordinary Service | 901050330 | 14/04/2020 | 21/04/2020 | 4 | Scheduled
19EG00555 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901038491 | 14/04/2020 | 21/04/2020 | 4 | Scheduled
19LN5205 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | "2018HP-2[50,57]Off PlumbPlumb poles" | 900987690 | 14/04/2020 | 21/04/2020 | 4 | Scheduled
19LN5207 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | 2018HP-1[61]Replace Pole only | 900987688 | 14/04/2020 | 21/04/2020 | 4 | Scheduled
18EG10285 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | 110kV SF6 Cubicle Operational Test | 900942501 | 14/04/2020 | 21/04/2020 | 3 | Scheduled
20LN3799 | TO-20-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | 2019HP-1[60]Replace Pole only -Rot | 901086433 | 14/04/2020 | 21/04/2020 | 1 | Scheduled
20LN5193 | TO-20-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | Replace Pole No 45 due to Lightening Damage | 901128776 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5192 | TO-20-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | KILBARRY 110 | KNOCKRAHA 110 | 1 | Replace Pole No 42 due to lightening damage | 901128775 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD0187 | TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | KILBARRY 110 | KNOCKRAHA 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0164 | TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | KILBARRY 110 | KNOCKRAHA 110 | 2 | O1- T lightening arrester -Arcing Horns | 900938041 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0183 | TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | KILBARRY 110 | KNOCKRAHA 110 | 2 | Replace Bay Singnage | 901058701 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0165 | TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | KILBARRY 110 | KNOCKRAHA 110 | 2 | O1-Wire P.F. to next available contact. | 901061010 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0184 | TO-20-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | KILBARRY 110 | KNOCKRAHA 110 | 2 | O1-Change Signage on DL and DE | 901061013 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD0188 | TO-20-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | KILBARRY 110 | MALLOW 110 | 1 | Total Maintenance Outage Duration Requested |  | 04/06/2020 | 04/06/2020 |  | Scheduled
20EG10289 | TO-20-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | KILBARRY 110 | MALLOW 110 | 1 | 110kV MO Cubicle Operational Test | 901129483 | 04/06/2020 | 04/06/2020 | 4 | Scheduled
OD0189 | TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | KILBARRY 110 | MARINA 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 10/03/2020 |  | Scheduled
PROT2020098 | TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | KILBARRY 110 | MARINA 110 | 1 | P3 Protection maintenance of 7SA612, GRZ100 |  | 24/02/2020 | 10/03/2020 | 3 | Scheduled
PROT2020097 | TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | KILBARRY 110 | MARINA 110 | 1 | P3 Protection maintenance of 7SA511, REL521 |  | 24/02/2020 | 10/03/2020 | 3 | Scheduled
19EG10290 | TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | KILBARRY 110 | MARINA 110 | 1 | 110kV MO Cubicle Operational Test | 901050280 | 24/02/2020 | 10/03/2020 | 4 | Scheduled
20EG20051 | TO-20-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | KILBARRY 110 | MARINA 110 | 1 | Cable Insp. 110kV XLPE |  | 24/02/2020 | 10/03/2020 | 4 | Scheduled
OD0190 | TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | KILBARRY 110 | MARINA 110 | 2 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 10/03/2020 |  | Scheduled
20EG20064 | TO-20-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | KILBARRY 110 | MARINA 110 | 2 | Cable Insp. 110kV XLPE |  | 24/02/2020 | 10/03/2020 | 4 | Scheduled
TOP200727153641 | TO-20-KBY-T142-01 | DISTRIBUTION TRANSFORMER - KILBARRY 110-KILBARRY 38-T142 | KILBARRY 110 | KILBARRY 38 | T142 | Proximity for Kilbarry K1-2 |  | 17/08/2020 | 28/08/2020 |  | Reference
CAPX2020010910460154 | TO-20-KKY-110SA1-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | KILKENNY 110 | KILKENNY 110 | 110SA1 | As a consequence of KKY-110SA2: 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/05/2020 | 27/05/2020 |  | Scheduled
OD1317 | TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | KILKENNY 110 | KILKENNY 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 27/05/2020 |  | Scheduled
20CM0435 | TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | KILKENNY 110 | KILKENNY 110 | 110SA2 | Replacement of Stolen Earths | 901133696 | 25/05/2020 | 27/05/2020 | 1 | Scheduled
20EG04063 | TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | KILKENNY 110 | KILKENNY 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/05/2020 | 27/05/2020 | 4 | Scheduled
CAPX2020010910460155 | TO-20-KKY-110SA2-05 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | KILKENNY 110 | KILKENNY 110 | 110SA2 | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/05/2020 | 27/05/2020 |  | Scheduled
OD1373 | TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | KILKENNY 110 | KILKENNY 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 29/05/2020 |  | Scheduled
20CM0364 | TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | KILKENNY 110 | KILKENNY 110 | CAP2 | AC and DC Supplies:Carry out wiring mods | 901083041 | 25/05/2020 | 29/05/2020 | 1 | Scheduled
20CM0436 | TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | KILKENNY 110 | KILKENNY 110 | CAP2 | Replacement of Stolen Earths |  | 25/05/2020 | 29/05/2020 | 1 | Scheduled
CAPX2020010910460156 | TO-20-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | KILKENNY 110 | KILKENNY 110 | CAP2 | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/05/2020 | 29/05/2020 |  | Scheduled
CAPX2020010910460157 | TO-20-KKY-T142-03 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | KILKENNY 110 | KILKENNY 38 | T142 | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/05/2020 | 27/05/2020 |  | Reference
OD0894 | TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | KILL HILL 110 | KILL HILL 33 | T131 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 04/09/2020 |  | Scheduled
20EG02541 | TO-20-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | KILL HILL 110 | KILL HILL 33 | T131 | 110kV SF6 Cubicle Ordinary Service |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
OD0868 | TO-20-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | KILL HILL 110 | THURLES 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10096 | TO-20-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | KILL HILL 110 | THURLES 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02543 | TO-20-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | KILL HILL 110 | THURLES 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0296 | TO-20-KLN-KRA-1-05 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 17/11/2020 |  | Scheduled
CAPX2020021410064825 | TO-20-KLN-KRA-1-04 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020021410064843 | TO-20-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020060310121319 | TO-20-KLN-KRA-1-02 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN5310 | TO-20-KLN-KRA-1-05 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | 2018HP-1[40]ACGFit ACG | 900987793 | 16/11/2020 | 17/11/2020 | 4 | Scheduled
19LN5288 | TO-20-KLN-KRA-1-05 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | "2018HP-3[173,174,175]Stud RailingRepair | 900987776 | 16/11/2020 | 17/11/2020 | 4 | Scheduled
20LN3913 | TO-20-KLN-KRA-1-05 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | 2019HP-1[178]Insulator broken disc | 901084917 | 16/11/2020 | 17/11/2020 | 2 | Scheduled
CAPX2019101409072006 | TO-20-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | KILLONAN 220 | KNOCKRAHA 220 | 1 | EI: Install base(s) for post insulator(s) Post curing time - erect steel + post insulator(s) Line transfer, and tubular uprate and civil works on Killonan bay. | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081315594402 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage | CP0624 | 31/08/2020 | 06/11/2020 |  | Scheduled
OD0192 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | Total Maintenance Outage Duration Requested |  | 31/08/2020 | 06/11/2020 |  | Scheduled
20EG10296 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | 110kV Air Blast Cubicle Operational Test |  | 31/08/2020 | 06/11/2020 | 4 | Scheduled
18EG00574 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 900948291 | 31/08/2020 | 06/11/2020 | 3 | Scheduled
20CM0198 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | Low Gas / Leak | 901078074 | 31/08/2020 | 06/11/2020 | 1 | Scheduled
CAPX2020010910460166 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 31/08/2020 | 06/11/2020 |  | Scheduled
CAPX2019100209112201 | TO-20-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | KILLONAN 110 | LIMERICK 110 | 1 | EI: Line diversion work to enable construction of GIS building | CP0624 | 31/08/2020 | 06/11/2020 |  | Scheduled
CAPX2020081315594403 | TO-20-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage | CP0624 | 18/09/2020 | 23/09/2020 |  | Scheduled
TOP200909151413 | TO-20-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | Fix Disconnect on Killonan Limerick 2 |  | 18/09/2020 | 23/09/2020 |  | Scheduled
OD0193 | TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 28/08/2020 |  | Scheduled
19EG00578 | TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | 110kV SF6 Cubicle Ordinary Service | 901042304 | 24/02/2020 | 28/08/2020 | 4 | Scheduled
20LN5290 | TO-20-KLN-LIM-2-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | 2019LP-1[25]Replace Pole - Pole Rot | 901126082 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100209112200 | TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | EI: Line diversion work to enable construction of GIS building | CP0624 | 24/02/2020 | 28/08/2020 |  | Scheduled
20EG20074 | TO-20-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | Cable Insp. 110kV XLPE | 901129154 | 24/02/2020 | 28/08/2020 | 4 | Scheduled
CAPX2020010910331711 | TO-20-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | KILLONAN 110 | LIMERICK 110 | 2 | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 18/09/2020 | 23/09/2020 |  | Scheduled
PROT2020004 | TO-20-KLN-NEN-1-01 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | KILLONAN 110 | NENAGH 110 | 1 | P1 Protection maintenance of 7SA612, REL521 |  | 25/12/2500 | 25/12/2500 | 1 | Reference (Unscheduled)
TOP200831134439 | TO-20-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | Studied proximity CP1058 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020011 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | P1 Protection maintenance of 7SA513, REL521 |  | 11/05/2020 | 28/05/2020 | 1 | Scheduled
15EG00890 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 220kV Cubicle Condition Assessment | 900775936 | 11/05/2020 | 28/05/2020 | 1 | Scheduled
20CM0172 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | Pressure Vessel Statutory Inspection | 901045697 | 11/05/2020 | 28/05/2020 | 1 | Scheduled
17EG00887 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 220kV Air Blast Cubicle Ordinary Service | 900858887 | 11/05/2020 | 28/05/2020 | 2 | Scheduled
19EG10458 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 220kV SF6 Cubicle Operational Test |  | 11/05/2020 | 28/05/2020 | 4 | Scheduled
19EG00889 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 220kV Cubicle Condition Assessment | 901038533 | 11/05/2020 | 28/05/2020 | 4 | Scheduled
19LN0662 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 1[57]Repairs of damaged members on Tower | 900978885 | 11/05/2020 | 28/05/2020 | 1 | Scheduled
12LN2366 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 1[180]Fit anti climb device | 900404035 | 11/05/2020 | 28/05/2020 | 1 | Scheduled
19EG10457 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 220kV Air Blast Cubicle Operational Test |  | 11/05/2020 | 28/05/2020 | 4 | Scheduled
20LN3976 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 2019HP-1[240]Insulator broken insulator | 901084919 | 11/05/2020 | 28/05/2020 | 4 | Scheduled
20LN3960 | TO-20-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | KILLONAN 220 | SHANNONBRIDGE 220 | 1 | 2019HP-1[22]Insulator broken insulator | 901084918 | 11/05/2020 | 28/05/2020 | 4 | Scheduled
OD0195 | TO-20-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | KILLONAN 110 | SINGLAND 110 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 20/11/2020 |  | Scheduled
TOP201022145125 | TO-20-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | KILLONAN 110 | SINGLAND 110 | 1 | Proximity outage for CA on Singland T101 |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG00582 | TO-20-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | KILLONAN 110 | SINGLAND 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
OD0770 | TO-20-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | KILLONAN 220 | KILLONAN 110 | T2101 | Total Maintenance Outage Duration Requested |  | 22/09/2020 | 24/09/2020 |  | Scheduled
20EG11104 | TO-20-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | KILLONAN 220 | KILLONAN 110 | T2101 | 220kV Air Blast Cubicle Operational Test |  | 22/09/2020 | 24/09/2020 | 4 | Scheduled
20EG11105 | TO-20-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | KILLONAN 220 | KILLONAN 110 | T2101 | 220/110 & 275/220 Trafo Operational Test |  | 22/09/2020 | 24/09/2020 | 4 | Scheduled
20EG20585 | TO-20-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | KILLONAN 220 | KILLONAN 110 | T2101 | Annual Insp. 110kV Station OF Cable |  | 22/09/2020 | 24/09/2020 | 4 | Scheduled
OD0771 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 28/08/2020 |  | Scheduled
20EG01944 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 110kV Air Blast Cubicle Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01943 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 110kV Air Blast Cubicle Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01945 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 220/110 & 275/220 - Ordinary Service |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01946 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01947 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 220KV CUBICLE CONDITION ASSESSMENT |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01948 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG01949 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | 220/110kV Trafo Tap Changer Inspection |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
20EG20598 | TO-20-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | Annual Insp. 110kV Station OF Cable |  | 10/08/2020 | 28/08/2020 | 4 | Scheduled
OD0899 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020040 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | P2 Protection maintenance of 7SA612, 7SA612, RET670 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG02245 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02249 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | 220/110kV Trafo Tap Changer Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02248 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02247 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02246 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | 220/110 & 275/220 - Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20717 | TO-20-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | KILLONAN 220 | KILLONAN 110 | T2103 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0773 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 10/03/2020 |  | Scheduled
20CM0173 | TO-20-KLN-T2104-02 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | ESB Networks Oil filtration plant was no | 901078075 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0367 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | Replacement of faulty oil DGA monitoring | 901090977 | 24/02/2020 | 10/03/2020 | 1 | Scheduled
20EG01952 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | 220/110 & 275/220 Trafo Ordinary Service | 901130045 | 24/02/2020 | 10/03/2020 | 4 | Scheduled
20EG01951 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | 220kV SF6 Cubicle Ordinary Service | 901129999 | 24/02/2020 | 10/03/2020 | 4 | Scheduled
20EG01950 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | 110kV SF6 Cubicle Ordinary Service | 901129908 | 24/02/2020 | 10/03/2020 | 4 | Scheduled
20EG20607 | TO-20-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | KILLONAN 220 | KILLONAN 110 | T2104 | Cable Insp. 110kV XLPE |  | 24/02/2020 | 10/03/2020 | 4 | Scheduled
CAPX2020091010492111 | TO-20-KLN-TB-1-05 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | KILLONAN 220 | TARBERT 220 | 1 | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 06/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492104 | TO-20-KLN-TB-1-05 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | KILLONAN 220 | TARBERT 220 | 1 | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 06/10/2020 | 07/10/2020 |  | Scheduled
OD0298 | TO-20-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | KILLONAN 220 | TARBERT 220 | 1 | Total Maintenance Outage Duration Requested |  | 02/06/2020 | 18/11/2020 |  | Scheduled
19LN5370 | TO-20-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | KILLONAN 220 | TARBERT 220 | 1 | 2018HP-1[151]ACGFit ACG | 900987854 | 02/06/2020 | 18/11/2020 | 4 | Scheduled
CAPX2019100412180720 | TO-20-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | KILLONAN 220 | TARBERT 220 | 1 | Outage for diversion of line into Kilpaddoge station to cable into GIS building. Feeder will become Killonan Kilpaddoge | CP0647 | 02/06/2020 | 18/11/2020 |  | Scheduled
OD1318 | TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 13/08/2020 |  | Scheduled
20EG04064 | TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 10/08/2020 | 13/08/2020 | 4 | Scheduled
CAPX2020010910460159 | TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA1 | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 10/08/2020 | 13/08/2020 |  | Scheduled
CAPX2020010910460162 | TO-20-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA1 | As a consequence of KTN-110SA2: 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 10/08/2020 | 13/08/2020 |  | Scheduled
OD1319 | TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 12/08/2020 |  | Scheduled
20EG04065 | TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 10/08/2020 | 12/08/2020 | 4 | Scheduled
CAPX2020010910460160 | TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA2 | As a consequence of KTN-110SA1: 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 10/08/2020 | 12/08/2020 |  | Scheduled
CAPX2020010910460163 | TO-20-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | KILLOTERAN 110 | KILLOTERAN 110 | 110SA2 | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 10/08/2020 | 12/08/2020 |  | Scheduled
CAPX2020010910460161 | TO-20-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | KILLOTERAN 110 | KILLOTERAN 10 | T101 | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 10/08/2020 | 13/08/2020 |  | Reference
CAPX2020010910460164 | TO-20-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | KILLOTERAN 110 | KILLOTERAN 10 | T102 | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910460165 | TO-20-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | KILLOTERAN 110 | WATERFORD 110 | 1 | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601128 | TO-20-KTN-WAT-1-02 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | KILLOTERAN 110 | WATERFORD 110 | 1 | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713114551 | TO-20-110 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | KILPADDOGE 110 | KILPADDOGE 110 | 110A1 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713114719 | TO-20-110 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | KILPADDOGE 110 | KILPADDOGE 110 | 110A2 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713115242 | TO-20-110 kV A3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | KILPADDOGE 110 | KILPADDOGE 110 | 110A3 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713115537 | TO-20-110 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A4 | KILPADDOGE 110 | KILPADDOGE 110 | 110A4 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713114804 | TO-20-110 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | KILPADDOGE 110 | KILPADDOGE 110 | 110B1 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713114845 | TO-20-110 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | KILPADDOGE 110 | KILPADDOGE 110 | 110B2 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713115345 | TO-20-110 kV B3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | KILPADDOGE 110 | KILPADDOGE 110 | 110B3 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713115716 | TO-20-110 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B4 | KILPADDOGE 110 | KILPADDOGE 110 | 110B4 | BB changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200820145431 | TO-20-220 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | KILPADDOGE 220 | KILPADDOGE 220 | 220A1 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492112 | TO-20-220 kV A2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | KILPADDOGE 220 | KILPADDOGE 220 | 220A2 | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
TOP200707100944 | TO-20-220 kV A2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | KILPADDOGE 220 | KILPADDOGE 220 | 220A2 | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2 |  | 27/07/2020 | 14/08/2020 |  | Scheduled
TOP200716122801 | TO-20-220 kV A2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | KILPADDOGE 220 | KILPADDOGE 220 | 220A2 | Busbar changeover |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293802 | TO-20-220 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | KILPADDOGE 220 | KILPADDOGE 220 | 220A2 | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200625160500 | TO-20-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | KILPADDOGE 220 | KILPADDOGE 220 | 220A3 | A3/B3 in turn for replacement of DC contactors |  | 14/07/2020 | 24/07/2020 |  | Scheduled
TOP200820145525 | TO-20-220 kV A3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | KILPADDOGE 220 | KILPADDOGE 220 | 220A3 | Busbar Changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091011302105 | TO-20-220 kV A4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | KILPADDOGE 220 | KILPADDOGE 220 | 220A4 | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
TOP200716123404 | TO-20-220 kV A4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | KILPADDOGE 220 | KILPADDOGE 220 | 220A4 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200707101528 | TO-20-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | KILPADDOGE 220 | KILPADDOGE 220 | 220A4 | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler |  | 31/08/2020 | 11/09/2020 |  | Scheduled
TOP200716123849 | TO-20-220 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | KILPADDOGE 220 | KILPADDOGE 220 | 220B1 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492113 | TO-20-220 kV B2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | KILPADDOGE 220 | KILPADDOGE 220 | 220B2 | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
TOP200707101343 | TO-20-220 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | KILPADDOGE 220 | KILPADDOGE 220 | 220B2 | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2 |  | 27/07/2020 | 14/08/2020 |  | Scheduled
TOP200716124129 | TO-20-220 kV B2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | KILPADDOGE 220 | KILPADDOGE 220 | 220B2 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293803 | TO-20-220 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | KILPADDOGE 220 | KILPADDOGE 220 | 220B2 | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200716124333 | TO-20-220 kV B3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | KILPADDOGE 220 | KILPADDOGE 220 | 220B3 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200625160637 | TO-20-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | KILPADDOGE 220 | KILPADDOGE 220 | 220B3 | A3/B3 in turn for replacement of DC contactors |  | 14/07/2020 | 24/07/2020 |  | Scheduled
TOP200707101651 | TO-20-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | KILPADDOGE 220 | KILPADDOGE 220 | 220B4 | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler |  | 31/08/2020 | 11/09/2020 |  | Scheduled
TOP200716124652 | TO-20-220 kV B4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | KILPADDOGE 220 | KILPADDOGE 220 | 220B4 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492106 | TO-20-220 kV B4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | KILPADDOGE 220 | KILPADDOGE 220 | 220B4 | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492107 | TO-20-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | KILPADDOGE 220 | KILPADDOGE 220 | 220K4 | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492108 | TO-20-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | KILPADDOGE 220 | KILPADDOGE 220 | 220K4 | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492114 | TO-20-KPG-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SA1-2CB | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492115 | TO-20-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SA2-4CB | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492109 | TO-20-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SA2-4CB | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2020091010492116 | TO-20-KPG-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB1-2CB | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
CAPX2019100209293806 | TO-20-KPG-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB1-2CB | As a consequence of 220 kV B2 @ KPG: 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492117 | TO-20-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB2-4CB | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
OD1205 | TO-20-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB2-4CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091010492110 | TO-20-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB2-4CB | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths | CP0647 | 05/10/2020 | 07/10/2020 |  | Scheduled
19EG23619 | TO-20-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | KILPADDOGE 220 | KILPADDOGE 220 | 220SB2-4CB | 220kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200505123353 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | Proximity outage for 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 (Hotspots 7 and 8 to be repaired; DC Cable Tower No. 160) |  | 21/05/2020 | 22/05/2020 |  | Scheduled
OD0976 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | Total Maintenance Outage Duration Requested |  | 21/05/2020 | 22/05/2020 |  | Scheduled
19LN5539 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | 2018HP-1[47]Insulator-strain insul | 900988027 | 21/05/2020 | 22/05/2020 | 4 | Scheduled
20EG10375 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | 110kV GIS Cubicle Operational Test | 901129517 | 21/05/2020 | 22/05/2020 | 4 | Scheduled
19EG21382 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | 110kV SF6 Cubicle Operational Test | 901129707 | 21/05/2020 | 22/05/2020 | 4 | Scheduled
CAPX2019100214564000 | TO-20-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | EI: Replacing polesets, hardware, insulators & crossarms. Foundation reinforcement required at angle masts. Towers to be painted. | CP0902 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21016 | TO-20-KPG-KNR-1-110-02 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | KILPADDOGE 110 | KNOCKANURE 110 | 1-110 | Cable Insp. 110kV XLPE |  | 21/05/2020 | 22/05/2020 | 4 | Scheduled
OD1105 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0406 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Aux Relay - replace contactors |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0408 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Aux Relay - replace contactors |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG23315 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | 220kV GIS Cubicle Operational Test | 901043819 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100209293800 | TO-20-KPG-KNR-1-220-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Re-lable circuit to Kipaddoge-Knockanure No. 1 | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019112814362502 | TO-20-KPG-KNR-1-220-02 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder | CP0883 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21049 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21046 | TO-20-KPG-KNR-1-220-03 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100215315700 | TO-20-KPG-KNR-1-220-04 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | KILPADDOGE 220 | KNOCKANURE 220 | 1-220 | Proximity outage to bore wall and pull cable | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1106 | TO-20-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 1 | Total Maintenance Outage Duration Requested |  | 21/09/2020 | 30/09/2020 |  | Scheduled
20CM0423 | TO-20-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 1 | Aux Relay - replace contactors |  | 21/09/2020 | 30/09/2020 | 4 | Scheduled
CAPX2020091010492118 | TO-20-KPG-MP GIS-2-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 2 | EI: EI of Kilpaddoge - Killonan | CP0647 | 08/10/2020 | 09/10/2020 |  | Scheduled
OD1372 | TO-20-KPG-MP GIS-2-04 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 2 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 02/12/2020 |  | Tentative
CAPX2020061914460703 | TO-20-KPG-MP GIS-2-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 2 | EI: EI of Kilpaddoge - Tarbert 2 | CP0647 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0398 | TO-20-KPG-MP GIS-2-04 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 2 | Aux Relay - replace contactors |  | 23/11/2020 | 02/12/2020 | 2 | Tentative
CAPX2019100209293814 | TO-20-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | KILPADDOGE 220 | MONEYPOINT GIS 220 | 2 | EI: Energise the new Kilpaddoge- Knocknaure 2 cable | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0235 | TO-20-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | Total Maintenance Outage Duration Requested |  | 17/11/2020 | 17/11/2020 |  | Scheduled
19EG10361 | TO-20-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | 110kV MO Cubicle Operational Test |  | 17/11/2020 | 17/11/2020 | 4 | Scheduled
19LN6885 | TO-20-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | 2018HP-1[130]ITSOul&HW Replace check | 900989470 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN6884 | TO-20-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | 2018HP-1[125]ITSOul&HW Replace check | 900989469 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN6886 | TO-20-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | 2018HP-1[134]Off Plumb | 900989471 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN6887 | TO-20-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | KILPADDOGE 110 | RATHKEALE 110 | 1 | 2018HP-1[135]ACG-Replace | 900989472 | 17/11/2020 | 17/11/2020 | 2 | Scheduled
OD1141 | TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | Total Maintenance Outage Duration Requested |  | 26/03/2020 | 02/04/2020 |  | Scheduled
OD1377 | TO-20-KPG-T2101-03 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 21/10/2020 |  | Scheduled
19EG235566 | TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | 220/110 & 275/220 Trafo Operational Test | 901045373 | 26/03/2020 | 02/04/2020 | 4 | Scheduled
19CM0107 | TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | Corrosion on MR Messko Temp Gauges ( requires stainless surround to stop water from top cover) and fans Fans Q4 not working ceased | 901039259 | 26/03/2020 | 02/04/2020 | 2 | Scheduled
20CM0405 | TO-20-KPG-T2101-03 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | Aux Relay - replace contactors |  | 12/10/2020 | 21/10/2020 | 2 | Scheduled
19EG23560 | TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | 220kV GIS Cubicle Operational Test | 901045526 | 26/03/2020 | 02/04/2020 | 4 | Scheduled
19EG23555 | TO-20-KPG-T2101-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | KILPADDOGE 220 | KILPADDOGE 110 | T2101 | 110kV GIS Cubicle Operational Test | 901045439 | 26/03/2020 | 02/04/2020 | 4 | Scheduled
OD1208 | TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 04/09/2020 |  | Scheduled
20CM0402 | TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | Aux Relay - replace contactors |  | 01/09/2020 | 04/09/2020 | 2 | Scheduled
20EG23584 | TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
CAPX2019100209293801 | TO-20-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | Proximity outage of F4 bay to enable termination of cable in F6 bay. | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23588 | TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | 220kV GIS Cubicle Operational Test |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
20EG23620 | TO-20-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | KILPADDOGE 220 | KILPADDOGE 110 | T2102 | 110kV GIS Cubicle Operational Test |  | 01/09/2020 | 04/09/2020 | 4 | Scheduled
CAPX2020032414240823 | TO-20-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | Proximity outage of DC mast - remove lead-in and drops, strip down the CSEs | CP0647 | 26/05/2020 | 28/05/2020 |  | Scheduled
OD1107 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 23/10/2020 |  | Scheduled
20EG00791 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | 220kV Cubicle Condition Assessment |  | 12/10/2020 | 23/10/2020 | 4 | Scheduled
19EG00789 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | 220kV MO Cubicle Ordinary Service | 901050439 | 12/10/2020 | 23/10/2020 | 4 | Scheduled
20EG00789 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | 220kV MO Cubicle Ordinary Service |  | 12/10/2020 | 23/10/2020 | 4 | Scheduled
20CM0403 | TO-20-KPG-TB-1-08 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | Aux Relay - replace contactors |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
18EG23318 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | 220kV GIS Cubicle Operational Test | 900942471 | 12/10/2020 | 23/10/2020 | 3 | Scheduled
18EG23422 | TO-20-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | KILPADDOGE 220 | TARBERT 220 | 1 | Annual Insp. 400 & 220 Feeder XLPE Cable | 901006581 | 12/10/2020 | 23/10/2020 | 3 | Scheduled
OD1099 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN7084 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 2018HP-1[99]Off PlumbPlumb poleset | 900989675 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN7081 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 2018HP-1[31]Off PlumbPlumb poleset | 900989672 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN7083 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 2018HP-1[98]Off PlumbPlumb poleset | 900989674 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN7085 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 2018HP-1[100]Off PlumbPlumb poleset | 900989676 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG23372 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 110kV GIS Cubicle Operational Test | 901043757 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20701 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23375 | TO-20-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | KILPADDOGE 110 | TRALEE 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0197 | TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | KILTEEL 110 | MAYNOOTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10307 | TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | KILTEEL 110 | MAYNOOTH 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18LN1470 | TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | KILTEEL 110 | MAYNOOTH 110 | 1 | 2017HP-1[11]Off Plumb -Poles | 900897418 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
10LN0170 | TO-20-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | KILTEEL 110 | MAYNOOTH 110 | 1 | Replace Member mast no 86 replace bent b | 900247574 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0198 | TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | KILTEEL 110 | MONREAD 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/06/2020 | 08/06/2020 |  | Scheduled
20CM0251 | TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | KILTEEL 110 | MONREAD 110 | 1 | Low Gas | 901076758 | 02/06/2020 | 08/06/2020 | 1 | Scheduled
19EG10308 | TO-20-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | KILTEEL 110 | MONREAD 110 | 1 | 110kV SF6 Cubicle Operational Test | 901055117 | 02/06/2020 | 08/06/2020 | 4 | Scheduled
OD0933 | TO-20-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG02548 | TO-20-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 901042964 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02547 | TO-20-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 901042963 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02549 | TO-20-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | 110kV SF6 Cubicle Ordinary Service | 901042251 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351105 | TO-20-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351101 | TO-20-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | KINNEGAD 110 | KINNEGAD 110 | 110SA1-2CB | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1100 | TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 21/07/2020 |  | Scheduled
CAPX2020010910351102 | TO-20-KIN-MUL-1-03 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019121014363900 | TO-20-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | EI: Install 2 new towers under the line, divert line and re-energise from remote end | CP1054 | 20/07/2020 | 09/10/2020 |  | Scheduled
CAPX2020010910351133 | TO-20-KIN-MUL-1-03 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23225 | TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 20/07/2020 | 21/07/2020 | 4 | Scheduled
20EG23228 | TO-20-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | KINNEGAD 110 | MULLINGAR 110 | 1 | 110kV SF6 Cubicle Operational Test | 901118292 | 20/07/2020 | 21/07/2020 | 4 | Scheduled
OD0548 | TO-20-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | KINNEGAD 110 | KINNEGAD 10 | T101 | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
20CM0176 | TO-20-KIN-T101-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | KINNEGAD 110 | KINNEGAD 10 | T101 | replacement of the CT’s in Kinnegad T101 | 901068813 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG01476 | TO-20-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | KINNEGAD 110 | KINNEGAD 10 | T101 | 110kV SF6 Cubicle Ordinary Service | 901042268 | 27/10/2020 | 30/10/2020 | 4 | Scheduled
CAPX2020010910351103 | TO-20-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | KINNEGAD 110 | KINNEGAD 10 | T101 | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0549 | TO-20-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | KINNEGAD 110 | KINNEGAD 10 | T102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10866 | TO-20-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | KINNEGAD 110 | KINNEGAD 10 | T102 | 110kV SF6 Cubicle Operational Test | 901080654 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351106 | TO-20-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | KINNEGAD 110 | KINNEGAD 10 | T102 | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713120105 | TO-20-110 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | KNOCKANURE 110 | KNOCKANURE 110 | 110A1 | BB changeover | BB0001 | 23/09/2020 | 23/09/2020 |  | Scheduled
TOP200713120317 | TO-20-110 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A2 | KNOCKANURE 110 | KNOCKANURE 110 | 110A2 | BB changeover | BB0001 | 23/09/2020 | 23/09/2020 |  | Scheduled
TOP200713120359 | TO-20-110 kV A4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A4 | KNOCKANURE 110 | KNOCKANURE 110 | 110A4 | BB changeover | BB0001 | 23/09/2020 | 23/09/2020 |  | Scheduled
TOP200713120445 | TO-20-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | KNOCKANURE 110 | KNOCKANURE 110 | 110B1 | BB changeover | BB0001 | 23/09/2020 | 23/09/2020 |  | Scheduled
TOP200713120536 | TO-20-110 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B2 | KNOCKANURE 110 | KNOCKANURE 110 | 110B2 | BB changeover | BB0001 | 23/09/2020 | 23/09/2020 |  | Scheduled
TOP200713120713 | TO-20-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | KNOCKANURE 220 | KNOCKANURE 220 | 220A1 | BB changeover | BB0001 | 24/09/2020 | 24/09/2020 |  | Scheduled
TOP200713120755 | TO-20-220 kV A2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | KNOCKANURE 220 | KNOCKANURE 220 | 220A2 | BB changeover | BB0001 | 24/09/2020 | 24/09/2020 |  | Scheduled
CAPX2019100215315702 | TO-20-220 kV A2 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | KNOCKANURE 220 | KNOCKANURE 220 | 220A2 | 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293808 | TO-20-220 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | KNOCKANURE 220 | KNOCKANURE 220 | 220A2 | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713120905 | TO-20-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | KNOCKANURE 220 | KNOCKANURE 220 | 220B1 | BB changeover | BB0001 | 24/09/2020 | 24/09/2020 |  | Scheduled
TOP200713121231 | TO-20-220 kV B2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | KNOCKANURE 220 | KNOCKANURE 220 | 220B2 | BB changeover | BB0001 | 24/09/2020 | 24/09/2020 |  | Scheduled
CAPX2019100215315703 | TO-20-220 kV B2 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | KNOCKANURE 220 | KNOCKANURE 220 | 220B2 | 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293809 | TO-20-220 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | KNOCKANURE 220 | KNOCKANURE 220 | 220B2 | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1019 | TO-20-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | KNOCKANURE 220 | KNOCKANURE 220 | 220K1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21176 | TO-20-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | KNOCKANURE 220 | KNOCKANURE 220 | 220K1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1020 | TO-20-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293811 | TO-20-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293810 | TO-20-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21179 | TO-20-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100215315708 | TO-20-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | EI: Energisation of F6 reactor inc. soft closing and 24hr cable soak | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100215315705 | TO-20-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100215315704 | TO-20-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | KNOCKANURE 220 | KNOCKANURE 220 | 220K2 | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1021 | TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21181 | TO-20-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SA1-2CB | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100215315706 | TO-20-KNR-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SA1-2CB | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293812 | TO-20-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SA1-2CB | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1022 | TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SB1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209293813 | TO-20-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SB1-2CB | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay | CP0726 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21186 | TO-20-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SB1-2CB | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100215315707 | TO-20-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | KNOCKANURE 220 | KNOCKANURE 220 | 220SB1-2CB | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning | CP0936 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1048 | TO-20-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | KNOCKANURE 220 | KNOCKANURE 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21266 | TO-20-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | KNOCKANURE 220 | KNOCKANURE 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21259 | TO-20-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | KNOCKANURE 220 | KNOCKANURE 110 | T2101 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21261 | TO-20-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | KNOCKANURE 220 | KNOCKANURE 110 | T2101 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1049 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | Total Maintenance Outage Duration Requested |  | 26/02/2020 | 12/03/2020 |  | Scheduled
19CM0126 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | Knockanure T2101 & T2102 Transformers: Check position of fans adjacent to pumps | 901130270 | 26/02/2020 | 12/03/2020 | 3 | Scheduled
20CM0179 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | Low Oil / Leak. Low Oil alarm being gene | 900982980 | 26/02/2020 | 12/03/2020 | 2 | Scheduled
20EG21275 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | Cable Insp. 110kV XLPE |  | 26/02/2020 | 12/03/2020 | 4 | Scheduled
20EG21284 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service | 901129834 | 26/02/2020 | 12/03/2020 | 4 | Scheduled
20EG21278 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | 220kV GIS Cubicle Ordinary Service | 901129806 | 26/02/2020 | 12/03/2020 | 4 | Scheduled
20EG21273 | TO-20-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | KNOCKANURE 220 | KNOCKANURE 110 | T2102 | 110kV GIS Cubicle Ordinary Service | 901129752 | 26/02/2020 | 12/03/2020 | 4 | Scheduled
OD0977 | TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | KNOCKANURE 110 | TRIEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 10/06/2020 | 11/06/2020 |  | Scheduled
20EG21017 | TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | KNOCKANURE 110 | TRIEN 110 | 1 | Cable Insp. 110kV XLPE |  | 10/06/2020 | 11/06/2020 | 4 | Scheduled
20EG21024 | TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | KNOCKANURE 110 | TRIEN 110 | 1 | Cable Insp. 110kV XLPE |  | 10/06/2020 | 11/06/2020 | 4 | Scheduled
CAPX2020010910351197 | TO-20-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | KNOCKANURE 110 | TRIEN 110 | 1 | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21021 | TO-20-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | KNOCKANURE 110 | TRIEN 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129634 | 10/06/2020 | 11/06/2020 | 4 | Scheduled
OD0978 | TO-20-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | KNOCKANURE 110 | TRIEN 110 | 2 | Total Maintenance Outage Duration Requested |  | 12/06/2020 | 12/06/2020 |  | Scheduled
20EG10376 | TO-20-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | KNOCKANURE 110 | TRIEN 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 12/06/2020 | 12/06/2020 | 4 | Scheduled
CAPX2020010910351173 | TO-20-KNR-TRI-2-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | KNOCKANURE 110 | TRIEN 110 | 2 | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200806090256 | TO-20-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110A1 | Busbar changeover | BB0001 | 29/10/2020 | 29/10/2020 |  | Scheduled
CAPX2020091508195803 | TO-20-110 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110A1 | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103 | CP0796 + CP0973 | 05/10/2020 | 09/10/2020 |  | Scheduled
TOP200806090358 | TO-20-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110A2 | Busbar changeover | BB0001 | 29/10/2020 | 29/10/2020 |  | Scheduled
CAPX2020091508195804 | TO-20-110 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110B1 | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103 | CP0796 + CP0973 | 05/10/2020 | 09/10/2020 |  | Scheduled
TOP200806090718 | TO-20-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110B1 | Busbar changeover | BB0001 | 29/10/2020 | 29/10/2020 |  | Scheduled
TOP200806091306 | TO-20-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110B2 | Busbar changeover | BB0001 | 29/10/2020 | 29/10/2020 |  | Scheduled
OD0413 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01180 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01179 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01178 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01177 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01176 | TO-20-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | KNOCKRAHA 110 | KNOCKRAHA 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020091508195806 | TO-20-220 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A1 | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 11/10/2020 | 12/10/2020 |  | Scheduled
TOP200814125746 | TO-20-220 kV A1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A1 | Busbar Changeover | BB0001 | 05/11/2020 | 05/11/2020 |  | Scheduled
TOP200814125841 | TO-20-220 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A2 | Busbar Changeover | BB0001 | 05/11/2020 | 05/11/2020 |  | Scheduled
CAPX2020060310121315 | TO-20-220 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A2 | Droppers to be connected, followed by EI. | CP0796 + CP0973 | 17/06/2020 | 19/06/2020 |  | Scheduled
CAPX2019101410530312 | TO-20-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A2 | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530315 | TO-20-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A2 | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530317 | TO-20-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220A2 | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091508195807 | TO-20-220 kV B1 @ KRA-05 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 11/10/2020 | 12/10/2020 |  | Scheduled
TOP200814125919 | TO-20-220 kV B1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | Busbar Changeover | BB0001 | 05/11/2020 | 05/11/2020 |  | Scheduled
CAPX2019101409072035 | TO-20-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102414563236 | TO-20-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409072032 | TO-20-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409072029 | TO-20-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B1 | 220 kV A1/B1 IN TURN @ KRA: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020060310121316 | TO-20-220 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B2 | Droppers to be connected, followed by EI. | CP0796 + CP0973 | 22/06/2020 | 24/06/2020 |  | Scheduled
TOP200814125959 | TO-20-220 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B2 | Busbar Changeover | BB0001 | 05/11/2020 | 05/11/2020 |  | Scheduled
CAPX2019101410530313 | TO-20-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B2 | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530316 | TO-20-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B2 | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530318 | TO-20-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220B2 | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020060310121320 | TO-20-KRA-220K1-2-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0414 | TO-20-KRA-220K1-2-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG01184 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0181 | TO-20-KRA-220K1-2-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | O1-Hotspot 220kv SA2 T Phase on A2 Side | 901047457 | 16/11/2020 | 20/11/2020 | 1 | Scheduled
20EG01183 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10679 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039154 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01185 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01186 | TO-20-KRA-220K1-2-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
20EG01187 | TO-20-KRA-220K1-2-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 16/11/2020 | 20/11/2020 | 4 | Scheduled
19EG10680 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039155 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01182 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019101410530309 | TO-20-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409072046 | TO-20-KRA-220K1-2-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101411492624 | TO-20-KRA-220K1-2-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | KNOCKRAHA 220 | KNOCKRAHA 220 | 220K1-2 | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0201 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200121161756 | TO-20-KRA-MID-1-02 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | studied outage to move 12 day outage for CP0868 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10313 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0185 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | O1-Repair SF6 Gauge signs of corrosion | 901059062 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0239 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | Replce Bay Signage | 901078152 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20LN5215 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | Hotspot 1 (AT No.50 Span 49/50) Right phase jumper terminal (Repair by 28th August 2020) | 901130581 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN4123 | TO-20-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | 2019HP-7[7,8,9,10,11,12,13]Off Plumb | 901084995 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100212153003 | TO-20-KRA-MID-1-02 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | KNOCKRAHA 110 | MIDLETON 110 | 1 | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21 | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0299 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Total Maintenance Outage Duration Requested |  | 24/02/2020 | 23/05/2020 |  | Scheduled
CAPX2020021212041311 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2) | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020060310182314 | TO-20-KRA-RAF-1-04 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | EI: Outage for EI, line switched out at start of works | CP0796 + CP0973 | 17/06/2020 | 24/06/2020 |  | Scheduled
CAPX2020021410064808 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 23/05/2020 |  | Scheduled
19CM0331 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Replace stolen earths | 901129378 | 24/02/2020 | 23/05/2020 | 1 | Scheduled
18LN2393 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 2017HP-1[DCAT5]Arching Horns -Replace | 900897880 | 24/02/2020 | 23/05/2020 | 3 | Scheduled
16LN2375 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 2015HP-1[54]Insulator Broken str insul | 900727347 | 24/02/2020 | 23/05/2020 | 3 | Scheduled
18LN2392 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 2017HP-1[DCET1]Arching Horns -Replace | 900897879 | 24/02/2020 | 23/05/2020 | 3 | Scheduled
CAPX2019101410530310 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101409163504 | TO-20-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2019101409072005 | TO-20-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower. | CP0796 + CP0973 | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2019101409072001 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | For Energisation of A4/B4 busbar | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100212153008 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100810285609 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | EI: Simultaneous KRA-RAF-1 + KRA-RAF-1: Energisation using either feeder bay CB | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100212153006 | TO-20-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen | CP0868 | 24/02/2020 | 30/04/2020 |  | Scheduled
CAPX2020010910331721 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Proximity outage for work on Aghada-Raffeen 220 kV | PR0001 | 24/02/2020 | 23/05/2020 |  | Scheduled
CAPX2019100212153004 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21 | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100212153001 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21 | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100212153000 | TO-20-KRA-RAF-1-03 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 220 kV Line refurbishment, re-sagging and foundation reinforcement works. | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN4126 | TO-20-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | KNOCKRAHA 220 | RAFFEEN 220 | 1 | 2019HP-2[2,3]Vib Dampers Replace EW VD | 901085223 | 24/02/2020 | 23/05/2020 | 4 | Scheduled
OD0774 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | Total Maintenance Outage Duration Requested |  | 08/07/2020 | 23/07/2020 |  | Scheduled
20CM0187 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | Spare Parts for Disconnect | 900877126 | 08/07/2020 | 23/07/2020 | 2 | Scheduled
18CM0622 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | O2- OLTC silica gel needs changing | 900959190 | 08/07/2020 | 23/07/2020 | 2 | Scheduled
18CM1207 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | O2-Fans 2,6,9 not working | 900973655 | 08/07/2020 | 23/07/2020 | 2 | Scheduled
19EG01957 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | 110kV SF6 Cubicle Ordinary Service | 901042315 | 08/07/2020 | 23/07/2020 | 4 | Scheduled
20EG01959 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service | 901130039 | 08/07/2020 | 23/07/2020 | 4 | Scheduled
19EG01958 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | 220kV SF6 Cubicle Ordinary Service | 901042177 | 08/07/2020 | 23/07/2020 | 4 | Scheduled
20CM0188 | TO-20-KRA-T2101-04 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | Carry out oil regeneration, wire up PRD | 900908018 | 08/07/2020 | 23/07/2020 | 2 | Scheduled
CAPX2019101411460142 | TO-20-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101411492625 | TO-20-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2101 | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0775 | TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11116 | TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | 220kV SF6 Cubicle Operational Test | 901129728 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11117 | TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | 220/110 & 275/220 Trafo Operational Test | 901129737 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11115 | TO-20-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | 110kV SF6 Cubicle Operational Test | 901129577 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019102414563237 | TO-20-KRA-T2102-03 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530311 | TO-20-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101410530319 | TO-20-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2102 | Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020091508195805 | TO-20-KRA-T2103-03 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | Remove from system to allow for offline F9 wing coupler build | CP0796 + CP0973 | 12/10/2020 | 03/03/2021 |  | Scheduled
OD0776 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020060310121322 | TO-20-KRA-T2103-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline | CP0796 + CP0973 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020041 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | P2 Protection maintenance of 7SA612, 7SA612, RET670 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG11226 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | 220/110 & 275/220 Trafo Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11225 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11224 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18CM0621 | TO-20-KRA-T2103-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | KNOCKRAHA 220 | KNOCKRAHA 110 | T2103 | O2- Low oil level on OLTC tank | 900959193 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD1101 | TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | KNOCKRAHA 110 | WOODHOUSE 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 13/07/2020 |  | Scheduled
20CM0191 | TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | KNOCKRAHA 110 | WOODHOUSE 110 | 1 | O1-Replace Surge Counter | 901036906 | 06/07/2020 | 13/07/2020 | 2 | Scheduled
20EG00466 | TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | KNOCKRAHA 110 | WOODHOUSE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129859 | 06/07/2020 | 13/07/2020 | 4 | Scheduled
20EG11413 | TO-20-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | KNOCKRAHA 110 | WOODHOUSE 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 06/07/2020 | 13/07/2020 | 4 | Scheduled
CAPX2019100212153002 | TO-20-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | KNOCKRAHA 110 | WOODHOUSE 110 | 1 | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21 | CP0868 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200814130101 | TO-20-110 kV A1 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A1 | KNOCKRANNY 110 | KNOCKRANNY 110 | 110A1 | Busbar Changeover | BB0001 | 12/11/2020 | 12/11/2020 |  | Scheduled
TOP200814130150 | TO-20-110 kV A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | KNOCKRANNY 110 | KNOCKRANNY 110 | 110A2 | Busbar Changeover | BB0001 | 12/11/2020 | 12/11/2020 |  | Scheduled
TOP200814130232 | TO-20-110 kV B1 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B1 | KNOCKRANNY 110 | KNOCKRANNY 110 | 110B1 | Busbar Changeover | BB0001 | 12/11/2020 | 12/11/2020 |  | Scheduled
TOP200814130310 | TO-20-110 kV B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | KNOCKRANNY 110 | KNOCKRANNY 110 | 110B2 | Busbar Changeover | BB0001 | 12/11/2020 | 12/11/2020 |  | Scheduled
OD0957 | TO-20-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | KNOCKRANNY 110 | KNOCKRANNY 110 | FILTER1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG21338 | TO-20-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | KNOCKRANNY 110 | KNOCKRANNY 110 | FILTER1 | HV Filter Ordinary Service | 901146372 | 16/11/2020 | 20/11/2020 | 4 | Scheduled
OD0980 | TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | KNOCKRANNY 110 | SALTHILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 07/04/2020 | 08/04/2020 |  | Scheduled
OD1379 | TO-20-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | KNOCKRANNY 110 | SALTHILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 04/09/2020 |  | Scheduled
20CM0485 | TO-20-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | KNOCKRANNY 110 | SALTHILL 110 | 1 | CSE Inspection, ref. Galway cubicle CSE Failure in Salthill (FO 19-26) |  | 01/09/2020 | 04/09/2020 | 1 | Scheduled
18EG21315 | TO-20-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | KNOCKRANNY 110 | SALTHILL 110 | 1 | 110kV GIS Cubicle Operational Test | 900858560 | 01/09/2020 | 04/09/2020 | 3 | Scheduled
20CM0393 | TO-20-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | KNOCKRANNY 110 | SALTHILL 110 | 1 | Visual inspection of HIS HV cable sealing end | 901129456 | 07/04/2020 | 08/04/2020 | 1 | Scheduled
OD0981 | TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | KNOCKRANNY 110 | SCREEBE 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/06/2020 | 10/06/2020 |  | Reference
17EG21325 | TO-20-KNY-SCR-1-02 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | KNOCKRANNY 110 | SCREEBE 110 | 1 | Annual Insp. 110kV Feeder XLPE Cable | 901006383 | 25/12/2500 | 25/12/2500 | 2 | Reference (Unscheduled)
18EG21323 | TO-20-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | KNOCKRANNY 110 | SCREEBE 110 | 1 | 110kV GIS Cubicle Operational Test | 900942465 | 09/06/2020 | 10/06/2020 | 3 | Reference
OD0982 | TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | KNOCKRANNY 110 | UGGOOL 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21331 | TO-20-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | KNOCKRANNY 110 | UGGOOL 110 | 1 | 110kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0415 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01188 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01189 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01190 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | 110kV SF6 Cubicle Ordinary Service | 901129877 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351108 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351113 | TO-20-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | LANESBORO 110 | LANESBORO 110 | 110SA1-2CB | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5232 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | L2 205 - 206 Left Mid span joint. Replace joint during the next planned outage | 901110469 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910351109 | TO-20-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5228 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | R1 206 - 207 Right Mid span joint Replace joint within 6 months pending TSO review. | 901110465 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5229 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | C1 206 - 207 Centre Mid span joint Replace joint within 3 months pending TSO review. | 901110466 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5230 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | L1 206 - 207 Left Mid span joint Replace joint within 6 months pending TSO review. | 901110467 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910351134 | TO-20-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5231 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | R2 205 - 206 Right Mid span joint Replace joint within 6 months pending TSO review | 901110468 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5234 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | Am No.75 75 - 76 Left Dead end termination Replace joint within 1 month pending TSO review | 901110515 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5233 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | C2 205 - 206 Centre Mid span joint Replace joint within 6 months pending TSO review. | 901110514 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5235 | TO-20-LA-MUL-1-03 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | LANESBORO 110 | MULLINGAR 110 | 1 | R1 74 - 75 Right Mid span joint Replace joint during the next planned outage. | 901110516 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910351110 | TO-20-LA-RIC-1-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-1 | LANESBORO 110 | RICHMOND 110 | 1 | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351114 | TO-20-LA-RIC-2-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | LANESBORO 110 | RICHMOND 110 | 2 | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0983 | TO-20-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | LANESBORO 110 | SLIABH BAWN 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21335 | TO-20-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | LANESBORO 110 | SLIABH BAWN 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042297 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351115 | TO-20-LA-SLB-1-02 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | LANESBORO 110 | SLIABH BAWN 110 | 1 | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0659 | TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | LANESBORO 110 | LANESBORO G4 | T104 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351116 | TO-20-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | LANESBORO 110 | LANESBORO G4 | T104 | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351111 | TO-20-LA-T141-01 | DISTRIBUTION TRANSFORMER - LANESBORO 110-LANESBORO 38-T141 | LANESBORO 110 | LANESBORO 38 | T141 | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1281 | TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | LETTERKENNY 110 | LETTERKENNY 110 | 110SA1-3CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23775 | TO-20-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | LETTERKENNY 110 | LETTERKENNY 110 | 110SA1-3CB | 110kV SF6 Cubicle Operational Test | 901080653 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100209481104 | TO-20-LET-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | LETTERKENNY 110 | LETTERKENNY 110 | 110SA1-3CB | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0345 | TO-20-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | LETTERKENNY 110 | LETTERKENNY 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0192 | TO-20-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | LETTERKENNY 110 | LETTERKENNY 110 | CAP2 | N O 1 Misc- work not on other C | 900332304 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
PROT2020135 | TO-20-LET-M/CAP1-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | LETTERKENNY 110 | LETTERKENNY 110 | M/CAP1 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2019100209481105 | TO-20-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | LETTERKENNY 110 | LETTERKENNY 110 | M/CAP1 | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200110112848 | TO-20-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | LETTERKENNY 110 | STRABANE 110 | PST | P1 Protection maintenance of 7SA511, MX3P3A |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0206 | TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | LETTERKENNY 110 | STRABANE 110 | PST | Total Maintenance Outage Duration Requested |  | 31/08/2020 | 04/09/2020 |  | Scheduled
20CM0194 | TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | LETTERKENNY 110 | STRABANE 110 | PST | maintenane req on "S" phase arm of mecha | 900952919 | 31/08/2020 | 04/09/2020 | 1 | Scheduled
20EG00619 | TO-20-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | LETTERKENNY 110 | STRABANE 110 | PST | 110kV SF6 Cubicle Ordinary Service |  | 31/08/2020 | 04/09/2020 | 4 | Scheduled
CAPX2019100209481106 | TO-20-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | LETTERKENNY 110 | STRABANE 110 | PST | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0347 | TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 17/07/2020 |  | Scheduled
20EG05054 | TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | 110kV SF6 Cubicle Ordinary Service |  | 13/07/2020 | 17/07/2020 | 4 | Scheduled
19EG05097 | TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | Annual Inspection of SVC | 901006304 | 13/07/2020 | 17/07/2020 | 4 | Scheduled
18CM0071 | TO-20-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | Replace 10kV LV Bushing at SVC | 900863569 | 13/07/2020 | 17/07/2020 | 1 | Scheduled
CAPX2019100313352500 | TO-20-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | SVC Refurbishment | MC0330 | 13/07/2020 | 20/08/2020 |  | Scheduled
CAPX2019100209481107 | TO-20-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | LETTERKENNY 110 | LETTERKENNY 110 | SVC | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209481108 | TO-20-LET-T141-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | LETTERKENNY 110 | LETTERKENNY 38 | T141 | 110 kV A1 @ LET: EI: Energise T141 | CP0740 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100209481100 | TO-20-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | LETTERKENNY 110 | LETTERKENNY 38 | T141 | Facilitate the demolition of existing CT/VT supports and installation of new CT/VT and associated steelwork on T141 Bay | CP0740 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1246 | TO-20-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | LETTERKENNY 110 | TIEVEBRACK 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/11/2020 | 13/11/2020 |  | Scheduled
20EG23767 | TO-20-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | LETTERKENNY 110 | TIEVEBRACK 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 12/11/2020 | 13/11/2020 | 4 | Scheduled
20EG23761 | TO-20-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | LETTERKENNY 110 | TIEVEBRACK 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 12/11/2020 | 13/11/2020 | 4 | Scheduled
20EG23802 | TO-20-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | LETTERKENNY 110 | TIEVEBRACK 110 | 1 | Cable Insp. 110kV XLPE |  | 12/11/2020 | 13/11/2020 | 4 | Scheduled
CAPX2019100209481109 | TO-20-LET-TLK-1-01 | 110kV FEEDER - LETTERKENNY 110-TRILLICK 110-1 | LETTERKENNY 110 | TRILLICK 110 | 1 | Proximity outage to install new lightning monopole | CP0740 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1247 | TO-20-LIB-MR-1-01 | 110kV FEEDER - LIBERTY STREET 110-MARINA 110-1 | LIBERTY STREET 110 | MARINA 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
20EG10321 | TO-20-LIB-MR-1-01 | 110kV FEEDER - LIBERTY STREET 110-MARINA 110-1 | LIBERTY STREET 110 | MARINA 110 | 1 | 110kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Reference (Unscheduled)
CAPX2020010910331712 | TO-20-LIM-110SA1-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | LIMERICK 110 | LIMERICK 110 | 110SA1 | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460167 | TO-20-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | LIMERICK 110 | LIMERICK 110 | 110SA1 | As a consequence of LIM-110SA2: 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Scheduled
OD1320 | TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | LIMERICK 110 | LIMERICK 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Scheduled
20EG04075 | TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | LIMERICK 110 | LIMERICK 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 07/09/2020 | 11/09/2020 | 4 | Scheduled
CAPX2020010910331713 | TO-20-LIM-110SA2-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | LIMERICK 110 | LIMERICK 110 | 110SA2 | As a consequence of LIM-110SA1: 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460168 | TO-20-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | LIMERICK 110 | LIMERICK 110 | 110SA2 | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Scheduled
OD0210 | TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | LIMERICK 110 | MONETEEN 110 | 1 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Scheduled
20EG10323 | TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | LIMERICK 110 | MONETEEN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 07/09/2020 | 11/09/2020 | 4 | Scheduled
14LN3521 | TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | LIMERICK 110 | MONETEEN 110 | 1 | 3[509,510,511] DCIMP5 badly kinked (IMP49 KIL-LIM 1) | 900567326 | 07/09/2020 | 11/09/2020 | 1 | Scheduled
CAPX2020010910460169 | TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | LIMERICK 110 | MONETEEN 110 | 1 | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Scheduled
CAPX2020010910460180 | TO-20-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | LIMERICK 110 | MONETEEN 110 | 1 | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Scheduled
OD0211 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/10/2020 | 16/10/2020 |  | Scheduled
PROT2020052 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | P2 Protection maintenance of R1Z23b |  | 14/10/2020 | 16/10/2020 | 2 | Scheduled
20EG10326 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | 110kV MO Cubicle Operational Test |  | 14/10/2020 | 16/10/2020 | 4 | Scheduled
20EG10325 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 14/10/2020 | 16/10/2020 | 4 | Scheduled
19LN5797 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | 2018HP-1[42-43]Conflicts-No Guard Wire | 900988374 | 14/10/2020 | 16/10/2020 | 4 | Scheduled
20EG20077 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | Cable Insp. 110kV XLPE |  | 14/10/2020 | 16/10/2020 | 4 | Scheduled
CAPX2020010910331714 | TO-20-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | LIMERICK 110 | RATHKEALE 110 | 1 | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 14/10/2020 | 16/10/2020 |  | Scheduled
CAPX2020010910460170 | TO-20-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | LIMERICK 110 | LIMERICK 38 | T141 | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Reference
CAPX2020010910331715 | TO-20-LIM-T142-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T142 | LIMERICK 110 | LIMERICK 38 | T142 | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1217 | TO-20-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | LISDRUM 110 | LISDRUM 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04076 | TO-20-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | LISDRUM 110 | LISDRUM 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039705 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460171 | TO-20-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | LISDRUM 110 | LISDRUM 110 | 110SA1 | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331716 | TO-20-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | LISDRUM 110 | LISDRUM 110 | 110SA1 | As a consequence of LIS-110SA2: 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV | PR0001 | 11/05/2020 | 15/05/2020 |  | Proposed
CAPX2020010910331717 | TO-20-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | LISDRUM 110 | LISDRUM 110 | 110SA2 | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV | PR0001 | 11/05/2020 | 15/05/2020 |  | Proposed
CAPX2020010910460172 | TO-20-LIS-110SA2-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | LISDRUM 110 | LISDRUM 110 | 110SA2 | As a consequence of LIS-110SA1: 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460173 | TO-20-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | LISDRUM 110 | LISDRUM 110 | CAP1 | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1197 | TO-20-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | LISDRUM 110 | LISDRUM 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0199 | TO-20-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | LISDRUM 110 | LISDRUM 110 | CAP2 | Contact resistance measurement on the ci | 901078676 | 10/08/2020 | 10/08/2020 | 1 | Scheduled
CAPX2020010910331718 | TO-20-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | LISDRUM 110 | LISDRUM 110 | CAP2 | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0212 | TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | LISDRUM 110 | LOUTH 110 | 1 | Total Maintenance Outage Duration Requested |  | 16/07/2020 | 17/07/2020 |  | Scheduled
20EG10327 | TO-20-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | LISDRUM 110 | LOUTH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901129596 | 16/07/2020 | 17/07/2020 | 4 | Scheduled
20CM0208 | TO-20-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | LISDRUM 110 | LOUTH 110 | 1 | Surge counters need replacement on R/S/T | 900982920 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910460174 | TO-20-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | LISDRUM 110 | LOUTH 110 | 1 | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5223 | TO-20-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | LISDRUM 110 | LOUTH 110 | 1 | Hotspot 1 (SC AM No.52 Span 51/52) Jumper terminal (Repair ASAP) |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD1391 | TO-20-LIS-SKL-1-03 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0213 | TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 11/05/2020 | 15/05/2020 |  | Proposed
TOP200429163455 | TO-20-LIS-SKL-1-02 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | Hot spot detected on Lisdrum Cubicle DA S Pha |  | 14/09/2020 | 25/09/2020 |  | Scheduled
20EG00639 | TO-20-LIS-SKL-1-04 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | 110kV SF6 Cubicle Ordinary Service. do under OD1391 | 901129864 | 21/09/2020 | 25/09/2020 | 4 | Proposed
20EG00640 | TO-20-LIS-SKL-1-04 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | 110kV MO Cubicle Ordinary Service.do under OD1391 | 901129823 | 21/09/2020 | 25/09/2020 | 4 | Proposed
CAPX2020010910331719 | TO-20-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | LISDRUM 110 | SHANKILL 110 | 1 | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV | PR0001 | 11/05/2020 | 15/05/2020 |  | Proposed
CAPX2020010910460175 | TO-20-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | LISDRUM 110 | LISDRUM 38 | T141 | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331720 | TO-20-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | LISDRUM 110 | LISDRUM 38 | T142 | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV | PR0001 | 11/05/2020 | 15/05/2020 |  | Reference (Proposed)
CAPX2020010910351154 | TO-20-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | LISHEEN 110 | LISHEEN 110 | 110SA1-2 | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351155 | TO-20-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | LISHEEN 110 | LISHEEN 110 | 110SA2-4 | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200611120400 | TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | LISHEEN 110 | LISHEEN 20 | T122 | Customer outage request for 2 WD |  | 06/07/2020 | 07/07/2020 |  | Scheduled
OD0561 | TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | LISHEEN 110 | LISHEEN 20 | T122 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 07/07/2020 |  | Scheduled
19EG11186 | TO-20-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | LISHEEN 110 | LISHEEN 20 | T122 | 110kV SF6 Cubicle Operational Test |  | 06/07/2020 | 07/07/2020 | 4 | Scheduled
CAPX2020010910351156 | TO-20-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | LISHEEN 110 | LISHEEN 20 | T122 | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351157 | TO-20-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | LISHEEN 110 | LISHEEN 38 | T142 | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200114103334 | TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | LISHEEN 110 | THURLES 110 | 1 | P3 Protection maintenance of 7SA612 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0214 | TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | LISHEEN 110 | THURLES 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN5918 | TO-20-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | LISHEEN 110 | THURLES 110 | 1 | 2018HP-1[25]Bird Nestsremove asap | 900988512 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19LN5924 | TO-20-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | LISHEEN 110 | THURLES 110 | 1 | 2018HP-1[47]Bird Nestsremove asap | 900988515 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910351158 | TO-20-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | LISHEEN 110 | THURLES 110 | 1 | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0905 | TO-20-LWD-110SA1-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23205 | TO-20-LWD-110SA1-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA1 | 110kV Sect / Dist Operational Test | 901042978 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351124 | TO-20-LWD-110SA1-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA1 | As a consequence of LWD-110SA2: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351120 | TO-20-LWD-110SA1-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA1 | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1092 | TO-20-LWD-110SA2-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351121 | TO-20-LWD-110SA2-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA2 | As a consequence of LWD-110SA1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23206 | TO-20-LWD-110SA2-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA2 | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351125 | TO-20-LWD-110SA2-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | LODGEWOOD 110 | LODGEWOOD 110 | 110SA2 | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0416 | TO-20-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | LODGEWOOD 220 | LODGEWOOD 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02151 | TO-20-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | LODGEWOOD 220 | LODGEWOOD 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02159 | TO-20-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | LODGEWOOD 220 | LODGEWOOD 220 | 220K1-2 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02153 | TO-20-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | LODGEWOOD 220 | LODGEWOOD 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02152 | TO-20-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | LODGEWOOD 220 | LODGEWOOD 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0777 | TO-20-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | LODGEWOOD 220 | LODGEWOOD 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11194 | TO-20-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | LODGEWOOD 220 | LODGEWOOD 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02194 | TO-20-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | LODGEWOOD 220 | LODGEWOOD 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02190 | TO-20-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | LODGEWOOD 220 | LODGEWOOD 110 | T2102 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351126 | TO-20-LWD-T2102-02 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | LODGEWOOD 220 | LODGEWOOD 110 | T2102 | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0660 | TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | LONG POINT 220 | LONG POINT G1 | T2002 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 21/07/2020 |  | Scheduled
20EG10965 | TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | LONG POINT 220 | LONG POINT G1 | T2002 | 2200kV SF6 Cubicle Operational Test | 901129732 | 20/07/2020 | 21/07/2020 | 4 | Scheduled
20EG20361 | TO-20-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | LONG POINT 220 | LONG POINT G1 | T2002 | Cable Insp. 400 & 220kV Feeder XLPE | 901129020 | 20/07/2020 | 21/07/2020 | 4 | Scheduled
TOP200713132559 | TO-20-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | LOUTH 110 | LOUTH 110 | 110A1 | BB changeover | BB0001 | 27/08/2020 | 27/08/2020 |  | Scheduled
TOP200713132700 | TO-20-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | LOUTH 110 | LOUTH 110 | 110A2 | BB changeover | BB0001 | 27/08/2020 | 27/08/2020 |  | Scheduled
TOP200713132743 | TO-20-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | LOUTH 110 | LOUTH 110 | 110B1 | BB changeover | BB0001 | 27/08/2020 | 27/08/2020 |  | Scheduled
TOP200713132829 | TO-20-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | LOUTH 110 | LOUTH 110 | 110B2 | BB changeover | BB0001 | 27/08/2020 | 27/08/2020 |  | Scheduled
TOP200713132912 | TO-20-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | LOUTH 220 | LOUTH 220 | 220A1 | BB changeover | BB0001 | 03/09/2020 | 03/09/2020 |  | Scheduled
TOP200713132955 | TO-20-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | LOUTH 220 | LOUTH 220 | 220A2 | BB changeover | BB0001 | 03/09/2020 | 03/09/2020 |  | Scheduled
TOP200713133033 | TO-20-220 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | LOUTH 220 | LOUTH 220 | 220B1 | BB changeover | BB0001 | 03/09/2020 | 03/09/2020 |  | Scheduled
CAPX2019101011582103 | TO-20-220 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | LOUTH 220 | LOUTH 220 | 220B1 | Energise new coupler DB1 and coupler CB | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011582102 | TO-20-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | LOUTH 220 | LOUTH 220 | 220B1 | connection between new DB1 and DA1 | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011582101 | TO-20-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | LOUTH 220 | LOUTH 220 | 220B1 | Replace DB1 and coupler CB | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101011582104 | TO-20-220 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | LOUTH 220 | LOUTH 220 | 220B1 | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713133114 | TO-20-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | LOUTH 220 | LOUTH 220 | 220B2 | BB changeover | BB0001 | 03/09/2020 | 03/09/2020 |  | Scheduled
OD0418 | TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | LOUTH 220 | LOUTH 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 23/11/2020 | 25/11/2020 |  | Scheduled
20CM0202 | TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | LOUTH 220 | LOUTH 220 | 220K1-2 | N O 1 F00 220 Coupler Switching and Ex | 901074162 | 23/11/2020 | 25/11/2020 | 1 | Scheduled
18EG10692 | TO-20-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | LOUTH 220 | LOUTH 220 | 220K1-2 | 220kV MO Cubicle Operational Test | 901038920 | 23/11/2020 | 25/11/2020 | 3 | Scheduled
CAPX2019101011582100 | TO-20-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | LOUTH 220 | LOUTH 220 | 220K1-2 | Replacement of coupler | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0782 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 22/07/2020 |  | Scheduled
20CM0203 | TO-20-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | Replace Drycol Breather | 900821328 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG02004 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 220/110 & 275/220 TRAFO COND. ASSESSMENT | 901129265 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
20EG02003 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 275KV CUBICLE CONDITION ASSESSMENT | 901129257 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
20EG02005 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 220/110kV Trafo Tap Changer Inspection | 901130086 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
19CM0088 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | Louth AT1 Transformer: Drycol Replacement | 901039328 | 29/06/2020 | 22/07/2020 | 2 | Scheduled
19EG01999 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 220kV MO Cubicle Ordinary Service | 901041554 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
19EG02000 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 275kV MO Cubicle Ordinary Service | 901041555 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
19EG02001 | TO-20-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | LOUTH 220 | LOUTH 275 | AT1 | 220/110 & 275/220 Trafo Ordinary Service | 901042117 | 29/06/2020 | 22/07/2020 | 4 | Scheduled
OD0783 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | Total Maintenance Outage Duration Requested |  | 30/07/2020 | 20/08/2020 |  | Scheduled
20EG02007 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | 275kV SF6 Cubicle Ordinary Service |  | 30/07/2020 | 20/08/2020 | 4 | Scheduled
18CM0273 | TO-20-LOU-AT2-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | O 1 AT2 Trafo mech box Excessive conde | 900962773 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG02008 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | 220/110 & 275/220 Trafo Ordinary Service |  | 30/07/2020 | 20/08/2020 | 4 | Scheduled
20EG02006 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | 220kV SF6 Cubicle Ordinary Service |  | 30/07/2020 | 20/08/2020 | 4 | Scheduled
20CM0204 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | Invesigate system fault | 901059811 | 30/07/2020 | 20/08/2020 | 1 | Scheduled
20EG20608 | TO-20-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | LOUTH 220 | LOUTH 275 | AT2 | Cable Insp. 400 & 220kV Feeder XLPE |  | 30/07/2020 | 20/08/2020 | 4 | Scheduled
OD0784 | TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Total Maintenance Outage Duration Requested |  | 23/07/2020 | 29/07/2020 |  | Scheduled
20CM0206 | TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Replace Sensor | 901059908 | 23/07/2020 | 29/07/2020 | 1 | Scheduled
20CM0207 | TO-20-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Replace Conservator tank supports AT3 | 900908057 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19CM0087 | TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Louth AT3 Transformer: Drycol Replacement | 901039329 | 23/07/2020 | 29/07/2020 | 2 | Scheduled
20CM0205 | TO-20-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Replace Drycol Breather | 900821331 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG20609 | TO-20-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | LOUTH 220 | LOUTH 275 | AT3 | Cable Insp. 400 & 220kV Feeder XLPE | 901129023 | 23/07/2020 | 29/07/2020 | 4 | Scheduled
20CM0201 | TO-20-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | LOUTH 110 | LOUTH 110 | CAP1 | Surge counters/Ammeters on R/S/T phases | 900982921 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD0215 | TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | LOUTH 110 | MEATH HILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 05/05/2020 | 08/05/2020 |  | Scheduled
20CM0372 | TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | LOUTH 110 | MEATH HILL 110 | 1 | EMP AMS: Check VT bellows on R,S and T p | 901087475 | 05/05/2020 | 08/05/2020 | 1 | Scheduled
20LN4366 | TO-20-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | LOUTH 110 | MEATH HILL 110 | 1 | 2019HP-1[72]Stays-Replace broken | 901085133 | 05/05/2020 | 08/05/2020 | 4 | Scheduled
OD0216 | TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | LOUTH 110 | MULLAGHARLIN 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/11/2020 | 06/11/2020 |  | Scheduled
20CM0209 | TO-20-LOU-MLN-1-03 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | LOUTH 110 | MULLAGHARLIN 110 | 1 | N O 1 H01 Mullagharlin Switching and | 901059534 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG10335 | TO-20-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | LOUTH 110 | MULLAGHARLIN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 06/11/2020 | 06/11/2020 | 4 | Scheduled
CAPX2020010910460185 | TO-20-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | LOUTH 110 | MULLAGHARLIN 110 | 1 | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10337 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00653 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 110kV MO Cubicle Ordinary Service | 901050323 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN4436 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 2019HP-1[126]Bird Nests | 901084320 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN4438 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 2019HP-1[128]Bird Nests | 901084321 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN4440 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 2019HP-1[130]Bird Nests | 901084322 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20LN4458 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 2019HP-1[197]Insulator broken aux string | 901084924 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460199 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5224 | TO-20-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | Am No.165 165 - 166 Right Dead end termination Replace joint within 3 months pending TSO review. | 901110486 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5225 | TO-20-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | R1 107 - 108 Right Mid span joint Replace joint within 6 months pending TSO review. | 901110487 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5226 | TO-20-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | Am No.51 51 - 52 Right Dead end termination Replace joint immediately pending TSO review. | 901110488 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN4433 | TO-20-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | LOUTH 110 | RATRUSSAN 110 | 1 | 2019HP-1[123]Bird Nests | 901084279 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0778 | TO-20-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | LOUTH 220 | LOUTH 110 | T2101 | Total Maintenance Outage Duration Requested |  | 03/11/2020 | 05/11/2020 |  | Scheduled
20EG11120 | TO-20-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | LOUTH 220 | LOUTH 110 | T2101 | 220/110 & 275/220 Trafo Operational Test |  | 03/11/2020 | 05/11/2020 | 4 | Scheduled
19CM0086 | TO-20-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | LOUTH 220 | LOUTH 110 | T2101 | Louth T2101 Transformer: Camlin Totus G9 Gas in Oil Monitor | 901039288 | 03/11/2020 | 05/11/2020 | 2 | Scheduled
OD0779 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 20/03/2020 |  | Scheduled
PROT2020042 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | P2 Protection maintenance of R1Z23b, ISM21 |  | 09/03/2020 | 20/03/2020 | 2 | Scheduled
20CM0215 | TO-20-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | ABB to repair an oil leak on Louth T2102 | 900950041 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0214 | TO-20-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | Shot blast and treat main cover corrosio | 900908033 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0213 | TO-20-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | Repair leak on LV bushing, bushing needs | 900908023 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0212 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | repair leak on LV bushings | 900789878 | 09/03/2020 | 20/03/2020 | 1 | Scheduled
19CM0085 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | Louth T2102 Transformer: Repair leak on LV bushing, bushing needs to be removed and seals replaced by ABB Repeat tan delta and FDS tests on transformer | 901039286 | 09/03/2020 | 20/03/2020 | 2 | Scheduled
20EG11122 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | 220kV MO Cubicle Operational Test | 901129539 | 09/03/2020 | 20/03/2020 | 4 | Scheduled
20EG11121 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | 110kV MO Cubicle Operational Test | 901129471 | 09/03/2020 | 20/03/2020 | 4 | Scheduled
20CM0373 | TO-20-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | LOUTH 220 | LOUTH 110 | T2102 | EMP AMS Replace CB Counter | 901087467 | 09/03/2020 | 20/03/2020 | 1 | Scheduled
OD0780 | TO-20-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | LOUTH 220 | LOUTH 110 | T2103 | Total Maintenance Outage Duration Requested |  | 12/10/2020 | 23/10/2020 |  | Scheduled
19EG01987 | TO-20-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | LOUTH 220 | LOUTH 110 | T2103 | 220/110 & 275/220 Trafo Ordinary Service | 901042116 | 12/10/2020 | 23/10/2020 | 4 | Scheduled
19EG01986 | TO-20-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | LOUTH 220 | LOUTH 110 | T2103 | 220kV SF6 Cubicle Ordinary Service | 901042343 | 12/10/2020 | 23/10/2020 | 4 | Scheduled
20EG11124 | TO-20-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | LOUTH 220 | LOUTH 110 | T2103 | 110kV SF6 Cubicle Operational Test |  | 12/10/2020 | 23/10/2020 | 4 | Scheduled
20EG06014 | TO-20-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | LOUTH 220 | LOUTH 110 | T2103 | HV Pressure Vessel Inspection |  | 12/10/2020 | 23/10/2020 | 4 | Scheduled
PROT2020043 | TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | P2 Protection maintenance of 7SA511, 7SA511, 7UT92 |  | 04/03/2020 | 06/03/2020 | 2 | Scheduled
OD0781 | TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | Total Maintenance Outage Duration Requested |  | 04/03/2020 | 06/03/2020 |  | Scheduled
19EG11127 | TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | 110kV SF6 Cubicle Operational Test | 901038927 | 04/03/2020 | 06/03/2020 | 4 | Scheduled
20CM0217 | TO-20-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | ESBIN01 GE are to supply a new Hydran 20 | 900873633 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG11128 | TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | 220kV SF6 Cubicle Operational Test | 901038922 | 04/03/2020 | 06/03/2020 | 4 | Scheduled
19EG11129 | TO-20-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | LOUTH 220 | LOUTH 110 | T2104 | 220/110 & 275/220 Trafo Operational Test | 901045371 | 04/03/2020 | 06/03/2020 | 4 | Scheduled
PROT2020037 | TO-20-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | LOUTH 275 | TANDRAGEE 275 | 2 | P2 Protection maintenance of 7SA513, LFZP111 |  | 30/07/2020 | 20/08/2020 | 2 | Scheduled
TOP191202115939 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 2018HP-1[189]Check Struct/Found/etc-base | 900988614 | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202115954 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 2018HP-1[Am 128]Bird Nests | 900988605 | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202115900 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 1[67] Replace all composite strain insulators with glass | 900944377 | 25/05/2020 | 19/06/2020 |  | Scheduled
OD0300 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202120016 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV MO Cubicle Ordinary Service |  | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202115831 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV SF6 Cubicle Ordinary Service |  | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202120222 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | P3 Protection Maintenance of 7SA612, REL521 |  | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202115806 | TO-20-LOU-WOO-1-03 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020125 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | P3 Protection maintenance of 7SA612, REL521 |  | 25/05/2020 | 19/06/2020 | 3 | Scheduled
PROT2020126 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | P3 Protection maintenance of 7SA513, REL521 |  | 25/05/2020 | 19/06/2020 | 3 | Scheduled
CAPX2020022810422500 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | Uprate bay conductor on Louth - Woodland circuit | MC0334 | 25/05/2020 | 19/06/2020 |  | Scheduled
TOP191202120240 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | P3 Protection Maintenance of 7SA513, REL521 |  | 25/05/2020 | 19/06/2020 |  | Scheduled
20CM0218 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | N O 1 Woodland F03 Switching and Extra | 901081602 | 25/05/2020 | 19/06/2020 | 1 | Scheduled
15EG00901 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV Cubicle Condition Assessment | 901038535 | 25/05/2020 | 19/06/2020 | 1 | Scheduled
14EG00899 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV MO Cubicle Ordinary Service | 901050446 | 25/05/2020 | 19/06/2020 | 1 | Scheduled
20CM0331 | TO-20-LOU-WOO-1-04 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | O. ESBI Inspect and test all the cylind | 900444614 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
16EG00900 | TO-20-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | 220kV SF6 Cubicle Ordinary Service | 901042336 | 25/05/2020 | 19/06/2020 | 1 | Scheduled
CAPX2019101011582105 | TO-20-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | LOUTH 220 | WOODLAND 220 | 1 | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB | CP0799 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1341 | TO-20-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | MACETOWN 110 | MACETOWN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04079 | TO-20-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | MACETOWN 110 | MACETOWN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039707 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1251 | TO-20-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | MACETOWN 110 | SNUGBOROUGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 16/11/2020 | 18/11/2020 |  | Scheduled
20EG11333 | TO-20-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | MACETOWN 110 | SNUGBOROUGH 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 16/11/2020 | 18/11/2020 | 4 | Scheduled
19EG23699 | TO-20-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | MACETOWN 110 | SNUGBOROUGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901068538 | 16/11/2020 | 18/11/2020 | 4 | Scheduled
20EG20709 | TO-20-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | MACETOWN 110 | SNUGBOROUGH 110 | 1 | Cable Insp. 110kV XLPE |  | 16/11/2020 | 18/11/2020 | 4 | Scheduled
PROT2020183 | TO-20-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | MACETOWN 110 | MACETOWN 20 | T121 | P3 Protection maintenance of 7SJ511 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0565 | TO-20-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | MACETOWN 110 | MACETOWN 20 | T124 | Total Maintenance Outage Duration Requested |  | 17/11/2020 | 17/11/2020 |  | Scheduled
18EG10881 | TO-20-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | MACETOWN 110 | MACETOWN 20 | T124 | 110kV SF6 Cubicle Operational Test | 901038753 | 17/11/2020 | 17/11/2020 | 3 | Scheduled
OD1342 | TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 16/03/2020 |  | Scheduled
TOP200224110915 | TO-20-MAC-110SA1-06 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Proximity outage (SA2) |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18CM0189 | TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | NO 2 -"T" missing from upright support | 900955833 | 09/03/2020 | 16/03/2020 | 2 | Scheduled
CAPX2019100210345707 | TO-20-MAC-110SA1-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay. | CP0829 | 09/03/2020 | 16/03/2020 |  | Scheduled
CAPX2019100210345710 | TO-20-MAC-110SA1-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345711 | TO-20-MAC-110SA1-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Old SA 1 is to be decommissioned and removed from underneath the busbar. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345715 | TO-20-MAC-110SA1-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345718 | TO-20-MAC-110SA1-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345722 | TO-20-MAC-110SA1-04 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345731 | TO-20-MAC-110SA1-05 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | MACROOM 110 | MACROOM 110 | 110SA1 | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200224110807 | TO-20-MAC-110SA2-03 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | MACROOM 110 | MACROOM 110 | 110SA2 | Proximity outage (SA1) |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345716 | TO-20-MAC-110SA2-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | MACROOM 110 | MACROOM 110 | 110SA2 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345703 | TO-20-MAC-110SA2-01 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | MACROOM 110 | MACROOM 110 | 110SA2 | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019102112121226 | TO-20-MAC-110SA2-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | MACROOM 110 | MACROOM 110 | 110SA2 | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345719 | TO-20-MAC-110SA2-02 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA2 | MACROOM 110 | MACROOM 110 | 110SA2 | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar. | CP0829 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100210345704 | TO-20-MAC-T142-01 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | MACROOM 110 | MACROOM 38 | T142 | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2. | CP0829 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100210345717 | TO-20-MAC-T142-02 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | MACROOM 110 | MACROOM 38 | T142 | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2 | CP0829 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019102112121227 | TO-20-MAC-T142-03 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | MACROOM 110 | MACROOM 38 | T142 | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1. | CP0829 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0420 | TO-20-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | MARINA 110 | MARINA 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19LN0893 | TO-20-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | MARINA 110 | MARINA 110 | 110K1-2 | O1-110kv SA interlocking not working cor | 900981433 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1299 | TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | MARINA 110 | MARINA GT | T107 | Total Maintenance Outage Duration Requested |  | 23/07/2020 | 23/07/2020 |  | Scheduled
20EG10967 | TO-20-MR-T107-02 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | MARINA 110 | MARINA GT | T107 | 110KV GIS Cubicle Operational Test |  | 23/07/2020 | 23/07/2020 | 4 | Scheduled
TOP200210150628 | TO-20-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | MARINA 110 | TRABEG 110 | 1 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020102 | TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | MARINA 110 | TRABEG 110 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 21/09/2020 | 24/09/2020 | 3 | Scheduled
OD0220 | TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | MARINA 110 | TRABEG 110 | 2 | Total Maintenance Outage Duration Requested |  | 21/09/2020 | 24/09/2020 |  | Scheduled
TOP200210150446 | TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | MARINA 110 | TRABEG 110 | 2 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 21/09/2020 | 24/09/2020 |  | Scheduled
18EG10341 | TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | MARINA 110 | TRABEG 110 | 2 | 110kV SF6 Cubicle Operational Test | 901038815 | 21/09/2020 | 24/09/2020 | 3 | Scheduled
20EG20711 | TO-20-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | MARINA 110 | TRABEG 110 | 2 | Cable Insp. 110kV XLPE |  | 21/09/2020 | 24/09/2020 | 4 | Scheduled
TOP200814130538 | TO-20-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | MAYNOOTH 110 | MAYNOOTH 110 | 110A1 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814130624 | TO-20-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | MAYNOOTH 110 | MAYNOOTH 110 | 110A2 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814130708 | TO-20-110 kV A3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | MAYNOOTH 110 | MAYNOOTH 110 | 110A3 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814130751 | TO-20-110 kV A4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A4 | MAYNOOTH 110 | MAYNOOTH 110 | 110A4 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814130832 | TO-20-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | MAYNOOTH 110 | MAYNOOTH 110 | 110B1 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814130914 | TO-20-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | MAYNOOTH 110 | MAYNOOTH 110 | 110B2 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814131006 | TO-20-110 kV B3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | MAYNOOTH 110 | MAYNOOTH 110 | 110B3 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
TOP200814131115 | TO-20-110 kV B4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B4 | MAYNOOTH 110 | MAYNOOTH 110 | 110B4 | Busbar Changeover | BB0001 | 19/11/2020 | 19/11/2020 |  | Scheduled
OD0421 | TO-20-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | MAYNOOTH 110 | MAYNOOTH 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01209 | TO-20-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | MAYNOOTH 110 | MAYNOOTH 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0422 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020168 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG01215 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110kV Sect / Dist Ordinary Service | 901038577 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01216 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110kV SF6 Cubicle Ordinary Service | 901042253 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01214 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110kV Sect / Dist Ordinary Service | 901038576 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01213 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110kV Sect / Dist Ordinary Service | 901038575 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01212 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110kV Sect / Dist Ordinary Service | 901038574 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01217 | TO-20-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | MAYNOOTH 110 | MAYNOOTH 110 | 110K3-4 | 110KV CUBICLE CONDITION ASSESSMENT | 900858412 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200814131212 | TO-20-220 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | MAYNOOTH 220 | MAYNOOTH 220 | 220A1 | Busbar Changeover | BB0001 | 26/11/2020 | 26/11/2020 |  | Scheduled
CAPX2020011309233000 | TO-20-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | MAYNOOTH 220 | MAYNOOTH 220 | 220A1 | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200814131255 | TO-20-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | MAYNOOTH 220 | MAYNOOTH 220 | 220A2 | Busbar Changeover |  | 26/11/2020 | 26/11/2020 |  | Scheduled
TOP200814131338 | TO-20-220 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | MAYNOOTH 220 | MAYNOOTH 220 | 220B1 | Busbar Changeover | BB0001 | 26/11/2020 | 26/11/2020 |  | Scheduled
CAPX2020011309233001 | TO-20-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | MAYNOOTH 220 | MAYNOOTH 220 | 220B1 | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200814131417 | TO-20-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | MAYNOOTH 220 | MAYNOOTH 220 | 220B2 | Busbar Changeover | BB0001 | 26/11/2020 | 26/11/2020 |  | Scheduled
OD0423 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 15/09/2020 | 17/09/2020 |  | Scheduled
20CM0475 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | Maynooth 220kV Coupler Sectionaliser SA1 T Phas e Hotspot found on T phase SA1 sectionaliser disconnect DUE: next available opportunity. |  | 15/09/2020 | 17/09/2020 | 1 | Scheduled
20EG10712 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | 220kV SF6 Cubicle Operational Test |  | 15/09/2020 | 17/09/2020 | 4 | Scheduled
20CM0476 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | Maynooth 220kV Coupler Sectionaliser SA2 All, left to right R,S & T Hotspot found on all 3 phases ofSA2 sectionaliser disconnects DUE : next available opportunity. |  | 15/09/2020 | 17/09/2020 | 1 | Scheduled
20EG10709 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | 220kV Sect / Dist Operational Test |  | 15/09/2020 | 17/09/2020 | 4 | Scheduled
20EG10710 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | 220kV Sect / Dist Operational Test |  | 15/09/2020 | 17/09/2020 | 4 | Scheduled
20EG10708 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | 220kV Sect / Dist Operational Test |  | 15/09/2020 | 17/09/2020 | 4 | Scheduled
20EG10711 | TO-20-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | MAYNOOTH 220 | MAYNOOTH 220 | 220K1-2 | 220kV Sect / Dist Operational Test |  | 15/09/2020 | 17/09/2020 | 4 | Scheduled
OD0221 | TO-20-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | MAYNOOTH 110 | RINAWADE 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10343 | TO-20-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | MAYNOOTH 110 | RINAWADE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038949 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00665 | TO-20-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | MAYNOOTH 110 | RINAWADE 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042239 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601107 | TO-20-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | MAYNOOTH 110 | RINAWADE 110 | 1 | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351131 | TO-20-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | MAYNOOTH 110 | RINAWADE 110 | 1 | Proximity outage for work on Maynooth 220 kV K3-4 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101511561317 | TO-20-MAY-RYB GIS-1-04 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | MAYNOOTH 110 | RYEBROOK GIS 110 | 1 | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131 | CP1056 | 12/11/2020 | 13/11/2020 |  | Proposed
CAPX2020101511561321 | TO-20-MAY-RYB GIS-1-04 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | MAYNOOTH 110 | RYEBROOK GIS 110 | 1 | EI: Energise T131 | CP1056 | 12/11/2020 | 13/11/2020 |  | Proposed
CAPX2020010910351132 | TO-20-MAY-RYB GIS-1-05 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | MAYNOOTH 110 | RYEBROOK GIS 110 | 1 | Proximity outage for work on Maynooth 110 kV K3-4 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101113002149 | TO-20-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | MAYNOOTH 110 | RYEBROOK GIS 110 | 1 | EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
OD0301 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | Total Maintenance Outage Duration Requested |  | 22/06/2020 | 02/07/2020 |  | Scheduled
17LN3058 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | 2016HP-2[2 & 3]Insulator Fit Dups | 900819839 | 22/06/2020 | 02/07/2020 | 2 | Scheduled
19EG00906 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | 220kV Cubicle Condition Assessment | 901038544 | 22/06/2020 | 02/07/2020 | 4 | Scheduled
19CM0318 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled | 901076415 | 22/06/2020 | 02/07/2020 | 1 | Scheduled
20LN5196 | TO-20-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | Hotspot 2 (R2 Span 255/256) Right phase midspan (Repair by 17th July 2020) | 901110131 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN4588 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | 2019HP-1[47-48]Conflicts 10/20kV pole | 901090694 | 22/06/2020 | 02/07/2020 | 4 | Scheduled
20LN5195 | TO-20-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | Hotspot 1 (R1 Span 81/82) Right phase midspan (Repair by 17th July 2020) | 901110127 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN5197 | TO-20-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | Hotspot 3 (R1 Span 271/272) Right phase midspan (Repair by 17th July 2020) | 901110136 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN4591 | TO-20-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | MAYNOOTH 220 | SHANNONBRIDGE 220 | 1 | 2019HP-1[51-52]Conflicts 10/20kV pole | 901090695 | 22/06/2020 | 02/07/2020 | 4 | Scheduled
OD0785 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02021 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02020 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02022 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | 220/110 & 275/220 - Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02023 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02024 | TO-20-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | MAYNOOTH 220 | MAYNOOTH 110 | T2101 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0786 | TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | Total Maintenance Outage Duration Requested |  | 14/07/2020 | 17/07/2020 |  | Scheduled
19EG11144 | TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | 220/110 & 275/220 Trafo Operational Test | 901080655 | 14/07/2020 | 17/07/2020 | 3 | Scheduled
15CM0095 | TO-20-MAY-T2102-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | Replace/repair rust on main cover bolts and channel on top of the tank | 900693054 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17CM0194 | TO-20-MAY-T2102-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | O 1. ESBI Inpsect transformer (Tamini) f | 900373274 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG11142 | TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | 110kV SF6 Cubicle Operational Test | 901038584 | 14/07/2020 | 17/07/2020 | 3 | Scheduled
19CM0083 | TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | Maynooth T2102 Transformer: Drycol Replacement | 901039322 | 14/07/2020 | 17/07/2020 | 2 | Scheduled
20EG11143 | TO-20-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | MAYNOOTH 220 | MAYNOOTH 110 | T2102 | 220kV MO Cubicle Operational Test |  | 14/07/2020 | 17/07/2020 | 4 | Scheduled
OD0787 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 09/09/2020 |  | Scheduled
20CM0455 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | Hotspot 1 (110kV T-phase DB) Repair by 19th Sep 2020 | 901128564 | 07/09/2020 | 09/09/2020 | 1 | Scheduled
20EG11146 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | 220kV SF6 Cubicle Operational Test |  | 07/09/2020 | 09/09/2020 | 4 | Scheduled
20EG11147 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | 220/110 & 275/220 Trafo Operational Test |  | 07/09/2020 | 09/09/2020 | 4 | Scheduled
20EG11145 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | 110kV SF6 Cubicle Operational Test |  | 07/09/2020 | 09/09/2020 | 4 | Scheduled
19CM0082 | TO-20-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | MAYNOOTH 220 | MAYNOOTH 110 | T2103 | maynooth T2103 Transformer: E6 dial stat faulty, shot blast and treat major main cover corrosion, retest CT and LV S phase bushing, repair several fans | 901039289 | 07/09/2020 | 09/09/2020 | 2 | Scheduled
OD0788 | TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | Total Maintenance Outage Duration Requested |  | 04/08/2020 | 07/08/2020 |  | Scheduled
PROT2020044 | TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | P2 Protection maintenance of 7SA511, 7SA612, RET521 |  | 04/08/2020 | 07/08/2020 | 2 | Scheduled
18EG11149 | TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | 220kV SF6 Cubicle Operational Test | 901039022 | 04/08/2020 | 07/08/2020 | 3 | Scheduled
18EG11150 | TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | 220/110 & 275/220 Trafo Operational Test | 901045376 | 04/08/2020 | 07/08/2020 | 3 | Scheduled
20CM0235 | TO-20-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | Silica On T2104 To Be Replaced | 901080648 | 04/08/2020 | 07/08/2020 | 2 | Scheduled
19CM0080 | TO-20-MAY-T2104-03 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | Maynooth T2104 Transformer: Refurbish fans and treat corrosion on top cover. Can be done as part of next OS | 901039290 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19CM0081 | TO-20-MAY-T2104-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | MAYNOOTH 220 | MAYNOOTH 110 | T2104 | Maynooth T2104 Transformer: Drycol Replacement | 901039323 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
TOP200617143317 | TO-20-MAY-TH-1-03 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | S Phase Hotspot found on S Phase HV connection by 6th July | 20CM0450 | 06/07/2020 | 07/07/2020 |  | Scheduled
OD0302 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG20186 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 901005625 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0236 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | Low Oil / Leak- CB Oil Low | 901080651 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN6216 | TO-20-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | 2018HP-1[5]Insulatorfit duplicate | 900988793 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN6222 | TO-20-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | 2018HP-1[6]Insulatorfit duplicate | 900988794 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0384 | TO-20-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | Full overhaul of Circuit Breaker | 901087476 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0385 | TO-20-MAY-TH-1-02 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | 1.Replace R phase CB pole and drive insu | 901084687 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19LN6215 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | 2018HP-1[173]Insulatorbroken | 900988802 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0450 | TO-20-MAY-TH-1-04 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | S Phase Hotspot found on S Phas HV Connection by 6th July 2020 | 901128568 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20LN4679 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | 2019HP-1[99]Insulator Broken insulator | 901084925 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
CAPX2019100309362400 | TO-20-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | MAYNOOTH 220 | TURLOUGH HILL 220 | 1 | EI: Replacement and Commissioning of PLC Equipment | CP1022 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191107132228 | TO-20-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled | 901076417 | 07/09/2020 | 11/09/2020 |  | Tentative
OD0303 | TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Tentative
19CM0319 | TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled | 901076417 | 07/09/2020 | 11/09/2020 | 1 | Tentative
17LN3126 | TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | 2016HP-1[5-71]Check Structure -Painting | 900819860 | 07/09/2020 | 11/09/2020 | 2 | Tentative
18EG06030 | TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | HV Pressure Vessel Inspection | 900943534 | 07/09/2020 | 11/09/2020 | 3 | Tentative
19LN6274 | TO-20-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | MAYNOOTH 220 | WOODLAND 220 | 1 | 2018HP-1[5]Check Struct/Found/etc-base | 900988803 | 07/09/2020 | 11/09/2020 | 4 | Tentative
TOP200110113709 | TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | MEENTYCAT 110 | MEENTYCAT 20 | T121 | As a consequence of work on Drumkeen-Meentycat 110 kV |  | 14/09/2020 | 18/09/2020 |  | Scheduled
OD0571 | TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | MEENTYCAT 110 | MEENTYCAT 20 | T121 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
20EG00434 | TO-20-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | MEENTYCAT 110 | MEENTYCAT 20 | T121 | 110kV SF6 Cubicle Ordinary Service |  | 14/09/2020 | 18/09/2020 | 4 | Scheduled
CAPX2020010910460176 | TO-20-MID-110SA1-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | MIDLETON 110 | MIDLETON 110 | 110SA1 | As a consequence of MID-110SA2: 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1321 | TO-20-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | MIDLETON 110 | MIDLETON 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04085 | TO-20-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | MIDLETON 110 | MIDLETON 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460177 | TO-20-MID-110SA2-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | MIDLETON 110 | MIDLETON 110 | 110SA2 | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460178 | TO-20-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | MIDLETON 110 | MIDLETON 10 | T102 | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0223 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
TOP200116155349 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1) |  | 14/09/2020 | 18/09/2020 |  | Scheduled
19LN6298 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | "2018HP-2[41,42]Sus/Dup 110kV replace" | 900988883 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
20EG10347 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 110kV MO Cubicle Operational Test |  | 14/09/2020 | 18/09/2020 | 4 | Scheduled
20EG10346 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 14/09/2020 | 18/09/2020 | 4 | Scheduled
20LN4715 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 2019HP-1[22]Bird Nests Over Right phase | 901084330 | 14/09/2020 | 18/09/2020 | 2 | Scheduled
CAPX2020010910460179 | TO-20-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 14/09/2020 | 18/09/2020 |  | Scheduled
CAPX2020010910460181 | TO-20-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | MONETEEN 110 | MONETEEN 110 | 110SA1 | As a consequence of MTN-110SA2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Tentative
OD1343 | TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | MONETEEN 110 | MONETEEN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Tentative
19EG04087 | TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | MONETEEN 110 | MONETEEN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039690 | 07/09/2020 | 11/09/2020 | 4 | Tentative
CAPX2020010910460182 | TO-20-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | MONETEEN 110 | MONETEEN 110 | 110SA2 | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Tentative
OD0224 | TO-20-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | MONETEEN 110 | MUNGRET 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00677 | TO-20-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | MONETEEN 110 | MUNGRET 110 | 1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0225 | TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | MONETEEN 110 | MUNGRET 110 | 2 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Tentative
20EG10349 | TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | MONETEEN 110 | MUNGRET 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 07/09/2020 | 11/09/2020 | 4 | Tentative
CAPX2020010910460183 | TO-20-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | MONETEEN 110 | MUNGRET 110 | 2 | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Tentative
TOP191128132548 | TO-20-400 kV A1 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400A1 | MONEYPOINT 400 | MONEYPOINT 400 | 400A1 | A1 / A3 BB In Turn, SA1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191128132341 | TO-20-400 kV A2 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400A2 | MONEYPOINT 400 | MONEYPOINT 400 | 400A2 | A2 / A4 BB In Turn, SA2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191128132629 | TO-20-400 kV B1 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400B1 | MONEYPOINT 400 | MONEYPOINT 400 | 400B1 | B1 / B3 BB In Turn, SB1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191128132456 | TO-20-400 kV B2 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400B2 | MONEYPOINT 400 | MONEYPOINT 400 | 400B2 | B2 / B4 BB In Turn , SB2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1158 | TO-20-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | MONEYPOINT GIS 110 | MONEYPOINT GIS 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23266 | TO-20-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | MONEYPOINT GIS 110 | MONEYPOINT GIS 110 | 110SA1-2CB | 110KV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200110102522 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | Total Maintenance Outage Duration Requested | OD0321 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103148 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | Cable Insp. 400kV XLPE | 19EG23677 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103319 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[166]Bird Nests | 20LN4741 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103441 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[13]Insul&HW Replace check | 19LN6395 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103438 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[27]Insul&HW Replace check | 19LN6396 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103434 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[55A]Insulator-replace | 19LN6398 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103431 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-2[11]Insul&HW Replace check | 19LN6393 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103322 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[11]Insulator Broken | 20LN4755 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110102909 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2017HP-1[199]Earths-Check S/W hardware | 18LN1616 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103413 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-3[8]Insul&HW Replace check | 19LN6392 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110102636 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 400kV SF6 Cubicle Operational Test | 18EG10486 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103316 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[175]Bird Nests | 20LN4743 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103253 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[183]Bird Nests | 20LN4744 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103240 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[191]Bird Nests | 20LN4745 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103220 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2019HP-1[55A]Insulator Broken | 20LN4756 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110102925 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2017HP-1[139]Earths-Check S/W hardware | 18LN1631 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110102648 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2017HP-1[55A]Insulator Broken | 18LN1618 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200110103427 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-3[15]Insul&HW Replace check | 19LN6394 | 21/05/2020 | 09/10/2020 |  | Scheduled
TOP200908105554 | TO-20-MP GIS-OST-1-04 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | studied outage for CP0824 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200110103423 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-3[3]Insul&HW Replace check | 19LN6391 | 21/05/2020 | 09/10/2020 |  | Scheduled
19LN6362 | TO-20-MP GIS-OST-1-05 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[191]Bird Nestsremove asap | 900988946 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN6399 | TO-20-MP GIS-OST-1-05 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[74]Bird Nestsremove asap | 900988976 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN6377 | TO-20-MP GIS-OST-1-05 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[166]Bird Nestsremove asap | 900988931 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19LN6370 | TO-20-MP GIS-OST-1-05 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | 2018HP-1[176]Bird Nestsremove asap | 900988938 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2019102114275001 | TO-20-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting (part 2) | CP0824 | 21/05/2020 | 09/10/2020 |  | Scheduled
CAPX2019100210172702 | TO-20-MP GIS-OST-1-03 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet | CP0824 | 13/07/2020 | 17/07/2020 |  | Scheduled
CAPX2019100210172700 | TO-20-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | MONEYPOINT GIS 400 | OLDSTREET 400 | 1 | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting | CP0824 | 24/02/2020 | 02/04/2020 |  | Scheduled
OD1175 | TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | MONEYPOINT GIS 110 | MONEYPOINT GIS 20 | T121 | Total Maintenance Outage Duration Requested |  | 24/07/2020 | 24/07/2020 |  | Scheduled
18EG23262 | TO-20-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | MONEYPOINT GIS 110 | MONEYPOINT GIS 20 | T121 | 110KV GIS Cubicle Operational Test | 900938612 | 24/07/2020 | 24/07/2020 | 3 | Scheduled
OD1142 | TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | Total Maintenance Outage Duration Requested |  | 02/03/2020 | 06/03/2020 |  | Scheduled
20CM0244 | TO-20-MP GIS-T2102-02 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | Main Tank Conservator oil level gauge is | 901059126 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
18EG23279 | TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | 220/110 & 275/220 Trafo Operational Test | 900944114 | 02/03/2020 | 06/03/2020 | 3 | Scheduled
18EG23277 | TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | 220kV GIS Cubicle Operational Test | 900944165 | 02/03/2020 | 06/03/2020 | 3 | Scheduled
19CM0071 | TO-20-MP GIS-T2102-03 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | Replacement Oil Level Indicator for Moneypoint T2102 Main OLTC Conservator. Original oil level gauge faulty contacts and activating a contsant low oil level alarm evndo the oil level when check is ok. | 901028665 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
18CM1164 | TO-20-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | MONEYPOINT GIS 220 | MONEYPOINT GIS 110 | T2102 | The minitrans unit on T2102 in Moneypoin | 900970626 | 02/03/2020 | 06/03/2020 | 1 | Scheduled
OD0667 | TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | MONEYPOINT GIS 400 | MONEYPOINT GIS G3 | T4003 | Total Maintenance Outage Duration Requested |  | 10/06/2020 | 17/06/2020 | 2 | Scheduled
20CM0399 | TO-20-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | MONEYPOINT GIS 400 | MONEYPOINT GIS G3 | T4003 | Aux Relay - replace contactors |  | 10/06/2020 | 17/06/2020 | 2 | Scheduled
TOP191024090547 | TO-20-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4201 | Forced outage |  | 01/01/2020 | 31/12/2500 |  | Forced Out
20CM0245 | TO-20-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4201 | As part of the Fault Investigation into | 901037956 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19CM0074 | TO-20-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4201 | Ref- T4201 Bucholz alarm | 901028372 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD1223 | TO-20-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0246 | TO-20-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | Camlin Power are to install an Intego bu | 901073579 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG11152 | TO-20-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | 400kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11151 | TO-20-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0248 | TO-20-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | Atlantic Projects Company were required | 901067748 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG23485 | TO-20-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23486 | TO-20-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | MONEYPOINT GIS 400 | MONEYPOINT GIS 220 | T4202 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020127 | TO-20-MP-PRO-1-02 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | MONEYPOINT 220 | PROSPECT 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0304 | TO-20-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | MONEYPOINT 220 | PROSPECT 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG20379 | TO-20-MP-PRO-1-03 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | MONEYPOINT 220 | PROSPECT 220 | 1 | Insp. 400 & 220 Station XLPE Cable | 901129060 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10471 | TO-20-MP-PRO-1-01 | 220kV FEEDER - MONEYPOINT 220-PROSPECT 220-1 | MONEYPOINT 220 | PROSPECT 220 | 1 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1221 | TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | MONEYPOINT 400 | MONEYPOINT G1 | T4001 | Total Maintenance Outage Duration Requested |  | 24/11/2020 | 26/11/2020 |  | Scheduled
19EG23791 | TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | MONEYPOINT 400 | MONEYPOINT G1 | T4001 | Insp. 400 & 220 Station XLPE Cable | 901005716 | 24/11/2020 | 26/11/2020 | 4 | Scheduled
20EG06020 | TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | MONEYPOINT 400 | MONEYPOINT G1 | T4001 | HV Pressure Vessel Inspection |  | 24/11/2020 | 26/11/2020 | 4 | Scheduled
20EG10968 | TO-20-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | MONEYPOINT 400 | MONEYPOINT G1 | T4001 | 400kV GIS Cubicle Operational Test |  | 24/11/2020 | 26/11/2020 | 1 | Scheduled
PROT2020176 | TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | MOUNTLUCAS 110 | MOUNTLUCAS 20 | T121 | P3 Protection maintenance of 7SA612 |  | 10/06/2020 | 10/06/2020 | 3 | Scheduled
OD0838 | TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | MOUNTLUCAS 110 | MOUNTLUCAS 20 | T121 | Total Maintenance Outage Duration Requested |  | 10/06/2020 | 10/06/2020 |  | Scheduled
20EG11368 | TO-20-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | MOUNTLUCAS 110 | MOUNTLUCAS 20 | T121 | 110kV SF6 Cubicle Operational Test |  | 10/06/2020 | 10/06/2020 | 4 | Scheduled
OD1198 | TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | MOY 110 | MOY 110 | CAP1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 22/10/2020 |  | Scheduled
19EG05061 | TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | MOY 110 | MOY 110 | CAP1 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment | 901050225 | 09/03/2020 | 22/10/2020 | 4 | Scheduled
19EG05060 | TO-20-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | MOY 110 | MOY 110 | CAP1 | 110kV SF6 Cubicle Ordinary Service | 901042293 | 09/03/2020 | 22/10/2020 | 4 | Scheduled
PROT2020137 | TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | MOY 110 | MOY 110 | CAP2 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD1199 | TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | MOY 110 | MOY 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG05064 | TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | MOY 110 | MOY 110 | CAP2 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment | 901050226 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG05063 | TO-20-MOY-CAP2-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | MOY 110 | MOY 110 | CAP2 | 110kV SF6 Cubicle Ordinary Service | 901042294 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0226 | TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | MOY 110 | TAWNAGHMORE 110 | 1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 22/10/2020 |  | Scheduled
PROT2020103 | TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | MOY 110 | TAWNAGHMORE 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 09/03/2020 | 22/10/2020 | 3 | Scheduled
18EG23216 | TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | MOY 110 | TAWNAGHMORE 110 | 1 | 110kV SF6 Cubicle Operational Test | 900942733 | 09/03/2020 | 22/10/2020 | 3 | Scheduled
20CM0382 | TO-20-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | MOY 110 | TAWNAGHMORE 110 | 1 | An SF6 leak was detected on the pipework | 901090593 | 09/03/2020 | 22/10/2020 | 1 | Scheduled
OD0227 | TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | MOY 110 | TAWNAGHMORE 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG00683 | TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | MOY 110 | TAWNAGHMORE 110 | 2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23202 | TO-20-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | MOY 110 | TAWNAGHMORE 110 | 2 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020061011241501 | TO-20-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA1 | 110 kV A1 @ MLN: Civil works on bay H1 and H0 | CP1101 | 13/08/2020 | 18/09/2020 |  | Scheduled
20CM0253 | TO-20-MLN-110SA1-02 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA1 | N O 1 H00 SA2 Switching and Extra hou | 901059536 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX2020010910460186 | TO-20-MLN-110SA1-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA1 | As a consequence of MLN-110SA2: 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 13/08/2020 | 18/09/2020 |  | Scheduled
CAPX2020100909273808 | TO-20-MLN-110SA2-02 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA2 | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: 1 - H3-T121 Transfomer relabelling to H3-T123 | CP1101 | 27/10/2020 | 29/10/2020 |  | Scheduled
OD1344 | TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020061011241502 | TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA2 | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: Civil works on bay H1 and H0 | CP1101 | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04093 | TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039708 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460187 | TO-20-MLN-110SA2-01 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | MULLAGHARLIN 110 | MULLAGHARLIN 110 | 110SA2 | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0577 | TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T121 | Total Maintenance Outage Duration Requested |  | 13/08/2020 | 18/09/2020 |  | Scheduled
TOP200717132127 | TO-20-MLN-T121-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T121 | Customer outage request |  | 06/08/2020 | 07/08/2020 |  | Scheduled
CAPX2020061011241504 | TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T121 | T121 Trafo Relabelling to T123 | CP1101 | 13/08/2020 | 18/09/2020 |  | Scheduled
CAPX2020061011241503 | TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T121 | 110 kV A1 @ MLN: Civil works on bay H1 and H0 | CP1101 | 13/08/2020 | 18/09/2020 |  | Scheduled
19EG10892 | TO-20-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T121 | 110kV SF6 Cubicle Operational Test |  | 13/08/2020 | 18/09/2020 | 4 | Scheduled
TOP200717132017 | TO-20-MLN-T122-03 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T122 | Customer outage request |  | 04/08/2020 | 05/08/2020 |  | Scheduled
CAPX2020010910460188 | TO-20-MLN-T122-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | MULLAGHARLIN 110 | MULLAGHARLIN 20 | T122 | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0953 | TO-20-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | MULLINGAR 110 | MULLINGAR 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18EG04094 | TO-20-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | MULLINGAR 110 | MULLINGAR 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039452 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG02969 | TO-20-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | MULLINGAR 110 | MULLINGAR 110 | 110SA1-2CB | 110kV SF6 Cubicle Ordinary Service | 901129883 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331732 | TO-20-MUL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | MULLINGAR 110 | MULLINGAR 110 | 110SA1-2CB | 110 kV A2 @ MUL: Proximity outage for work on CAP2 | PR0001 | 06/07/2020 | 09/07/2020 |  | Scheduled
CAPX2020010910351135 | TO-20-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | MULLINGAR 110 | MULLINGAR 110 | 110SA1-2CB | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351136 | TO-20-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | MULLINGAR 110 | MULLINGAR 110 | CAP1 | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
18CM0027 | TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | MULLINGAR 110 | MULLINGAR 110 | CAP2 | Replace Densimeters on Circuit Breaker | 900869763 | 06/07/2020 | 09/07/2020 | 1 | Scheduled
20EG23621 | TO-20-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | MULLINGAR 110 | MULLINGAR 110 | CAP2 | 220kV SF6 Cubicle Operational Test | 901129545 | 06/07/2020 | 09/07/2020 | 4 | Scheduled
CAPX2020010910331733 | TO-20-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | MULLINGAR 110 | MULLINGAR 110 | CAP2 | 110 kV A2 @ MUL: Proximity outage for work on CAP2 | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351137 | TO-20-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | MULLINGAR 110 | MULLINGAR 10 | T101 | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331734 | TO-20-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | MULLINGAR 110 | MULLINGAR 10 | T102 | 110 kV A2 @ MUL: Proximity outage for work on CAP2 | PR0001 | 06/07/2020 | 09/07/2020 |  | Reference
CAPX2020010910351138 | TO-20-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | MULLINGAR 110 | MULLINGAR 38 | T141 | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910331735 | TO-20-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | MULLINGAR 110 | MULLINGAR 38 | T142 | 110 kV A2 @ MUL: Proximity outage for work on CAP2 | PR0001 | 06/07/2020 | 09/07/2020 |  | Reference
OD1300 | TO-20-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | MULREAVY 110 | MULREAVY 33 | T131 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG21305 | TO-20-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | MULREAVY 110 | MULREAVY 33 | T131 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200707112803 | TO-20-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | MUNGRET 110 | MUNGRET 10 | T101 | Customer outage requestfor tap changer maintenance on incoming transformer T101 |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910460184 | TO-20-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | MUNGRET 110 | MUNGRET 10 | T102 | As a consequence of MTN-MUN-2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 07/09/2020 | 11/09/2020 |  | Reference
OD0824 | TO-20-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | NAVAN 110 | NAVAN 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020169 | TO-20-NAV-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | NAVAN 110 | NAVAN 110 | 110SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG11349 | TO-20-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | NAVAN 110 | NAVAN 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11348 | TO-20-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | NAVAN 110 | NAVAN 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11347 | TO-20-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | NAVAN 110 | NAVAN 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP191122143225 | TO-20-NAV-M/CAP1-01 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | NAVAN 110 | NAVAN 110 | M/CAP1 | forced out |  | 01/01/2020 | 31/12/2500 |  | Forced Out
20EG05066 | TO-20-NAV-M/CAP1-02 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | NAVAN 110 | NAVAN 110 | M/CAP1 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1345 | TO-20-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG04098 | TO-20-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039710 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460190 | TO-20-NEW-110SA1-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA1 | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460196 | TO-20-NEW-110SA1-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA1 | As a consequence of NEW-110SA2: 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1323 | TO-20-NEW-110SA2-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04099 | TO-20-NEW-110SA2-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460191 | TO-20-NEW-110SA2-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA2 | As a consequence of NEW-110SA1: 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910460197 | TO-20-NEW-110SA2-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | NEWBRIDGE 110 | NEWBRIDGE 110 | 110SA2 | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0228 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | Total Maintenance Outage Duration Requested |  | 02/03/2020 | 20/03/2020 |  | Scheduled
19LN6473 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[139]Insul&HW Replace check | 900989037 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
18LN6436 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 1[214]Install Duplicate Suspension Insul | 900973635 | 02/03/2020 | 20/03/2020 | 3 | Scheduled
19LN6444 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[56-57]Conflicts-LV/MV pole | 900989023 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
19LN6445 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-2[68]Cattle Guards | 900989024 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
19LN6472 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[145]Insul&HW Replace check | 900989038 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
19LN6474 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[138]Insul&HW Replace check | 900989036 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
19LN6475 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[137]Insul&HW Replace check | 900989035 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
19LN6488 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[106]ACGFit ACG | 900989025 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
20CM0257 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | O1-Small SF6 piping to be changed on CB. | 901060158 | 02/03/2020 | 20/03/2020 | 1 | Scheduled
20CM0256 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | Replace SF6 pipework | 901059566 | 02/03/2020 | 20/03/2020 | 1 | Scheduled
19LN6469 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2018HP-1[201]Conductor Check-Top Rot | 900989041 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
20LN4815 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2019HP-1[106]Bird Nests -Remove | 901084324 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
20LN4799 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 2019HP-1[2-3]Conflicts 20kV cable pole | 901084851 | 02/03/2020 | 20/03/2020 | 4 | Scheduled
CAPX2020010910460192 | TO-20-NEW-PLS-1-02 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN5188 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | Hotspot 1 (Angle Tower No. 48, span 48/49), left Jumper Terminal | 901128694 | 02/03/2020 | 20/03/2020 | 1 | Scheduled
20LN5190 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | Hotspot 3 (Angle Tower No. 117, span 116/117), right jumper terminal | 901146901 | 02/03/2020 | 20/03/2020 | 1 | Scheduled
20LN5189 | TO-20-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | NEWBRIDGE 110 | PORTLAOISE 110 | 1 | Hotspot 2 (Angle Tower No. 116, span 115A/116), right deadend | 901146902 | 02/03/2020 | 20/03/2020 | 1 | Scheduled
CAPX2020010910460193 | TO-20-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | NEWBRIDGE 110 | NEWBRIDGE 38 | T141 | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910460198 | TO-20-NEW-T142-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T142 | NEWBRIDGE 110 | NEWBRIDGE 38 | T142 | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0305 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020129 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
PROT2020128 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG00919 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
18EG20199 | TO-20-NW-PB-1-01 | 220KV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 900913186 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG10473 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | 220kV GIS Cubicle Operational Test | 901039122 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00920 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00922 | TO-20-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | 220kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331729 | TO-20-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | NORTH WALL 220 | POOLBEG 220 | 1 | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910331730 | TO-20-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | NORTH WALL 220 | NORTH WALL G4/5 | T2004/5 | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113091528 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | Operator approval evaluations |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0790 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG02056 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 400/220kV Transformer Ordinary Service | 901041548 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02058 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 220kV Cubicle Condition Assessment | 901038565 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19EG02060 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 400/220KV TRAFO CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG02061 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 400/220kV Trafo Tap Changer Inspection |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19CM0077 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | Oldstreet T4202 Transformer: Drycol Replacement | 901039331 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG02059 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 400KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
19CM0076 | TO-20-OST-T4202-04 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | Oldstreet T4202 Transformer: Transfix G9 Installation | 901039294 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0374 | TO-20-OST-T4202-03 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | Following the increase of H2 gas within | 901090507 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG02057 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02055 | TO-20-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | 400kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601116 | TO-20-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601122 | TO-20-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601121 | TO-20-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | OLDSTREET 400 | OLDSTREET 220 | T4202 | As a consequence of OST-TY-1: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP191129100124 | TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | 220kV SF6 Cubicle Operational Test | 901039105 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0306 | TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10476 | TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0458 | TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | 220kV SF6 Cubicle Ordinary Service DUE : 17-Jul-20 | 901133678 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
CAPX20200109104601124 | TO-20-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601123 | TO-20-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601117 | TO-20-OST-TY-1-02 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN4848 | TO-20-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | OLDSTREET 220 | TYNAGH 220 | 1 | 2019HP-1[17]Bird Nests | 901084335 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200113163242 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | P1 Protection maintenance of 7SL32, FYS3L, FYG2L |  | 17/10/2020 | 30/10/2020 |  | Scheduled
OD0322 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | Total Maintenance Outage Duration Requested |  | 17/10/2020 | 30/10/2020 |  | Scheduled
19LN6530 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2018HP-1[100]Replace Memberrakers | 900989128 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
19LN6531 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2018HP-1[99]Replace Memberrakers | 900989127 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
19LN6633 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2018HP-1[115]Insulator-broken c/ph | 900989185 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
19LN6636 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2018HP-1[162]Check(General)Remove object | 900989188 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
19EG10487 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 400kV SF6 Cubicle Operational Test | 901039088 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20CM0335 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | Misc- work not on other CORRECT counters | 900788839 | 17/10/2020 | 30/10/2020 | 2 | Scheduled
20CM0337 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | SF6 leak repair | 901046071 | 17/10/2020 | 30/10/2020 | 1 | Scheduled
20EG06037 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | HV Pressure Vessel Inspection |  | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20CM0338 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | O/1 Repair to leak in concrete of Bund | 900724385 | 17/10/2020 | 30/10/2020 | 1 | Scheduled
20CM0339 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | Some work done in 2014 Beltec 2 leaks HV | 900821342 | 17/10/2020 | 30/10/2020 | 1 | Scheduled
20LN4858 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[100]Replace Member | 901086388 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4852 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[76]Bird Nests | 901084336 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4854 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[79]Bird Nests | 901084337 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4857 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[93]Bird Nests | 901084338 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4859 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[103]Insulator Broken | 901084928 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4860 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[115]Insulator Broken | 901084929 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4861 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[120]Replace Member | 901086389 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4882 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[272]Insulator Remove old insul | 901084930 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
20LN4856 | TO-20-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | OLDSTREET 400 | WOODLAND 400 | 1 | 2019HP-1[90 ]Replace Member | 901086387 | 17/10/2020 | 30/10/2020 | 4 | Scheduled
PROT2020063 | TO-20-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | OUGHTRAGH 110 | OUGHTRAGH 38 | T141 | P2 Protection maintenance of 7SJ511 |  | 14/09/2020 | 18/09/2020 | 2 | Reference
OD1249 | TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | OUGHTRAGH tee | KNOCKEARAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
PROT2020006 | TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | OUGHTRAGH tee | KNOCKEARAGH 110 | 1 | P1 Protection maintenance of 7SA511, REL521 |  | 14/09/2020 | 18/09/2020 | 1 | Scheduled
19EG10354 | TO-20-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | OUGHTRAGH tee | KNOCKEARAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038793 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
OD1250 | TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | OUGHTRAGH tee | OUGHTRAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
19LN7129 | TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | OUGHTRAGH tee | OUGHTRAGH 110 | 1 | 2018HP-1[192-193]Re-sag conductor | 900989804 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
20LN4924 | TO-20-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | OUGHTRAGH tee | OUGHTRAGH 110 | 1 | 2019HP-1[227]Earths-Replace earth wire | 901084875 | 14/09/2020 | 18/09/2020 | 2 | Scheduled
PROT2020032 | TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | OUGHTRAGH tee | TRALEE 110 | 1 | P2 Protection maintenance of 7SA511, REL521 |  | 14/09/2020 | 18/09/2020 | 2 | Scheduled
OD0231 | TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | OUGHTRAGH tee | TRALEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
19EG10355 | TO-20-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | OUGHTRAGH tee | TRALEE 110 | 1 | 110kV SF6 Cubicle Operational Test | 901038831 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
TOP191210140457 | TO-20-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | PLATIN 110 | PLATIN 10 | T105 | Customer works |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0588 | TO-20-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | PLATIN 110 | PLATIN 10 | T105 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0375 | TO-20-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | PLATIN 110 | PLATIN 10 | T105 | Replace CB Counter | 901087478 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
TOP200902102854 | TO-20-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | POLLAPHUCA 110 | POLLAPHUCA 110 | 110SA1 | As a consequence of works on Stratford tee Pollaphuca |  | 24/08/2020 | 21/09/2020 |  | Scheduled
TOP200902102950 | TO-20-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | POLLAPHUCA 110 | POLLAPHUCA 110 | 110SA2 | As a consequence of works on Stratford tee Pollaphuca |  | 24/08/2020 | 21/09/2020 |  | Scheduled
TOP200902103248 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | As a consequence of works on Stratford tee Pollaphuca |  | 24/08/2020 | 21/09/2020 |  | Scheduled
PROT2020177 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | P3 Protection maintenance of 7SA511 |  | 24/08/2020 | 21/09/2020 | 3 | Scheduled
OD0669 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 21/09/2020 |  | Scheduled
20CM0376 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | EMP AMS: Replace CB Counter | 901087470 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
20CM0259 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | Check the bellows of the current transfo | 901079398 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
20CM0260 | TO-20-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | POLLAPHUCA 110 | POLLAPHUCA G1 | T101 | Change the oil in the circuit breaker | 901079400 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
20EG01230 | TO-20-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | POOLBEG 220 | POOLBEG 220 | 220K2-3 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01229 | TO-20-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | POOLBEG 220 | POOLBEG 220 | 220K2-3 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01228 | TO-20-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | POOLBEG 220 | POOLBEG 220 | 220K2-3 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0426 | TO-20-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | POOLBEG 220 | POOLBEG 220 | 220K3-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020170 | TO-20-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | POOLBEG 220 | POOLBEG 220 | 220K3-4 | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG01234 | TO-20-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | POOLBEG 220 | POOLBEG 220 | 220K3-4 | 220kV GIS Cubicle Ordinary Service | 901042163 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01233 | TO-20-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | POOLBEG 220 | POOLBEG 220 | 220K3-4 | 220kV Sect / Dist Ordinary Service | 901039698 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01232 | TO-20-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | POOLBEG 220 | POOLBEG 220 | 220K3-4 | 220kV Sect / Dist Ordinary Service | 901039697 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465528 | TO-20-PB-220SA1-2-02 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | POOLBEG 220 | POOLBEG 220 | 220SA1-2 | Proximity outage for work on Poolbeg 220kV K1-3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0725 | TO-20-PB-220SA1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | POOLBEG 220 | POOLBEG 220 | 220SA1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01761 | TO-20-PB-220SA1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | POOLBEG 220 | POOLBEG 220 | 220SA1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465529 | TO-20-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | POOLBEG 220 | POOLBEG 220 | 220SB1-2 | Proximity outage for work on Poolbeg 220kV K1-3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1152 | TO-20-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | POOLBEG 220 | POOLBEG 220 | R2001 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
18EG23421 | TO-20-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | POOLBEG 220 | POOLBEG 220 | R2001 | Insp. 400 & 220 Feeder XLPE Cable | 900944063 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG23354 | TO-20-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | POOLBEG 220 | POOLBEG 220 | R2001 | 220kV SF6 Cubicle Operational Test | 900942637 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
18EG23357 | TO-20-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | POOLBEG 220 | POOLBEG 220 | R2001 | HV Reactor Operational Test | 900944210 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD1275 | TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | POOLBEG 220 | POOLBEG 220 | R2002 | Total Maintenance Outage Duration Requested |  | 10/06/2020 | 12/06/2020 |  | Scheduled
19EG23634 | TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | POOLBEG 220 | POOLBEG 220 | R2002 | HV Reactor Operational Test | 901038596 | 10/06/2020 | 12/06/2020 | 4 | Scheduled
19EG23633 | TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | POOLBEG 220 | POOLBEG 220 | R2002 | Insp. 400 & 220 Feeder XLPE Cable | 901038594 | 10/06/2020 | 12/06/2020 | 4 | Scheduled
20EG23635 | TO-20-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | POOLBEG 220 | POOLBEG 220 | R2002 | 220kV SF6 Cubicle Operational Test |  | 10/06/2020 | 12/06/2020 | 4 | Scheduled
TOP201030155414 | TO-20-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | FS6 repair |  | 24/11/2020 | 17/12/2020 |  | Scheduled
OD0686 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10990 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | 220kV GIS Cubicle Operational Test | 901038941 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10992 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | HV Reactor Operational Test | 901045341 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10991 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | 220kV GIS Cubicle Operational Test | 901038945 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17EG01725 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | 220KV REACTOR CONDITION ASSESSMENT | 900858397 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17EG01724 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | 220KV CUBICLE CONDITION ASSESSMENT | 900858465 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
17EG01723 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | 220KV CUBICLE CONDITION ASSESSMENT | 900858466 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG20525 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20524 | TO-20-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | POOLBEG 220 | POOLBEG 220 | R223-4 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465538 | TO-20-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | POOLBEG 220 | SHELLYBANKS 220 | 1 | Proximity outage for work on Shellybanks 220kV D2/CB3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465530 | TO-20-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | POOLBEG 220 | SHELLYBANKS 220 | 1 | Proximity outage for work on Shellybanks 220kV D1/CB3 | PR0004 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200825180453 | TO-20-PB-SHL-1-03 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | POOLBEG 220 | SHELLYBANKS 220 | 1 | Density Switch Replacement |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0813 | TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Total Maintenance Outage Duration Requested |  | 27/08/2020 | 28/08/2020 |  | Scheduled
20EG11277 | TO-20-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | 400kV SF6 Cubicle Operational Test |  | 27/08/2020 | 28/08/2020 | 4 | Scheduled
OD0323 | TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG02318 | TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | 400kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02316 | TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | 400kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20693 | TO-20-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | Cable Insp. 400 & 220kV Feeder XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351139 | TO-20-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | PORTLAOISE 110 | PORTLAOISE 110 | 110A1 | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351141 | TO-20-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | PORTLAOISE 110 | PORTLAOISE 110 | 110A2 | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351140 | TO-20-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | PORTLAOISE 110 | PORTLAOISE 110 | 110B1 | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351142 | TO-20-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | PORTLAOISE 110 | PORTLAOISE 110 | 110B2 | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0427 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10726 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901042976 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG10724 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | 110kV SF6 Cubicle Operational Test | 901038676 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
17EG01236 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service | 900859306 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
17EG01239 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service | 900859298 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
19EG10723 | TO-20-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | PORTLAOISE 110 | PORTLAOISE 110 | 110K1-2 | 110kV Sect / Dist Operational Test | 901042975 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200629114243 | TO-20-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Prox outage required for pipeline survey |  | 27/07/2020 | 28/07/2020 |  | Scheduled
TOP200709162731 | TO-20-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Prox outage required for pipeline survey |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0308 | TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 03/07/2020 |  | Scheduled
19EG20213 | TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Annual Insp. 400 & 220 Feeder OF Cable | 901113198 | 29/06/2020 | 03/07/2020 | 4 | Scheduled
19CM0002 | TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Replacement of Cathodic Protection Battery | 900952297 | 29/06/2020 | 03/07/2020 | 1 | Scheduled
20EG10481 | TO-20-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 220kV MO Cubicle Operational Test | 901129537 | 29/06/2020 | 03/07/2020 | 4 | Scheduled
PROT2020171 | TO-20-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | RAFFEEN 110 | RAFFEEN 110 | 110K1-2 | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0429 | TO-20-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020172 | TO-20-RAF-220K1-2-02 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG06065 | TO-20-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | HV Pressure Vessel Inspection | 901045776 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01247 | TO-20-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service | 900942645 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01246 | TO-20-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service | 901039742 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG01248 | TO-20-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | RAFFEEN 220 | RAFFEEN 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service | 901042176 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1276 | TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | RAFFEEN 110 | RAFFEEN 110 | CAP2 | Total Maintenance Outage Duration Requested |  | 06/10/2020 | 13/10/2020 |  | Scheduled
PROT2020138 | TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | RAFFEEN 110 | RAFFEEN 110 | CAP2 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 06/10/2020 | 13/10/2020 | 3 | Scheduled
20EG05072 | TO-20-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | RAFFEEN 110 | RAFFEEN 110 | CAP2 | 110kV SF6 Cubicle Ordinary Service | 901129961 | 06/10/2020 | 13/10/2020 | 4 | Scheduled
OD0232 | TO-20-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | RAFFEEN 110 | RINGASKIDDY 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
PROT2020007 | TO-20-RAF-RSY-1-02 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | RAFFEEN 110 | RINGASKIDDY 110 | 1 | P1 Protection maintenance of 7SA612, GRZ100 |  | 25/12/2500 | 25/12/2500 | 1 | Reference (Unscheduled)
18EG10356 | TO-20-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | RAFFEEN 110 | RINGASKIDDY 110 | 1 | 110kV SF6 Cubicle Operational Test | 900942660 | 25/12/2500 | 25/12/2500 | 3 | Reference (Unscheduled)
OD0793 | TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | Total Maintenance Outage Duration Requested |  | 20/10/2020 | 21/10/2020 |  | Scheduled
TOP200128134157 | TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | P2 Protection maintenance of 7SA511, 7SA511, 7UT512 | PROT | 20/10/2020 | 21/10/2020 |  | Scheduled
19CM0334 | TO-20-RAF-T2101-03 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | Replace stolen earths |  | 20/10/2020 | 22/10/2020 | 1 | Scheduled
20EG02066 | TO-20-RAF-T2101-02 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02067 | TO-20-RAF-T2101-02 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0279 | TO-20-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | Degas oil completely T2101 | 900908059 | 20/10/2020 | 21/10/2020 | 2 | Scheduled
20EG02068 | TO-20-RAF-T2101-02 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | RAFFEEN 220 | RAFFEEN 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0794 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0283 | TO-20-RAF-T2102-02 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | Replace Earths | 901075226 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG11162 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11163 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG06042 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | HV Pressure Vessel Inspection |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG11164 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0281 | TO-20-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | RAFFEEN 220 | RAFFEEN 110 | T2102 | Replace Signs on Trafo's and Assoicated | 901060347 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
TOP200210150340 | TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | RAFFEEN 110 | TRABEG 110 | 1 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 21/09/2020 | 24/09/2020 |  | Scheduled
OD0233 | TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | RAFFEEN 110 | TRABEG 110 | 1 | Total Maintenance Outage Duration Requested |  | 21/09/2020 | 24/09/2020 |  | Scheduled
20CM0284 | TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | RAFFEEN 110 | TRABEG 110 | 1 | Replce Bay Signage | 901074427 | 21/09/2020 | 24/09/2020 | 2 | Scheduled
19CM0335 | TO-20-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | RAFFEEN 110 | TRABEG 110 | 1 | Replace stolen earths |  | 21/09/2020 | 24/09/2020 | 1 | Scheduled
PROT2020107 | TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 16/03/2020 | 24/03/2020 | 3 | Scheduled
PROT2020106 | TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | P3 Protection maintenance of 7SA612, GRL100 |  | 16/03/2020 | 24/03/2020 | 3 | Scheduled
OD0234 | TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | Total Maintenance Outage Duration Requested |  | 16/03/2020 | 24/03/2020 |  | Scheduled
TOP200210150606 | TO-20-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 14/09/2020 | 17/09/2020 |  | Scheduled
20CM0441 | TO-20-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | Clean cable sealing ends (and stand-off insulators) at line/cable interface compound at Trabeg station. | 901133690 | 14/09/2020 | 17/09/2020 | 2 | Scheduled
20LN4990 | TO-20-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | RAFFEEN 110 | TRABEG 110 | 2 | 2019HP-3[20,22,23]Off Plumb -plumb poles | 901085002 | 16/03/2020 | 24/03/2020 | 4 | Scheduled
OD1347 | TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 09/03/2020 | 10/03/2020 |  | Scheduled
OD1387 | TO-20-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG04102 | TO-20-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601103 | TO-20-RRU-110SA1-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA1 | As a consequence of RRU-110SA2: 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 18/05/2020 | 20/05/2020 |  | Scheduled
CAPX20200109104601100 | TO-20-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA1 | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 09/03/2020 | 10/03/2020 |  | Scheduled
OD1348 | TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 20/05/2020 |  | Scheduled
20EG04103 | TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 18/05/2020 | 20/05/2020 | 4 | Scheduled
CAPX20200109104601104 | TO-20-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA2 | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 18/05/2020 | 20/05/2020 |  | Scheduled
CAPX20200109104601101 | TO-20-RRU-110SA2-02 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | RATRUSSAN 110 | RATRUSSAN 110 | 110SA2 | As a consequence of RRU-110SA1: 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 09/03/2020 | 10/03/2020 |  | Scheduled
TOP200429175916 | TO-20-RRU-SKL-1-02 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | Proximity for hot spot work LIS-SKL cubicle |  | 14/09/2020 | 25/09/2020 |  | Scheduled
OD0236 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 22/05/2020 |  | Scheduled
PROT2020108 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | P3 Protection maintenance of 7SA612, GRL100 |  | 18/05/2020 | 22/05/2020 | 3 | Scheduled
19LN6898 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 2018HP-1[48]Bird Nests | 900989485 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20EG10363 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20EG00710 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901129196 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20EG00708 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129889 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
CAPX20200109104601105 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 18/05/2020 | 22/05/2020 |  | Scheduled
20LN5025 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 2019HP-1[48]Bird Nests | 901084327 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
20LN5020 | TO-20-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | RATRUSSAN 110 | SHANKILL 110 | 1 | 2019HP-1[33]Bird Nests | 901084326 | 18/05/2020 | 22/05/2020 | 4 | Scheduled
OD0594 | TO-20-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | RATRUSSAN 110 | RATRUSSAN 20 | T121 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601102 | TO-20-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | RATRUSSAN 110 | RATRUSSAN 20 | T121 | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0595 | TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 20/05/2020 |  | Scheduled
TOP200907161814 | TO-20-RRU-T122-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | Customer outage request |  | 29/09/2020 | 01/10/2020 |  | Scheduled
TOP200114105410 | TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | P3 Protection maintenance of 7SA612 |  | 18/05/2020 | 20/05/2020 |  | Scheduled
20CM0286 | TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | Re-Test - Condition Assessment of the Cu | 900990024 | 18/05/2020 | 20/05/2020 | 1 | Scheduled
20EG10907 | TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | 110kV SF6 Cubicle Operational Test |  | 18/05/2020 | 20/05/2020 | 4 | Scheduled
CAPX20200109104601106 | TO-20-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | RATRUSSAN 110 | RATRUSSAN 20 | T122 | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 18/05/2020 | 20/05/2020 |  | Scheduled
TOP201015101819 | TO-20-REM-110SA1-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | REAMORE 110 | REAMORE 110 | 110SA1 | As a consequence of Reamore Tralee 110kV Circuit |  | 03/11/2020 | 04/11/2020 |  | Scheduled
TOP201015102249 | TO-20-REM-110SA2-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | REAMORE 110 | REAMORE 110 | 110SA2 | As a consequence of Reamore Tralee 110kV Circuit |  | 03/11/2020 | 04/11/2020 |  | Scheduled
TOP201015102824 | TO-20-REM-T142-02 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | REAMORE 110 | REAMORE 38 | T142 | As a consequence of Reamore Tralee 110kV Circuit |  | 03/11/2020 | 04/11/2020 |  | Reference
OD0822 | TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | REAMORE 110 | TRALEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 03/11/2020 | 04/11/2020 |  | Scheduled
20EG11334 | TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | REAMORE 110 | TRALEE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 03/11/2020 | 04/11/2020 | 4 | Scheduled
20EG11335 | TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | REAMORE 110 | TRALEE 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 03/11/2020 | 04/11/2020 | 4 | Scheduled
20EG20712 | TO-20-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | REAMORE 110 | TRALEE 110 | 1 | Cable Insp. 110kV XLPE |  | 03/11/2020 | 04/11/2020 | 4 | Scheduled
OD1349 | TO-20-RNW-110SA1-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | RINAWADE 110 | RINAWADE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04106 | TO-20-RNW-110SA1-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | RINAWADE 110 | RINAWADE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601108 | TO-20-RNW-110SA1-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | RINAWADE 110 | RINAWADE 110 | 110SA1 | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601112 | TO-20-RNW-110SA1-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA1 | RINAWADE 110 | RINAWADE 110 | 110SA1 | As a consequence of RNW-110SA2: 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1324 | TO-20-RNW-110SA2-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | RINAWADE 110 | RINAWADE 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04107 | TO-20-RNW-110SA2-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | RINAWADE 110 | RINAWADE 110 | 110SA2 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601109 | TO-20-RNW-110SA2-02 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | RINAWADE 110 | RINAWADE 110 | 110SA2 | As a consequence of RNW-110SA1: 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601113 | TO-20-RNW-110SA2-01 | SECTIONALISING DISCONNECT - RINAWADE 110-RINAWADE 110-110SA2 | RINAWADE 110 | RINAWADE 110 | 110SA2 | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0596 | TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | RINAWADE 110 | RINAWADE 20 | T121 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200114085942 | TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | RINAWADE 110 | RINAWADE 20 | T121 | P2 Protection maintenance of 7SJ511 |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10908 | TO-20-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | RINAWADE 110 | RINAWADE 20 | T121 | 110kV SF6 Cubicle Operational Test | 901038951 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601110 | TO-20-RNW-T121-02 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | RINAWADE 110 | RINAWADE 20 | T121 | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0597 | TO-20-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | RINAWADE 110 | RINAWADE 20 | T122 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG10909 | TO-20-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | RINAWADE 110 | RINAWADE 20 | T122 | 110kV SF6 Cubicle Operational Test | 901038952 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601114 | TO-20-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | RINAWADE 110 | RINAWADE 20 | T122 | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101511561318 | TO-20-110 kV A1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A1 | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131 | CP1056 | 04/11/2020 | 05/11/2020 |  | Scheduled
CAPX2020110215262824 | TO-20-110 kV A1 @ RYB GIS-03 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A1 | EI: Energise T131 | CP1056 | 12/11/2020 | 13/11/2020 |  | Proposed
CAPX2020072014372511 | TO-20-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A1 | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2) | CP1056 | 29/10/2020 | 02/11/2020 |  | Scheduled
CAPX2020100215423928 | TO-20-110 kV A1/A2/A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1-A2-A4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A1-A2-A4 | EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
CAPX2020101511561300 | TO-20-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A3 | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
CAPX2020101511561307 | TO-20-110 kV A3 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110A3 | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133 | CP1056 | 26/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020072014372512 | TO-20-110 kV B1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110B1 | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2) | CP1056 | 29/10/2020 | 02/11/2020 |  | Scheduled
CAPX2020101511561301 | TO-20-110 kV B3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110B3 | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
CAPX2020022115154821 | TO-20-110 kV B4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110B4 | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101511561302 | TO-20-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K3 | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
CAPX2020101511561303 | TO-20-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K3 | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
OD1027 | TO-20-RYB GIS-110K3-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101511561308 | TO-20-RYB GIS-110K3-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K3 | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133 | CP1056 | 26/11/2020 | 27/11/2020 |  | Scheduled
18EG21193 | TO-20-RYB GIS-110K3-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K3 | 110kV GIS Cubicle Operational Test | 900942678 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020101511561325 | TO-20-RYB GIS-110K4-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K4 | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020100215423929 | TO-20-RYB GIS-110K4-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K4 | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
OD1028 | TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K4 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020022115154822 | TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K4 | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
18EG21194 | TO-20-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110K4 | 110kV GIS Cubicle Operational Test | 900942679 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020100215423930 | TO-20-RYB GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-2CB | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
CAPX2020072014372513 | TO-20-RYB GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2) | CP1056 | 09/11/2020 | 11/11/2020 |  | Proposed
CAPX2020101511561319 | TO-20-RYB GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131 | CP1056 | 04/11/2020 | 05/11/2020 |  | Scheduled
CAPX2020110215262825 | TO-20-RYB GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-2CB | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131 | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020100215423931 | TO-20-RYB GIS-110SA1-3CB-05 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-3CB | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
CAPX2020110215262826 | TO-20-RYB GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-3CB | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131 | CP1056 | 12/11/2020 | 13/11/2020 |  | Proposed
CAPX2020101511561320 | TO-20-RYB GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-3CB | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131 | CP1056 | 12/11/2020 | 13/11/2020 |  | Proposed
CAPX2020101511561309 | TO-20-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-3CB | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133 | CP1056 | 26/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020101511561304 | TO-20-RYB GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA1-3CB | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
CAPX2020100215423932 | TO-20-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SA2-4CB | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days | CP1056 | 21/10/2020 | 22/10/2020 |  | Scheduled
CAPX2020072014372515 | TO-20-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB1-2CB | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2) | CP1056 | 29/10/2020 | 02/11/2020 |  | Scheduled
CAPX2020110311441917 | TO-20-RYB GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB1-3CB | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2) | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1033 | TO-20-RYB GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB1-3CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020101511561305 | TO-20-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB1-3CB | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133 | CP1056 | 23/11/2020 | 25/11/2020 |  | Scheduled
20EG21219 | TO-20-RYB GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB1-3CB | 110kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020101512415224 | TO-20-RYB GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | RYEBROOK GIS 110 | RYEBROOK GIS 110 | 110SB2-4CB | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0602 | TO-20-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T105 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20256 | TO-20-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T105 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG21289 | TO-20-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T105 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0603 | TO-20-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T106 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020110215262815 | TO-20-RYB GIS-T106-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T106 | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched. | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01576 | TO-20-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T106 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1057 | TO-20-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T107 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
17EG21292 | TO-20-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T107 | INSP. 110 STATION XLPE CABLE | 900926063 | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
20EG21293 | TO-20-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T107 | 110kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020110215262816 | TO-20-RYB GIS-T108-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T108 | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched. | CP1056 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23272 | TO-20-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T108 | INSP. 110 STATION XLPE CABLE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1058 | TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T109 | Total Maintenance Outage Duration Requested |  | 26/05/2020 | 02/06/2020 |  | Scheduled
20EG21297 | TO-20-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | RYEBROOK GIS 110 | RYEBROOK GIS 10 | T109 | 110kV GIS Cubicle Ordinary Service | 901129747 | 26/05/2020 | 02/06/2020 | 4 | Scheduled
CAPX2020110215262828 | TO-20-RYB GIS-T131-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T131 | RYEBROOK GIS 110 | RYEBROOK GIS 33 | T131 | Intel request to test transformer oil from T131. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched. | CP1056 | 16/11/2020 | 16/11/2020 |  | Scheduled
CAPX2020110215262817 | TO-20-RYB GIS-T131-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T131 | RYEBROOK GIS 110 | RYEBROOK GIS 33 | T131 | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched. | CP1056 | 16/11/2020 | 16/11/2020 |  | Scheduled
PROT2020060 | TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | SALTHILL 110 | SALTHILL 110 | 110SA1-2CB | P2 Protection maintenance of 7SJ611 |  | 01/09/2020 | 04/09/2020 | 2 | Scheduled
OD0431 | TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | SALTHILL 110 | SALTHILL 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 04/09/2020 |  | Scheduled
18EG02338 | TO-20-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | SALTHILL 110 | SALTHILL 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 900944542 | 01/09/2020 | 04/09/2020 | 3 | Scheduled
TOP200807100858 | TO-20-SAL-T102-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T102 | SALTHILL 110 | SALTHILL 10 | T102 | Proximity for SA2 Maintenance |  | 01/09/2020 | 04/09/2020 |  | Reference
TOP200826173035 | TO-20-SK-T103-03 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | SEALROCK 110 | SEALROCK G3 | T103 | As a consequence of AUG-SK-3: 110 kV A1 @ AUG |  | 08/09/2020 | 08/09/2020 |  | Scheduled
OD0673 | TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | SEALROCK 110 | SEALROCK G3 | T103 | Total Maintenance Outage Duration Requested |  | 20/07/2020 | 24/07/2020 |  | Scheduled
20CM0440 | TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | SEALROCK 110 | SEALROCK G3 | T103 | Gas Leak Repar S Phase | 901137683 | 20/07/2020 | 24/07/2020 | 1 | Scheduled
20EG20466 | TO-20-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | SEALROCK 110 | SEALROCK G3 | T103 | Cable Insp. 110kV XLPE | 901129121 | 20/07/2020 | 24/07/2020 | 4 | Scheduled
CAPX2020010910331749 | TO-20-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | SEALROCK 110 | SEALROCK G3 | T103 | As a consequence of AUG-SK-3: 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200821135317 | TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | Outage start @ 14:00 07 Sept 2020, Outage end @ 15:00 10 Sept 2020 |  | 08/09/2020 | 10/09/2020 |  | Scheduled
TOP200821135227 | TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | Customer outage request |  | 08/09/2020 | 10/09/2020 |  | Scheduled
TOP200821135145 | TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | 4 day customer outage |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200826173647 | TO-20-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | As a consequence of AUG-SK-4: 110 kV |  | 08/09/2020 | 10/09/2020 |  | Scheduled
20EG10978 | TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | 110KV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910331755 | TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | As a consequence of AUG-SK-4: 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2) | PR0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20467 | TO-20-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | SEALROCK 110 | SEALROCK G4 | T104 | Cable Insp. 110kV XLPE |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200429180801 | TO-20-SKL-110SA1-01 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | SHANKILL 110 | SHANKILL 110 | 110SA1 | Proximity for hot spot work LIS-SKL cubicle |  | 14/09/2020 | 25/09/2020 |  | Scheduled
TOP200429175802 | TO-20-SKL-T141-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | SHANKILL 110 | SHANKILL 38 | T141 | Proximity for hot spot work LIS-SKL cubicle |  | 14/09/2020 | 25/09/2020 |  | Reference
TOP200713133350 | TO-20-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110A1 | Busbar changeover | BB0001 | 01/10/2020 | 01/10/2020 |  | Scheduled
CAPX2020010910351143 | TO-20-110 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110A1 | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713133441 | TO-20-110 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110A2 | Busbar changeover | BB0001 | 01/10/2020 | 01/10/2020 |  | Scheduled
CAPX2020010910351145 | TO-20-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110A2 | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713133529 | TO-20-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110B1 | Busbar changeover | BB0001 | 01/10/2020 | 01/10/2020 |  | Scheduled
CAPX2020010910351144 | TO-20-110 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110B1 | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713133609 | TO-20-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110B2 | Busbar changeover | BB0001 | 01/10/2020 | 01/10/2020 |  | Scheduled
CAPX2020010910351146 | TO-20-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110B2 | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102214323104 | TO-20-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0432 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01255 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01256 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01257 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01254 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01258 | TO-20-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | SHANNONBRIDGE 110 | SHANNONBRIDGE 110 | 110K1-2 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200713133647 | TO-20-220 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A1 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351147 | TO-20-220 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A1 | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2 | PR0002 | 24/03/2020 | 25/03/2020 |  | Scheduled
CAPX2020102214323100 | TO-20-220 kV A2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs. | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200713133727 | TO-20-220 kV A2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534000 | TO-20-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534008 | TO-20-220 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo). | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534003 | TO-20-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs. | CP1058 | 02/11/2020 | 27/11/2020 |  | Scheduled
CAPX2020010910351149 | TO-20-220 kV A2 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220A2 | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2 | PR0002 | 24/03/2020 | 25/03/2020 |  | Scheduled
TOP200713133807 | TO-20-220 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B1 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351148 | TO-20-220 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B1 | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2 | PR0002 | 24/03/2020 | 25/03/2020 |  | Scheduled
TOP200713133845 | TO-20-220 kV B2 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | Busbar changeover | BB0001 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020102214323101 | TO-20-220 kV B2 @ SH-08 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs. | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534002 | TO-20-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | Errection and installation of circuti breaker. B2 proximity outage required | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351150 | TO-20-220 kV B2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2 | PR0002 | 24/03/2020 | 25/03/2020 |  | Scheduled
CAPX2019101111534001 | TO-20-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534004 | TO-20-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs. | CP1058 | 02/11/2020 | 27/11/2020 |  | Scheduled
CAPX2019101111534005 | TO-20-220 kV B2 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | Installation of tube between DA, DB and to CB | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101111534009 | TO-20-220 kV B2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220B2 | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo). | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0433 | TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 24/03/2020 | 25/03/2020 |  | Scheduled
20EG10743 | TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901130126 | 24/03/2020 | 25/03/2020 | 4 | Scheduled
20EG10742 | TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901130125 | 24/03/2020 | 25/03/2020 | 4 | Scheduled
20CM0295 | TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | O.2.esbi reqd.moving contact to be repla | 900315850 | 24/03/2020 | 25/03/2020 | 1 | Scheduled
20EG10744 | TO-20-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901130127 | 24/03/2020 | 25/03/2020 | 4 | Scheduled
CAPX2019101111534006 | TO-20-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | SHANNONBRIDGE 220 | SHANNONBRIDGE 220 | 220K1-2 | Coupler outage. Testing of interlocking between new trafo and coupler (drive sharfts on pantographs removed) | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0675 | TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | SHANNONBRIDGE 110 | SHANNONBRIDGE G4 | T104 | Total Maintenance Outage Duration Requested |  | 01/09/2020 | 02/09/2020 |  | Scheduled
CAPX2020102214323105 | TO-20-SH-T104-02 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | SHANNONBRIDGE 110 | SHANNONBRIDGE G4 | T104 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20468 | TO-20-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | SHANNONBRIDGE 110 | SHANNONBRIDGE G4 | T104 | Cable Insp. 110kV XLPE |  | 01/09/2020 | 02/09/2020 | 4 | Scheduled
OD0796 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | Total Maintenance Outage Duration Requested |  | 18/05/2020 | 26/05/2020 |  | Scheduled
20EG02080 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | 110kV MO Cubicle Ordinary Service |  | 18/05/2020 | 26/05/2020 | 4 | Scheduled
20EG02081 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | 110kV SF6 Cubicle Ordinary Service |  | 18/05/2020 | 26/05/2020 | 4 | Scheduled
20EG02082 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | 220/110 & 275/220 Trafo Ordinary Service |  | 18/05/2020 | 26/05/2020 | 4 | Scheduled
20EG02084 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | 220KV CUBICLE CONDITION ASSESSMENT |  | 18/05/2020 | 26/05/2020 | 4 | Scheduled
20CM0297 | TO-20-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | Replace Sensor | 901059910 | 18/05/2020 | 26/05/2020 | 1 | Scheduled
CAPX2019101111534007 | TO-20-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2101 | EI: Feeder outage to accmodate EI of T224 (DA, DB and trafo). | CP1058 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020081409432528 | TO-20-SH-T2102-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | EI: EI to prove the new station & customer transformer T121 including 24 hour soak. Use T2102 in Shannonbridge to energise Derrycarney station on tail | CP1057 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0797 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | Total Maintenance Outage Duration Requested |  | 27/05/2020 | 10/06/2020 |  | Scheduled
CAPX2020102214323106 | TO-20-SH-T2102-05 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201014143506 | TO-20-SH-T2102-04 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | Shannonbridge T2102 - VT replacement required |  | 02/11/2020 | 27/11/2020 |  | Scheduled
20EG02087 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 110kV MO Cubicle Ordinary Service |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
20CM0298 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | ESBIN01 GE are to supply replacement hyd | 900867382 | 27/05/2020 | 10/06/2020 | 1 | Scheduled
20CM0299 | TO-20-SH-T2102-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | Investigate unit fault | 901059909 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG02092 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
20EG02091 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 220KV CUBICLE CONDITION ASSESSMENT |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
20EG02090 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
20EG02088 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 220kV SF6 Cubicle Ordinary Service |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
20EG02089 | TO-20-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | SHANNONBRIDGE 220 | SHANNONBRIDGE 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 27/05/2020 | 10/06/2020 | 4 | Scheduled
CAPX2020010910465545 | TO-20-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB1 | Proximity outage for work on Shellybanks 220kV T2016 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
CAPX2020010910465533 | TO-20-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB1 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
CAPX2020010910465542 | TO-20-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB1 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
OD0687 | TO-20-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG10993 | TO-20-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB1 | 220kV GIS Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465540 | TO-20-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB2 | Proximity outage for work on Shellybanks 220kV T2014 | PR0004 | 21/08/2020 | 25/08/2020 |  | Scheduled
OD0688 | TO-20-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB2 | Total Maintenance Outage Duration Requested |  | 21/08/2020 | 25/08/2020 |  | Scheduled
20EG10994 | TO-20-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB2 | 220kV GIS Cubicle Operational Test |  | 21/08/2020 | 25/08/2020 | 4 | Scheduled
CAPX2020010910465541 | TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB3 | Proximity outage for work on Shellybanks 220kV T2014 | PR0004 | 17/08/2020 | 25/08/2020 |  | Scheduled
OD0689 | TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB3 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 25/08/2020 |  | Scheduled
20EG01730 | TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB3 | 220kV GIS Cubicle Ordinary Service |  | 17/08/2020 | 25/08/2020 | 4 | Scheduled
20EG01731 | TO-20-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D1/CB3 | 220KV CUBICLE CONDITION ASSESSMENT |  | 17/08/2020 | 25/08/2020 | 4 | Scheduled
CAPX2020010910465534 | TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
OD0690 | TO-20-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910465543 | TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
CAPX2020010910465546 | TO-20-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | Proximity outage for work on Shellybanks 220kV T2016 | PR0004 | 01/06/2020 | 03/06/2020 |  | Tentative
20EG01732 | TO-20-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01733 | TO-20-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB1 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0691 | TO-20-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0301 | TO-20-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB2 | D5 disconnect failed to operate correctl | 901079135 | 05/06/2020 | 07/06/2020 | 2 | Scheduled
20EG01735 | TO-20-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB2 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01734 | TO-20-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB2 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0692 | TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01736 | TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB3 | 220kV GIS Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01737 | TO-20-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | SHELLYBANKS 220 | SHELLYBANKS 220 | D2/CB3 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910465531 | TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | SHELLYBANKS 220 | SHELLYBANKS G4 | T2014 | Proximity outage for work on Shellybanks 220kV D1/CB3 | PR0004 | 17/08/2020 | 20/08/2020 |  | Scheduled
OD0676 | TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | SHELLYBANKS 220 | SHELLYBANKS G4 | T2014 | Total Maintenance Outage Duration Requested |  | 17/08/2020 | 20/08/2020 |  | Scheduled
20EG01703 | TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | SHELLYBANKS 220 | SHELLYBANKS G4 | T2014 | 220kV Sect / Dist Ordinary Service |  | 17/08/2020 | 20/08/2020 | 4 | Scheduled
17EG20469 | TO-20-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | SHELLYBANKS 220 | SHELLYBANKS G4 | T2014 | Annual Insp. 400 & 220 Statn. XLPE Cable | 900838786 | 17/08/2020 | 20/08/2020 | 3 | Scheduled
CAPX2020010910465539 | TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | SHELLYBANKS 220 | SHELLYBANKS G5 | T2015 | Proximity outage for work on Shellybanks 220kV D2/CB3 | PR0004 | 08/06/2020 | 11/06/2020 |  | Scheduled
OD0677 | TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | SHELLYBANKS 220 | SHELLYBANKS G5 | T2015 | Total Maintenance Outage Duration Requested |  | 08/06/2020 | 11/06/2020 |  | Scheduled
CAPX2020010910465537 | TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | SHELLYBANKS 220 | SHELLYBANKS G5 | T2015 | Proximity outage for work on Shellybanks 220kV D2/CB2 | PR0004 | 08/06/2020 | 11/06/2020 |  | Scheduled
20EG01704 | TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | SHELLYBANKS 220 | SHELLYBANKS G5 | T2015 | 220kV Sect / Dist Ordinary Service | 901130137 | 08/06/2020 | 11/06/2020 | 4 | Scheduled
20EG20470 | TO-20-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | SHELLYBANKS 220 | SHELLYBANKS G5 | T2015 | Cable Insp. 400 & 220kV Feeder XLPE | 901129026 | 08/06/2020 | 11/06/2020 | 4 | Scheduled
OD0678 | TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200520160410 | TO-20-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | Resolve DL S6 Leak |  | 01/06/2020 | 04/06/2020 |  | Scheduled
CAPX2020010910465544 | TO-20-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016 | PR0004 | 01/06/2020 | 04/06/2020 |  | Scheduled
CAPX2020010910465535 | TO-20-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1 | PR0004 | 01/06/2020 | 04/06/2020 |  | Scheduled
20EG01705 | TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | 220kV Sect / Dist Ordinary Service | 901130138 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG20471 | TO-20-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | SHELLYBANKS 220 | SHELLYBANKS G6 | T2016 | Cable Insp. 400 & 220kV Feeder XLPE | 901129027 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP201022100304 | TO-20-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | SHELTON ABBEY 110 | SHELTON ABBEY 10 | T102 | proximity outage to allow ESBN carry out the replacement of the corroded gantry in Shelton Abbey compound |  | 23/11/2020 | 17/12/2020 |  | Reference
OD0434 | TO-20-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 27/10/2020 | 30/10/2020 |  | Scheduled
TOP201009104246 | TO-20-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | DSO proximity request for works on SNG T102 |  | 27/10/2020 | 30/10/2020 |  | Scheduled
TOP201022145759 | TO-20-SNG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | proximity for CA on Singland T101 |  | 16/11/2020 | 20/11/2020 |  | Scheduled
20EG10746 | TO-20-SNG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 16/11/2020 | 20/11/2020 | 4 | Proposed
20EG10747 | TO-20-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
20EG10748 | TO-20-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | SINGLAND 110 | SINGLAND 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test |  | 27/10/2020 | 30/10/2020 | 4 | Scheduled
TOP201022145318 | TO-20-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | SINGLAND 110 | SINGLAND 10 | T101 | CA on Singland T101 |  | 16/11/2020 | 20/11/2020 |  | Reference
TOP201001091640 | TO-20-SNG-T102-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T102 | SINGLAND 110 | SINGLAND 10 | T102 | DSO request for CA on SNG T102 |  | 27/10/2020 | 30/10/2020 |  | Reference
TOP200525133620 | TO-20-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | SLIABH BAWN 110 | SLIABH BAWN 110 | 110A2 | Busbar Changeover | BB0000 | 02/07/2020 | 02/07/2020 |  | Scheduled
TOP200525133752 | TO-20-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | SLIABH BAWN 110 | SLIABH BAWN 110 | 110B2 | Busbar Changeover | BB0000 | 02/07/2020 | 02/07/2020 |  | Scheduled
OD0853 | TO-20-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | SLIGO 110 | SLIGO 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020173 | TO-20-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | SLIGO 110 | SLIGO 110 | 110SA1-2CB | P3 Protection maintenance of 7SJ611 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG11383 | TO-20-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | SLIGO 110 | SLIGO 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901080653 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020139 | TO-20-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | SLIGO 110 | SLIGO 110 | CAP1 | P3 Protection maintenance of SPAJ, 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0237 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020109 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | P3 Protection maintenance of 7SA511, REL551 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
PROT2020161 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | P3 Protection maintenance of 7SA511 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
19EG00714 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT | 901038567 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG00712 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901042241 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG10365 | TO-20-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | 110kV MO Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019100308102514 | TO-20-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | SLIGO 110 | SRANANAGH 110 | 1 | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends | CP0942 | 23/10/2020 | 23/10/2020 |  | Scheduled
OD0238 | TO-20-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | SLIGO 110 | SRANANAGH 110 | 2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20CM0303 | TO-20-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | SLIGO 110 | SRANANAGH 110 | 2 | ESBI 02 non outage. Repeat online leakag | 900535714 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20CM0304 | TO-20-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | SLIGO 110 | SRANANAGH 110 | 2 | Replace the pipework on the 110kV circui | 901059776 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
OD1282 | TO-20-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG23697 | TO-20-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | 110kV SF6 Cubicle Operational Test | 901068540 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1283 | TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23691 | TO-20-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1284 | TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SB1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG23694 | TO-20-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SB1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
TOP200109135519 | TO-20-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | SOMERSET 110 | SOMERSET 38 | T142 | Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset |  | 06/07/2020 | 10/07/2020 |  | Reference
CAPX2019101713403448 | TO-20-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | SOMERSET 110 | SOMERSET 38 | T142 | As a consequence of SOM,T-SOM-1: EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019101715102540 | TO-20-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | SOMERSET 110 | SOMERSET 38 | T142 | As a consequence of SOM,T-SOM-1: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised | CP1032 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD0239 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 10/07/2020 |  | Scheduled
16LN0794 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2015HP-1[77]Insulator Broken R/ph | 900727084 | 06/07/2020 | 10/07/2020 | 1 | Scheduled
20CM0060 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Counter not working. To be replaced. | 900907890 | 06/07/2020 | 10/07/2020 | 1 | Scheduled
18LN0270 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[95]Found/Site repair -Sleeper | 900902255 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
18LN0287 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[173]Off Plumb Poles | 900902263 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
19LN2856 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2018HP-1[152]Foundation/Site repair-stay | 900984945 | 06/07/2020 | 10/07/2020 | 4 | Scheduled
18LN0261 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[87]Off Plumb Poles | 900902253 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
18LN0288 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[175]Off Plumb Poles | 900902264 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
18LN0290 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[184]Off Plumb Insuls | 900902266 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
18LN0293 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2017CP-1[220]Off Plumb Insuls | 900902268 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
19EG10369 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 110kV MO Cubicle Operational Test | 901076462 | 06/07/2020 | 10/07/2020 | 4 | Scheduled
20LN1392 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2019HP-1[260]Bird Nests | 901084266 | 06/07/2020 | 10/07/2020 | 4 | Scheduled
CAPX2019101713403444 | TO-20-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403447 | TO-20-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101713403449 | TO-20-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1371 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2019HP-1[181]Bird Nests | 901084265 | 06/07/2020 | 10/07/2020 | 4 | Scheduled
CAPX2019101715102541 | TO-20-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715140344 | TO-20-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla Shannonbridge 110 kV bay at cashla station. | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20LN1358 | TO-20-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | SOMERSET tee | CASHLA 110 | 1 | 2019HP-1[77]Insulator Broken R/ph | 901084838 | 06/07/2020 | 10/07/2020 | 4 | Scheduled
CAPX2020102214323107 | TO-20-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB | CP1058_OS | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0240 | TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/07/2020 | 10/07/2020 |  | Scheduled
PROT2020110 | TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | P3 Protection maintenance of 7SA612, REL521 |  | 06/07/2020 | 10/07/2020 | 3 | Scheduled
18LN0446 | TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | 2017CP-1[3]Vibration Dampers -Replace | 900902328 | 06/07/2020 | 10/07/2020 | 3 | Scheduled
CAPX2019101713403450 | TO-20-SOM,T-SH-1-02 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715102542 | TO-20-SOM,T-SH-1-01 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG20108 | TO-20-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | SOMERSET tee | SHANNONBRIDGE 110 | 1 | Cable Insp. 110kV XLPE |  | 06/07/2020 | 10/07/2020 | 4 | Scheduled
TOP200109135355 | TO-20-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | SOMERSET tee | SOMERSET 110 | 1 | Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset |  | 06/07/2020 | 10/07/2020 |  | Scheduled
CAPX2019101713403451 | TO-20-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | SOMERSET tee | SOMERSET 110 | 1 | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019101715102543 | TO-20-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | SOMERSET tee | SOMERSET 110 | 1 | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised | CP1032 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100209481110 | TO-20-SOR-T122-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T122 | SORNE HILL 110 | SORNE HILL 20 | T122 | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole | CP0740 | 04/08/2020 | 04/08/2020 |  | Reference (Proposed)
CAPX2019100209481111 | TO-20-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | SORNE HILL 110 | SORNE HILL 20 | T124 | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole | CP0740 | 04/08/2020 | 04/08/2020 |  | Reference (Proposed)
CAPX2019100209481112 | TO-20-SOR-TLK-1-01 | 110kV FEEDER - SORNE HILL 110-TRILLICK 110-1 | SORNE HILL 110 | TRILLICK 110 | 1 | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole | CP0740 | 04/08/2020 | 04/08/2020 |  | Reference (Proposed)
TOP200819165355 | TO-20-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | 110SA1 | As a consequence of Bellacorick - Srahnakilly |  | 31/08/2020 | 04/09/2020 |  | Scheduled
TOP201015104945 | TO-20-SKY-110SA1-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | 110SA1 | As a consequence of Bellacorick - Srahnakilly |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200819165516 | TO-20-SKY-110SA2-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | 110SA2 | As a consequence of Bellacorick - Srahnakilly |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP201015105429 | TO-20-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | T131 | As a consequence of Bellacorick - Srahnakilly |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200819165608 | TO-20-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | T131 | As a consequence of Bellacorrick - Srahnakilly |  | 31/08/2020 | 04/09/2020 |  | Scheduled
OD1302 | TO-20-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | T131 | Total Maintenance Outage Duration Requested |  | 31/08/2020 | 04/09/2020 |  | Scheduled
20EG23735 | TO-20-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | SRAHNAKILLY 110 | SRAHNAKILLY 110 | T131 | 110kV SF6 Cubicle Operational Test |  | 31/08/2020 | 04/09/2020 | 4 | Scheduled
TOP200525133923 | TO-20-110 kV A1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | SRANANAGH 110 | SRANANAGH 110 | 110A1 | Busbar Changeover | BB0000 | 09/07/2020 | 09/07/2020 |  | Scheduled
CAPX2019100715473301 | TO-20-110 kV A1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | SRANANAGH 110 | SRANANAGH 110 | 110A1 | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh | CP0942 | 24/02/2020 | 25/02/2020 |  | Scheduled
TOP200525134031 | TO-20-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | SRANANAGH 110 | SRANANAGH 110 | 110A2 | Busbar Changeover | BB0000 | 09/07/2020 | 09/07/2020 |  | Scheduled
TOP200525134120 | TO-20-110 kV B1 @ SRA-03 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | SRANANAGH 110 | SRANANAGH 110 | 110B1 | Busbar Changeover | BB0000 | 09/07/2020 | 09/07/2020 |  | Scheduled
CAPX2020100609510412 | TO-20-110 kV B1 @ SRA-04 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | SRANANAGH 110 | SRANANAGH 110 | 110B1 | EI: Simultaneous 110 kV B1 @ SRA + SLI-SRA-1: EI - Energise DB on Corderry bay | CP0942 | 14/10/2020 | 14/10/2020 |  | Proposed
CAPX2020100609510407 | TO-20-110 kV B1 @ SRA-05 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | SRANANAGH 110 | SRANANAGH 110 | 110B1 | Connect new Jumpers on B1 BB Section In Srananagh & energise DB on Corderry bay | CP0942 | 12/10/2020 | 15/10/2020 |  | Proposed
CAPX2019100715473302 | TO-20-110 kV B1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | SRANANAGH 110 | SRANANAGH 110 | 110B1 | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh | CP0942 | 24/02/2020 | 25/02/2020 |  | Scheduled
TOP200525134210 | TO-20-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | SRANANAGH 110 | SRANANAGH 110 | 110B2 | Busbar Changeover | BB0000 | 09/07/2020 | 09/07/2020 |  | Scheduled
CAPX2019111916535008 | TO-20-SRA-220SA1-01 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA1 | SRANANAGH 220 | SRANANAGH 220 | 220SA1 | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019111916535009 | TO-20-SRA-220SA2-01 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA2 | SRANANAGH 220 | SRANANAGH 220 | 220SA2 | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0798 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020046 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | P2 Protection maintenance of 7SA511, 7SA511, 7UT512 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG02307 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 220/110 & 275/220 Trafo Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
15CM0045 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | Replace timber supports | 900693061 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG02306 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 220KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02311 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02310 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 110KV CUBICLE CONDITION ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02309 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 220/110kV Trafo Tap Changer Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02308 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 220/110 & 275/220 TRAFO COND. ASSESSMENT |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02312 | TO-20-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | 110kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2019110709503610 | TO-20-SRA-T2102-01 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | SRANANAGH 220 | SRANANAGH 110 | T2102 | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit | MC9999 | 25/12/2500 | 25/12/2500 |  | Unscheduled
TOP200113155916 | TO-20-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | STRATFORD 110 | STRATFORD 38 | T141 | Full tee out for STRATFORD tee-POLLAPHUCA out |  | 24/08/2020 | 21/09/2020 |  | Reference
OD0242 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 21/09/2020 |  | Scheduled
19LN7123 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2018HP-1[94]Check Structure-top rot - Ch | 900989809 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
20EG10371 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 110kV SF6 Cubicle Operational Test |  | 24/08/2020 | 21/09/2020 | 4 | Scheduled
17LN3586 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[110]Replace Pole only -Rotten | 900864822 | 24/08/2020 | 21/09/2020 | 1 | Scheduled
19LN2445 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2018HP-1[90]ACGfit ACG | 900984379 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
17LN3584 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[109]H-ware Susp Clamps corroded | 900864820 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
17LN3582 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[109]Vibration Dampers Replace | 900864818 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
17LN3581 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[109]Replace Pole Bolt -Bent | 900864817 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
17LN3580 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[109]Off Plumb Pole & insulators | 900864816 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
17LN3585 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2016CP-1[109]Crossarm Replacement | 900864821 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
20LN1075 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2019HP-1[110]Replace Pole only -Rot | 901086426 | 24/08/2020 | 21/09/2020 | 1 | Scheduled
20LN1077 | TO-20-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | STRATFORD tee | CARLOW 110 | 1 | 2019HP-1[124]Check Structure -Check Rot | 901086400 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
OD0243 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 21/09/2020 |  | Scheduled
18CM1185 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 1[53]Install ACG on mast no. 53 | 900975368 | 24/08/2020 | 21/09/2020 | 1 | Scheduled
17LN3507 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 2016CP-1[13]Off Plumb Poles | 900864747 | 24/08/2020 | 21/09/2020 | 2 | Scheduled
20EG00726 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 110KV CUBICLE CONDITION ASSESSMENT |  | 24/08/2020 | 21/09/2020 | 4 | Scheduled
20EG00725 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 110kV MO Cubicle Ordinary Service |  | 24/08/2020 | 21/09/2020 | 4 | Scheduled
18CM1186 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 1[33]Replace Rotten Pole | 900973774 | 24/08/2020 | 21/09/2020 | 1 | Scheduled
18LN3231 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 2017HP-1[14]Crossarm Replacement Replace | 900898188 | 24/08/2020 | 21/09/2020 | 3 | Scheduled
19LN6814 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 2018HP-1[15]Off Plumb-Poles | 900989394 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
20LN4930 | TO-20-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | STRATFORD tee | POLLAPHUCA 110 | 1 | 2019HP-1[13]Off Plumb -plumb poles | 900864747 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
OD1210 | TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | STRATFORD tee | STRATFORD 110 | 1 | Total Maintenance Outage Duration Requested |  | 24/08/2020 | 21/09/2020 |  | Scheduled
19LN7066 | TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | STRATFORD tee | STRATFORD 110 | 1 | 2018HP-1[192]ACGfit ACG on TEE tower | 900989656 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
20LN5155 | TO-20-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | STRATFORD tee | STRATFORD 110 | 1 | 2019HP-1[2]Check Structure -Check Rot | 901086414 | 24/08/2020 | 21/09/2020 | 4 | Scheduled
CAPX2020010910351151 | TO-20-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | TARBERT 110 | TARBERT 110 | 110A1 | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2 | PR0002 | 06/04/2020 | 09/04/2020 |  | Scheduled
CAPX2020010910351152 | TO-20-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | TARBERT 110 | TARBERT 110 | 110B1 | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2 | PR0002 | 06/04/2020 | 09/04/2020 |  | Scheduled
OD0436 | TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | TARBERT 110 | TARBERT 110 | 110K1-2 | Total Maintenance Outage Duration Requested |  | 06/04/2020 | 09/04/2020 |  | Scheduled
18CM1235 | TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | TARBERT 110 | TARBERT 110 | 110K1-2 | leak on S-Phase ( weep on CSE valve to be replaced) | 900973548 | 06/04/2020 | 09/04/2020 | 1 | Scheduled
17EG01274 | TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | TARBERT 110 | TARBERT 110 | 110K1-2 | 110kV Sect / Dist Ordinary Service | 900859451 | 06/04/2020 | 09/04/2020 | 3 | Scheduled
20EG20240 | TO-20-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | TARBERT 110 | TARBERT 110 | 110K1-2 | Annual Insp. 110kV Station OF Cable |  | 06/04/2020 | 09/04/2020 | 4 | Scheduled
OD0437 | TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | TARBERT 220 | TARBERT 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 03/07/2020 |  | Scheduled
19EG10757 | TO-20-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | TARBERT 220 | TARBERT 220 | 220K1-2 | 220kV Sect / Dist Operational Test | 901039188 | 29/06/2020 | 03/07/2020 | 4 | Scheduled
20CM0477 | TO-20-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | TARBERT 220 | TARBERT 220 | 220K1-2 | T Phase 220kV Coupler. Hotspot T Phase DB1 pantograph hinge DUE : next available opportunity. | 901134801 | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
PROT2020066 | TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | TARBERT 110 | TARBERT G1 | T101 | P2 Protection maintenance of 7SA513 |  | 06/04/2020 | 07/04/2020 | 2 | Scheduled
20EG20476 | TO-20-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | TARBERT 110 | TARBERT G1 | T101 | Annual Insp. 110kV Station OF Cable |  | 06/04/2020 | 07/04/2020 | 4 | Scheduled
PROT2020067 | TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | TARBERT 110 | TARBERT G2 | T102 | P2 Protection maintenance of 7SA513 |  | 02/04/2020 | 03/04/2020 | 2 | Scheduled
20EG20489 | TO-20-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | TARBERT 110 | TARBERT G2 | T102 | Annual Insp. 110kV Station OF Cable |  | 02/04/2020 | 03/04/2020 | 4 | Scheduled
OD0681 | TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | TARBERT 220 | TARBERT G3 | T2003 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 03/07/2020 |  | Scheduled
20EG10985 | TO-20-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | TARBERT 220 | TARBERT G3 | T2003 | 220kV MO Cubicle Operational Test | 901129535 | 29/06/2020 | 03/07/2020 | 4 | Scheduled
PROT2020038 | TO-20-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | TARBERT 220 | TARBERT G4 | T2004 | P2 Protection maintenance of R1Z23b, S Type Overcurrent |  | 04/08/2020 | 05/08/2020 | 2 | Scheduled
OD0799 | TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | TARBERT 220 | TARBERT 110 | T2101 | Total Maintenance Outage Duration Requested |  | 06/04/2020 | 08/04/2020 |  | Scheduled
19EG20640 | TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | TARBERT 220 | TARBERT 110 | T2101 | Annual Insp. 110kV Station OF Cable | 901005821 | 06/04/2020 | 08/04/2020 | 4 | Scheduled
18EG11172 | TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | TARBERT 220 | TARBERT 110 | T2101 | 220kV MO Cubicle Operational Test | 901038969 | 06/04/2020 | 08/04/2020 | 3 | Scheduled
18EG11171 | TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | TARBERT 220 | TARBERT 110 | T2101 | 110kV MO Cubicle Operational Test | 901038971 | 06/04/2020 | 08/04/2020 | 3 | Scheduled
18EG11173 | TO-20-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | TARBERT 220 | TARBERT 110 | T2101 | 220/110 & 275/220 Trafo Operational Test | 901045378 | 06/04/2020 | 08/04/2020 | 3 | Scheduled
OD0800 | TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | TARBERT 220 | TARBERT 110 | T2102 | Total Maintenance Outage Duration Requested |  | 29/06/2020 | 03/07/2020 |  | Scheduled
20CM0307 | TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | TARBERT 220 | TARBERT 110 | T2102 | Rust / Corrosion Station Equipment | 901059334 | 29/06/2020 | 03/07/2020 | 2 | Scheduled
20EG11176 | TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | TARBERT 220 | TARBERT 110 | T2102 | 220/110 & 275/220 Trafo Operational Test |  | 29/06/2020 | 03/07/2020 | 4 | Scheduled
20EG11174 | TO-20-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | TARBERT 220 | TARBERT 110 | T2102 | 110kV SF6 Cubicle Operational Test |  | 29/06/2020 | 03/07/2020 | 4 | Scheduled
TOP191120141301 | TO-20-TB-TRL-1-04 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | TARBERT 110 | TRALEE 110 | 1 | Outage for maps, circuit is now Kilpaddoge - Tralee |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD1086 | TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | TAWNAGHMORE 110 | TAWNAGHMORE 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 14/10/2020 | 15/10/2020 |  | Scheduled
19EG23199 | TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | TAWNAGHMORE 110 | TAWNAGHMORE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test | 901050340 | 14/10/2020 | 15/10/2020 | 4 | Scheduled
19EG21396 | TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | TAWNAGHMORE 110 | TAWNAGHMORE 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test | 901043730 | 14/10/2020 | 15/10/2020 | 4 | Scheduled
19CM0004 | TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | TAWNAGHMORE 110 | TAWNAGHMORE 110 | 110SA1-2CB | STATUS OF CONTROL SELECTOR SWITCH IS NOT | 900978748 | 14/10/2020 | 15/10/2020 | 1 | Scheduled
20EG23198 | TO-20-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | TAWNAGHMORE 110 | TAWNAGHMORE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 14/10/2020 | 15/10/2020 | 4 | Scheduled
OD1084 | TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | TAWNAGHMORE 110 | TAWNAGHMORE 10 | T1/T2 | Total Maintenance Outage Duration Requested |  | 10/08/2020 | 12/08/2020 |  | Scheduled
19EG23628 | TO-20-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | TAWNAGHMORE 110 | TAWNAGHMORE 10 | T1/T2 | Cable Insp. 110kV XLPE |  | 10/08/2020 | 12/08/2020 | 4 | Scheduled
OD1085 | TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | TAWNAGHMORE 110 | TAWNAGHMORE 10 | T3 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG21394 | TO-20-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | TAWNAGHMORE 110 | TAWNAGHMORE 10 | T3 | 110kV SF6 Cubicle Operational Test | 901043728 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910460132 | TO-20-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | THORNSBERRY 110 | THORNSBERRY 38 | T141 | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910460133 | TO-20-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | THORNSBERRY 110 | THORNSBERRY 38 | T142 | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351159 | TO-20-THU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | THURLES 110 | THURLES 110 | 110SA1-2CB | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020140 | TO-20-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | THURLES 110 | THURLES 110 | CAP1 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
CAPX2020010910351160 | TO-20-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | THURLES 110 | THURLES 110 | CAP2 | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351161 | TO-20-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | THURLES 110 | THURLES 38 | T142 | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2 | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
TOP200717115452 | TO-20-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | TRABEG 110 | TRABEG 110 | 110A1 | A1/A2 BB in turn |  | 06/08/2020 | 06/08/2020 |  | Scheduled
TOP200717115623 | TO-20-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | TRABEG 110 | TRABEG 110 | 110A2 | A1/A2 BB in turn |  | 06/08/2020 | 06/08/2020 |  | Scheduled
TOP200717120133 | TO-20-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | TRABEG 110 | TRABEG 110 | 110B1 | B1/B2 BB in turn |  | 06/08/2020 | 06/08/2020 |  | Scheduled
TOP200717120310 | TO-20-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | TRABEG 110 | TRABEG 110 | 110B2 | B1/B2 BB in turn |  | 06/08/2020 | 06/08/2020 |  | Scheduled
PROT2020174 | TO-20-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | TRABEG 110 | TRABEG 110 | 110K1-2 | P3 Protection maintenance of 7SJ611 |  | 14/09/2020 | 17/09/2020 | 3 | Scheduled
20EG23793 | TO-20-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | TRABEG 110 | TRABEG 110 | 110K1-2 | Clean busbar insulators (Indoor AIS) |  | 14/09/2020 | 17/09/2020 | 1 | Scheduled
20EG23792 | TO-20-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | TRABEG 110 | TRABEG 110 | 110K1-2 | Clean busbar insulators (Indoor AIS) |  | 21/09/2020 | 24/09/2020 | 1 | Scheduled
TOP200210150648 | TO-20-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | TRABEG 110 | TRABEG 10 | T101 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 14/09/2020 | 17/09/2020 |  | Reference
TOP200210150516 | TO-20-TBG-T102-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T102 | TRABEG 110 | TRABEG 10 | T102 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 21/09/2020 | 24/09/2020 |  | Reference
TOP200210150710 | TO-20-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | TRABEG 110 | TRABEG 38 | T141 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 14/09/2020 | 17/09/2020 |  | Reference
TOP200210150540 | TO-20-TBG-T142-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T142 | TRABEG 110 | TRABEG 38 | T142 | Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS) |  | 21/09/2020 | 24/09/2020 |  | Reference
OD0439 | TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | TRALEE 110 | TRALEE 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11300 | TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | TRALEE 110 | TRALEE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11299 | TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | TRALEE 110 | TRALEE 110 | 110SA1-2CB | 110kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11298 | TO-20-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | TRALEE 110 | TRALEE 110 | 110SA1-2CB | 110kV Sect / Dist Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
PROT2020141 | TO-20-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | TRALEE 110 | TRALEE 110 | CAP2 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD1095 | TO-20-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG02520 | TO-20-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110kV SF6 Cubicle Ordinary Service | 901042136 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02519 | TO-20-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02518 | TO-20-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110kV Sect / Dist Ordinary Service | 901042289 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351168 | TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
CAPX2020010910351174 | TO-20-TRI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351182 | TO-20-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | TRIEN 110 | TRIEN 110 | 110SA1-2CB | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
OD1096 | TO-20-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG02517 | TO-20-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | 110kV GIS Cubicle Ordinary Service | 901042137 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
19EG02514 | TO-20-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | 110kV Sect / Dist Ordinary Service | 901042966 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX2020010910351169 | TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
CAPX2020010910351198 | TO-20-TRI-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2020010910351183 | TO-20-TRI-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | TRIEN 110 | TRIEN 110 | 110SA1-3CB | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
OD1277 | TO-20-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | TRIEN 110 | TRIEN 110 | CAP1 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 11/09/2020 |  | Scheduled
PROT2020142 | TO-20-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | TRIEN 110 | TRIEN 110 | CAP1 | P3 Protection maintenance of KVFG142, SPAJ 160C |  | 07/09/2020 | 11/09/2020 | 3 | Scheduled
20EG05087 | TO-20-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | TRIEN 110 | TRIEN 110 | CAP1 | 110kV SF6 Cubicle Ordinary Service |  | 07/09/2020 | 11/09/2020 | 4 | Scheduled
CAPX2020010910351184 | TO-20-TRI-CAP1-02 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | TRIEN 110 | TRIEN 110 | CAP1 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
CAPX2020010910351170 | TO-20-TRI-CAP1-02 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | TRIEN 110 | TRIEN 110 | CAP1 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Scheduled
CAPX2020010910351171 | TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | TRIEN 110 | TRIEN 38 | T141 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Reference
CAPX2020010910351185 | TO-20-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | TRIEN 110 | TRIEN 38 | T141 | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/02/2020 | 26/02/2020 |  | Reference
CAPX2020010910351175 | TO-20-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | TRIEN 110 | TRIEN 38 | T142 | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351199 | TO-20-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | TRIEN 110 | TRIEN 38 | T143 | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351172 | TO-20-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | TRIEN 110 | TRIEN 38 | T143 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2020010910351186 | TO-20-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | TRIEN 110 | TRIEN 38 | T143 | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX20200109103511100 | TO-20-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | TRIEN 110 | TRIEN 38 | T143 | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3) | PR0002 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100209481113 | TO-20-TLK-T141-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T141 | TRILLICK 110 | TRILLICK 38 | T141 | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole | CP0740 | 04/08/2020 | 04/08/2020 |  | Reference (Proposed)
CAPX2019100209481114 | TO-20-TLK-T142-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T142 | TRILLICK 110 | TRILLICK 38 | T142 | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole | CP0740 | 04/08/2020 | 04/08/2020 |  | Reference (Proposed)
CAPX2020062514561311 | TO-20-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | TULLABRACK 110 | TULLABRACK 38 | T141 | As a consequence of TBK,T-TBK-1: BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A) | CP0824 | 27/07/2020 | 31/07/2020 |  | Reference
PROT2020039 | TO-20-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | TULLABRACK 110 | TULLABRACK 38 | T141 | P2 Protection maintenance of 7SA612, 7VK611 |  | 27/07/2020 | 31/07/2020 | 2 | Reference
OD0248 | TO-20-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | TULLABRACK tee | BOOLTIAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 31/07/2020 |  | Scheduled
CAPX2020062514561312 | TO-20-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | TULLABRACK tee | BOOLTIAGH 110 | 1 | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A) | CP0824 | 27/07/2020 | 31/07/2020 |  | Scheduled
20EG00735 | TO-20-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | TULLABRACK tee | BOOLTIAGH 110 | 1 | 110kV SF6 Cubicle Ordinary Service | 901129965 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
CAPX2020062514561313 | TO-20-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | TULLABRACK tee | MONEYPOINT GIS 110 | 1 | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A) | CP0824 | 27/07/2020 | 31/07/2020 |  | Scheduled
OD0249 | TO-20-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | TULLABRACK tee | MONEYPOINT GIS 110 | 1 | Total Maintenance Outage Duration Requested |  | 27/07/2020 | 31/07/2020 |  | Scheduled
19LN6316 | TO-20-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | TULLABRACK tee | MONEYPOINT GIS 110 | 1 | 2018HP-1[98]Off PlumbPlumb poleset | 900988895 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
20LN4737 | TO-20-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | TULLABRACK tee | MONEYPOINT GIS 110 | 1 | 2019HP-1[99]Off Plumb -plumb poles | 901082688 | 27/07/2020 | 31/07/2020 | 4 | Scheduled
CAPX2020062514561314 | TO-20-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | TULLABRACK tee | TULLABRACK 110 | 1 | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A) | CP0824 | 27/07/2020 | 31/07/2020 |  | Scheduled
TOP200825113332 | TO-20-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | TURLOUGH HILL 220 | TURLOUGH HILL 220 | 220B2 | Black Start Test |  | 25/09/2020 | 25/09/2020 |  | Scheduled
OD0440 | TO-20-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | TURLOUGH HILL 220 | TURLOUGH HILL 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01292 | TO-20-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | TURLOUGH HILL 220 | TURLOUGH HILL 220 | 220K1-2 | 220kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0683 | TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | TURLOUGH HILL 220 | TURLOUGH HILL G1 | T2001/2 | Total Maintenance Outage Duration Requested |  | 13/07/2020 | 14/07/2020 | 2 | Scheduled
18EG20502 | TO-20-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | TURLOUGH HILL 220 | TURLOUGH HILL G1 | T2001/2 | Annual Insp. 400 & 220 Station OF Cable | 901005766 | 13/07/2020 | 14/07/2020 | 3 | Scheduled
TOP200825112637 | TO-20-TH-T2003/4-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | TURLOUGH HILL 220 | TURLOUGH HILL G1 | T2003/4 | Black Start Test |  | 25/09/2020 | 25/09/2020 |  | Scheduled
18EG20515 | TO-20-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | TURLOUGH HILL 220 | TURLOUGH HILL G1 | T2003/4 | Annual Insp. 400 & 220 Station OF Cable | 901005768 | 29/06/2020 | 30/06/2020 | 3 | Scheduled
20EG01716 | TO-20-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | TURLOUGH HILL 220 | TURLOUGH HILL G1 | T2003/4 | 110kV MO Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0730 | TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | TYNAGH 220 | TYNAGH 220 | 220SA1 | Total Maintenance Outage Duration Requested |  | 30/03/2020 | 31/03/2020 |  | Planned
19EG01763 | TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | TYNAGH 220 | TYNAGH 220 | 220SA1 | 220kV Sect / Dist Ordinary Service | 901039728 | 30/03/2020 | 31/03/2020 | 4 | Planned
CAPX20200109104601118 | TO-20-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | TYNAGH 220 | TYNAGH 220 | 220SA1 | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/03/2020 | 31/03/2020 |  | Planned
CAPX20200109104601125 | TO-20-TY-220SA1-02 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | TYNAGH 220 | TYNAGH 220 | 220SA1 | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0731 | TO-20-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | TYNAGH 220 | TYNAGH 220 | 220SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG01764 | TO-20-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | TYNAGH 220 | TYNAGH 220 | 220SA2 | 220kV Sect / Dist Ordinary Service | 901039729 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601119 | TO-20-TY-220SA2-02 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | TYNAGH 220 | TYNAGH 220 | 220SA2 | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601126 | TO-20-TY-220SA2-02 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | TYNAGH 220 | TYNAGH 220 | 220SA2 | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0685 | TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | TYNAGH 220 | TYNAGH G1/2 | T2001/2 | Total Maintenance Outage Duration Requested |  | 30/03/2020 | 31/03/2020 |  | Scheduled
20EG10989 | TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | TYNAGH 220 | TYNAGH G1/2 | T2001/2 | 220kV SF6 Cubicle Operational Test | 901129555 | 30/03/2020 | 31/03/2020 | 4 | Scheduled
20CM0317 | TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | TYNAGH 220 | TYNAGH G1/2 | T2001/2 | Hot spot detected on T 2001/2 220kV R phase DA | 900990025 | 30/03/2020 | 31/03/2020 | 1 | Scheduled
CAPX20200109104601120 | TO-20-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | TYNAGH 220 | TYNAGH G1/2 | T2001/2 | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1) | PR0003 | 30/03/2020 | 31/03/2020 |  | Scheduled
OD1036 | TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | UGGOOL 110 | UGGOOL 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 08/09/2020 | 08/09/2020 |  | Scheduled
20EG21364 | TO-20-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | UGGOOL 110 | UGGOOL 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test |  | 08/09/2020 | 08/09/2020 | 4 | Scheduled
OD1042 | TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | UGGOOL 110 | UGGOOL 33 | T131 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 07/09/2020 |  | Scheduled
TOP200825174436 | TO-20-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | UGGOOL 110 | UGGOOL 33 | T131 | As a consequnce of Knockranny - Uggool 110kV |  | 08/09/2020 | 08/09/2020 |  | Scheduled
20EG21376 | TO-20-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | UGGOOL 110 | UGGOOL 33 | T131 | 110kV SF6 Cubicle Operational Test |  | 07/09/2020 | 07/09/2020 | 4 | Scheduled
OD1136 | TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | UGGOOL 110 | UGGOOL 33 | T132 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 07/09/2020 |  | Scheduled
TOP200825174535 | TO-20-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | UGGOOL 110 | UGGOOL 33 | T132 | As a consequnce of Knockranny - Uggool 110kV |  | 08/09/2020 | 08/09/2020 |  | Scheduled
20EG23242 | TO-20-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | UGGOOL 110 | UGGOOL 33 | T132 | 110kV SF6 Cubicle Operational Test |  | 07/09/2020 | 07/09/2020 | 4 | Scheduled
OD1135 | TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | UGGOOL 110 | UGGOOL 33 | T134 | Total Maintenance Outage Duration Requested |  | 07/09/2020 | 07/09/2020 |  | Scheduled
TOP200825174629 | TO-20-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | UGGOOL 110 | UGGOOL 33 | T134 | As a consequnce of Knockranny - Uggool 110kV |  | 08/09/2020 | 08/09/2020 |  | Scheduled
18EG23239 | TO-20-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | UGGOOL 110 | UGGOOL 33 | T134 | 110kV GIS Cubicle Operational Test | 900942781 | 07/09/2020 | 07/09/2020 | 3 | Scheduled
OD1350 | TO-20-WAT-110SA1-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | WATERFORD 110 | WATERFORD 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG04120 | TO-20-WAT-110SA1-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | WATERFORD 110 | WATERFORD 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
CAPX20200109104601129 | TO-20-WAT-110SA1-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | WATERFORD 110 | WATERFORD 110 | 110SA1 | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601130 | TO-20-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | WATERFORD 110 | WATERFORD 110 | 110SA2 | As a consequence of WAT-110SA1: 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601135 | TO-20-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | WATERFORD 110 | WATERFORD 110 | 110SA2 | 110 kV A2 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA2) | PR0003 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX20200109104601131 | TO-20-WAT-T141-01 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | WATERFORD 110 | WATERFORD 38 | T141 | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1) | PR0003 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100207582401 | TO-20-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | WEXFORD 110 | WEXFORD 110 | 110SA1 | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100208021801 | TO-20-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | WEXFORD 110 | WEXFORD 110 | 110SA1 | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100207582402 | TO-20-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | WEXFORD 110 | WEXFORD 110 | 110SA2 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100208021802 | TO-20-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | WEXFORD 110 | WEXFORD 110 | 110SA2 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100207582403 | TO-20-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | WEXFORD 110 | WEXFORD 110 | CAP2 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100208021803 | TO-20-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | WEXFORD 110 | WEXFORD 110 | CAP2 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100207582404 | TO-20-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | WEXFORD 110 | WEXFORD 110 | CAP4 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100208021804 | TO-20-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | WEXFORD 110 | WEXFORD 110 | CAP4 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Unscheduled
CAPX2019100207582405 | TO-20-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | WEXFORD 110 | WEXFORD 20 | T122 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100208021805 | TO-20-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | WEXFORD 110 | WEXFORD 20 | T122 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100207582406 | TO-20-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | WEXFORD 110 | WEXFORD 38 | T142 | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay | CP0486 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
CAPX2019100208021806 | TO-20-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | WEXFORD 110 | WEXFORD 38 | T142 | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment | CP0972 | 25/12/2500 | 25/12/2500 |  | Reference (Unscheduled)
OD1352 | TO-20-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | WHITEGATE 110 | WHITEGATE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
OD1325 | TO-20-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | WHITEGATE 110 | WHITEGATE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
19EG04124 | TO-20-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | WHITEGATE 110 | WHITEGATE 110 | 110SA1 | 110kV Sect / Dist Ordinary Service including busbar disconnects | 901039691 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
20CM0319 | TO-20-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | WHITEGATE 110 | WHITEGATE 110 | 110SA1 | O1- Replace disconnect due to severe rus | 901059046 | 14/09/2020 | 18/09/2020 | 2 | Scheduled
20CM0318 | TO-20-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | WHITEGATE 110 | WHITEGATE 110 | 110SA1 | 01-investigate interlocking issue betwee | 901059045 | 14/09/2020 | 18/09/2020 | 1 | Scheduled
TOP200116155208 | TO-20-WHI-110SA2-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA2 | WHITEGATE 110 | WHITEGATE 110 | 110SA2 | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1) |  | 14/09/2020 | 18/09/2020 |  | Scheduled
TOP200116155459 | TO-20-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | WHITEGATE 110 | WHITEGATE 10 | CKB-T101 | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1) |  | 14/09/2020 | 18/09/2020 |  | Scheduled
OD0632 | TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | WHITEGATE 110 | WHITEGATE 10 | CKB-T101 | Total Maintenance Outage Duration Requested |  | 14/09/2020 | 18/09/2020 |  | Scheduled
TOP200810160016 | TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | WHITEGATE 110 | WHITEGATE 10 | CKB-T101 | Customer outage request |  | 14/09/2020 | 18/09/2020 |  | Scheduled
20CM0322 | TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | WHITEGATE 110 | WHITEGATE 10 | CKB-T101 | O1-Water in CB Mech Box. | 901039125 | 14/09/2020 | 18/09/2020 | 2 | Scheduled
19EG00359 | TO-20-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | WHITEGATE 110 | WHITEGATE 10 | CKB-T101 | 110kV SF6 Cubicle Ordinary Service | 901042301 | 14/09/2020 | 18/09/2020 | 4 | Scheduled
OD1233 | TO-20-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | WHITEGATE 110 | WHITEGATE 10 | CKB-T102 | Total Maintenance Outage Duration Requested |  | 21/09/2020 | 25/09/2020 |  | Scheduled
20CM0323 | TO-20-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | WHITEGATE 110 | WHITEGATE 10 | CKB-T102 | O1-Replace bird guard on CB.Severely rus | 901059048 | 21/09/2020 | 25/09/2020 | 2 | Scheduled
OD1093 | TO-20-WOH-110SA1-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | WOODHOUSE 110 | WOODHOUSE 110 | 110SA1 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG20759 | TO-20-WOH-110SA1-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | WOODHOUSE 110 | WOODHOUSE 110 | 110SA1 | 110kV Sect / Dist Operational Test | 901039200 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1094 | TO-20-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | WOODHOUSE 110 | WOODHOUSE 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
19EG20761 | TO-20-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | WOODHOUSE 110 | WOODHOUSE 110 | 110SA2 | 110kV Sect / Dist Operational Test | 901039201 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD1097 | TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | WOODHOUSE 110 | WOODHOUSE 20 | T122 | Total Maintenance Outage Duration Requested |  | 22/06/2020 | 26/06/2020 |  | Scheduled
TOP200513083044 | TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | WOODHOUSE 110 | WOODHOUSE 20 | T122 | Oil leak on grid transformer |  | 22/06/2020 | 26/06/2020 |  | Scheduled
TOP200922113516 | TO-20-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | WOODHOUSE 110 | WOODHOUSE 20 | T122 | Customer works |  | 07/10/2020 | 07/10/2020 |  | Scheduled
20EG05112 | TO-20-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | WOODHOUSE 110 | WOODHOUSE 20 | T122 | 110kV SF6 Cubicle Operational Test | 901129682 | 22/06/2020 | 26/06/2020 | 4 | Scheduled
OD0441 | TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | WOODLAND 220 | WOODLAND 220 | 220K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG01296 | TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | WOODLAND 220 | WOODLAND 220 | 220K1-2 | 220kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01295 | TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | WOODLAND 220 | WOODLAND 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01294 | TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | WOODLAND 220 | WOODLAND 220 | 220K1-2 | 220kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG06045 | TO-20-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | WOODLAND 220 | WOODLAND 220 | 220K1-2 | HV Pressure Vessel Inspection |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
OD0442 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
PROT2020061 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | P2 Protection maintenance of 7TG17 |  | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00962 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01301 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Cubicle Condition Assessment |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01300 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01299 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00961 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG01298 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV SF6 Cubicle Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0325 | TO-20-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | O. ESBI Inspect and test all the cylind | 900444684 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20EG00960 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG00959 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | 400kV Sect / Dist Ordinary Service |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0326 | TO-20-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | WOODLAND 400 | WOODLAND 400 | 400K1-2 | Inspect and test all the cylinders, pist | 900531762 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
OD1392 | TO-20-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
OD0801 | TO-20-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11179 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | 400/220kV Transformer Operational Test. Use OD1392. | 901129762 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11178 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | 220kV SF6 Cubicle Operational Test. Use OD1392. | 900942806 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG02114 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | 400/220kV Trafo Tap Changer Inspection. Use OD1392. |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG06033 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | HV Pressure Vessel Inspection. Use OD1392 | 901114185 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20CM0341 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | o/1 air pressure alarm req for CB. Use OD1392 | 900801507 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0439 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | Partial Discharge Test on T4201.Use OD1392 |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
20EG11177 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | 400kV SF6 Cubicle Operational Test. Use OD1392. | 901146366 | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG23804 | TO-20-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | WOODLAND 400 | WOODLAND 220 | T4201 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1392. |  | 25/12/2500 | 25/12/2500 | 1 | Unscheduled
TOP200611084732 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | SF6 leak on transformer bays |  | 24/06/2020 | 03/07/2020 |  | Scheduled
OD0802 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | Total Maintenance Outage Duration Requested |  | 24/06/2020 | 03/07/2020 |  | Scheduled
20CM0346 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | SF6 GAUGE TO BE REPLACED AS PER ESBI | 901073092 | 24/06/2020 | 03/07/2020 | 2 | Scheduled
20CM0347 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | Corrective- T4202 220KV CB LOW | 901073407 | 24/06/2020 | 03/07/2020 | 2 | Scheduled
20CM0348 | TO-20-WOO-T4202-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | Inspect and test all the cylinders, pist | 900532120 | 25/12/2500 | 25/12/2500 | 2 | Unscheduled
20CM0349 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | Corrective- T4202 Surge Counters Unreada | 901081577 | 24/06/2020 | 03/07/2020 | 2 | Scheduled
20EG11180 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | 220kV SF6 Cubicle Operational Test |  | 24/06/2020 | 03/07/2020 | 4 | Scheduled
20EG11181 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | 400kV SF6 Cubicle Operational Test |  | 24/06/2020 | 03/07/2020 | 4 | Scheduled
20EG11182 | TO-20-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | WOODLAND 400 | WOODLAND 220 | T4202 | 400/220kV Transformer Operational Test |  | 24/06/2020 | 03/07/2020 | 4 | Scheduled
PROT2020151 | TO-20-WOO-T4204-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | WOODLAND 400 | WOODLAND 220 | T4204 | P3 Protection maintenance of 7SA612, 7SA612, RET670 |  | 25/12/2500 | 25/12/2500 | 3 | Unscheduled
OD0844 | TO-20-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | WOODLAND 400 | WOODLAND 220 | T4204 | Total Maintenance Outage Duration Requested |  | 25/12/2500 | 25/12/2500 |  | Unscheduled
20EG11362 | TO-20-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | WOODLAND 400 | WOODLAND 220 | T4204 | 220kV SF6 Cubicle Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled
20EG11364 | TO-20-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | WOODLAND 400 | WOODLAND 220 | T4204 | 400/220kV Transformer Operational Test |  | 25/12/2500 | 25/12/2500 | 4 | Unscheduled

## All
SECTIONALISING DISCONNECT - AGANNYGAL 110SA1
TO-20-AGL-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
OS | AGL | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-AGL-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-110SA2: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - AGANNYGAL 110SA2
TO-20-AGL-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-110SA1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - AGANNYGAL DERRYBRIEN [Derrybrien DY1]
TO-20-AGL-DYN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-AGL-DYN-1-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-AGL-DYN-1-02 ISO week: 37mo - 37sa Date: 07 Sep - 12 Sep Duration: 6 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | AGL | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | AGL | - | 900713712 | DO | 3 | 2 | CB - Siemens 3AP mod required to prevent spring charging lockout with loss of AC.
110kV FEEDER - AGANNYGAL ENNIS
TO-20-AGL-ENN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | ENN | - | 901129481 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-AGL-ENN-1-01 ISO week: 25mo - 25fr Date: 15 Jun - 19 Jun Duration: 5 Days (5 WD) Status: Scheduled
TRAN |  | - | 900982973 | DO | 1 | 4 | 2018HP-1[124]Off PlumbPlumb insulators
OS | AGL | - | 901129954 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AGANNYGAL SHANNONBRIDGE
TO-20-AGL-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous AGL-SH-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-AGL-SH-1-03 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-AGL-SH-1-01 ISO week: 32tu - 32fr Date: 04 Aug - 07 Aug Duration: 4 Days (4 WD) Status: Scheduled
OS | AGL | - | 901129955 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | SH |  | 901081611 | DO | 3 | 1 | Replace faulty isolation block.
CORRECT | SH |  | 901087472 | DO | 3 | 1 | EMP AMS: Spring charge locking out with
CORRECT | SH |  | 901087473 | DO | 3 | 2 | EMP AMS: Peplace Fuse Holders on all CTV
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
BUSBAR SECTION - AGHADA 220 kV A1
TO-20-220 kV A1 @ AD-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV A2
TO-20-220 kV A2 @ AD-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV B1
TO-20-220 kV B1 @ AD-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV B1/B2
TO-20-220 kV B1/B2 @ AD-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart test
BUSBAR SECTION - AGHADA 220 kV B2
TO-20-220 kV B2 @ AD-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover
COUPLER/SECTIONALISING CB - AGHADA 220K1-2
TO-20-AD-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of ISM21
CORRECT | AD |  | 900891284 | DO | 3 | 2 | V-string busbar insulator has corrosion
CORRECT | AD |  | 900912297 | DO | 2 | 1 | O1-Hotspot Sectionaliser SA
FM | AD | - | 901045781 | DO | 1 | 4 | HV Pressure Vessel Inspection
220kV FEEDER - AGHADA GLANAGOW
TO-20-AD-GGO-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | - |  | DO | 3 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-AD-GGO-1-01 Status: Unscheduled
Blackstart Test
220kV FEEDER - AGHADA KNOCKRAHA 1
TO-20-AD-KRA-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-AD-KRA-1-05 Status: Unscheduled
OS | AD | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | AD | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
OS | KRA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | KRA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KRA | - | 900719850 | DO | 1 | 2 | O1-Surge Counters have moisture inside.
TO-20-AD-KRA-1-06 ISO week: 29su - 30sa Date: 19 Jul - 25 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901098961 | CLO | 2 | 1 | Hotspot 3 (Lwr 1 Span 28/29) Lower phase midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098964 | CLO | 2 | 1 | Hotspot 4 (Lwr 2 Span 28/29) Lower phase midspan joint (Repair by 30th Jul 2020)
TRAN | - | Line | 901098965 | CLO | 2 | 1 | Hotspot 1 (C1 Span 61/62) Centre Midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098966 | CLO | 2 | 1 | Hotspot 2 (Upr 1 Span 61 / 62) Upper midspan joint (Measure resistance during next available outage)
220kV FEEDER - AGHADA KNOCKRAHA 2
TO-20-AD-KRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-AD-KRA-2-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-AD-KRA-2-05 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-AD-KRA-2-04 ISO week: 29su - 30sa Date: 19 Jul - 25 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901098967 | CLO | 2 | 1 | Hotspot 3 (C2 Span 28/29) Centre Midspan (Repair by 30th Jul 2020)
TRAN | - | Line | 901098968 | CLO | 2 | 1 | Hotspot 4 (Upr 1 Span 28/29) Upper Midspan (Repair by 30th Oct 2020)
TRAN | - | Line | 901098969 | CLO | 2 | 1 | Hotspot 5 (Upr 2 Span 28/29) Upper Midspan (Repair by 30th Oct 2020)
TRAN | - | Line | 901098970 | CLO | 2 | 1 | Hotspot 2 (C1 Span 61/62) Centre midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098971 | CLO | 2 | 1 | Hotspot 1 (C2 Span 61/62) Centre midspan joint (Repair by 30th Jul 2020)
220kV FEEDER - AGHADA LONG POINT
TO-20-AD-LPT-1-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
220kV FEEDER - AGHADA RAFFEEN
TO-20-AD-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2)
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-AD-RAF-1-01 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TRAN |  | - | 900983098 | DO | 1 | 4 | 2018HP-1[9]Vib Dampers-Replace
OS | AD | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | AD | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CORRECT | RAF |  | 901028751 | DO |  | 2 | O1-Aghada 220kv Gantree Glass Insulator
GENERATOR TRANSFORMER - AGHADA ST101 [ESB GWM]
TO-20-AD-ST101-03 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | CP0794 |  | 2 |  | Proximity outge for civil works
GENERATOR TRANSFORMER - AGHADA T2011/12 [ESB GWM AT11/AT12]
TO-20-AD-T2011/12-02 ISO week: 9mo - 23tu Date: 24 Feb - 02 Jun Duration: 100 Days (67 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | AD | - | 901130028 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | AD | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
AMCAB | AD | - | 901129053 | CLO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
FM | AD | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - AGHADA T2014 [ESB GWM AT4]
TO-20-AD-T2014-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-AD-T2014-02 ISO week: 32we - 32th Date: 05 Aug - 06 Aug Duration: 2 Days (2 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7UT92
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | AD | - |  | DO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
TRANSFORMER - AGHADA T2102
TO-20-AD-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 10 |  | Total Maintenance Outage Duration Requested
OS | AD | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | AD | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | AD | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | AD | TRAFO |  | DO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | AD | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CA | AD | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | AD | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | AD | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-AD-T2102-01 ISO week: 32we - 32fr Date: 05 Aug - 07 Aug Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | AD |  | 900908020 | DO | 3 | 2 | Oil sampling of cable boxes on T2102 Tra
TO-20-AD-T2102-04 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | CP0794 |  | 2 |  | Proximity outage. To facilitate crossing of 110kV cable
110kV FEEDER - AGHADA WHITEGATE [Irving Oil]
TO-20-AD-WHI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 | 2 | Total Maintenance Outage Duration Requested
OS | AD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - AHANE KILLONAN 2 [SDCC]
TO-20-AHA-KLN-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA513
110kV FEEDER - ANNER DOON
TO-20-ANR-DOO-1-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | DOO | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
| DOO |  |  | DO | 1 | 1 | Replacement of Stolen Earths
OPT | DOO | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - ANNER T101 [Medite]
TO-20-ANR-T101-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
TSO CUSTOMER TRANSFORMER - ANNER T103 [Medite]
TO-20-ANR-T103-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV A3
TO-20-110 kV A3 @ AA GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | Energisation of T104 from Drumline
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV B1
TO-20-110 kV B1 @ AA GIS-02 ISO week: 33we Date: 12 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PROX |  | 1 |  | Proximity for T103 black start
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV B3
TO-20-110 kV B3 @ AA GIS-02 ISO week: 33we Date: 12 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 1 |  | Proximity for T103 black start
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110K3
TO-20-AA GIS-110K3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | AA | - | 901076456 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
TO-20-AA GIS-110K3-01 Status: Unscheduled
CAPX |  |  | CP1065 | DO | 2 |  | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline
TO-20-AA GIS-110K3-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SA1-3CB
TO-20-AA GIS-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SB1-2CB
TO-20-AA GIS-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ AA GIS: 110 kV A2/B2 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover
TO-20-AA GIS-110SB1-2CB-02 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | AA |  | 901053225 | DO | 4 | 1 | OEM Fault Investigation / Repair on SB2.
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SB1-3CB
TO-20-AA GIS-110SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover
110kV FEEDER - ARDNACRUSHA GIS DRUMLINE
TO-20-AA GIS-DRU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | Energisation of T104 from Drumline
TO-20-AA GIS-DRU-1-02 ISO week: 45tu - 45fr Date: 03 Nov - 06 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | DRU | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARDNACRUSHA GIS ENNIS
TO-20-AA GIS-ENN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | CANC |  |  | Total Maintenance Outage Duration Requested
TO-20-AA GIS-ENN-1-03 ISO week: 46tu Date: 10 Nov Duration: 1 Day (1 WD) Status: Scheduled
operator training
TO-20-AA GIS-ENN-1-01 ISO week: 11mo - 11fr Date: 09 Mar - 13 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900725270 | DO | 1 | 1 | 2015CP-1[132]Off Plumb Poles
FO_MISC |  | - | 900725277 | DO | 1 | 1 | 2015CP-1[149]Off Plumb Poles
OPT | AA | - | 901045735 | CLO | 2 | 4 | 110kV GIS Cubicle Operational Test
AMCAB | AA | - | 901129157 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
OS | ENN | - | 901129840 | CLO | 4 | 4 | 110kV MO Cubicle Ordinary Service
110kV FEEDER - ARDNACRUSHA GIS LIMERICK
TO-20-AA GIS-LIM-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-AA GIS-LIM-1-01 Status: Unscheduled
FO_MISC |  | - | 900816798 | CANC | 1 | 2 | 2016CP-1[32]Off Plumb Poles leaning
FO_MISC |  | - | 900816810 | CANC | 1 | 2 | 2016CP-1[72]Off Plumb Insulators
OPT | LIM |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARDNACRUSHA GIS SINGLAND
TO-20-AA GIS-SNG-1-01 ISO week: 30mo - 30th Date: 20 Jul - 23 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | AA | - | 901018827 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
TO-20-AA GIS-SNG-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Proposed
DSO request for CA on SNG T102
OPT | SNG | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T101 [ESB GWM AA1]
TO-20-AA GIS-T101-01 ISO week: 25tu Date: 16 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 0 |  | Total Maintenance Outage Duration Requested
OPT | AA | - | 901050256 | DO | 1 | 4 | 110KV MO Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T103 [ESB GWM AA3]
TO-20-AA GIS-T103-01 ISO week: 17mo Date: 20 Apr Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| AA |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | AA | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T104 [ESB GWM AA4]
TO-20-AA GIS-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 38 |  | Outage of transformer to faciliatet trafo replacement (IPP request)
110kV FEEDER - ARDNAGAPPARY TIEVEBRACK
TO-20-AGP-TIV-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TIV | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARIGNA tee CARRICK ON SHANNON
TO-20-ARI,T-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085136 | DO | 2 | 4 | 2019HP-1[188]Vib Dampers Loose
FO_STDMG |  |  | 901086390 | DO | 1 | 4 | 2019HP-2[182, 183]Replace Pole Bolt
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
110kV FEEDER - ARIGNA tee CORDERRY
TO-20-ARI,T-CDY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDY | - | 901039100 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - ARKLOW 110 kV A1
TO-20-110 kV A1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV A2
TO-20-110 kV A2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV B1
TO-20-110 kV B1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV B2
TO-20-110 kV B2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV A1
TO-20-220 kV A1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV A2
TO-20-220 kV A2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV B1
TO-20-220 kV B1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV B2
TO-20-220 kV B2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover
COUPLER/SECTIONALISING CB - ARKLOW 220K1-2
TO-20-ARK-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | ARK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
110kV FEEDER - ARKLOW BALLYBEG
TO-20-ARK-BEG-1-01 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084881 | CLO | 2 | 2 | 2019HP-1[51]Insulator Broken Lower/ph
OPT | BEG | - | 901129646 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARKLOW BANOGE
TO-20-ARK-BOG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085135 | DO | 1 | 2 | 2019HP-1[129]Vib Dampers EW Damper
CM | ARK | 110-DL | 901134734 | DO | 2 | 1 | R phase Banoge 110kV CubicleDL., R phase connectio hotpot repair due by 17thAugust 2020
OPT | BOG | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - ARKLOW CARRICKMINES GIS
TO-20-ARK-CKM GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CKM |  | 900532102 | CANC |  | 2 | ESBi Repeat Insulation Tests on VT all p
TO-20-ARK-CKM GIS-1-01 ISO week: 22mo - 42fr Date: 25 May - 16 Oct Duration: 145 Days (103 WD) Status: Forced Out
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
YM03 |  | - | 900979480 | CLO | 1 | 2 | Timber HAZCNF_20M (122-123)
CM | ARK | - | 901134735 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GISbushing connection DUE : 17-Nov-20
CM | ARK | - | 901134736 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GIS Copper earth strap DUE : 17-Jul-20
CM | ARK | 110-DL | 901134737 | DO | 2 | 1 | T phase Carrickmines 220kVCubicle. T phase GIS Copper earth strp hotspot DUE : IMMEDIATELY
YM03 | ARK | - | 900978744 | CANC | 1 | 2 | Replace SF6 density gauge on GIS to AIS
OPT | ARK | - | 901039045 | DO | 1 | 3 | 220kV GIS Cubicle Operational Test
OS | CKM | - | 901042325 | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | CKM |  | 900596268 | DO | 2 | 2 | 01 outage required. Hot Spots
220kV FEEDER - ARKLOW LODGEWOOD
TO-20-ARK-LWD-1-03 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
MC0335 | [6 empty] | Proximity outage of the Arklow Lodgewood
TO-20-ARK-LWD-1-01 ISO week: 40we - 42fr Date: 30 Sep - 16 Oct Duration: 17 Days (13 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084299 | DO | 1 | 2 | 2019HP-1[21]Bird Nests remove birds nest
CORRECT | ARK |  | 900908600 | DO |  | 2 | Wire in low air alarm as per original de
OPT | LWD | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CM | LWD | - | 901134792 | DO | 1 | 1 | T Phase Arklow 220kV Cubicle. T Phase VT connection DUE : 17-Jul-20
110kV FEEDER - ARKLOW SHELTON ABBEY 2
TO-20-ARK-SHE-2-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
Proximity to allow ESBN to replace corroded gantry in Shelton Abbey Compound
OS | ARK | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | SHE | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TRANSFORMER - ARKLOW T2101
TO-20-ARK-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | ARK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
110kV FEEDER - ARVA CARRICK ON SHANNON
TO-20-ARV-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | COS | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-ARV-COS-1-02 Status: Unscheduled
|  | - | 901148340 | CLO | 2 | 1 | Hotspot 1 (ET No.1, Span 1-2) Left Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148341 | CLO | 2 | 1 | Hotspot 2 (AT No.6, Span 6-7) Right Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148343 | CLO | 2 | 1 | Hotspot 4 (AT No.10, Span 10-11) Centre Deadend Terminiation (Repair by 6th June 2020)
|  | - | 901148345 | CLO | 2 | 1 | Hotspot 5 (AT No.11, Span 10-11) Right Deadend Termination (Repair by 6th Aug 2020)
|  | - | 901148346 | CLO | 2 | 1 | Hotspot 6 (AT No.154, Span 153-154) Centre Jumper Terminal (Repair by 6th Nov 2020)
|  | - | 901148348 | CLO | 2 | 1 | Hotspot 7 (R1, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148349 | CLO | 2 | 1 | Hotspot 8 (R2, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148350 | CLO | 2 | 1 | Hotspot 9 (C1, Span 204-205) Centre Midspan Joint (Repair Immediately)
|  | - | 901148351 | CLO | 2 | 1 | Hotspot 10 (C1, Span 204-205) Right Midspan Joint (Measure resistance by while repairing Hotspot 9))
|  | - | 901148352 | CLO | 2 | 1 | Hotspot 11 (R2, Span 168-169) Centre Midspan Joints (Measure resistance by 6th Aug 2020)
TO-20-ARV-COS-1-03 ISO week: 47mo - 47th Date: 16 Nov - 19 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | 901148342 | DO | 2 |  | Hotspot 3 (AT No.10, Span 9-10) Centre Deadend Terminiation (Repair by 6th Nov 2020)
110kV FEEDER - ARVA GORTAWEE
TO-20-ARV-GWE-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-ARV-GWE-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084866 | DO | 1 | 4 | 2019HP-1[157]Earths-Replace LPH e/w
FO_MISC |  |  | 901084867 | DO | 1 | 4 | 2019HP-1[158]Earths-Replace RPH e/w
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA612, REL521
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA NAVAN
TO-20-ARV-NAV-1-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086419 | DO | 2 | 1 | 2019HP-1[132]Replace Pole only -Rot
FOSTRHW |  |  | 901086420 | DO | 2 | 1 | 2019HP-1[191]Replace Pole only -Rot
TO-20-ARV-NAV-1-01 ISO week: 9mo - 10fr Date: 24 Feb - 06 Mar Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084868 | DO | 2 | 4 | 2019HP-1[6]Earths-Replace earth lead
FOSTRHW |  |  | 901086415 | DO | 2 | 1 | 2019HP-1[4]Replace Pole only -Rot
FOSTRHW |  |  | 901086416 | DO | 2 | 1 | 2019HP-1[58]Replace Pole only -Rot
FOSTRHW |  |  | 901086417 | DO | 2 | 1 | 2019HP-1[63]Replace Pole only -Rot
FOSTRHW |  |  | 901086418 | CLO | 2 | 1 | 2019HP-1[128]Replace Pole only -Rot
FOSTRHW |  |  | 901086421 | CLO | 2 | 1 | 2019HP-1[199]Replace Pole only -Rot
FOSTRHW |  |  | 901086422 | CLO | 2 | 1 | 2019HP-1[229]Replace Pole only -Rot
FOSTRHW |  |  | 901086423 | CLO | 2 | 1 | 2019HP-1[230]Replace Pole only -Rot
FOSTRHW |  |  | 901086424 | CLO | 2 | 1 | 2019HP-1[319]Replace Pole only -Rot
CA | NAV | - | 901129179 | CLO | 5 | 4 | 110kV CUBICLE CONDITION ASSESSMENT
OS | NAV | - | 901129885 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA SHANKILL 1
TO-20-ARV-SKL-1-01 ISO week: 44th - 44fr Date: 29 Oct - 30 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  |  | 901084300 | DO | 2 | 4 | 2019HP-1[21]Bird Nests
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | SKL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARVA SHANKILL 2
TO-20-ARV-SKL-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | SKL |  | 901028567 | CANC |  | 1 | O 1 O 1 ARVA 2 C.B. MONITORING TEMI
CORRECT | SKL |  | 901045926 | CANC |  | 1 | Investigate CB gas leak & repair if poss
TO-20-ARV-SKL-2-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
PROT |  | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983642 | DO | 2 | 4 | 2018HP-1[Am 35]Bird Nests
PROX |  |  | PR0001 |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
TRAN |  | - | 900983641 | DO | 1 | 4 | 2018HP-1[Am 29]Bird Nests
FO_MISC |  |  | 901084301 | DO | 1 | 4 | 2019HP-1[143]Bird Nests
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612, GRL100
OS | SKL | - |  | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
AMCAB | SKL | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | SKL | 110 | 901068797 | CANC | 2 | 1 | Visual inspection of HIS HV cable sealin
COUPLER/SECTIONALISING CB - ATHEA 110SA1-2CB
TO-20-ATE-110SA1-2CB-01 ISO week: 35mo - 35tu Date: 24 Aug - 25 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATE |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | ATE | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | ATE | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - ATHEA DROMADA
TO-20-ATE-DRO-1-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATE | - | 901043693 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - ATHEA KNOCKANURE
TO-20-ATE-KNR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | ATE | - | 901042193 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | ATE | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | KNR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | KNR | - | 901043731 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - ATHEA T121 [Athea AH1]
TO-20-ATE-T121-01 ISO week: 35mo - 35th Date: 24 Aug - 27 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | ATE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | ATE | 110 | 901043038 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - ATHLONE 110SA1-2CB
TO-20-ATH-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATH | - | 901039013 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
OPT | ATH | 110-SA1 | 901039204 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | ATH | 110-SA2 | 901039205 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
TO-20-ATH-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
CAPACITOR/SVC/REACTOR - ATHLONE CAP3
TO-20-ATH-CAP3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
TO-20-ATH-CAP3-01 ISO week: 26mo - 26fr Date: 22 Jun - 26 Jun Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | ATH |  | 901078674 | CLO | 2 | 2 | Contact resistance measurement on the ci
110kV FEEDER - ATHLONE LANESBORO
TO-20-ATH-LA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
YM03 |  | - | 901046063 | CLO | 5 | 4 | Conductor Sampling section 179-199
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-ATH-LA-1-03 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
CAPACITOR/SVC/REACTOR - ATHLONE M/CAP1
TO-20-ATH-M/CAP1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
TO-20-ATH-M/CAP1-01 ISO week: 27tu - 27we Date: 30 Jun - 01 Jul Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | ATH |  | 901067981 | CLO | 2 | 2 | O1- Spray Weeds Cap 1 Cubicle
110kV FEEDER - ATHLONE SHANNONBRIDGE
TO-20-ATH-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983699 | DO | 1 | 4 | 2018HP-1[Am 75]Bird Nests
FO_MISC |  |  | 901084302 | DO | 1 | 4 | 2019HP-1[75]Bird Nests
FOSTRHW |  |  | 901086374 | DO | 1 | 4 | 2019HP-1[23]Check Structure -Check Rot
FOSTRHW |  |  | 901086375 | DO | 1 | 4 | 2019HP-1[43]Check Structure -Check Rot
OPT | ATH |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-ATH-SH-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - ATHLONE T141 [SDCC]
TO-20-ATH-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - ATHLONE T142 [SDCC]
TO-20-ATH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
SECTIONALISING DISCONNECT - ATHY 110SA1
TO-20-ATY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 3 |  | Total Maintenance Outage Duration Requested
OS | ATY | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-ATY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - ATHY 110SA2
TO-20-ATY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of ATY-110SA1: 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - ATHY CARLOW
TO-20-ATY-CLW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
TO-20-ATY-CLW-1-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
TO-20-ATY-CLW-1-01 ISO week: 9mo - 9fr Date: 24 Feb - 28 Feb Duration: 5 Days (5 WD) Status: Scheduled
FO_MISC |  |  | 901074611 |  | 5 |  | End Tower 122 - Station Gantry in Carlow Replace insulators. Fit corona rings
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084078 |  | 2 |  | 2019HP-1[122]Anti-Cl. Guard -Replace. Wrong type fitted
OPT | CLW |  | 901128701 | CLO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ATHY PORTLAOISE
TO-20-ATY-PLS-1-02 ISO week: 18mo - 18fr Date: 27 Apr - 01 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  | - | 900606197 | CLO | 2 | 1 | 1[57] Replace pole - wayleave issue
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
TRAN |  | - | 900989777 | DO | 1 | 4 | 2018HP-1[128]Check Structure-top rot
FOSTRHW |  |  | 901086377 | DO | 1 | 4 | 2019HP-1[129]Check Structure -Check Rot
FOSTRHW |  |  | 901086378 | DO | 1 | 4 | 2019HP-1[130]Check Structure -Check Rot
H7 cubicle ordinary service
OS | ATY | - | 901042196 | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | ATY | - | 901038563 | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | PLS | - | 901050572 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | PLS |  | 901146375 | CLO | 3 | 1 | Replacement of Stolen Earths
CORRECT | PLS |  | 901072095 | DO | 1 | 2 | lamp in mech box o/o/o , corrision on wa
CORRECT | PLS |  | 901087221 | DO | 1 | 1 | moisture in surge counters
DISTRIBUTION TRANSFORMER - ATHY T101 [SDCC]
TO-20-ATY-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - AUGHINISH 110SA1-2CB
TO-20-AUG-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
OS | AUG | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-AUG-110SA1-2CB-01 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO | 1 |  | P1 Protection maintenance of ISM21
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | AUG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - AUGHINISH CASTLEFARM 1
TO-20-AUG-CFM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
OS | AUG | - | 901129898 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | AUG | - | 901129107 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-AUG-CFM-1-02 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Scheduled
1[EM 48] replacement of 110kV strain/duplicate insulator
Customer outage request
As a consequence of CFM T101
110kV FEEDER - AUGHINISH CASTLEFARM 2
TO-20-AUG-CFM-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-CFM-2-03 Status: Unscheduled
CORRECT | AUG |  | 901030139 | CANC | 1 | 2 | Assist with Relay Testing
TO-20-AUG-CFM-2-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SJ611, RADSB
901158967 | [6 empty] | Paint 110kV Tower
901158971 | [6 empty] | Replacement of Insulators
As a consequence of CFM-T102
Customer outage 14 @ CFM T102 14 Sept - 02 Oct
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AUGHINISH KILPADDOGE
TO-20-AUG-KPG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | KPG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| KPG |  |  |  | 3 |  | Outstanding issues with the AR Supervisory scheme on the bay including testing and recommissioning of the BCU and testing of new commands and PI back to NCC
TO-20-AUG-KPG-1-02 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901110437 | CLO | 2 | 1 | Hotspot 8 (DC Cable Tower No.160 Span 159/160) Lower (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110438 | CLO | 2 | 1 | Hotspot 7 (DC Cable Tower No.160 Span 159/160) Top (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110439 | CLO | 2 | 1 | Hotspot 4 (Transposition Tower No. 58 Span 57/58) Left Jumper Terminal (Repair by 24th Jul)
TRAN | - | Line | 901110456 | CLO | 2 | 1 | Hotspot 2 (Transposition Tower No. 58 Span 58/59) Centre Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110457 | CLO | 2 | 1 | Hotspot 3 (Transposition Tower No. 58 Span 58/59) Left Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110460 | CLO | 2 | 1 | Hotspot 5 (Transposition Tower No. 58 Span 57/58) Centre Jumper Terminal (Repair by 24th May)
TRAN | - | Line | 901110461 | CLO | 2 | 1 | Hotspot 6 (Transposition Tower No. 58 Span 57/58) Right Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110462 | CLO | 2 | 1 | Hotspot 1 (Transposition Tower No. 58 Span 58/59) Right Jumper Terminal (Repair by 24th Oct)
110kV FEEDER - AUGHINISH MONETEEN
TO-20-AUG-MTN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
FO_MISC |  |  | 901084931 | DO | 1 | 4 | 2019HP-1[19]Off Plumb -plumb poles
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MTN |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - AUGHINISH SEALROCK 3
TO-20-AUG-SK-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | AUG |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-AUG-SK-3-02 Status: Unscheduled
OPT | AUG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-AUG-SK-3-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - | 901129109 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - AUGHINISH SEALROCK 4
TO-20-AUG-SK-4-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-SK-4-02 Status: Unscheduled
Outage start @ 06:00 09 Nov 2020, Outage end @ 18:00 12 Nov 2020
Customer outage request
TO-20-AUG-SK-4-01 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - BALLYBEG 110SA2
TO-20-BEG-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | BEG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - BALLYBEG CARRICKMINES GIS
TO-20-BEG-CKM GIS-1-01 ISO week: 46tu - 46fr Date: 10 Nov - 13 Nov Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
YM03 |  | - | 900979776 | DO | 1 | 4 | 2018HP-1[104]Foundation/Site repair
OS | BEG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CKM | - | 900944045 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
SECTIONALISING DISCONNECT - BALLYDINE 110SA1
TO-20-BDN-110SA1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
CM | BAL |  | 901091973 | CLO | 3 | 1 | Replacement of Stolen Earths
OS | BDN | SA1 | 900782940 | CLO | 3 | 1 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BALLYDINE 110SA2
TO-20-BDN-110SA2-01 ISO week: 26we - 26fr Date: 24 Jun - 26 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BDN-110SA1: 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BALLYDINE CULLENAGH
TO-20-BDN-CUL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727019 | CANC | 3 | 1 | 2015HP-3[26,35,40]Off Plumb Poles
TO-20-BDN-CUL-1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BDN-CUL-1-02 ISO week: 37we - 37fr Date: 09 Sep - 11 Sep Duration: 3 Days (3 WD) Status: Scheduled
FO_MISC |  | - | 900649538 | DO | 4 | 1 | 2014HP-[27,35,40,48,55,56]Off Plumb
FO_MISC |  | - | 900649539 | DO | 4 | 1 | 2014HP-[58,59,60,77,97,99,107]Off Plumb
110kV FEEDER - BALLYDINE DOON
TO-20-BDN-DOO-1-01 ISO week: 31th - 32th Date: 30 Jul - 06 Aug Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983907 | CLO | 2 | 1 | 2018HP-1[2]Replace Pole only-Rot
OS | BDN | - | 901151576 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | BDN |  | 901091975 | CLO | 3 | 1 | Replacement of Stolen Earths
OPT | DOO |  | 901129614 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK1 [Merck Sharp & Dohme]
TO-20-BDN-MRK1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
Replace Stolen Earths
OPT | BDN |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK3 [Merck Sharp & Dohme]
TO-20-BDN-MRK3-01 ISO week: 29mo - 30mo Date: 13 Jul - 20 Jul Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BDN | - | 901042188 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
CM | BDN | - | 901091974 | CLO | 3 | 1 | Replace Stolen Earths
DISTRIBUTION TRANSFORMER - BALLYDINE T141 [SDCC]
TO-20-BDN-T141-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BALLYLICKEY DUNMANWAY [SDCC]
TO-20-BLI-DMY-1-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-DMY-1-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BALLYLICKEY T142 [SDCC]
TO-20-BLI-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-T142-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-T142-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-T142-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
BUSBAR SECTION - BALLYNAHULLA 110 kV A1
TO-20-110 kV A1 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV A2
TO-20-110 kV A2 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV B1
TO-20-110 kV B1 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV B2
TO-20-110 kV B2 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110K1
TO-20-BYH-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110K1-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901050244 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110K2
TO-20-BYH-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110SA1-2CB
TO-20-BYH-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043737 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110SB1-2CB
TO-20-BYH-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110SB1-2CB-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043738 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220K1
TO-20-BYH-220K1-01 ISO week: 9th - 10tu Date: 27 Feb - 03 Mar Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BYH | - | 901129779 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | BYH |  | 901078169 | CLO | 2 | 1 | PI from DEM1 & DEM2 not working followin
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220K2
TO-20-BYH-220K2-01 ISO week: 10we - 11tu Date: 04 Mar - 10 Mar Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BYH | - | 901129804 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | BYH |  | 901078168 | CLO | 2 | 1 | PI from DEM1 & DEM2 not working followin
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220SA1-2CB
TO-20-BYH-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043813 | DO | 2 | 4 | 220kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220SB1-2CB
TO-20-BYH-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043800 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - BALLYNAHULLA BALLYVOUSKILL
TO-20-BYH-BVK-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
Maintenance
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | BYH | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | BYH | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-BYH-BVK-1-01 ISO week: 46th - 47fr Date: 12 Nov - 20 Nov Duration: 9 Days (7 WD) Status: Scheduled
CM | BVK | - |  | DO | 6 | 2 | Aux Relay - replace contactors
CM | BYH | - |  | DO | 6 | 2 | Aux Relay - replace contactors
110kV FEEDER - BALLYNAHULLA CORDAL
TO-20-BYH-CDL-1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901128997 | DO | 3 | 3 | Insp. 110kV Feeder XLPE Cable
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CDL |  | 901129678 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALLYNAHULLA GLENLARA
TO-20-BYH-GLE-1-01 ISO week: 13th Date: 26 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| - | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH |  | 901129526 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | GLE | - | 901129703 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - BALLYNAHULLA KNOCKANURE
TO-20-BYH-KNR-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 5 |  | Proximity outage to move link box
CAPX |  |  | CP0936 | DO | 2 |  | Proximity outage to remove scaffolding
TO-20-BYH-KNR-1-02 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 2 |  | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder
TO-20-BYH-KNR-1-04 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 100 |  | Line uprate works - restringing, foundation reinforcement, hardware etc
TO-20-BYH-KNR-1-05 Status: Unscheduled
FOINSHW |  | - | 900897561 | DO | 2 | 3 | 2017HP-1[37]Susp/Dup 220kV replacement
FO_MISC |  |  | 901084882 | DO |  | 2 | 2019HP-1[80]Insulator Broken disc
OS | BYH | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
TO-20-BYH-KNR-1-01 ISO week: 44tu - 46we Date: 27 Oct - 11 Nov Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 4 |  | SF6 repairs in Knockanure
CM | BYH | - |  | DO | 6 | 2 | Aux Relay - replace contactors
AMCAB | BYH | - | 901051722 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
CM | KNR | - |  | DO | 6 | 1 | Aux Relay - replace contactors
AMCAB | KNR | - | 901051726 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
TRANSFORMER - BALLYNAHULLA T2101
TO-20-BYH-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | BYH | 110 | 901129028 | CANC | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-BYH-T2101-01 Status: Unscheduled
| BYH | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | BYH | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TRANSFORMER - BALLYNAHULLA T2102
TO-20-BYH-T2102-01 ISO week: 36tu - 36th Date: 01 Sep - 03 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| BYH | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | BYH | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | BYH | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
CORRECT | BYH | TRAFO | 901075872 | DO | 1 | 2 | False low oil alarm & DC earth fault com
CORRECT | BYH | TRAFO | 901079981 | DO | 1 | 2 | Following the malfunction fault on oil m
BUSBAR SECTION - BALLYVOUSKILL 110 kV A1
TO-20-110 kV A1 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV A2
TO-20-110 kV A2 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV B1
TO-20-110 kV B1 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV B2
TO-20-110 kV B2 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110K1
TO-20-BVK-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110K2
TO-20-BVK-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110SA1-2CB
TO-20-BVK-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
TO-20-BVK-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | BVK | - | 901043740 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110SB1-2CB
TO-20-BVK-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220K1
TO-20-BVK-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220K2
TO-20-BVK-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
220kV FEEDER - BALLYVOUSKILL CLASHAVOON
TO-20-BVK-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101
TO-20-BVK-CLA-1-02 Status: Unscheduled
CM | BVK | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TO-20-BVK-CLA-1-03 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | BVK | - | 901050433 | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | CLA | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CLA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - BALLYVOUSKILL COOMATAGGART
TO-20-BVK-COT-1-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | - | 110 | 901132973 | DO | 5 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BALLYVOUSKILL GARROW
TO-20-BVK-GRO-1-01 ISO week: 27tu - 27fr Date: 30 Jun - 03 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CM |  |  | 901056104 | DO | 3 | 1 | Water ingress into JB01 Link Box – Raise
CM |  |  | 901068796 | CANC | 3 | 2 | Visual inspection of HIS HV cable sealin
OPT | GRO |  | 901129712 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - BALLYVOUSKILL T2101
TO-20-BVK-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | BVK | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | BVK | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | BVK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | BVK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - BALLYVOUSKILL T2102
TO-20-BVK-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | BVK | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | BVK | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | BVK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | BVK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BALLYWATER CRANE [Ballywater BW1]
TO-20-BWR-CRA-1-01 ISO week: 23tu Date: 02 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CRA |  | 901129684 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALTRASNA CORDUFF
TO-20-BAL-CDU-1-01 ISO week: 32we Date: 05 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BAL |  | 901129589 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALTRASNA DRYBRIDGE
TO-20-BAL-DRY-1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086425 | CLO | 3 | 1 | 2019HP-1[56]Replace Pole only -Rot
TRAN |  | - | 900983998 | CLO | 2 | 4 | 2018HP-1[98]Insul&HW Replace check
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | BAL |  | 901129588 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DRY |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - BANDON 110SA1
TO-20-BAN-110SA1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OS | BAN | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BANDON 110SA2
TO-20-BAN-110SA2-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-110SA1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BANDON BRINNY 1
TO-20-BAN-BRI-1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON BRINNY 2
TO-20-BAN-BRI-2-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| BAN | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
CAPACITOR/SVC/REACTOR - BANDON CAP1
TO-20-BAN-CAP1-02 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BAN-CAP1-01 ISO week: 23tu - 23fr Date: 02 Jun - 05 Jun Duration: 4 Days (4 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | BAN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| BAN | CAP1/CAP3 |  | DO | 3 | 2 | Resolve the issue regarding the isolator switch to the motor circuit for manual charging of closing coil.
CORRECT | BAN |  | 901079629 | CLO |  | 1 | O1- R Phase Manual Handle Limit Switch n
110kV FEEDER - BANDON DUNMANWAY
TO-20-BAN-DMY-1-02 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BAN-DMY-1-04 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
As consequence of Bandon-Brinny 110kV outage
TO-20-BAN-DMY-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  | 901129476 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON RAFFEEN
TO-20-BAN-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900984137 | DO | 1 | 4 | 2018HP-1[MP141]Arcing horns-Replace
FO_MISC |  |  | 900995455 | DO | 1 | 2 | 2019HP-1[141]Arching Horns -Missing
TO-20-BAN-RAF-1-01 ISO week: 37we - 38tu Date: 09 Sep - 15 Sep Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084834 | DO | 2 | 2 | 2019HP-1[151]Insulator broken aux insul
TRAN |  | - | 900984142 | DO | 1 | 4 | 2018HP-1[77]Off PlumbPlumb poles
OPT | BAN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | RAF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | RAF | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | RAF | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | RAF |  | 901147760 | DO | 2 | 1 | Hotspot 1 (Strain Pole No.114, Span 114/115) Centre Jumper Terminal (Repair by 6th Nov)
CORRECT | RAF |  | 901028752 | DO | 1 | 1 | O1-Bandon 110kv Cubicle Moss Build Up
CORRECT | RAF |  | 901028753 | DO | 1 | 1 | O1-Bandon 110kv CB SF6 Indicator corrode
DISTRIBUTION TRANSFORMER - BANDON T101 [SDCC]
TO-20-BAN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BANDON T141 [SDCC]
TO-20-BAN-T141-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BANOGE CRANE
TO-20-BOG-CRA-1-01 ISO week: 48fr Date: 27 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BOG | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CRA | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BARNAHELY RAFFEEN 1 [SDCC]
TO-20-BRY-RAF-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
110kV FEEDER - BARNAHELY RAFFEEN 2 [SDCC]
TO-20-BRY-RAF-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
COUPLER/SECTIONALISING CB - BARODA 110SA1-2CB
TO-20-BDA-110SA1-2CB-01 ISO week: 30mo - 30we Date: 20 Jul - 22 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CORRECT | BDA |  | 901087481 | DO | 2 | 1 | Arrange outage to complete testing of Ci
110kV FEEDER - BARODA MONREAD
TO-20-BDA-MON-1-01 ISO week: 13mo - 13fr Date: 23 Mar - 27 Mar Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | BDA | - | 901129957 | CLO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | BDA | - | 900567665 | DO | 2 | 4 | Repair Mid-Point Link Box
CA | BDA | - | 901129183 | CLO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | BDA | - | 900567665 | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CORRECT | BDA |  | 901076771 | DO | 1 | 1 | Reclosing sw protection panel : while tu
OS | MON | - | 901129932 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | MON |  | 901076757 | DO | 1 | 1 | PI on DL/DE o/o/o
CORRECT | MON |  | 901076765 | DO | 1 | 1 | CT T-phase insulator damaged
110kV FEEDER - BARODA NEWBRIDGE
TO-20-BDA-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BDA-NEW-1-01 Status: Unscheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | BDA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | BDA | - |  | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CA | NEW | - |  | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | NEW | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | DO | 3 | 1 | surge counter illigable
TSO CUSTOMER TRANSFORMER - BARODA T101 [Pfizer]
TO-20-BDA-T101-01 ISO week: 35mo - 36we Date: 24 Aug - 02 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - |  | DO | 4 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | BDA |  | 900796245 | DO | 1 | 1 | Fire alarm to be certafied
TSO CUSTOMER TRANSFORMER - BARODA T102 [Pfizer]
TO-20-BDA-T102-01 ISO week: 30mo - 31we Date: 20 Jul - 29 Jul Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - | 901129202 | CLO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - | 901129127 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BARRYMORE tee KNOCKRAHA
TO-20-BAR,T-KRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_COND | - | - | 901046848 | CANC | 2 | 1 | Hotspot 5 (Angle Tower No.278, span 278/279) Left Deadend (repair by October 2019)
TO-20-BAR,T-KRA-1-03 Status: Unscheduled
FO_COND | - | - | 901046847 | CANC | 2 | 2 | Hotspot 4 (Angle Tower No. 278, span 277/278) Right Deadend (repair by October 2019)
BUSBAR SECTION - BELCAMP 110 kV A1
TO-20-110 kV A1 @ BLC-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
BUSBAR SECTION - BELCAMP 110 kV A3
TO-20-110 kV A3 @ BLC-01 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
BUSBAR SECTION - BELCAMP 110 kV B1
TO-20-110 kV B1 @ BLC-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
BUSBAR SECTION - BELCAMP 110 kV B3
TO-20-110 kV B3 @ BLC-01 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
COUPLER/SECTIONALISING CB - BELCAMP 110K1
TO-20-BLC-110K1-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | EI: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110K1-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110K3
TO-20-BLC-110K3-02 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | EI: Energise Belcamp-Darndale-3
TO-20-BLC-110K3-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110SA1-3CB
TO-20-BLC-110SA1-3CB-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110SA1-3CB-03 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
TO-20-BLC-110SA1-3CB-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110SB1-3CB
TO-20-BLC-110SB1-3CB-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110SB1-3CB-03 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
TO-20-BLC-110SB1-3CB-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
110kV FEEDER - BELCAMP DARNDALE 1
TO-20-BLC-DND-1-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
110kV FEEDER - BELCAMP DARNDALE 3
TO-20-BLC-DND-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013_OS | DO | 2 |  | EI: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-BLC-DND-3-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
220kV FEEDER - BELCAMP FINGLAS
TO-20-BLC-FIN-1-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
TRANSFORMER - BELCAMP T2103
TO-20-BLC-T2103-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
SECTIONALISING DISCONNECT - BELLACORICK 110SA1
TO-20-BK-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA2: 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-110SA1-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA1 | 900942127 | DO | 1 | 2 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - BELLACORICK 110SA2
TO-20-BK-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-BK-110SA2-02 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA1: 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BELLACORICK CASTLEBAR
TO-20-BK-CBR-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-CBR-1-02 ISO week: 46th - 47th Date: 12 Nov - 19 Nov Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
YM03 | - | Line | 900979811 | DO | 3 | 1 | 2018HP-40m[59-60]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901088171 | DO | 3 | 1 | 2019HP-30m[168-169]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901060073 | DO | 2 | 1 | HAZ CNF 80m[101-102] 8-9m High Timber U
OPT | BK | - | 901050277 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | CBR | - | 901050314 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
AMCAB | CBR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BELLACORICK MOY
TO-20-BK-MOY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BK-MOY-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
| BK | - |  | DO | 2 | 4 | Cable Inspection XLPE
110kV FEEDER - BELLACORICK SRAHNAKILLY
TO-20-BK-SKY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 1 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-SKY-1-01 Status: Unscheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | CAB | 110 |  | DO | 5 | 4 | Cable Insp. 110kV XLPE
OPT | SKY |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-BK-SKY-1-03 ISO week: 29tu - 29we Date: 14 Jul - 15 Jul Duration: 2 Days (2 WD) Status: Scheduled
| BK |  | 901137803 | DO | 3 | 1 | NCC CANNOT OPERATE CB
OPT | BK |  | 901129688 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - BELLACORICK T122 [NDCC]
TO-20-BK-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0850 |  | 3 |  | Bay Outage for BZP
TO-20-BK-T122-02 Status: Reference (Unscheduled)
PROX |  |  | PR0002 | DO | 1 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - BELLACORICK T141 [NDCC]
TO-20-BK-T141-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - BINBANE 110SA1
TO-20-BIN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | As a consequence of BIN-110SA2: Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
SECTIONALISING DISCONNECT - BINBANE 110SA2
TO-20-BIN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
110kV FEEDER - BINBANE CATHALEENS FALL
TO-20-BIN-CF-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-CF-1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
TO-20-BIN-CF-1-03 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
TO-20-BIN-CF-1-04 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
TO-20-BIN-CF-1-06 Status: Unscheduled
FO_COND | - | - | 901153752 | CLO | 2 | 1 | Hotspot 1 (AM No.110, Span 109-110) Centre Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153753 | CLO | 2 | 1 | Hotspot 2 (AM No.110, Span 109-110) Right Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153754 | CLO | 2 | 1 | Hotspot 3 (AM No.110, Span 110-111) Centre Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153755 | CLO | 2 | 1 | Hotspot 4 (AM No.110, Span 110-111) Right Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153756 | CLO | 2 | 1 | Hotspot 5 (AM No.116, Span 116-117) Left Deadend Termination (Repair by 5th Jul 2020)
FO_COND | - | - | 901153757 | CLO | 2 | 1 | Hotspot 6 (AM No.116, Span 116-117) Centre Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153758 | CLO | 2 | 1 | Hotspot 7 (AM No.116, Span 116-117) Right Deadend Termination (Repair immediately)
FO_COND | - | - | 901153759 | CLO | 2 | 1 | Hotspot 8 (AM No.116, Span 115-116) Centre Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153940 | CLO | 2 | 1 | Hotspot 9 (AM No.116, Span 115-116) Right Deadend Termination (Repair by 5th Dec 2020)
TO-20-BIN-CF-1-05 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, GRZ100
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - BINBANE T141 [NDCC]
TO-20-BIN-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T142 [NDCC]
TO-20-BIN-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T142-01 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
TO-20-BIN-T142-05 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
TO-20-BIN-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
TO-20-BIN-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
TO-20-BIN-T142-04 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T143 [NDCC]
TO-20-BIN-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T143-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
110kV FEEDER - BINBANE TIEVEBRACK
TO-20-BIN-TIV-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-TIV-1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BLAKE T142 [NDCC]
TO-20-BLK-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
110kV FEEDER - BLAKE tee BLAKE
TO-20-BLK,T-BLK-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
TO-20-BLK,T-BLK-1-01 Status: Unscheduled
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
110kV FEEDER - BLAKE tee MAYNOOTH
TO-20-BLK,T-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900400277 | DO | 7 | 1 | 7[3,8,11,14,23,24,28]Replace damaged mem
TRAN |  | - | 900988632 | DO | 1 | 4 | 2018HP-1[31]Check Struct/Found/etc-Base
OS | MAY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | MAY | - | 900691700 | DO | 4 | 3 | Step bolts required [2,3,4,5,6,8,10,13,14,17,19,20,21,23,24,25,26,27,28,29,31,33,34,35,37]
CM | MAY | - | 901076412 | DO | 3 | 1 | Copper earths stolen from 110kV CTs to be reinstalled
110kV FEEDER - BLAKE tee NEWBRIDGE
TO-20-BLK,T-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BLK,T-NEW-1-03 Status: Unscheduled
[5 empty] | 1 |  | Break jumpers for maintenance on Blake Tee Maynooth
TO-20-BLK,T-NEW-1-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 1 |  | Remake jumpers following maintenance on Blake Tee Maynooth & Blake Tee Newbridge
TRAN |  | - | 900989018 | DO | 1 | 4 | 2018HP-1[171]Off Plumbplumb poles
TRAN |  | - | 900989019 | DO | 1 | 4 | 2018HP-1[171]Earths-Replace-E/W broken
TRAN |  | - | 900989020 | DO | 1 | 4 | 2018HP-1[180]Off Plumbplumb poles
TRAN |  | - | 900989021 | DO | 1 | 4 | 2018HP-1[181]Off Plumbplumb poles
FO_MISC |  | - | 901038281 | DO | 1 | 4 | 2018CP-1[171]Vibration Dampers -rusty
FO_MISC |  | - | 901038283 | DO | 1 | 4 | 2018CP-1[171]Stays - Replace
FO_MISC |  | - | 901038284 | DO | 1 | 4 | 2018CP-1[171]Earths - Replace (E strap)
FO_MISC |  | - | 901038290 | DO | 1 | 4 | 2018CP-1[168]Earths - Replace (HW Rusty)
FO_MISC |  |  | 901084873 | DO | 1 | 4 | 2019HP-1[170]Earths-Replace broken x2
FO_MISC |  |  | 901084874 | DO | 1 | 4 | 2019HP-1[171]Earths-Replace broken x2
OS | NEW | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | 20CM0255 | 3 | 1 | surge counter illigable
CA | NEW | - |  | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
SECTIONALISING DISCONNECT - BOGGERAGH 110SA1
TO-20-BGH-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
SECTIONALISING DISCONNECT - BOGGERAGH 110SA2
TO-20-BGH-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA2-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BGH | 110-SA2 | 901130115 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - BOGGERAGH CLASHAVOON
TO-20-BGH-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-CLA-1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - | 901129114 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | CLA |  | 900989872 | CLO | 2 | 1 | O1- Hotspot Boggeragh CT T Phase.
CORRECT | CLA |  | 900973236 | CLO |  | 1 | O1-Main ON sign in c.b. chassis is very
GENERATOR TRANSFORMER - BOGGERAGH T121 [Boggeragh BG1]
TO-20-BGH-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T121-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
GENERATOR TRANSFORMER - BOGGERAGH T132 [Boggeragh BG2]
TO-20-BGH-T132-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T132-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
DISTRIBUTION TRANSFORMER - BOGGERAGH T142 [SDCC]
TO-20-BGH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T142-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Reference
As a consequence of work on Boggeragh-Clashavoon 110 kV
110kV FEEDER - BOOLTIAGH ENNIS
TO-20-BOL-ENN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | BOL |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OS | ENN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - BOOLTIAGH T121 [Booltiagh BT1/BT2]
TO-20-BOL-T121-01 ISO week: 30mo - 30th Date: 20 Jul - 23 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BOL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - BRINNY T101 [Merck Sharp & Dohme]
TO-20-BRI-T101-02 ISO week: 36we - 36th Date: 02 Sep - 03 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-BRI-1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BRI-T101-01 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | BRI | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA1
TO-20-BUT-110SA1-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA2: 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA2
TO-20-BUT-110SA2-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA1: 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA2 | 901146318 | CLO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - BUTLERSTOWN CULLENAGH
TO-20-BUT-CUL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | CUL | - | 901080692 | CANC | 3 | 1 | Copper earths stolen from DL, DE, all 110kV CT’s, VT’s and surge arrestors to be reinstalled
TO-20-BUT-CUL-1-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084937 | DO | 2 | 4 | 2019HP-2[49,50]Off Plumb -plumb poles
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084678 | DO | 1 | 2 | 2019HP-1[23]Check (General) -LPh weight
OPT | BUT |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BUTLERSTOWN KILLOTERAN
TO-20-BUT-KTN-1-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL551
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BUT |  | 901129602 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KTN |  | 901129696 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T141 [SDCC]
TO-20-BUT-T141-01 ISO week: 33we - 33fr Date: 12 Aug - 14 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T142 [SDCC]
TO-20-BUT-T142-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
COUPLER/SECTIONALISING CB - CAHIR 110K1-2
TO-20-CAH-110K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | CAH | - | 901134760 | CLO | 2 | 1 | R Phase Bus coupler 110kV Cubicle. R Phase CT.DUE : 17-Aug-20
CM | CAH | - | 901134761 | CLO | 2 | 1 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA. DUE : 17-Aug-20
CM | CAH | - | 901134762 | CLO | 2 | 1 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA & T Phase CT connection DUE : 17-Aug-20
CM | CAH | - | 901134763 | CLO | 2 | 1 | T Phase Bus coupler 110kV Cubicle. T Phase Bus coupler DB DUE : 17-Jul-20
110kV FEEDER - CAHIR DOON
TO-20-CAH-DOO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900897597 | DO | 5 | 2 | 2017HP-5[5,12,13,33,37]Off Plumb
FO_MISC |  | - | 900897598 | DO | 3 | 2 | 2017HP-4[47,56,72,75]Off Plumb
FO_MISC |  |  | 901084938 | DO | 3 | 2 | 2019HP-5[14,29,30,37,38]Off Plumb
FO_MISC |  |  | 901084939 | DO | 1 | 2 | 2019HP-3[53,56,72]Off Plumb -plumb poles
|  |  | 901132793 |  |  |  | Poles currently in crop, good chance it will be cut by 13th of July KK
CM | CAH | - | 901134764 | CLO | 2 | 1 | T Phase Doon 110kV Cubicle. TPhase CB connection DUE : 17-Nov-2 hotspot
OPT | CAH |  | 901129607 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DOO | - | 901129615 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CAHIR KILL HILL
TO-20-CAH-KHL-1-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084942 | DO | 2 | 4 | 2019HP-1[47]Off Plumb -plumb poles
TRAN |  | - | 900984365 | DO | 1 | 4 | 2018HP-1[47]Off Plumb
OPT | CAH |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CAHIR TIPPERARY
TO-20-CAH-TIP-1-01 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984368 | DO | 3 | 4 | "2018HP-5[25,26,29,34,35]Off Plumb-Poles
TRAN |  | - | 900984369 | DO | 3 | 4 | "2018HP-5[36,55,84,90,91]Off Plumb-Poles
TRAN |  | - | 900984378 | DO | 1 | 4 | 2018HP-1[2]Earths-Replace-Broken
BUSBAR SECTION - CARLOW 110 kV A1
TO-20-110 kV A1 @ CLW-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLW |  | PROX |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
110kV FEEDER - CARLOW KELLIS 1
TO-20-CLW-KLS-1-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | CLW |  | 901075041 | DO | 2 | 1 | busbar disconnect seized at top , bird c
OPT | KLS | - | 901038904 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CARLOW KELLIS 2
TO-20-CLW-KLS-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084945 | DO | 2 | 4 | 2019HP-1[16]Off Plumb -plumb poles
FO_MISC |  |  | 901084946 | DO | 2 | 4 | 2019HP-1[17]Off Plumb -plumb poles
OS | CLW | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CLW-KLS-2-01 ISO week: 13tu - 14th Date: 24 Mar - 02 Apr Duration: 10 Days (8 WD) Status: Forced Out
PROT |  |  |  | DO | 1 |  | P1 Protection maintenance of 7SA511
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
DISTRIBUTION TRANSFORMER - CARLOW T141 [SDCC]
TO-20-CLW-T141-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110SA1-2CB
TO-20-COS-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
TO-20-COS-110SA1-2CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | COS | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - CARRICK ON SHANNON FLAGFORD 1
TO-20-COS-FLA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder
TO-20-COS-FLA-1-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 1 110 kV bay at flagford station
TO-20-COS-FLA-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-COS-FLA-1-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-COS-FLA-1-05 ISO week: 48th - 49tu Date: 26 Nov - 01 Dec Duration: 6 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | COS |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | FLA |  | 901053361 | DO |  | 1 | O1 Replacement coupling required on H3 d
CORRECT | FLA |  | 901053362 | DO |  | 1 | O1 Investigate control circuit including
110kV FEEDER - CARRICK ON SHANNON FLAGFORD 2
TO-20-COS-FLA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 2 110 kV Bay at flagford station
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TO-20-COS-FLA-2-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-COS-FLA-2-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-COS-FLA-2-04 Status: Unscheduled
Studied outage for potential extension of CP1031 due to CV-19
BUSBAR SECTION - CARRICKMINES 220 kV A1
TO-20-220 kV A1 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV A2
TO-20-220 kV A2 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV B1
TO-20-220 kV B1 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV B2
TO-20-220 kV B2 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES 220K1-2
TO-20-CKM-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | CKM |  | 900959119 | DO | 2 | 2 | O/1 Missing 220kV coupler on Indicator R
BUSBAR SECTION - CARRICKMINES GIS 220 kV A1
TO-20-220 kV A1 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A2
TO-20-220 kV A2 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A3
TO-20-220 kV A3 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A4
TO-20-220 kV A4 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B1
TO-20-220 kV B1 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B2
TO-20-220 kV B2 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B3
TO-20-220 kV B3 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B4
TO-20-220 kV B4 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220K3
TO-20-CKM GIS-220K3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220K4
TO-20-CKM GIS-220K4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
TO-20-CKM GIS-220K4-02 ISO week: 27mo - 27tu Date: 29 Jun - 30 Jun Duration: 2 Days (2 WD) Status: Scheduled
Outage for EI of T2101
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA1-2CB
TO-20-CKM GIS-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA1-3CB
TO-20-CKM GIS-220SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA2-4CB
TO-20-CKM GIS-220SA2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB1-2CB
TO-20-CKM GIS-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB1-3CB
TO-20-CKM GIS-220SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB2-4CB
TO-20-CKM GIS-220SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
220kV FEEDER - CARRICKMINES GIS DUNSTOWN
TO-20-CKM GIS-DSN-1-01 ISO week: 17mo - 17fr Date: 20 Apr - 24 Apr Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984573 | DO | 1 | 4 | 2018HP-1[8]Check Struct/Found/etc-Base
TRAN |  | - | 900984585 | DO | 1 | 4 | 2018HP-1[34]Check Struct/Found/etc-Base
TRAN |  | - | 900984592 | DO | 1 | 4 | 2018HP-1[48]Check Struct/Found/etc-Base
TRAN |  | - | 900984613 | DO | 1 | 4 | 2018HP-1[123]Check Struct/Found/etc-Base
TRAN |  | - | 900984617 | DO | 1 | 4 | 2018HP-1[131]Check Struct/Found/etc-Base
OPT | CKM | - | 901038749 | CLO | 1 | 1 | 220kV MO Cubicle Operational Test
CORRECT | DSN |  | 900444584 | DO | 5 | 2 | O. ESBI Inspect and test all the cylinde
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
220kV FEEDER - CARRICKMINES GIS IRISHTOWN
TO-20-CKM GIS-ISH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | placeholder for maintenance
CAPACITOR/SVC/REACTOR - CARRICKMINES GIS R2001
TO-20-CKM GIS-R2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SJ611, RET670, POW-RPH3
220kV FEEDER - CARRICKMINES POOLBEG
TO-20-CKM-PB-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
TO-20-CKM-PB-1-01 ISO week: 47mo - 48fr Date: 16 Nov - 27 Nov Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
| Cable | - |  | DO | 10 | 1 | Detection and repair of fluid leak
AMCAB | Cable | - | 900925587 | DO | 10 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OS | CKM | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | CKM | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TRANSFORMER - CARRICKMINES PST2201
TO-20-CKM-PST2201-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | As a consequence of CKM-PB-1: Proximity outage for work on Poolbeg 220kV K1-3
CAPACITOR/SVC/REACTOR - CARRICKMINES R2001
TO-20-CKM-R2001-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CKM | R2001 | 901038711 | CANC |  | 2 | Carrickmines R2001 Shunt Reactor: Fit bushing monitor (HV and LV)
TO-20-CKM-R2001-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
OPT | CKM | 220-R2001 |  | DO | 1 | 4 | HV Reactor Operational Test
CORRECT | CKM |  | 900525391 | DO |  | 2 | N 0 1 non outage(important)
TRANSFORMER - CARRICKMINES T2102 [NDCC]
TO-20-CKM-T2102-01 ISO week: 31we Date: 29 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
110kV FEEDER - CARRIGADROHID KILBARRY
TO-20-CD-KBY-1-02 ISO week: 30mo - 35fr Date: 20 Jul - 28 Aug Duration: 40 Days (29 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1037 | DO | 21 |  | Proximity outage due to proximity of the bays within the station.
TO-20-CD-KBY-1-01 ISO week: 38mo - 48fr Date: 14 Sep - 27 Nov Duration: 75 Days (54 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 55 |  | Terminating 110 kV cable at station bay and end masts
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
FO_MISC |  |  | 901084947 | DO |  | 2 | 2019HP-1[120]Off Plumb -plumb poles
OS | CD | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | CD | - | 900973233 | DO | 1 | 1 | O1-Cb,CT & DA slight algae growth.
OS | KBY | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CORRECT | KBY |  | 900894946 | DO |  | 1 | O1-DA not showing open position indicati
110kV FEEDER - CARRIGADROHID MACROOM
TO-20-CD-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-CD-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-CD-MAC-1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-CD-MAC-1-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of REL521, REL551
OPT | CD |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | MAC | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
GENERATOR TRANSFORMER - CARRIGADROHID T103 [ESB GWM LE3]
TO-20-CD-T103-01 ISO week: 25tu - 26tu Date: 16 Jun - 23 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CD |  | 901129579 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
110kV FEEDER - CARRIGDANGAN DUNMANWAY [Carrigdangan CDN1]
TO-20-CDN-DMY-1-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-CDN-DMY-1-07 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-CDN-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-CDN-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - CARROWBEG CASTLEBAR [SDCC]
TO-20-CBG-CBR-1-01 ISO week: 41fr Date: 09 Oct Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
XLPE inspection
DISTRIBUTION TRANSFORMER - CARROWBEG T142 [SDCC]
TO-20-CBG-T142-01 ISO week: 41mo - 42fr Date: 05 Oct - 16 Oct Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO maintenance
As a consequence of work on Carrowbeg-Castlebar 110 kV
BUSBAR SECTION - CASHLA 110 kV A1
TO-20-110 kV A1 @ CSH-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-110 kV A1 @ CSH-06 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
TO-20-110 kV A1 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-110 kV A1 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
TO-20-110 kV A1 @ CSH-07 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV A1 @ CSH-08 Status: Unscheduled
CAPX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB
TO-20-110 kV A1 @ CSH-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-110 kV A1 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
BUSBAR SECTION - CASHLA 110 kV A2
TO-20-110 kV A2 @ CSH-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
TO-20-110 kV A2 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
TO-20-110 kV A2 @ CSH-05 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV A2 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
TO-20-110 kV A2 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-110 kV A2 @ CSH-06 Status: Unscheduled
CAPX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB
BUSBAR SECTION - CASHLA 110 kV B1
TO-20-110 kV B1 @ CSH-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
TO-20-110 kV B1 @ CSH-05 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-110 kV B1 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-110 kV B1 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
TO-20-110 kV B1 @ CSH-07 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV B1 @ CSH-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-110 kV B1 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
BUSBAR SECTION - CASHLA 110 kV B1/B2
TO-20-110 kV B1/B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
BUSBAR SECTION - CASHLA 110 kV B2
TO-20-110 kV B2 @ CSH-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
TO-20-110 kV B2 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
TO-20-110 kV B2 @ CSH-05 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV B2 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-110 kV B2 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
COUPLER/SECTIONALISING CB - CASHLA 110K1-2
TO-20-CSH-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
CAPX |  |  | CP1032 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla 110 kV Coupler bay at Cashla station
TO-20-CSH-110K1-2-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder
TO-20-CSH-110K1-2-04 Status: Unscheduled
CM | CSH |  | 901133361 | DO | 2 | 1 | DB 110kV Coupler R Phse Disconnect DUE : next available opportunity.
TO-20-CSH-110K1-2-03 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH |  | 901058830 | DO | 2 | 1 | O1 SA failed to open intermittently
CORRECT | CSH |  | 901058832 | DO | 2 | 1 | O1 DA2 seems to be operating slower than
BUSBAR SECTION - CASHLA 220 kV A1
TO-20-220 kV A1 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB
TO-20-220 kV A1 @ CSH-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV A2
TO-20-220 kV A2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV A4
TO-20-220 kV A4 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B1
TO-20-220 kV B1 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-220 kV B1 @ CSH-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B1/B2
TO-20-220 kV B1/B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
BUSBAR SECTION - CASHLA 220 kV B2
TO-20-220 kV B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B4
TO-20-220 kV B4 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover
COUPLER/SECTIONALISING CB - CASHLA 220K1-2
TO-20-CSH-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
TO-20-CSH-220K1-2-01 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-220K1-2-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
CAPX |  |  | CP1032 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 220 kV Circuit breaker replacement in the Cashla 220 kV Coupler bay at Cashla station
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CSH | - | 901041551 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
TO-20-CSH-220K1-2-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-220K1-2-05 ISO week: 41we - 43fr Date: 07 Oct - 23 Oct Duration: 17 Days (13 WD) Status: Scheduled
CM | CSH | - | 901133364 | DO | 2 | 1 | 220 kV Coupler k1-2 R Phase DB2 Pantograph. DUE : next available opportunity.
CM | CSH |  | 901133643 | DO | 2 | 1 | 220 kV Coupler k1-2 R Phas DA Pantograph DUE : next available opportunity.
CM | CSH | 220-SB2-4 | 901133644 | DO | 2 | 1 | 220 kV Coupler SB 2-4 S and T Phse Disconnect DUE : next available opportunity.
COUPLER/SECTIONALISING CB - CASHLA 220K2-4
TO-20-CSH-220K2-4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CSH | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TO-20-CSH-220K2-4-03 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
TO-20-CSH-220K2-4-01 ISO week: 12mo - 12we Date: 16 Mar - 18 Mar Duration: 3 Days (2 WD) Status: Scheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
CAPACITOR/SVC/REACTOR - CASHLA CAP1
TO-20-CSH-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
CAPACITOR/SVC/REACTOR - CASHLA CAP2
TO-20-CSH-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
110kV FEEDER - CASHLA CLOON
TO-20-CSH-CLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 1110 kV Circuit breaker replacement in the 110 kV Cloon bay at Cashla station
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-CSH-CLN-1-02 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900876649 | DO | 1 | 3 | 2017CP-1[2]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876650 | DO | 1 | 3 | 2017CP-4[5]Vib Damp Replace
FO_MISC |  | - | 900876651 | DO | 1 | 3 | 2017CP-1[8]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876652 | DO | 1 | 3 | 2017CP-1[12]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876653 | DO | 1 | 3 | 2017CP-1[16]Off Plumb Poles
FO_MISC |  | - | 900876654 | DO | 1 | 3 | 2017CP-1[18]Off Plumb Poles
FO_MISC |  | - | 900876655 | DO | 1 | 3 | 2017CP-1[22]Off Plumb Poles
FO_MISC |  | - | 900876656 | DO | 1 | 3 | 2017CP-2[22]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876657 | DO | 1 | 3 | 2017CP-6[23]Vib Damp Replace-All Phases
FO_MISC |  | - | 900876658 | DO | 1 | 3 | 2017CP-1[31]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876659 | DO | 1 | 3 | 2017CP-1[53]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876660 | DO | 1 | 3 | 2017CP-1[55]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876661 | DO | 1 | 3 | 2017CP-2[61]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876662 | DO | 1 | 3 | 2017CP-1[63]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876663 | DO | 1 | 3 | 2017CP-1[64]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876664 | DO | 1 | 3 | 2017CP-2[65]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876665 | DO | 1 | 3 | 2017CP-1[66]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876666 | DO | 1 | 3 | 2017CP-1[67]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876667 | DO | 1 | 3 | 2017CP-2[68]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876668 | DO | 1 | 3 | 2017CP-3[71]Vib Damp Replace-All Phases
FO_MISC |  | - | 900876669 | DO | 1 | 3 | 2017CP-2[72]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876670 | DO | 1 | 3 | 2017CP-1[75]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876671 | DO | 1 | 3 | 2017CP-1[76]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876672 | DO | 1 | 3 | 2017CP-1[79]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876673 | DO | 1 | 3 | 2017CP-2[81]Vib Damp Replace-Mid & Right
FO_MISC |  | - | 900876674 | DO | 1 | 3 | 2017CP-2[83]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876675 | DO | 1 | 3 | 2017CP-1[84]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876676 | DO | 1 | 3 | 2017CP-1[86]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876677 | DO | 1 | 3 | 2017CP-1[87]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876678 | DO | 1 | 3 | 2017CP-1[89]Vib Damp Replace
FO_MISC |  | - | 900876679 | DO | 1 | 3 | 2017CP-1[90]Vib Damp Replace
FO_MISC |  | - | 900876680 | DO | 1 | 3 | 2017CP-1[91]Vib Damp Replace
FO_MISC |  | - | 900876681 | DO | 1 | 3 | 2017CP-1[93]Vib Damp Replace
FO_MISC |  | - | 900876682 | DO | 1 | 3 | 2017CP-1[94]Vib Damp Replace
FO_MISC |  | - | 900876683 | DO | 1 | 3 | 2017CP-1[95]Vib Damp Replace
FO_MISC |  | - | 900876684 | DO | 1 | 3 | 2017CP-1[100]Vib Damp Replace-Right Phas
FO_MISC |  | - | 900876685 | DO | 1 | 3 | 2017CP-6[105]Vib Damp Replace
FO_MISC |  | - | 900876686 | DO | 1 | 3 | 2017CP-1[106]Vib Damp Replace
FO_MISC |  | - | 900876687 | DO | 1 | 3 | 2017CP-3[108]Vib Damp Replace
FO_MISC |  | - | 900876688 | DO | 1 | 3 | 2017CP-1[110]Vib Damp Replace
FO_MISC |  | - | 900876689 | DO | 1 | 3 | 2017CP-2[111]Vib Damp Replace
FO_MISC |  | - | 900876690 | DO | 1 | 3 | 2017CP-1[116]Vib Damp Replace
FO_MISC |  | - | 900876691 | DO | 1 | 3 | 2017CP-1[121]Vib Damp Replace
FO_MISC |  | - | 900876692 | DO | 1 | 3 | 2017CP-1[122]Off Plumb Insulators
FO_MISC |  | - | 900876693 | DO | 1 | 3 | 2017CP-2[123]Vib Damp Replace
FO_MISC |  | - | 900876694 | DO | 1 | 3 | 2017CP-4[124]Stays New stays to be dug
FO_MISC |  | - | 900876695 | DO | 1 | 3 | 2017CP-1[124]Off Plumb Insulators
FO_MISC |  | - | 900876696 | DO | 1 | 3 | 2017CP-2[124]Vib Damp Replace
FO_MISC |  | - | 900876697 | DO | 1 | 3 | 2017CP-1[127]Earths - Replace Lead
FO_MISC |  | - | 900897288 | CLO | 1 | 4 | 2017HP-1[103]Off Plumb -Poles
FO_MISC |  |  | 901084835 | DO | 1 | 2 | 2019HP-1[Stn]Insulator Broken
FO_MISC |  |  | 901084869 | DO | 1 | 3 | 2019HP-1[128]Earths-Replace Broken R/ph
FOSTRHW |  |  | 901086427 | DO | 1 | 3 | 2019HP-1[106]Replace Pole only -Rot
OS | CLN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASHLA DALTON
TO-20-CSH-DLT-1-01 ISO week: 47fr - 48fr Date: 20 Nov - 27 Nov Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FOINSHW |  | - | 900564546 | DO | 2 | 1 | 2[166,167 ]Ins / H/D repl chk-Fi
FOINSHW |  | - | 900563143 | DO | 1 | 1 | 1[221]Ins & H/D repl chk-Fit Dup
TRAN |  | - | 900984695 | DO | 1 | 4 | 2018HP-1[9]Vib Dampers-Fatigue replace
TRAN |  | - | 900984733 | DO | 1 | 4 | 2018HP-1[212]Insulator-Off Plumb
OS | CSH | - | 900943159 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASHLA ENNIS
TO-20-CSH-ENN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-ENN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-CSH-ENN-1-02 ISO week: 25th - 26fr Date: 18 Jun - 26 Jun Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | CSH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | ENN | - |  | DO | 5 | 4 | 110kV MO Cubicle Ordinary Service
CA | ENN | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
220kV FEEDER - CASHLA FLAGFORD
TO-20-CSH-FLA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at flagford station in the Cashla 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at Cashla station in the Flagford 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB
TO-20-CSH-FLA-1-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-FLA-1-06 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB
TO-20-CSH-FLA-1-07 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-08 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-10 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984858 | DO | 1 | 4 | 2018HP-1[am 247]Insulatorfit duplicates
FO_MISC |  |  | 901084304 | DO | 1 | 4 | 2019HP-1[134]Bird Nests
FO_MISC |  |  | 901084305 | DO | 1 | 4 | 2019HP-1[203]Bird Nests
FO_MISC |  |  | 901084306 | DO | 1 | 4 | 2019HP-1[210]Bird Nests
FO_MISC |  |  | 901084307 | DO | 1 | 4 | 2019HP-1[211]Bird Nests
FO_MISC |  |  | 901084308 | DO | 1 | 4 | 2019HP-1[212]Bird Nests
FO_MISC |  |  | 901084309 | DO | 1 | 4 | 2019HP-1[215]Bird Nests
FO_MISC |  |  | 901084310 | DO | 1 | 4 | 2019HP-1[240]Bird Nests
FO_MISC |  |  | 901084311 | DO | 1 | 4 | 2019HP-1[73]Bird Nests
FO_MISC |  |  | 901084312 | DO | 1 | 4 | 2019HP-1[78]Bird Nests
FO_MISC |  |  | 901084313 | CLO | 1 | 4 | 2019HP-1[80]Bird Nests
FO_MISC |  |  | 901084836 | DO | 1 | 4 | 2019HP-1[247]Insulator Fit Duplicate
OS | CSH | - | 900943133 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
OS | FLA | - | 900943176 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
TO-20-CSH-FLA-1-09 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513., REL521
TO-20-CSH-FLA-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
110kV FEEDER - CASHLA GALWAY 1
TO-20-CSH-GAL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
TO-20-CSH-GAL-1-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 1 bay at Cashla station
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084837 | DO | 1 | 4 | 2019HP-1[12]Insulator Broken Insul
OS | CSH | - | 901042382 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | GAL | - | 901042209 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CSH-GAL-1-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-CSH-GAL-1-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
110kV FEEDER - CASHLA GALWAY 2
TO-20-CSH-GAL-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder
TO-20-CSH-GAL-2-05 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
TO-20-CSH-GAL-2-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 2 bay at Cashla station
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GAL | - | 901042210 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CSH-GAL-2-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-CSH-GAL-2-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
TO-20-CSH-GAL-2-06 ISO week: 24tu - 24th Date: 09 Jun - 11 Jun Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | LOU |  | 901139264 | CLO | 3 | 1 | Hotspot 1 (L1 Span 9/10) Left Midspan Joint (Repair by 27th Jul)
110kV FEEDER - CASHLA GALWAY 3
TO-20-CSH-GAL-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
TO-20-CSH-GAL-3-01 ISO week: 45we Date: 04 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GAL |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - CASHLA PROSPECT
TO-20-CSH-PRO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
110kV FEEDER - CASHLA SALTHILL
TO-20-CSH-SAL-1-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084949 | DO | 2 | 4 | 2019HP-1[85]Off Plumb -plumb poles
PROX | SAL |  |  |  | 2 |  | Proximity for Salthil SA2 maintenance
AMCAB | SAL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SAL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - CASHLA T2101
TO-20-CSH-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-T2101-02 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
TO-20-CSH-T2101-03 ISO week: 26fr - 28fr Date: 26 Jun - 10 Jul Duration: 15 Days (11 WD) Status: Scheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH | TRAFO | 901038716 | DO | 8 | 2 | Cashla T2101: Corrosion on Fan Box. Replace
OS | CSH | 220 | 901129992 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CSH | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | CSH | TRAFO | 900944214 | CLO | 3 | 1 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
TRAFO | CSH | TRAFO | 900944679 | CLO | 3 | 1 | 220/110kV Trafo Tap Changer Inspection
TRANSFORMER - CASHLA T2102
TO-20-CSH-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required
TO-20-CSH-T2102-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 60 |  | Install Sprecher & Schuh type HPF-514 220 kV Circuit breaker replacement in the T2102 220 kV Bay at Cashla station
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-CSH-T2102-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-CSH-T2102-02 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH | TRAFO | 901038717 | DO | 8 | 2 | Cashla T2102: Corrosion on Fan Box. Replace
OPT | CSH | 220 | 901038879 | DO | 1 | 4 | 220kV MO Cubicle Operational Test
OPT | CSH | 110 | 901038883 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
CORRECT | CSH | TRAFO | 901039321 | DO | 1 | 2 | Cashla T2102 Transformer: Drycol Replacement
OPT | CSH | TRAFO | 901045361 | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - CASHLA T2104
TO-20-CSH-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CSH | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CSH | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CSH | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
220kV FEEDER - CASHLA TYNAGH
TO-20-CSH-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-CSH-TY-1-05 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-TY-1-06 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required
TO-20-CSH-TY-1-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-09 Status: Unscheduled
CM | CSH | 220-DL | 901148822 | CLO | 2 | 1 | 01 Tynagh DL Fault
TO-20-CSH-TY-1-07 Status: Unscheduled
CAPX |  |  | CP1019 | DO | 7 |  | Fibre wrapping of the line - to be installed on OPGW earthwire
TO-20-CSH-TY-1-03 ISO week: 16th - 21th Date: 16 Apr - 21 May Duration: 36 Days (25 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985040 | DO | 1 | 4 | 2018HP-1[104]Vib DampersR/Ph
FO_MISC |  |  | 901084267 | DO | 1 | 4 | 2019HP-1[57]Bird Nests
FO_MISC |  |  | 901084268 | DO | 1 | 4 | 2019HP-1[107]Bird Nests
OPT | CSH | - | 901038878 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
YM03 | TYN | - | 900979523 | DO | 3 | 4 | DISC CONTACTS DAMAGED
OPT | TYN | - | 901039106 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CASTLEBAGGOT INCHICORE 1
TO-20-CBT-INC-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 10 |  | Proximity outage to allow for erection of HV equipment in interface compound.
220kV FEEDER - CASTLEBAGGOT INCHICORE 2
TO-20-CBT-INC-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 2 |  | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required
220kV FEEDER - CASTLEBAGOT MAYNOOTH 1
TO-20-CBT-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 10 |  | Proximity outage to allow for erection of HV equipment in interface compound.
COUPLER/SECTIONALISING CB - CASTLEBAR 110SA1-2CB
TO-20-CBR-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CBR | - | 901039130 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CASTLEBAR CLOON
TO-20-CBR-CLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085138 | DO | 3 | 4 | 2019HP-3[279,280,282]Vib Dampers -EW V/D
FO_STDMG |  | - | 901038334 | DO | 2 | 4 | 2018CP-1[72]Crossarm -Replace
FO_MISC |  |  | 901085137 | DO | 2 | 4 | 2019HP-2[59, 60]Vib Dampers -Replace
TRAN |  | - | 900985121 | DO | 1 | 4 | 2018HP-1[164]Vib Dampers-Fatigue replace
TRAN |  | - | 900985122 | DO | 1 | 4 | 2018HP-1[165]Vib Dampers-Fatigue replace
FO_MISC |  | - | 901038297 | DO | 1 | 4 | 2018CP-1[3]Off Plumb -Poles
FO_MISC |  | - | 901038298 | DO | 1 | 4 | 2018CP-1[12]Off Plumb -Poles
FO_MISC |  | - | 901038299 | DO | 1 | 4 | 2018CP-1[15]Off Plumb -Poles
FO_MISC |  | - | 901038300 | DO | 1 | 4 | 2018CP-1[15]Insulator -Off Plumb
FO_MISC |  | - | 901038301 | DO | 1 | 4 | 2018CP-1[17]Off Plumb -Poles
FO_MISC |  | - | 901038302 | DO | 1 | 4 | 2018CP-1[18]Off Plumb -Poles
FO_MISC |  | - | 901038303 | DO | 1 | 4 | 2018CP-1[19]Off Plumb -Poles
FO_MISC |  | - | 901038304 | DO | 1 | 4 | 2018CP-1[20]Off Plumb -Poles
FO_MISC |  | - | 901038305 | DO | 1 | 4 | 2018CP-1[21]Off Plumb -Poles
FO_MISC |  | - | 901038306 | DO | 1 | 4 | 2018CP-1[21]Insulator -Off Plumb
FO_MISC |  | - | 901038310 | DO | 1 | 4 | 2018CP-1[28]Vibration Dampers
FO_MISC |  | - | 901038311 | DO | 1 | 4 | 2018CP-1[30]Vibration Dampers
FO_STDMG |  | - | 901038312 | DO | 1 | 4 | 2018CP-1[30]Found/Site repair
FO_MISC |  | - | 901038313 | DO | 1 | 4 | 2018CP-1[31]Vibration Dampers
FO_MISC |  | - | 901038317 | DO | 1 | 4 | 2018CP-1[36]Anti Split Bolts
FO_STDMG |  | - | 901038319 | DO | 1 | 4 | 2018CP-1[43]Pole Bolt -Tighten
FO_MISC |  | - | 901038320 | DO | 1 | 4 | 2018CP-1[49]Off Plumb -Poles
FO_STDMG |  | - | 901038322 | DO | 1 | 4 | 2018CP-1[63]Pole Bolt -Tighten
FO_STDMG |  | - | 901038323 | DO | 1 | 4 | 2018CP-1[65]Pole Bolt -Tighten
FO_STDMG |  | - | 901038324 | DO | 1 | 4 | 2018CP-1[66]Pole Bolt -Tighten
FO_MISC |  | - | 901038327 | DO | 1 | 4 | 2018CP-1[82]Insulator -Off Plumb
FO_MISC |  | - | 901038328 | DO | 1 | 4 | 2018CP-1[77]Ubolts -Level
FO_MISC |  | - | 901038329 | DO | 1 | 4 | 2018CP-1[75]Insulator -Broken Disk
FO_MISC |  | - | 901038330 | DO | 1 | 4 | 2018CP-1[75]Anti Split Bolts
FO_MISC |  | - | 901038333 | DO | 1 | 4 | 2018CP-1[73]Anti Split Bolts
FO_MISC |  | - | 901038335 | DO | 1 | 4 | 2018CP-1[100]Off Plumb -Poles
FO_MISC |  | - | 901038336 | DO | 1 | 4 | 2018CP-1[101]Off Plumb -Poles
FO_MISC |  | - | 901038337 | DO | 1 | 4 | 2018CP-1[103]Off Plumb -Poles
FO_MISC |  | - | 901038338 | DO | 1 | 4 | 2018CP-1[105]Off Plumb -Poles
FO_MISC |  | - | 901038339 | DO | 1 | 4 | 2018CP-1[106]Off Plumb -Poles
FO_STDMG |  | - | 901038340 | DO | 1 | 4 | 2018CP-1[106]Found/Site repair
FO_MISC |  | - | 901038341 | DO | 1 | 4 | 2018CP-1[106]Insulator -Off Plumb
FO_STDMG |  | - | 901038342 | DO | 1 | 4 | 2018CP-1[108]Crossarm
FO_MISC |  | - | 901038343 | DO | 1 | 4 | 2018CP-1[109]Off Plumb -Poles
FO_MISC |  | - | 901038344 | DO | 1 | 4 | 2018CP-1[111]Off Plumb -Poles
FO_MISC |  | - | 901038345 | DO | 1 | 4 | 2018CP-1[111]Anti Split Bolts
FO_MISC |  | - | 901038346 | DO | 1 | 4 | 2018CP-1[114]Off Plumb -Poles
FO_MISC |  | - | 901038347 | DO | 1 | 4 | 2018CP-1[114]Insulator -Off Plumb
FO_MISC |  | - | 901038350 | DO | 1 | 4 | 2018CP-1[118]Off Plumb -Poles
FO_MISC |  | - | 901038351 | DO | 1 | 4 | 2018CP-1[119]Off Plumb -Poles
FO_STDMG |  | - | 901038353 | DO | 1 | 4 | 2018CP-1[121]Crossarm -Replace Bolt
FO_STDMG |  | - | 901038354 | DO | 1 | 4 | 2018CP-1[122]Crossarm -Tighten Bolt
FO_MISC |  | - | 901038355 | DO | 1 | 4 | 2018CP-1[123]Off Plumb -Poles
FO_MISC |  | - | 901038357 | DO | 1 | 4 | 2018CP-1[127]Off Plumb -Poles
FO_STDMG |  | - | 901038358 | DO | 1 | 4 | 2018CP-1[127]Found/Site repair -Sleepers
FO_MISC |  | - | 901038359 | DO | 1 | 4 | 2018CP-1[128]Off Plumb -Poles
FO_STDMG |  | - | 901038360 | DO | 1 | 4 | 2018CP-1[137]Pole Bolt -Replace
FO_MISC |  | - | 901038361 | DO | 1 | 4 | 2018CP-1[139]Off Plumb -Poles
FO_STDMG |  | - | 901038362 | DO | 1 | 4 | 2018CP-1[139]Crossarm
FO_MISC |  | - | 901038363 | DO | 1 | 4 | 2018CP-1[140]Off Plumb -Poles
FO_STDMG |  | - | 901038364 | DO | 1 | 4 | 2018CP-1[140]Crossarm
FO_STDMG |  | - | 901038366 | DO | 1 | 4 | 2018CP-1[147]Pole Bolt -Tighten
FO_MISC |  | - | 901038367 | DO | 1 | 4 | 2018CP-1[150]Vibration Dampers -Required
FO_MISC |  | - | 901038368 | DO | 1 | 4 | 2018CP-1[156]Stepbolts -Remove
FO_STDMG |  | - | 901038369 | DO | 1 | 4 | 2018CP-1[157]Pole Bolt -Tighten
FO_MISC |  | - | 901038370 | DO | 1 | 4 | 2018CP-1[157]Insulator -Off Plumb
FO_STDMG |  | - | 901038376 | DO | 1 | 4 | 2018CP-1[4]Pole Bolt -Bent
FO_MISC |  | - | 901038377 | DO | 1 | 4 | 2018CP-1[11]Earths - Replace -Bolt bent
FO_STDMG |  | - | 901038378 | DO | 1 | 4 | 2018CP-1[43]Pole Bolt -Bent
FO_STDMG |  | - | 901038383 | DO | 1 | 4 | 2018CP-1[165]Found/Site repair
FO_MISC |  | - | 901038385 | DO | 1 | 4 | 2018CP-1[178]Insulator -Off Plumb
FO_MISC |  | - | 901038388 | DO | 1 | 4 | 2018CP-1[187]Anti-Cl. Guard
FO_MISC |  | - | 901038393 | DO | 1 | 4 | 2018CP-1[214]Off Plumb -Poles
FO_MISC |  | - | 901038394 | DO | 1 | 4 | 2018CP-1[214]Insulator -Off Plumb
FO_MISC |  | - | 901038395 | DO | 1 | 4 | 2018CP-1[218]Off Plumb -Poles
FO_MISC |  | - | 901038396 | DO | 1 | 4 | 2018CP-1[218]Insulator -Off Plumb
FO_MISC |  | - | 901038400 | DO | 1 | 4 | 2018CP-1[233]Insulator -Off Plumb
FO_MISC |  | - | 901038403 | DO | 1 | 4 | 2018CP-1[246]Anti-Cl. Guard
FO_COND |  | - | 901038405 | DO | 1 | 4 | 2018CP-1[246]Conductor Check
FO_MISC |  | - | 901038418 | DO | 1 | 4 | 2018CP-1[260]Vibration Dampers -Replace
FO_MISC |  | - | 901038436 | DO | 1 | 4 | 2018CP-1[287]Off Plumb -Poles
FO_MISC |  | - | 901038437 | DO | 1 | 4 | 2018CP-1[288]Off Plumb -Poles
FO_STDMG |  | - | 901038443 | DO | 1 | 4 | 2018CP-1[277]Pole Bolt -Bent
FO_STDMG |  | - | 901038444 | DO | 1 | 4 | 2018CP-1[279]Pole Bolt -Bent
FO_MISC |  |  | 901084839 | DO | 1 | 4 | 2019HP-1[53]Insulator Broken Aux Insul
OS | CBR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CBR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | CLN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASTLEBAR DALTON
TO-20-CBR-DLT-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CBR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | DLT | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CAPACITOR/SVC/REACTOR - CASTLEBAR SVC
TO-20-CBR-SVC-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0331 | DO | 28 |  | SVC Refurbishment
TO-20-CBR-SVC-02 ISO week: 45mo - 46tu Date: 02 Nov - 10 Nov Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SJ511, CPR097
OS | CBR | - | 901042289 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CBR | - | 901042362 | DO | 3 | 4 | Capacitor/SVC Ordinary Service
CA | CBR | SVC | 901050222 | CLO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
110kV FEEDER - CASTLEDOCKRELL LODGEWOOD [Castledockrell CK1]
TO-20-CDK-LWD-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-CDK-LWD-1-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
OS | LWD | - | 901129863 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | LWD | - | 901129181 | CLO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CASTLEDOCKRELL T121 [Castledockrell CK1]
TO-20-CDK-T121-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CDK-LWD-1: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TSO CUSTOMER TRANSFORMER - CASTLEFARM T101 [Aughinish Alumina]
TO-20-CFM-T101-01 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of AUG-CFM-1
| CFM |  |  |  | 15 |  | Customer works
TSO CUSTOMER TRANSFORMER - CASTLEFARM T102 [Aughinish Alumina]
TO-20-CFM-T102-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | As a consequence of AUG-CFM-2
| CFM |  |  |  | 15 |  | Customer works
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA1
TO-20-CVW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA2
TO-20-CVW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA2 | 901038579 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CASTLEVIEW COW CROSS
TO-20-CVW-COW-1-01 ISO week: 19tu - 19fr Date: 05 May - 08 May Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, R1Z23b
OPT | COW |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
AMCAB | CVW | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CVW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | CVW |  | 901023280 | CLO | 1 | 1 | O1-Cowcross 7SA5111 Relay faulty display
CORRECT | CVW |  | 901052222 | CLO | 1 | 1 | O1-Scada not commissioned on this bay.
110kV FEEDER - CASTLEVIEW KNOCKRAHA
TO-20-CVW-KRA-1-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
OS | CVW | - | 901042211 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CVW | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | KRA | - | 901042300 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - CATHALEENS FALL 110 kV A1
TO-20-110 kV A1 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV A2
TO-20-110 kV A2 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV B1
TO-20-110 kV B1 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV B2
TO-20-110 kV B2 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover
CAPACITOR/SVC/REACTOR - CATHALEENS FALL CAP2
TO-20-CF-CAP2-01 ISO week: 36fr - 37fr Date: 04 Sep - 11 Sep Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | CF | CAP | 900616524 | DO | 5 | 2 | FI-011-11 Oil Sampling of Instrument tra
CA | CF | CAP | 901050223 | DO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
110kV FEEDER - CATHALEENS FALL CLIFF
TO-20-CF-CL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
110kV FEEDER - CATHALEENS FALL CLOGHER 1
TO-20-CF-CLO-1-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1011 | DO | 2 |  | Slit trenching and ducting in close proximity to C-Fall 1 circuit in Clogher station compound for new windfarm connection
[5 empty] | 5 |  | Telecoms- fibre works
110kV FEEDER - CATHALEENS FALL CLOGHER 2
TO-20-CF-CLO-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOINSHW |  | - | 900649885 | DO | 3 | 1 | 2014HP-2[20,21]Insulator Fit Dups. Proximity Outag of Cath Falls-Clogher 110kV. Wayleave Issue
FO_MISC |  | - | 900819397 | DO | 1 | 2 | 2016HP-1[20]Insulator Fit Dups
FO_MISC |  | - | 900819398 | DO | 1 | 2 | 2016HP-1[21]Insulator Fit Dups
TO-20-CF-CLO-2-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1011 | DO | 2 |  | Slit trenching and ducting in close proximity to C-Fall 2 circuit in Clogher station compound for new windfarm connection
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | CLO | - | 901043763 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
110kV FEEDER - CATHALEENS FALL CORRACLASSY
TO-20-CF-COR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900819396 | DO | 8 | 2 | 2016HP-1[14]Off Plumb
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900649865 | DO | 2 | 1 | 2014HP-1[299]Off Plumb
FO_MISC |  | - | 900649866 | DO | 2 | 1 | 2014HP-1[298]Off Plumb
FO_MISC |  | - | 900649867 | DO | 2 | 1 | 2014HP-1[296]Off Plumb
FO_MISC |  | - | 900649868 | DO | 2 | 1 | 2014HP-1[295]Off Plumb
FO_MISC |  |  | 901084870 | DO | 2 | 4 | 2019HP-1[13]Earths-Replace Left pole e/w
FO_MISC |  |  | 901084950 | DO | 2 | 4 | 2019HP-1[277]Off Plumb -plumb poles
FO_MISC |  | - | 900898249 | DO | 1 | 3 | 2017HP-1[4]Vib Damps Dampers fatigue (Landowner access available May-July)
TRAN |  | - | 900985204 | DO | 1 | 4 | 2018HP-1[287]Check(General)-rusty Xarm
TRAN |  | - | 900985205 | DO | 1 | 4 | 2018HP-1[282]Check(General)-rusty Xarm
TRAN |  | - | 900985206 | DO | 1 | 4 | 2018HP-1[281]Check(General)-rusty Xarm
TRAN |  | - | 900985207 | DO | 1 | 4 | 2018HP-1[278]Check(General)-rusty Xarm
TRAN |  | - | 900985208 | DO | 1 | 4 | 2018HP-1[228]Check(General)-rusty Xarm
TRAN |  | - | 900985209 | DO | 1 | 4 | 2018HP-1[169]Check(General)-rusty Xarm
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CATHALEENS FALL SRANANAGH 1
TO-20-CF-SRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
FO_MISC |  | - | 900819401 | CLO | 2 | 2 | 2016HP-1[194]Check-General Ground works
FO_MISC |  | - | 900898210 | DO | 1 | 3 | 2017HP-1[30]Anti-Cl. Guard -Fit
AMCAB | CF | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CF | - | 901068533 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CATHALEENS FALL SRANANAGH 2
TO-20-CF-SRA-2-01 ISO week: 36we - 37fr Date: 02 Sep - 11 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900898213 | CLO | 7 | 3 | 2017HP-3[74,75,76]Off Plumb Poles
FO_MISC |  |  | 901084951 | CLO | 2 | 4 | 2019HP-1[77]Off Plumb -plumb poles
FO_MISC |  |  | 901084952 | CLO | 2 | 4 | 2019HP-1[185]Off Plumb -plumb poles
FO_MISC |  |  | 901084953 | CLO | 2 | 4 | 2019HP-1[186]Off Plumb -plumb poles
TRAN |  | - | 900985321 | CLO | 1 | 4 | 2018HP-1[44]Check(General)-old Xarm
TRAN |  | - | 900985335 | CLO | 1 | 4 | 2018HP-1[93]Check(General)rusty crossarm
FO_MISC |  |  | 901084269 | DO | 1 | 4 | 2019HP-1[247]Bird Nests
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511, REL521
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CATHALEENS FALL T103 [ESB GWM ER3]
TO-20-CF-T103-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Extra work day for IPP works on
OS | CF | - | 901129790 | CLO | 4 | 4 | 110KV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - CAUTEEN 110SA1
TO-20-CTN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CTN-110SA2: 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CAUTEEN 110SA2
TO-20-CTN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
OPT | CTN | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - CAUTEEN KILLONAN
TO-20-CTN-KLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987741 | DO | 6 | 4 | "2018HP-6[5,15,47,48,51,64]Off Plumb"
TRAN |  | - | 900987742 | DO | 5 | 4 | "2018HP-5[72,85,102,105,121]Off Plumb"
TRAN |  | - | 900987743 | DO | 4 | 4 | "2018HP-4[122,123,127,128]Off Plumb"
TRAN |  | - | 900987744 | DO | 4 | 4 | "2018HP-4[134,135,136,137]Off Plumb"
TRAN |  | - | 900987748 | DO | 1 | 4 | 2018HP-1[AT11]Bird NestsCentre phase
OPT | CTN | - | 901038731 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KLN |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CAUTEEN T142 [SDCC]
TO-20-CTN-T142-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-T142-01 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
DISTRIBUTION TRANSFORMER - CAUTEEN T144 [SDCC]
TO-20-CTN-T144-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - CAUTEEN TIPPERARY
TO-20-CTN-TIP-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-TIP-1-01 ISO week: 41tu - 42th Date: 06 Oct - 15 Oct Duration: 10 Days (8 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985386 | DO | 2 | 4 | "2018HP-2[3,19]Off PlumbPlumb poles"
FO_MISC |  |  | 901084954 | DO | 2 | 4 | 2019HP-1[3]Off Plumb -plumb poles
FO_MISC |  |  | 901084270 | DO | 1 | 4 | 2019HP-1[4]Bird Nests Over Right phase
OS | CTN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | CTN | 110-DL | 901134773 | DO | 2 | 1 | R,S & T Phases Tipperary 110kV Cubicle.R,S & T Phase Dlconnections DUE : 17-Nov-20
OS | TIP | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CHARLEVILLE GLENLARA
TO-20-CHA-GLE-1-01 ISO week: 11tu - 11fr Date: 10 Mar - 13 Mar Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 4 |  | Total Maintenance Outage Duration Requested
OS | CHA | - | 901129798 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | GLE | - | 901116384 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CHARLEVILLE KILLONAN
TO-20-CHA-KLN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0624 | DO | 60 |  | EI: Line diversion work to enable construction of GIS building
TO-20-CHA-KLN-1-01 ISO week: 46tu - 47mo Date: 10 Nov - 16 Nov Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084958 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
TRAN |  | - | 900985430 | DO | 1 | 4 | 2018HP-1[68]Bird NestsRight phase
OPT | CHA |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
CM | CHA | 110-DL/DE | 901134774 | DO | 2 | 1 | T Phase Killonan 110kV cubicle. Tphase DL/DE connection DUE : 17-Aug-20
110kV FEEDER - CHARLEVILLE MALLOW
TO-20-CHA-MAL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985441 | CLO | 4 | 4 | "2018HP-6[16,19,62,72,81,92]Off Plumb"
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084959 | CLO | 1 | 2 | 2019HP-2[61,62]Off Plumb -plumb poles
OPT | CHA | - |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MAL | - | 901076481 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLAHANE T122 [Clahane CJ1]
TO-20-CLH-T122-01 ISO week: 21tu Date: 19 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer work
110kV FEEDER - CLAHANE TRALEE
TO-20-CLH-TRL-1-02 ISO week: 42mo - 43mo Date: 12 Oct - 19 Oct Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 901038454 | DO | 1 | 4 | 2018CP-1[49]Replace/Retire pole butts
FO_STDMG |  | - | 901038455 | DO | 1 | 4 | 2018CP-1[50]Found/Site repair -Sleepers
FO_STDMG |  | - | 901038457 | DO | 1 | 4 | 2018CP-1[50]Crossarm -Repair Grid Gain
FO_STDMG |  | - | 901038464 | DO | 1 | 4 | 2018CP-1[54]Crossarm -Repair Grid Gain
FO_STDMG |  | - | 901038480 | DO | 1 | 4 | 2018CP-1[62]Crossarm -Repair Grid Gain
FO_MISC |  | - | 901038483 | DO | 1 | 4 | 2018CP-1[63]Insulator -Replace (rust)
FO_MISC |  | - | 901038484 | DO | 1 | 4 | 2018CP-1[63]Ubolts -Replace (rust)
FO_MISC |  | - | 901038487 | DO | 1 | 4 | 2018CP-1[68]Off Plumb -Poleset
FO_MISC |  | - | 901038488 | DO | 1 | 4 | 2018CP-1[69]Off Plumb -Poleset
FOSTRHW |  | - | 901045854 | CLO | 1 | 1 | 2018CP-1[64]Replace Pole only -Rotten
AMCAB | TRL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | TRL | - |  | DO | 1 | 2 | Inspect Phisterer CSE & record serial number
110kV FEEDER - CLAHANE TRIEN
TO-20-CLH-TRI-1-01 ISO week: 9tu - 10mo Date: 25 Feb - 02 Mar Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985518 | CLO | 2 | 4 | 2018HP-1[42]Insul&HW Replace check
TRAN |  | - | 900985520 | CLO | 2 | 4 | 2018HP-1[44]Insul&HW Replace check
TRAN |  | - | 900985522 | CLO | 2 | 4 | 2018HP-1[57]Insul&HW Replace check
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
FOSTRHW |  | - | 900773923 | CLO | 1 | 3 | 2015CP-1[26]Off Plumb
FOINSHW |  | - | 900819428 | CLO | 1 | 3 | 2016HP-1[29]Insul&H-ware check
PROT |  |  |  | DO |  |  | P2 Protection maintenance of REL521, GRL100
CORRECT | CLH |  | 901080639 | CANC | 1 | 1 | Water in Tech. Box in H2 Trien CB-SS.
FM | TRI | - | 901114178 | CLO | 1 | 4 | HV Pressure Vessel Inspection
BUSBAR SECTION - CLASHAVOON 110 kV A1
TO-20-110 kV A1 @ CLA-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1)
TO-20-110 kV A1 @ CLA-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
TO-20-110 kV A1 @ CLA-02 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV A2
TO-20-110 kV A2 @ CLA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2)
TO-20-110 kV A2 @ CLA-01 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV B1
TO-20-110 kV B1 @ CLA-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1)
TO-20-110 kV B1 @ CLA-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
TO-20-110 kV B1 @ CLA-02 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV B2
TO-20-110 kV B2 @ CLA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2)
TO-20-110 kV B2 @ CLA-01 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover
COUPLER/SECTIONALISING CB - CLASHAVOON 110K1-2
TO-20-CLA-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
COUPLER/SECTIONALISING CB - CLASHAVOON 220K1-2
TO-20-CLA-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CLA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CLA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | CLA | 110-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | CLA | 110-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
110kV FEEDER - CLASHAVOON CLONKEEN
TO-20-CLA-CKN-1-01 ISO week: 9we - 22su Date: 26 Feb - 31 May Duration: 96 Days (64 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0996 | DO | 60 |  | EI: Realingment of the line to allow for the construction of the new N22 bypass. A number of new towers are being constructed and polesets moved
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084961 | CLO | 1 | 2 | 2019HP-1[131]Off Plumb -plumb poles
FO_MISC |  |  | 901084962 | CLO | 1 | 2 | 2019HP-2[91,92]Off Plumb -plumb poles
FO_MISC |  |  | 901084963 | CLO | 1 | 2 | 2019HP-2[76,77]Off Plumb -plumb poles
FO_MISC |  |  | 901084964 | DO | 1 | 2 | 2019HP-2[19,20]Off Plumb -plumb poles
AMCAB | CKN | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CKN |  | 901129659 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | CLA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - CLASHAVOON DUNMANWAY
TO-20-CLA-DMY-1-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
220kV FEEDER - CLASHAVOON KNOCKRAHA
TO-20-CLA-KRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-CLA-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-CLA-KRA-1-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-CLA-KRA-1-05 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | Proximity outage to allow for A1B1 busbar section to be retired
TO-20-CLA-KRA-1-04 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | Proximity outage to allow for A1/B1 busbar section to be retired
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, GRL100
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513, GRL100
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CLA | - | 901050471 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
CORRECT | KRA | - | 901091471 | DO | 5 | 1 | Replace stolen earths
OPT | KRA | - | 901038860 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - CLASHAVOON MACROOM 1
TO-20-CLA-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-CLA-MAC-1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-CLA-MAC-1-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-CLA-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-CLA-MAC-1-05 Status: Unscheduled
[5 empty] | 3 |  | Offline PD test on new cable
| - | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | MAC | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLASHAVOON MACROOM 2
TO-20-CLA-MAC-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-CLA-MAC-2-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-CLA-MAC-2-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-CLA-MAC-2-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084965 | CLO | 1 | 2 | 2019HP-1[12]Off Plumb -plumb poles
OPT | MAC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MAC |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TRANSFORMER - CLASHAVOON T2101
TO-20-CLA-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 85 |  | Remove old 125 MVA trafo and bund, constuct new bund, install and commission new 250 MVA trafo.
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
CAPX |  |  | CP0829 | DO | 2 |  | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CLA | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CLA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CLA | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | CLA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | CLA | - | 900973237 | DO | 1 | 2 | O1- S phase bushing low in oil.
TO-20-CLA-T2101-04 Status: Unscheduled
CORRECT | CLA |  | 900908038 | NS |  | 2 | Replace timber supports on T2101 Transfo
TRANSFORMER - CLASHAVOON T2102
TO-20-CLA-T2102-01 ISO week: 28mo - 30tu Date: 06 Jul - 21 Jul Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | CLA | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CLA | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | CLA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CLA | 220 |  | DO | 3 | 4 | 220kV CUBICLE CONDITION ASSESSMENT
CA | CLA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | CLA |  | 900879219 | DO | 3 | 2 | O1-OLTC Tap position not corresponding w
TRAFO | CLA | TRAFO | 901130541 | CLO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CORRECT | CLA | TRAFO | 900909472 | CLO | 2 | 2 | O1- Moss on all equipment in Cubicle
TRAFO | CLA | TRAFO | 901130545 | CLO | 1 | 4 | 220/110kV Trafo Tap Changer Inspection
GENERATOR TRANSFORMER - CLIFF T101 [ESB GWM ER1]
TO-20-CL-T101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CL |  | 901129648 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLIFF T102 [ESB GWM ER2]
TO-20-CL-T102-01 ISO week: 35tu Date: 25 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
OPT | CL |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA1
TO-20-CBA-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA1-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA1 | 900938714 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA2
TO-20-CBA-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | 110-SA2 |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA2-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA2 |  | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CLOGHBOOLA T122 [SDCC]
TO-20-CBA-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-T122-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Reference
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
GENERATOR TRANSFORMER - CLOGHBOOLA T131 [Cloghboola CL1]
TO-20-CBA-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-T131-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | 110 | 901068541 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHBOOLA TRIEN
TO-20-CBA-TRI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-TRI-1-01 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CBA | - | 901043718 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRI | - | 901050357 | CLO | 1 | 3 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - CLOGHER 110 kV A1
TO-20-110 kV A1 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV A2
TO-20-110 kV A2 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV B1
TO-20-110 kV B1 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV B2
TO-20-110 kV B2 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHER 110K1-2
TO-20-CLO-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CLO | - | 901043754 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | CLO | SA | 901050343 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - CLOGHER DRUMKEEN
TO-20-CLO-DRM-1-01 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084871 | DO | 1 | 4 | 2019HP-1[47]Earths-Replace
AMCAB | CLO | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | DRM | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CLOGHER MULREAVY
TO-20-CLO-MRY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
BUSBAR SECTION - CLOGHRAN 110 kV A1
TO-20-110 kV A1 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV A2
TO-20-110 kV A2 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV B1
TO-20-110 kV B1 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV B2
TO-20-110 kV B2 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110K1
TO-20-CLG-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110K2
TO-20-CLG-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110SA1-2CB
TO-20-CLG-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110SB1-2CB
TO-20-CLG-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
110kV FEEDER - CLOGHRAN CORDUFF
TO-20-CLG-CDU-1-02 ISO week: 27tu - 27th Date: 30 Jun - 02 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 900637313 | CLO | 2 | 2 | O/1 SURGE ARRESTOR BROKEN
OPT | CDU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CLG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHRAN FINGLAS GIS
TO-20-CLG-FIN GIS-1-01 ISO week: 48we - 48fr Date: 25 Nov - 27 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | CLO | - | 900840443 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
AMCAB | FIN | - | 901115062 | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - CLOGHRAN T121 [Amazon]
TO-20-CLG-T121-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
| CLG |  |  |  | 5 |  | 5 Day Customer Outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T122 [Amazon]
TO-20-CLG-T122-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T123 [Amazon]
TO-20-CLG-T123-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 5 |  | 5 Day Customer outage
OPT | CLG | 110 | 901030848 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLOGHRAN T124 [Amazon]
TO-20-CLG-T124-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 4 |  | 4 day customer outage
AMCAB | CLG | 110 | 901006517 | DO | 3 | 3 | Annual Insp. 110kV Feeder XLPE Cable
TSO CUSTOMER TRANSFORMER - CLOGHRAN T126 [Amazon]
TO-20-CLG-T126-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
BUSBAR SECTION - CLONEE 220 kV A1
TO-20-220 kV A1 @ CLE-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-220 kV A1 @ CLE-03 ISO week: 44we - 47we Date: 28 Oct - 18 Nov Duration: 22 Days (16 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 17 |  | Civil and Electrical Installation Works associated with new F1 bay
BUSBAR SECTION - CLONEE 220 kV A2
TO-20-220 kV A2 @ CLE-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
BUSBAR SECTION - CLONEE 220 kV B1
TO-20-220 kV B1 @ CLE-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-220 kV B1 @ CLE-03 ISO week: 47th - 48fr Date: 19 Nov - 27 Nov Duration: 9 Days (7 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 7 |  | Civil and Electrical Installation Works associated with new F1 bay
BUSBAR SECTION - CLONEE 220 kV B2
TO-20-220 kV B2 @ CLE-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
COUPLER/SECTIONALISING CB - CLONEE 220K1
TO-20-CLE-220K1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-CLE-220K1-06 ISO week: 47th - 48fr Date: 19 Nov - 27 Nov Duration: 9 Days (7 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 7 |  | As a consequence of 220 kV B1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay
TO-20-CLE-220K1-05 ISO week: 44we - 47we Date: 28 Oct - 18 Nov Duration: 22 Days (16 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 17 |  | As a consequence of 220 kV A1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay
COUPLER/SECTIONALISING CB - CLONEE 220K2
TO-20-CLE-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
220kV FEEDER - CLONEE CORDUFF
TO-20-CLE-CDU-1-01 ISO week: 47th - 49we Date: 19 Nov - 02 Dec Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | CLE | - | 901045472 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLONEE T221 [Facebook]
TO-20-CLE-T221-02 ISO week: 39mo - 41mo Date: 21 Sep - 05 Oct Duration: 15 Days (11 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 10 |  | Customer outage request
TSO CUSTOMER TRANSFORMER - CLONEE T224 [Facebook]
TO-20-CLE-T224-01 ISO week: 37we - 38th Date: 09 Sep - 17 Sep Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CLE |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CLONEE WOODLAND
TO-20-CLE-WOO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985608 | DO | 1 | 4 | 2018HP-1[3]Check Struct/Found/etc-base
OS | WOO | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | WOO | - | 901046058 | DO | 1 | 4 | HV Pressure Vessel Inspection
COUPLER/SECTIONALISING CB - CLONKEEN 110SA1-2CB
TO-20-CKN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CKN | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | CKN | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | CKN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CKN-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
110kV FEEDER - CLONKEEN COOMAGEARLAHY
TO-20-CKN-CGL-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129698 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CKN |  | 901129658 | CLO | 3 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLONKEEN GARROW
TO-20-CKN-GRO-1-01 ISO week: 24mo - 24fr Date: 08 Jun - 12 Jun Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of REL521, GRL100
CM |  | 110 | 901068795 | CANC | 1 | 1 | Visual inspection of HIS HV cable sealin
OS | CKN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CKN | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | GRO | - | 901129956 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | GRO | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CLONKEEN KNOCKEARAGH
TO-20-CKN-KER-1-01 ISO week: 23th - 23fr Date: 04 Jun - 05 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7SA511
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
TRAN |  | - | 900985669 | CLO | 1 | 4 | 2018HP-1[33]Off PlumbPlumb poles
FO_MISC |  |  | 901084966 | CLO | 1 | 2 | 2019HP-1[32]Off Plumb -plumb poles
OPT | CKN |  | 901129657 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | CKN | 110-DL | 901134777 | CLO | 1 | 1 | R Phase Knockearagh 110kV Cubicle. R Phase DL contact. DUE : 17-Aug-20 hotspot
BUSBAR SECTION - CLOON 110 kV A2
TO-20-110 kV A2 @ CLN-01 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PR0001 |  | 2 |  | Proximity for EI of CLN T142
SECTIONALISING DISCONNECT - CLOON 110SA1
TO-20-CLN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CLN-110SA2: 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CLOON 110SA2
TO-20-CLN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
OS | CLN | SA2 | 901039700 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CLOON LANESBORO
TO-20-CLN-LA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-LA-1-03 Status: Unscheduled
[5 empty] | 2 |  | Proximity for EI of CLN T142
TO-20-CLN-LA-1-04 Status: Unscheduled
CORRECT | LA | - | 900957961 | CANC | 3 | 1 | Repair fault busbar disconnect
TO-20-CLN-LA-1-05 Status: Unscheduled
FO_MISC |  | - | 900819454 | CANC | 1 | 2 | 2016HP-1[97]Stays - Check Check stays
TO-20-CLN-LA-1-01 ISO week: 42mo - 42fr Date: 12 Oct - 16 Oct Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085132 | DO | 1 | 4 | 2019HP-1[97]Stays-Replace Broken
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
OS | CLN | - | 901042219 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | LA | - | 901042220 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - CLOON T142 [SDCC]
TO-20-CLN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-T142-02 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Reference (Tentative)
|  |  | PR0001 |  | 2 |  | EI of CLN T142 request from RC
COUPLER/SECTIONALISING CB - COLLEGE PARK 110SA1-2CB
TO-20-COL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS_LO | COL | 110-DEA1(Q13) | 900744240 | DO | 3 | 3 | 110kV Sect / Dist Ordinary Service
OPT | COL | - | 900839239 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
OPT_LO | COL | 110-SA1/DEM1 | 900859195 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT_LO | COL | 110-SA2/DEM2 | 900859196 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | COL | 110-DEA2(Q14) | 900859226 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-COL-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - COLLEGE PARK 110SA1-3CB
TO-20-COL-110SA1-3CB-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-COL-110SA1-3CB-01 Status: Unscheduled
|  |  | PROT |  |  |  | P1 Protection maintenance of 7SJ511
TO-20-COL-110SA1-3CB-02 Status: Unscheduled
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS_LO | COL | 110-SA1 | 900744242 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service
OS | COL | - | 900777933 | DO | 3 | 1 | 110kV GIS Cubicle Ordinary Service
OS_LO | COL | 110-DEA1(Q12) | 900778172 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service
OS_LO | COL | 110-DEA3(Q11) | 900745182 | DO | 2 | 1 | 110kV Sect / Dist Ordinary Service
OS_LO | COL | 110-SA3 | 900778168 | DO | 2 | 1 | 110kV Sect / Dist Ordinary Service
OPT | COL | 110-SA1 | 901076464 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
TO-20-COL-110SA1-3CB-03 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
110kV FEEDER - COLLEGE PARK CORDUFF
TO-20-COL-CDU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-COL-CDU-1-01 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
TO-20-COL-CDU-1-02 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | COL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | COL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-COL-CDU-1-04 Status: Unscheduled
CM | COR | - | 900981227 | CLO | 2 | 1 | R Phase Hotspot found on R Phase CT HV Connection DUE IMMEDIATELY0
110kV FEEDER - COLLEGE PARK FINGLAS GIS
TO-20-COL-FIN GIS-1-01 ISO week: 9th - 10tu Date: 27 Feb - 03 Mar Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086432 | CLO | 2 | 2 | 2019HP-1[14]Replace Pole only -Rot
OS | COL | - | 901128698 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - COLLEGE PARK T101 [NDCC]
TO-20-COL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - COLLEGE PARK T103 [NDCC]
TO-20-COL-T103-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
110kV FEEDER - COOLNANOONAGH KILPADDOGE
TO-20-CNO-KPG-1-01 ISO week: 44we - 45mo Date: 28 Oct - 02 Nov Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage to facilitate customer's work
GENERATOR TRANSFORMER - COOLNANOONAGH T131
TO-20-CNO-T131-01 ISO week: 36mo Date: 31 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Black start testing
TO-20-CNO-T131-02 ISO week: 47fr - 48tu Date: 20 Nov - 24 Nov Duration: 5 Days (3 WD) Status: Tentative
Outage to facilitate customer's work
110kV FEEDER - COOLROE INNISCARRA
TO-20-CRO-IA-1-01 ISO week: 23we - 23fr Date: 03 Jun - 05 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084967 | CLO | 1 | 2 | 2019HP-2[8,9]Off Plumb -plumb poles
OPT | IA |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - COOLROE KILBARRY
TO-20-CRO-KBY-1-02 ISO week: 39mo - 41fr Date: 21 Sep - 09 Oct Duration: 19 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1037 | DO | 34 |  | Proximity outage to facilitate the civil works and installation of the commercial fibre, cable pull, scaffolding erection and calbe termination
TO-20-CRO-KBY-1-01 ISO week: 27mo - 37fr Date: 29 Jun - 11 Sep Duration: 75 Days (54 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 55 |  | Terminating 110 kV cable at station bay and end masts
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511, REL521
AMCAB | KBY | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA1
TO-20-CGL-110SA1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | CGL | - | 900801826 | DO | 2 | 2 | O2.Sectionaliser not working from Mimic.
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA2
TO-20-CGL-110SA2-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Prox for SA1
110kV FEEDER - COOMAGEARLAHY GLANLEE
TO-20-CGL-GAE-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129700 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T121 [Coomagearlahy CG3]
TO-20-CGL-T121-01 ISO week: 29mo - 29th Date: 13 Jul - 16 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129701 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T122 [Coomagearlahy CG1/CG2]
TO-20-CGL-T122-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129699 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - COOMATAGGART 110SA1
TO-20-COT-110SA1-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
SECTIONALISING DISCONNECT - COOMATAGGART 110SA2
TO-20-COT-110SA2-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
GENERATOR TRANSFORMER - COOMATAGGART T132 [Grousemount GD1]
TO-20-COT-T132-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
DISTRIBUTION TRANSFORMER - COOMATAGGART T141 [SDCC]
TO-20-COT-T141-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
SECTIONALISING DISCONNECT - CORDAL 110SA1
TO-20-CDL-110SA1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA1 | 901130105 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - CORDAL 110SA2
TO-20-CDL-110SA2-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA2 | 901146308 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - CORDAL T132
TO-20-CDL-T132-01 ISO week: 33tu - 33fr Date: 11 Aug - 14 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | CDL |  | 901074069 | DO | 2 | 1 | Replair replace bonding leads (damaged)
OPT | CDL |  | 901118391 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CORDAL T141 [SDCC]
TO-20-CDL-T141-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Ballynahulla-Cordal 110 kV circuit
SECTIONALISING DISCONNECT - CORDERRY 110SA1
TO-20-CDY-110SA1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA1-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
SECTIONALISING DISCONNECT - CORDERRY 110SA2
TO-20-CDY-110SA2-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA2-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
110kV FEEDER - CORDERRY GARVAGH
TO-20-CDY-GRV-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRAN | - | Line | 900985802 | NS | 1 | 4 | 2018HP-1[Am11]Bird Nests
| CDY | - | 901129384 | CLO | 5 | 1 | Leak detection on CB & repair if required
OPT | CDY |  | 901129706 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDERRY SRANANAGH
TO-20-CDY-SRA-1-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends
TO-20-CDY-SRA-1-01 ISO week: 9mo - 43fr Date: 24 Feb - 23 Oct Duration: 243 Days (169 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 170 |  | 110 kV OHL outage
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
FOSTRHW |  | - | 900725307 | DO | 8 | 1 | 2015CP-3[16,19,30]Replace Pole only
FOSTRHW |  | - | 900725308 | DO | 1 | 1 | 2015CP-1[28]Check Structure Worm Holes
P1 Protection maintenance of REL521, REL551
OPT | CDY | - | 901039099 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
DISTRIBUTION TRANSFORMER - CORDERRY T122 [NDCC]
TO-20-CDY-T122-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-T122-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
BUSBAR SECTION - CORDUFF 110 kV A1
TO-20-110 kV A1 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV A2
TO-20-110 kV A2 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV A2 @ CDU-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2
TO-20-110 kV A2 @ CDU-01 ISO week: 23tu - 25we Date: 02 Jun - 17 Jun Duration: 16 Days (12 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 12 |  | Install DA bases on H2
BUSBAR SECTION - CORDUFF 110 kV A3
TO-20-110 kV A3 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV A3 @ CDU-06 Status: Unscheduled
CAPX |  |  | CP1009_OS | DO | 15 |  | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay
TO-20-110 kV A3 @ CDU-05 ISO week: 38tu - 38th Date: 15 Sep - 17 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | To facilitate CB connection works associated with DN0241/CP1025 Corduff
TO-20-110 kV A3 @ CDU-03 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | 110 kV A3/B3 IN TURN @ CDU: Test interlocking
TO-20-110 kV A3 @ CDU-02 ISO week: 23tu - 24fr Date: 02 Jun - 12 Jun Duration: 11 Days (9 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11
BUSBAR SECTION - CORDUFF 110 kV A4
TO-20-110 kV A4 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B1
TO-20-110 kV B1 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B2
TO-20-110 kV B2 @ CDU-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2
TO-20-110 kV B2 @ CDU-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 12 |  | Install DB bases on H2
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B3
TO-20-110 kV B3 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV B3 @ CDU-05 Status: Unscheduled
CAPX |  |  | CP1009_OS | DO | 15 |  | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay
TO-20-110 kV B3 @ CDU-03 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | 110 kV A3/B3 IN TURN @ CDU: Test interlocking
TO-20-110 kV B3 @ CDU-02 ISO week: 23tu - 24fr Date: 02 Jun - 12 Jun Duration: 11 Days (9 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11
BUSBAR SECTION - CORDUFF 110 kV B4
TO-20-110 kV B4 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover
COUPLER/SECTIONALISING CB - CORDUFF 110K1-2
TO-20-CDU-110K1-2-01 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 3 |  | Test interlocking
COUPLER/SECTIONALISING CB - CORDUFF 110K1-3
TO-20-CDU-110K1-3-01 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 3 |  | Test interlocking
SECTIONALISING DISCONNECT - CORDUFF 110SA2-4
TO-20-CDU-110SA2-4-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 901087518 | DO | 4 | 2 | Misc- earthing required
OPT | CDU | 110-SA |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | 110-SA2-4 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
BUSBAR SECTION - CORDUFF 220 kV A1
TO-20-220 kV A1 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 5 |  | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV A2
TO-20-220 kV A2 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV A3
TO-20-220 kV A3 @ CDU-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0005 | DO | 5 |  | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3
BUSBAR SECTION - CORDUFF 220 kV B1
TO-20-220 kV B1 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 5 |  | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV B2
TO-20-220 kV B2 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV B3
TO-20-220 kV B3 @ CDU-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0005 | DO | 5 |  | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3
COUPLER/SECTIONALISING CB - CORDUFF 220K1-2
TO-20-CDU-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
Proximity outage of Corduff 220 kV A1/B1 IN TURN required for this outage
CORRECT | CDU |  | 900909533 | DO | 5 | 2 | O/1 FIT EARTHING STIRRUPS TO CUBICLE
COUPLER/SECTIONALISING CB - CORDUFF 220K1-3
TO-20-CDU-220K1-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU |  | 900909532 | DO | 5 | 2 | o/1 FIT EARTHING STIRRUPS TO CUBICLE
CORRECT | CDU | - | 900889827 | CANC | 2 | 1 | Repair PI fault on DA3
TO-20-CDU-220K1-3-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
OPT | CDU | 220-SB3 | 901076475 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | 220-SA3 | 901076476 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | - | 901076486 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CORDUFF FINGLAS 1
TO-20-CDU-FIN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDU | - | 901039067 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | FIN | - | 901038698 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-CDU-FIN-1-03 Status: Unscheduled
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A3/B3 @ CDU: Proximity outage for work on Corduff 220kV K1-3
TO-20-CDU-FIN-1-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
220kV FEEDER - CORDUFF FINGLAS 2
TO-20-CDU-FIN-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 2 |  | EI: Energise Belcamp-Finglas cable, Belcamp-T2103 and Belcamp 110 kV station
TO-20-CDU-FIN-2-08 ISO week: 39mo - 39tu Date: 21 Sep - 22 Sep Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 2 |  | Proximity outage required to remove scaffolding at the new Belcamp bay.
TO-20-CDU-FIN-2-07 ISO week: 37fr - 37su Date: 11 Sep - 13 Sep Duration: 3 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay
Switching to start from 18:00 11 Sept
TO-20-CDU-FIN-2-01 ISO week: 24we - 33mo Date: 10 Jun - 10 Aug Duration: 62 Days (43 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - | 901042328 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | FIN | - | 901031837 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CORDUFF HUNTSTOWN
TO-20-CDU-HN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 5 | 4 | Cable Insp. 220kV Feeder XLPE
110kV FEEDER - CORDUFF MACETOWN
TO-20-CDU-MCE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
CORRECT | MCE |  | 901072034 | CLO | 2 | 2 | CORDUFF SCADA SWITCH FAULTY
OPT | MCE |  | 901129598 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDUFF MULLINGAR
TO-20-CDU-MUL-1-02 ISO week: 28mo - 28we Date: 06 Jul - 08 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084099 | CLO | 2 | 2 | 2019HP-1[48]Arching Horns check
FO_MISC |  | - | 900902317 | DO | 1 | 3 | 2017CP-1[285]Off Plumb pole
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
TO-20-CDU-MUL-1-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
110kV FEEDER - CORDUFF PLATIN
TO-20-CDU-PLA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU |  | 900891899 | DO | 2 | 2 | O/1 Change R Phase surge counter
TO-20-CDU-PLA-1-03 ISO week: 39fr - 40mo Date: 25 Sep - 28 Sep Duration: 4 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985861 | DO | 1 | 4 | 2018HP-1[39]Check Struct/Found/etc-Base
TRAN |  | - | 900985862 | DO | 1 | 4 | 2018HP-1[41]Check Struct/Found/etc-Base
TRAN |  | - | 900985863 | DO | 1 | 4 | 2018HP-1[46]Check Struct/Found/etc-Base
TRAN |  | - | 900985864 | DO | 1 | 4 | 2018HP-1[50]Check Struct/Found/etc-Base
OPT | PLA |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - CORDUFF RYEBROOK GIS
TO-20-CDU-RYB GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0668 | DO | 30 |  | EI: Replacement of tower 29 on Corduff Ryebrook OHL.
TO-20-CDU-RYB GIS-1-01 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T133
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
110kV FEEDER - CORDUFF SNUGBOROUGH
TO-20-CDU-SNU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T101 and Coupler K1
TO-20-CDU-SNU-1-02 Status: Unscheduled
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T103
TO-20-CDU-SNU-1-03 Status: Unscheduled
De-gas 110kV Cubicles for repair
TRANSFORMER - CORDUFF T2101
TO-20-CDU-T2101-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU | TRAFO | 901039324 | NS | 1 | 2 | Corduff T2101 Transformer: Drycol Replacment
TO-20-CDU-T2101-01 Status: Unscheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 900776813 | DO | 5 | 2 | Repair faulty gas connections
OS | CDU | 220 | 901042339 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CDU | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CDU | TRAFO | 901042113 | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | CDU |  | 901090021 | DO | 1 | 2 | Misc- Silica gel needs replacing
TO-20-CDU-T2101-02 ISO week: 31we - 32we Date: 29 Jul - 05 Aug Duration: 8 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 5 |  | Outage on T2101 F3/H5 to facilitate excavation works for project CP1025 required under transformer flyover
TRANSFORMER - CORDUFF T2102
TO-20-CDU-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CDU | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CDU | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CDU | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | CDU | TRAFO | 901039325 | DO | 2 | 2 | Corduff T2102 Transformer: Drycol Replacment
220kV FEEDER - CORDUFF WOODLAND
TO-20-CDU-WOO-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| WOO | - | 901125085 | CLO | 5 | 1 | 0/1 Invetigate and Repair SF6 leak
TO-20-CDU-WOO-1-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900816866 | DO | 1 | 2 | 2016CP-1[18]Replace Member Raker
FO_STDMG |  | - | 900816871 | DO | 1 | 2 | 2016CP-1[33]Replace Member Stub-bars
FOSTRHW |  | - | 900819486 | DO | 1 | 2 | 2016HP-1[1-11]Check Structure -Painting
CORRECT | WOO |  | 900444597 | DO | 5 | 2 | O. ESBI Inspect and test all the cylind
CORRECT | WOO |  | 901038603 | DO | 5 | 2 | SF6 Cublicle Ordinary Serice DA, DB and
OS | WOO | - | 901042329 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | WOO | - | 901129132 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | WOO |  | 900532138 | NS |  | 2 | Inspect and test all the cylinders, pist
TO-20-CDU-WOO-1-01 ISO week: 34we - 35tu Date: 19 Aug - 25 Aug Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | MC0333 | DO | 5 |  | Uprate bay conductor on Corduff - Woodland circuit
[5 empty] | 2 |  | P2 Prot Maintenance
SF6 leak repairs
OPT | CDU | - | 901039068 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
BUSBAR SECTION - CORRACLASSY 110 kV A1
TO-20-110 kV A1 @ COR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | COR |  |  |  | 5 |  | Busbar outage for cubicle assessment on COR-ENS PST
TRANSFORMER - CORRACLASSY ENNISKILLEN PST
TO-20-COR-PST-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | COR | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | COR | 110-DA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - CORRACLASSY GORTAWEE
TO-20-COR-GWE-1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084872 | DO | 1 | 4 | 2019HP-1[69]Earths-Replace L/pole e/w
OS | COR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | COR | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | COR | 110-DA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - COW CROSS 110SA2
TO-20-COW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | COW | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - COW CROSS OLDCOURT 2 [SDCC]
TO-20-COW-OLD-2-01 ISO week: 9tu Date: 25 Feb Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
110kV FEEDER - COW CROSS RAFFEEN
TO-20-COW-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | RAF |  | 901065864 | CLO | 3 | 1 | Replacement of Stolen Earths
TO-20-COW-RAF-1-01 ISO week: 31mo - 32tu Date: 27 Jul - 04 Aug Duration: 9 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FOINSHW |  |  | 901085552 | DO | 2 | 2 | 2019HP-2[13,14]Insul&HW Replac check
OS | COW | - | 901129844 | CLO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CORRECT | COW |  | 900934544 | CLO |  | 1 | O1-Maintenance reqd on Raffeen 110 KV su
CORRECT | COW |  | 901068560 | CLO |  | 1 | O1-Top up with oil pole of CB as glass w
AMCAB | RAF | - | 901129143 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
FM | RAF | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
110kV FEEDER - COW CROSS WHITEGATE [Irving Oil]
TO-20-COW-WHI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900985959 | DO | 1 | 4 | "2018HP-2[50,73]Off PlumbPlumb poles"
FO_MISC |  |  | 901084968 | DO | 1 | 2 | 2019HP-2[71,72]Off Plumb -plumb poles
CORRECT | WHI |  | 901059047 | NS |  | 1 | O1- Disconnects heavily corroded.
TO-20-COW-WHI-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084140 | DO | 1 | 2 | 2019HP-1[40]Arching Horns -Replace
FO_MISC |  |  | 901084141 | DO | 1 | 2 | 2019HP-1[38]Arching Horns -Replace
FO_MISC |  |  | 901084142 | DO | 1 | 2 | 2019HP-1[36]Arching Horns -Replace
OPT | COW |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CRANE LODGEWOOD
TO-20-CRA-LWD-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-CRA-LWD-1-01 ISO week: 31mo - 31we Date: 27 Jul - 29 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900563038 | DO | 1 | 3 | 1[14]Off Plumb
FO_MISC |  | - | 900819497 | DO | 1 | 3 | 2016HP-1[14]Off Plumb Straighten P-set
FO_MISC |  | - | 900898042 | DO | 1 | 3 | 2017HP-1[14]Off Plumb -Poles
TRAN |  | - | 900985977 | DO | 1 | 4 | 2018HP-1[14]Off Plumb
TRAN |  | - | 900985979 | DO | 1 | 4 | 2018HP-1[25]Off Plumb
TRAN |  | - | 900985980 | DO | 1 | 4 | 2018HP-1[26]Off Plumb
FO_MISC |  |  | 901090924 | DO | 1 | 2 | 2019HP-1[14]Off Plumb -plumb poles
NOTE | [6 empty] | Final confirmaton on 25th of July regarding land access
AMCAB | CRA | - | 901113582 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CRA |  | 901129686 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | CRA | - | 901132793 | CLO | 1 | 2 | Inspect Pfisterer CSE and record serial number
OPT | LWD |  | 901129595 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CRANE WEXFORD
TO-20-CRA-WEX-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
TO-20-CRA-WEX-1-02 ISO week: 25we - 26we Date: 17 Jun - 24 Jun Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900902495 | DO | 3 | 2 | 2017CP-3[13, 24, 25]Off Plumb -Poles
FO_MISC |  | - | 900902451 | CLO | 1 | 2 | 2017CP-1[106]Off Plumb Insulator
FO_MISC |  | - | 900902473 | CLO | 1 | 2 | 2017CP-1[38]Shear Block - Repair
FO_STDMG |  | - | 900902474 | CLO | 1 | 2 | 2017CP-1[38]Replace Member -Bar 225
FO_MISC |  | - | 900902506 | CLO | 1 | 2 | 2017CP-1[106]Off Plumb -Poles
OPT | CRA |  | 901129685 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | WEX | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | WEX | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CRORY LODGEWOOD [SDCC]
TO-20-CRY-LWD-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA611, 7SJ804
OS | LWD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - CRORY T121 [SDCC]
TO-20-CRY-T121-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CRY-LWD-1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
BUSBAR SECTION - CULLENAGH 110 kV A1
TO-20-110 kV A1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV A1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV A2
TO-20-110 kV A2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV A2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV B1
TO-20-110 kV B1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV B1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV B2
TO-20-110 kV B2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV B2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover
COUPLER/SECTIONALISING CB - CULLENAGH 110K1-2
TO-20-CUL-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
110kV Sect / Dist Operational Test
TO-20-CUL-110K1-2-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CUL | 110-SB |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | CUL | 110-SA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-CUL-110K1-2-03 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ511
BUSBAR SECTION - CULLENAGH 220 kV A1
TO-20-220 kV A1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV A1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV A2
TO-20-220 kV A2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV A2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV B1
TO-20-220 kV B1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV B1 @ CUL-01 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV B2
TO-20-220 kV B2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV B2 @ CUL-01 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover
COUPLER/SECTIONALISING CB - CULLENAGH 220K1-2
TO-20-CUL-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | CUL | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CUL | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | CUL | 220-SB |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | CUL | 220-SA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-CUL-220K1-2-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
110kV FEEDER - CULLENAGH DUNGARVAN
TO-20-CUL-DGN-1-01 ISO week: 36mo - 36we Date: 31 Aug - 02 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985985 | DO | 3 | 4 | "2018HP-4[6,25,26,77]Off Plumb-Poles"
FO_MISC |  |  | 901084969 | DO | 1 | 2 | 2019HP-2[5,6]Off Plumb -plumb poles
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CUL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DGN |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - CULLENAGH GREAT ISLAND GIS
TO-20-CUL-GI GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
TO-20-CUL-GI GIS-1-02 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
TO-20-CUL-GI GIS-1-06 Status: Unscheduled
FO_MISC |  | - | 900855588 | CANC | 3 | 2 | Line Towers 35 - Replace angle insulator
OS | CUL | - | 900943447 | CANC | 6 | 3 | 220kV SF6 Cubicle Ordinary Service
CA | CUL | - | 900943872 | CANC | 3 | 3 | 220kV Cubicle Condition Assessment
AMCAB | GI | - | 901006385 | CANC | 2 | 2 | Cable Insp. 110kV XLPE
OPT | GI | - | 900840902 | CANC | 1 | 3 | 220kV MO Cubicle Operational Test
TO-20-CUL-GI GIS-1-04 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Proposed
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
FO_MISC |  | - | 900855589 | DO | 2 | 2 | Line Towers 35 & 36 (Angle & Intermediate) - Replace intermediate insulators and measurement of existing strain insulator chain length
FOINSHW |  |  | 901086391 | DO | 2 | 2 | 2019HP-3[27,28,29]Clean Insulators
220kV FEEDER - CULLENAGH KNOCKRAHA
TO-20-CUL-KRA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 7 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-CUL-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-CUL-KRA-1-01 ISO week: 9mo - 18th Date: 24 Feb - 30 Apr Duration: 67 Days (46 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Knockraha-Raffeen 220 kV
CORRECT | KRA |  | 901081935 | CLO | 3 | 2 | Ordinary service required on DB followin
TRANSFORMER - CULLENAGH T2101
TO-20-CUL-T2101-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CUL |  | 900908056 | DO | 30 | 2 | Refurbish main cover using Megalift devi
CORRECT | CUL | - | 900807712 | CLO | 3 | 1 | Repair oil leak on tertiary bushings
TO-20-CUL-T2101-02 Status: Unscheduled
|  | - |  |  | 30 |  | Total Maintenance Outage Duration Requested
CORRECT | CUL |  | 900706946 | CANC | 30 | 2 | Replace main cover gasket
OS | CUL | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TRAFO | CUL | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | CUL | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | CUL | TRAFO |  | DO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
CA | CUL | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CA | CUL | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | CUL | Trafo |  | DO | 3 | 4 | 220/110 & 275/220 - Ordinary Service
CORRECT | CUL |  | 900794262 | DO | 1 | 2 | Power Diagnostix are to carry out PD mea
TO-20-CUL-T2101-03 Status: Unscheduled
PROT |  |  |  | DO | 2 |  | P1 Protection maintenance of 7SA511, 7SA511, 7UT512
110kV FEEDER - CULLENAGH WATERFORD
TO-20-CUL-WAT-1-01 ISO week: 45mo - 45tu Date: 02 Nov - 03 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | WAT | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CUNGHILL 110SA1
TO-20-CUN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CUN-110SA2: 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CUNGHILL 110SA2
TO-20-CUN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
OS | CUN | SA2 | 901039702 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CUNGHILL GLENREE
TO-20-CUN-GLR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUN | - | 901042223 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | GLR | - | 901068536 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUN-GLR-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - CUNGHILL SLIGO
TO-20-CUN-SLI-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUN | - | 901042227 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CUN-SLI-1-01 Status: Unscheduled
OPT | SLI | - | 901038824 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUNGHILL T121 [Kingsmountain KGM/KG2]
TO-20-CUN-T121-01 ISO week: 25tu - 25we Date: 16 Jun - 17 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
COUPLER/SECTIONALISING CB - CUSHALING 110SA1-2CB
TO-20-CUS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS | SA1 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUS | SA2 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUS | - | 901038992 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUS-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ611
110kV FEEDER - CUSHALING MOUNTLUCAS
TO-20-CUS-MLC-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MLC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CUSHALING NEWBRIDGE
TO-20-CUS-NEW-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUS-NEW-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-CUS-NEW-1-03 Status: Unscheduled
[5 empty] | 2 |  | Timber Cutting
110kV FEEDER - CUSHALING PORTLAOISE
TO-20-CUS-PLS-1-01 ISO week: 24fr - 27we Date: 12 Jun - 01 Jul Duration: 20 Days (14 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 900898064 | DO | 2 | 1 | 2019HP-1[200]Replace Pole only -Rot
FO_STDMG |  | - | 900876709 | DO | 1 | 3 | 2017CP-1[28]Found/Site repair Fill base
FO_MISC |  | - | 900876727 | CLO | 1 | 3 | 2017CP-1[71]Off Plumb Poles
FO_STDMG |  | - | 900876728 | CLO | 1 | 3 | 2017CP-1[71]Found/Site repair Fill base
FO_MISC |  | - | 900876729 | CLO | 1 | 3 | 2017CP-1[73]Shear Block Repair all
FO_STDMG |  | - | 900876730 | CLO | 1 | 3 | 2017CP-1[73]Replace Member -Bent
FO_STDMG |  | - | 900876741 | CLO | 1 | 3 | 2017CP-1[89]Found/Site repair Sleepers
FO_MISC |  | - | 900876757 | CLO | 1 | 3 | 2017CP-2[102,103]Off Plumb Poles
FO_MISC |  | - | 900876759 | CLO | 1 | 3 | 2017CP-1[103]Off Plumb Insulator
FO_MISC |  | - | 900876760 | DO | 1 | 3 | 2017CP-1[104]Replace/Retire pole butts
FO_MISC |  | - | 900876761 | DO | 1 | 3 | 2017CP-1[105]Shear Block Repair all
FO_MISC |  | - | 900876791 | CLO | 1 | 3 | 2017CP-1[134]Off Plumb Poles
FO_MISC |  | - | 900876804 | DO | 1 | 3 | 2017CP-1[147]Shear Block Repair
FO_MISC |  | - | 900876809 | DO | 1 | 3 | 2017CP-1[150]Replace/Retire pole butts
FO_MISC |  | - | 900876833 | DO | 1 | 3 | 2017CP-1[167]Shear Block Repair all
FO_MISC |  | - | 900876864 | CLO | 1 | 3 | 2017CP-1[181]Shear Block Clear base
FO_MISC |  | - | 900876869 | DO | 1 | 3 | 2017CP-1[185]Off Plumb Pole & Insulator
FO_STDMG |  | - | 900876871 | DO | 1 | 3 | 2017CP-1[185]Found/Site repair Fill base
FO_MISC |  | - | 900876877 | CLO | 1 | 3 | 2017CP-1[190]Off Plumb Pole & Insulator
FO_STDMG |  | - | 900876881 | CLO | 1 | 3 | 2017CP-1[194]Found/Site repair Fill base
FO_MISC |  | - | 900876891 | CLO | 1 | 3 | 2017CP-1[204]Shear Block Clear base
FO_STDMG |  | - | 900876926 | DO | 1 | 3 | 2017CP-1[4]Pole Bolt Loose-Tighten
FO_STDMG |  | - | 900876929 | DO | 1 | 3 | 2017CP-1[103]Pole Bolt Loose-Tighten
FO_MISC |  | - | 900876937 | CLO | 1 | 3 | 2017CP-1[105]Stepbolts Missing-Fit
FO_MISC |  | - | 900876938 | CLO | 1 | 3 | 2017CP-1[110]Stepbolts Missing-Fit
FO_MISC |  | - | 900876939 | CLO | 1 | 3 | 2017CP-1[111]Stepbolts Missing-Fit
FO_MISC |  | - | 900876940 | CLO | 1 | 3 | 2017CP-1[130]Stepbolts Missing-Fit
FO_MISC |  | - | 900876941 | CLO | 1 | 3 | 2017CP-1[147]Stepbolts Missing-Fit
FO_MISC |  | - | 900876942 | CLO | 1 | 3 | 2017CP-1[167]Stepbolts Missing-Fit
FO_MISC |  | - | 900876943 | CLO | 1 | 3 | 2017CP-1[181]Stepbolts Missing-Fit
FO_MISC |  | - | 900876947 | DO | 1 | 3 | 2017CP-1[4]Earths Repair attach. point
FO_MISC |  | - | 900876948 | CLO | 1 | 3 | 2017CP-1[7]Off Plumb -Earth attach point
FO_MISC |  | - | 900876949 | DO | 1 | 3 | 2017CP-1[4]Earths Repair earth straps
FO_MISC |  | - | 900876950 | DO | 1 | 3 | 2017CP-1[6]Earths Reclip oxlip
FO_MISC |  | - | 900876951 | DO | 1 | 3 | 2017CP-1[7]Earths Reclip oxlip
FOSTRHW |  | - | 900898062 | DO | 1 | 3 | 2017HP-2[92]Check Structure Top Rot
FOSTRHW |  | - | 900898064 | DO | 1 | 3 | 2017HP-2[200]Check Structure Top Rot
FOINSHW |  |  | 901085553 | CLO | 1 | 4 | 2019HP-1[199]Insul&HW Replac check
OS | CUS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CUS | - |  | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CUSHALING T101 [Edenderry Power ED1]
TO-20-CUS-T101-01 ISO week: 28tu Date: 07 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUSHALING T103/5 [Edenderry Power ED3/ED5]
TO-20-CUS-T103/5-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - DALLOW T141 [SDCC]
TO-20-DAL-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 37 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 21 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL-T141-04 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 10 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL-T141-09 Status: Reference (Unscheduled)
CAPX |  |  | CP1057_OS | DO | 47 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL-T141-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 3 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL-T141-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL-T141-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL-T141-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 20 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee DALLOW
TO-20-DAL,T-DAL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-04 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-DAL-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-09 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL,T-DAL-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-DAL-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-DAL-1-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-DAL-1-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee PORTLAOISE
TO-20-DAL,T-PLS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-08 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | PLS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | PLS |  | 900965558 | DO | 3 | 1 | Moisture in LAs
CORRECT | PLS |  | 901072096 | DO | 3 | 1 | H6 , loose stripped cores in mech box ,
TO-20-DAL,T-PLS-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-PLS-1-03 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-PLS-1-01 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-PLS-1-04 ISO week: 39tu - 41mo Date: 22 Sep - 05 Oct Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-PLS-1-13 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee SHANNONBRIDGE
TO-20-DAL,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-SH-1-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-DAL,T-SH-1-11 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
TO-20-DAL,T-SH-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-SH-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-SH-1-04 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-SH-1-12 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
TO-20-DAL,T-SH-1-03 ISO week: 34mo - 38mo Date: 17 Aug - 14 Sep Duration: 29 Days (21 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-SH-1-06 ISO week: 41we - 48fr Date: 07 Oct - 27 Nov Duration: 52 Days (37 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084339 | DO | 1 | 4 | 2019HP-1[252]Bird Nests -Remove
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | SH | - | 901133675 | DO | 2 | 1 | T Phase DA Disconnect DUE: 17-Jul-20
CAPACITOR/SVC/REACTOR - DALTON CAP1
TO-20-DLT-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
TO-20-DLT-CAP1-02 Status: Unscheduled
CORRECT | DLT |  | 900945902 | CANC |  | 1 | Hot Spots Hot spot detected please refer
BUSBAR SECTION - DARNDALE 110 kV A1
TO-20-110 kV A1 @ DND-02 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
BUSBAR SECTION - DARNDALE 110 kV A2
TO-20-110 kV A2 @ DND-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
BUSBAR SECTION - DARNDALE 110 kV B1
TO-20-110 kV B1 @ DND-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
BUSBAR SECTION - DARNDALE 110 kV B2
TO-20-110 kV B2 @ DND-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-110 kV B2 @ DND-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110K1
TO-20-DND-110K1-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
COUPLER/SECTIONALISING CB - DARNDALE 110K2
TO-20-DND-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110K2-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110SA1-2CB
TO-20-DND-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110SA1-2CB-02 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
TO-20-DND-110SA1-2CB-03 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110SB1-2CB
TO-20-DND-110SB1-2CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013_OS | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110SB1-2CB-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
TO-20-DND-110SB1-2CB-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
GENERATOR TRANSFORMER - DERRYBRIEN T121 [Derrybrien DY1]
TO-20-DYN-T121-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-DYN-1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-DYN-T121-01 Status: Reference (Unscheduled)
CAPX |  |  | CP0824 | DO | 5 |  | As a consequence of AGL-DYN-1: Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-DYN-T121-03 ISO week: 37mo - 37sa Date: 07 Sep - 12 Sep Duration: 6 Days (5 WD) Status: Reference
As a consequence of AGL-DYN-110kV
SECTIONALISING DISCONNECT - DERRYIRON 110SA1
TO-20-DER-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-110SA2: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DER-110SA1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
OS | DER | SA1 | 901039703 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - DERRYIRON 110SA2
TO-20-DER-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
OS | DER | SA2 | 900666902 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-DER-110SA2-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-110SA1: 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DERRYIRON KINNEGAD
TO-20-DER-KIN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-DER-KIN-1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084275 | CLO | 1 | 4 | 2019HP-1[71]Bird Nests
CORRECT | DER |  | 900623151 | CLO | 1 | 1 | ESBI N01 non outage (important) Misc- wo
CORRECT | KIN |  | 901087474 | CLO | 1 | 2 | Measurement of copper conductor diameter
110kV FEEDER - DERRYIRON MAYNOOTH
TO-20-DER-MAY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | - | 901045929 | CANC | 3 | 1 | Investigate CB gas leak & repair if possible
TO-20-DER-MAY-1-01 ISO week: 39mo - 42fr Date: 21 Sep - 16 Oct Duration: 26 Days (20 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  |  |  | 2 |  | proximity needed of Derryiron - Maynooth for maintenance on Dunstown - Maynooth 2
FO_MISC |  |  | 901084970 | DO | 2 | 4 | 2019HP-1[4]Off Plumb -plumb poles
FO_MISC |  |  | 901084971 | DO | 2 | 4 | 2019HP-1[28]Off Plumb -plumb poles
FO_MISC |  |  | 901084972 | DO | 2 | 4 | 2019HP-1[29]Off Plumb -plumb poles
FO_MISC |  |  | 901084973 | DO | 2 | 4 | 2019HP-1[160]Off Plumb -plumb poles
FO_MISC |  |  | 901084974 | DO | 2 | 4 | 2019HP-1[161]Off Plumb -plumb poles
FO_MISC |  |  | 901084975 | DO | 2 | 4 | 2019HP-1[164]Off Plumb -plumb poles
FO_MISC |  |  | 901084976 | DO | 2 | 4 | 2019HP-1[181]Off Plumb -plumb poles
FO_MISC |  |  | 901084977 | DO | 2 | 4 | 2019HP-1[182]Off Plumb -plumb poles
FO_MISC |  |  | 901084978 | DO | 2 | 4 | 2019HP-1[183]Off Plumb -plumb poles
FOSTRHW |  |  | 901086429 | DO | 2 | 1 | 2019HP-1[75]Replace Pole only -Rot
FOSTRHW |  |  | 901086430 | DO | 2 | 1 | 2019HP-1[106]Replace Pole only -Rot
FOSTRHW |  |  | 901086431 | DO | 2 | 1 | 2019HP-1[124]Replace Pole only -Rot
PROX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Dunstown-Maynooth-2 220 kV
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
| - | Line | 901150823 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 116 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150824 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 117 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150825 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 118 need to be replaced by the autumn 2020 before winter storms commence.
OPT | DER |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY |  | 901080694 | DO | 3 | 2 | Missing Earths on Earths on CB
AMCAB | MAY | - | 900944029 | DO | 2 | 3 | Annual Insp. 110 Feeder OF Cable
GENERATOR TRANSFORMER - DERRYIRON RHODE T1/T2 [SSE Generation RP1/RP2]
TO-20-DER-T1/T2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
|  |  | PROT |  |  |  | P2 Protection maintenance of 7SA513
OPT | DER |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
110kV FEEDER - DERRYIRON THORNSBERRY
TO-20-DER-TSB-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DER-TSB-1-01 Status: Unscheduled
PROT |  |  |  | DO |  |  | P3 Protection maintenance of REL521
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
| - | 110 |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | DER | - | 900775276 | DO | 4 | 1 | 110kV SF6 Cubicle Ordinary Service
CA | DER | - | 900775914 | DO | 3 | 1 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - DROMADA T121 [Dromada DR1]
TO-20-DRO-T121-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | DRO | - | 901038511 | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - DRUMKEEN LETTERKENNY
TO-20-DRM-LET-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-DRM-LET-1-03 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
TO-20-DRM-LET-1-02 ISO week: 40tu Date: 29 Sep Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DRM | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - DRUMKEEN MEENTYCAT
TO-20-DRM-MEE-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
OS | DRM | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - DRUMLINE ENNIS
TO-20-DRU-ENN-1-02 ISO week: 46tu Date: 10 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Operator training
TO-20-DRU-ENN-1-01 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA511
TRAN |  | - | 900986381 | DO | 1 | 4 | 2018HP-1[18]Off PlumbPlumb poleset
TRAN |  | - | 900986388 | DO | 1 | 4 | 2018HP-1[75]Off PlumbPlumb poleset
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA1
TO-20-DRY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
OS | DRY | SA1 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-DRY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA2
TO-20-DRY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of DRY-110SA1: 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DRYBRIDGE GORMAN
TO-20-DRY-GOR-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085139 | DO | 2 | 4 | 2019HP-2[105]Vib Dampers -Replace
OS | DRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GOR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - DRYBRIDGE LOUTH
TO-20-DRY-LOU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-DRY-LOU-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | DRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - DRYBRIDGE PLATIN
TO-20-DRY-PLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | PLA |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-DRY-PLA-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DRYBRIDGE T141 [NDCC]
TO-20-DRY-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DUNDALK LOUTH
TO-20-DDK-LOU-1-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | DDK |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-DDK-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 901087469 | DO | 1 | 1 | EMP AMS Replace CB Counter
TO-20-DDK-LOU-1-03 Status: Unscheduled
CORRECT | DDK |  | 901082258 | CANC |  | 1 | N O 1 Louth H4 (Mal)Louth DL Fault
110kV FEEDER - DUNDALK MULLAGHARLIN
TO-20-DDK-MLN-1-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
DISTRIBUTION TRANSFORMER - DUNFIRTH T122 [NDCC]
TO-20-DFR-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR-T122-02 Status: Reference (Unscheduled)
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee DUNFIRTH
TO-20-DFR,T-DFR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR,T-DFR-1-02 Status: Unscheduled
[5 empty] | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee KINNEGAD
TO-20-DFR,T-KIN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | KIN | - | 901042225 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-DFR,T-KIN-1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-DFR,T-KIN-1-03 Status: Unscheduled
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee RINAWADE
TO-20-DFR,T-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DFR,T-RNW-1-01 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | RNW | - |  | DO | 10 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - DUNGARVAN 110SA1
TO-20-DGN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | DGN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - DUNGARVAN WOODHOUSE
TO-20-DGN-WOH-1-01 ISO week: 47th - 48th Date: 19 Nov - 26 Nov Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | DGN | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | WOO | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - DUNMANWAY 110SA1-2CB
TO-20-DMY-110SA1-2CB-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-110SA1-2CB-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-110SA1-2CB-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-DMY-110SA1-2CB-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-110SA1-2CB-02 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
OS | DMY | 110-SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
CAPACITOR/SVC/REACTOR - DUNMANWAY CAP2
TO-20-DMY-CAP2-01 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | DMY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-DMY-CAP2-02 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
110kV FEEDER - DUNMANWAY MACROOM
TO-20-DMY-MAC-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-DMY-MAC-1-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-DMY-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-DMY-MAC-1-10 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-MAC-1-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-MAC-1-07 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-MAC-1-04 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
TRAN |  | - | 900986469 | DO | 1 | 4 | 2018HP-1[84]Off PlumbPlumb poles
TRAN |  | - | 901148535 | DO | 1 | 1 | Oxlip earth position movement
Work on Location 124 to stop tripping
OPT | DMY | - | 901058948 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | MAC | - | 901050325 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - DUNMANWAY T141 [SDCC]
TO-20-DMY-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-T141-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-T141-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-T141-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DUNMANWAY T142 [SDCC]
TO-20-DMY-T142-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
BUSBAR SECTION - DUNSTOWN 220 kV A1
TO-20-220 kV A1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV A2
TO-20-220 kV A2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV B1
TO-20-220 kV B1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV B2
TO-20-220 kV B2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover
COUPLER/SECTIONALISING CB - DUNSTOWN 220K1-2
TO-20-DSN-220K1-2-01 ISO week: 46tu - 47th Date: 10 Nov - 19 Nov Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | DSN | 220-SA | 901080785 | DO | 5 | 1 | Replace stolen earths
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OPT | DSN | - | 901038890 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | DSN | 220-SA | 901039168 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | DSN | 220-SB | 901039169 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
BUSBAR SECTION - DUNSTOWN 400 kV A1
TO-20-400 kV A1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 400 kV A2
TO-20-400 kV A2 @ DSN-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover
TO-20-400 kV A2 @ DSN-02 ISO week: 38we - 38fr Date: 16 Sep - 18 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 3 |  | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI).
TO-20-400 kV A2 @ DSN-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
BUSBAR SECTION - DUNSTOWN 400 kV B1
TO-20-400 kV B1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 400 kV B2
TO-20-400 kV B2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover
COUPLER/SECTIONALISING CB - DUNSTOWN 400K1-2
TO-20-DSN-400K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | DSN |  | 900444678 | NS |  | 2 | O. ESBI Inspect and test all the cylind
TO-20-DSN-400K1-2-01 ISO week: 33mo - 35fr Date: 10 Aug - 28 Aug Duration: 19 Days (15 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | DSN | - |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CORRECT | DSN |  | 900531917 | DO | 5 | 2 | Inspect and test all the cylinders, pist
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OS | DSN | 400-SB |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-SA |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEB2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEB1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEA2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEA1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
220kV FEEDER - DUNSTOWN KELLIS
TO-20-DSN-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1017 | DO | 7 |  | Proximity outage for stringing of Donard Test Line
TO-20-DSN-KLS-1-03 Status: Unscheduled
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Great Island-Kellis 220 kV
TO-20-DSN-KLS-1-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Replace stolen earths
FO_MISC |  |  | 901084901 | DO | 2 | 4 | 2019HP-1[39]Insulator Strain insul
FOINSHW |  |  |  |  | 1 |  | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  |  |  |  | 1 |  | 2017HP-1[103]Anti-Cl. Guard fit
FOINSHW |  | - | 900819574 | DO | 1 | 2 | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  | - | 900898068 | DO | 1 | 3 | 2017HP-1[103]Anti-Cl. Guard fit
TRAN |  | - | 900986534 | DO | 1 | 4 | 2018HP-1[39]Insulatorbroken insulator
TRAN |  | - | 900986536 | DO | 1 | 4 | 2018HP-1[173]Earths-Replace-Earth Strap
TRAN |  | - | 900986537 | DO | 1 | 4 | 2018HP-1[174]Earths-Replace-Earth Strap
TRAN |  | - | 900986538 | DO | 1 | 4 | 2018HP-1[176-177]Vib Dampers-EW damper
TRAN |  | - | 900986539 | DO | 1 | 4 | 2018HP-1[178-179]Vib Dampers-EW damper
CORRECT | DSN |  | 900444600 | DO | 5 | 2 | O. ESBI Inspect and test all the cylind
CORRECT | DSN |  | 900566652 | DO | 2 | 2 | ESBI 01. VT Insulation retest Important
CM | DSN | - | 900719181 | DO | 2 | 2 | 2[140,143] Replace bent/damaged steel member
FM | DSN | - | 901045782 | DO | 2 | 4 | HV Pressure Vessel Inspection
OPT | DSN | - | 900955895 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
OPT | KLS | - | 900955894 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - DUNSTOWN MAYNOOTH 1
TO-20-DSN-MAY-1-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900986540 | DO | 4 | 4 | 2018HP-1[1]Insulatorfit dups on lead ins
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA513, 7SL32
CORRECT | DSN | - | 901080780 | CLO | 5 | 1 | Replace stolen earths
FM | DSN | - | 901043824 | DO | 1 | 4 | HV Pressure Vessel Inspection
CM | MAY | - | 901076413 | CLO | 3 | 1 | Copper earths stolen from 220kV DE and CTs to be reinstalled
FO_MISC | MAY |  | 901084902 | DO | 2 | 2 | 2019HP-1[Stn]Insulator BB in Maynooth
CORRECT | MAY |  | 901080649 | CLO |  | 2 | Oil Gauges To Be Cleaned
220kV FEEDER - DUNSTOWN MAYNOOTH 2
TO-20-DSN-MAY-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOINSHW |  | - | 900483534 | CANC | 2 | 1 | 2[77&am 78]Insulator fit duplicate. Proximity outage of Derryiron-Maynooth 110kV required
CM | DSN | - | 900943761 | NS | 5 |  | Replace Cylinders
CORRECT | DSN | - | 901080781 | CANC | 5 | 1 | Replace stolen earths
TO-20-DSN-MAY-2-01 ISO week: 41mo - 43fr Date: 05 Oct - 23 Oct Duration: 19 Days (15 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900986545 | DO | 1 | 4 | 2018HP-1[14]Insulatorbroken
TRAN |  | - | 900986550 | DO | 1 | 4 | 2018HP-1[39]Insulatorfit duplicates
TRAN |  | - | 900986551 | DO | 1 | 4 | 2018HP-1[40]Insulatorfit duplicates
TRAN |  | - | 900986552 | DO | 1 | 4 | 2018HP-1[57-57A]Conflicts-fit guard wire
TRAN |  | - | 900986554 | DO | 1 | 4 | 2018HP-1[77]Insulatorfit duplicates
TRAN |  | - | 900986555 | DO | 1 | 4 | 2018HP-1[78]Insulatorfit duplicates
FO_MISC |  |  | 901084903 | DO | 1 | 2 | 2019HP-1[14]Insulator Broken C/ph
OS | DSN | - | 901042331 | DO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
CA | DSN | - | 901038532 | DO | 3 | 1 | 220kV Cubicle Condition Assessment
OS | MAY | - | 901042332 | DO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
400kV FEEDER - DUNSTOWN MONEYPOINT GIS
TO-20-DSN-MP GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0873 | DO | 50 |  | EI: Line refurb works
CORRECT | DSN |  | 900531814 | DO | 5 | 2 | Inspect and test all the cylinders, pist
TO-20-DSN-MP GIS-1-03 Status: Unscheduled
FO_MISC |  |  | 901084904 | DO | 2 | 4 | 2019HP-1[361]Insulator Broken
FO_MISC |  |  | 901084905 | DO | 2 | 4 | 2019HP-1[371]Insulator Broken
FO_MISC |  |  | 901084906 | DO | 2 | 4 | 2019HP-1[396]Insulator Broken
FO_MISC |  |  | 901084907 | DO | 2 | 4 | 2019HP-1[402]Insulator Broken
FO_MISC |  |  | 901084908 | DO | 2 | 4 | 2019HP-1[410]Insulator Broken
FO_MISC |  |  | 901084909 | DO | 2 | 4 | 2019HP-1[486]Insulator Broken
FO_MISC |  |  | 901084910 | DO | 2 | 4 | 2019HP-1[563]Insulator Broken
FO_MISC |  |  | 901084911 | DO | 2 | 4 | 2019HP-1[564]Insulator Broken
TRAN |  | - | 900986826 | DO | 1 | 4 | 2018HP-1[214]ACGFit ACG
FO_MISC |  |  | 901084407 | DO | 1 | 4 | 2019HP-1[331]Bird Nests
FO_MISC |  |  | 901084408 | DO | 1 | 4 | 2019HP-1[567]Bird Nests
TRAN |  | - | 900986733 | NS |  | 1 | 2018HP-1[371]Bird Nestsremove asap
TRAN |  | - | 900986835 | NS |  | 1 | 2018HP-1[238]Bird Nestsremove asap
CORRECT | DSN | - | 901038719 | DO | 21 | 2 | Dunstown R4001 Reactor: Refurbush Reactor, regasket & paint
CORRECT | DSN |  | 900444627 | NS |  | 2 | O. ESBI Inspect and test all the cylinde
CORRECT | DSN |  | 900489556 | NS |  | 2 | O. ESBI Inspect and test all the cylind
CM | DSN | 400-R4001 | 900690047 | NS |  | 1 | O/1 R4001 DRYCOL INTERNAL FAULT
FM | MP | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TO-20-DSN-MP GIS-1-02 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Tentative
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FM | DSN | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TRANSFORMER - DUNSTOWN T4201
TO-20-DSN-T4201-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | DSN | TRAFO | 901038718 | CLO | 7 | 2 | Dunstown T4201: Refurb work on OLTC diverters and remove elemental sulphur Look at long term plan for this trafo with Eirgrid Install on line IDD/Camlin bushing monitor Long outage required in refurb is being done. Fit bushing monitor (HV and LV)
TO-20-DSN-T4201-03 Status: Unscheduled
CM | DSN | TRAFO | 901133926 | DO | 14 | 1 | Partial Discharge Test on T4201. Use OD1385.
CA | DSN | 220 | 901038531 | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT - Use OD1385
TRAFO | DSN | TRAFO | 901146361 | DO | 3 | 1 | 400/220kV Trafo Tap Changer Inspection. Use OD1385.
TO-20-DSN-T4201-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SL24, 7SL24, 7UT22
CA | DSN | 400 | 901129262 | DO | 3 | 4 | 400KV CUBICLE CONDITION ASSESSMENT Use OD1385
CORRECT | DSN | - | 900533460 | CLO | 1 | 1 | ESBI 0 1 - A Siemens transformer test sp
CORRECT | DSN | - | 900534083 | CLO | 1 | 1 | ESBI 01 outage required. A Siemens senio
CORRECT | DSN | TRAFO | 900546841 | CLO | 1 | 1 | Replace contacts in the trafo
CORRECT | DSN | - | 900606811 | NS | 1 | 2 | ESBI 01 outage required (important)Misc-
CORRECT | DSN | - | 900781800 | CLO | 1 | 1 | ESBI01 GE are to repair and recommission
CORRECT | DSN |  | 900543177 | NS |  | 2 | Earth Winding externally to facilitate t
CORRECT | DSN |  | 900543178 | NS |  | 2 | Online Oil Regen required due to high le
TO-20-DSN-T4201-01 ISO week: 12we - 16th Date: 18 Mar - 16 Apr Duration: 30 Days (20 WD) Status: Scheduled
|  | - |  |  | 25 |  | Total Maintenance Outage Duration Requested
OS | DSN | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | DSN | 220 | 901042340 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | DSN | 400 | 901130035 | CLO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
TRAFO | DSN | TRAFO | 901146154 | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1385.
CORRECT | DSN | - | 901045931 | CLO | 3 | 1 | Investigate CB gas leak & repair if possible
FM | DSN | - |  | NS | 1 | 4 | HV Pressure Vessel Inspection
FM | DSN | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | DSN | 220 | 901045943 | NS | 1 | 4 | Oil Sampling - VT's UTF245 ESBI
OS | DSN | TRAFO | 901130061 | CLO |  | 4 | 400/220kV Transformer Ordinary Service
TRANSFORMER - DUNSTOWN T4202
TO-20-DSN-T4202-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0316 | DO | 15 |  | Stand new equipment, install new post insulators and string new T4202 bay conductor as far as the 400 kV CB.
CAPX |  |  | MC0316 | DO | 3 |  | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI).
TO-20-DSN-T4202-02 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | DSN | - | 901080786 | DO | 4 | 1 | Replace stolen earths
OPT | DSN | 220 | 901038892 | DO | 3 | 3 | 220kV SF6 Cubicle Operational Test
OPT | DSN | TRAFO | 901045409 | DO | 3 | 3 | 400/220kV Transformer Operational Test
OPT | DSN | 400 | 901045732 | DO | 3 | 3 | 400kV SF6 Cubicle Operational Test
TO-20-DSN-T4202-03 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
220kV FEEDER - DUNSTOWN TURLOUGH HILL
TO-20-DSN-TH-1-02 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| TH |  |  |  | 1 |  | Relay Replacement at TH
TO-20-DSN-TH-1-01 ISO week: 9we - 10fr Date: 26 Feb - 06 Mar Duration: 10 Days (8 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
TRAN |  | - | 900986853 | CLO | 2 | 4 | 2018HP-1[39]Insulatorbroken
TRAN |  | - | 900986859 | CLO | 2 | 4 | 2018HP-1[82]Insulatorbroken
FO_MISC |  |  | 901084913 | CLO | 2 | 2 | 2019HP-1[45]Insulator Broken L/ph
CORRECT | DSN | - | 901080783 | CLO | 4 | 1 | Replace stolen earths
OPT | DSN | - | 901038891 | CLO | 1 | 3 | 220kV SF6 Cubicle Operational Test
AMCAB | TH | - | 900913182 | DO | 2 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | TH | - | 901038978 | CLO | 1 | 3 | 220kV MO Cubicle Operational Test
CORRECT | TH |  | 901083956 | DO | 1 | 2 | Misc- CT R-Phase cover to be refitted du
COUPLER/SECTIONALISING CB - ENNIS 110SA1-2CB
TO-20-ENN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
TO-20-ENN-110SA1-2CB-02 Status: Unscheduled
CORRECT | ENN | - | 901045923 | CANC | 0 | 1 | Investigate CB gas leak & repair if possible
110kV FEEDER - ENNIS SLIEVECALLAN
TO-20-ENN-SLC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | ENN | - | 901134782 | CLO | 2 | 1 | S Phase Slievecallan 110kv Cubicle. S phase se connectio hotspot n DUE : IMMEDIATELY
AMCAB | ENN | - | 901076133 | NS | 0 | 4 | Cable Insp. 110kV XLPE
TO-20-ENN-SLC-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CM | SLC | - | 901134796 | CLO | 2 | 1 | S Phase Ennis 110kv Cubicle. S Phase cable end bushing connectio hotspot DUE : 17-Jul-20 hotspot
CM | SLC | 110-DL/DE | 901134797 | CLO | 2 | 1 | R & S Phases Ennis 110kV cubicle. R & S Phase DL/DE DUE : 17-Aug-20hotspot
DISTRIBUTION TRANSFORMER - ENNIS T142 [SDCC]
TO-20-ENN-T142-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage requested by ESBN. DOF required following CA on T142 110kV cubicle
BUSBAR SECTION - FINGLAS 110 kV A1
TO-20-110 kV A1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A2
TO-20-110 kV A2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A3
TO-20-110 kV A3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B1
TO-20-110 kV B1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B2
TO-20-110 kV B2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B3
TO-20-110 kV B3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS 110K1-2
TO-20-FIN-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901038699 | DO | 1 | 3 | 110kV MO Cubicle Operational Test
OPT | FIN | 110-SB2 | 901039137 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SB1 | 901039138 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SA2 | 901039139 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SA1 | 901039140 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - FINGLAS 110K2-3
TO-20-FIN-110K2-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | FIN | - |  | DO | 6 | 4 | 110kV GIS Cubicle Ordinary Service
OS | FIN | 110-SB4 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SB3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SA4 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - FINGLAS 220 kV A1
TO-20-220 kV A1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV A2
TO-20-220 kV A2 @ FIN-11 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV B1
TO-20-220 kV B1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV B2
TO-20-220 kV B2 @ FIN-11 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS 220K1-2
TO-20-FIN-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901038696 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | FIN | 220-SA | 901039135 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | FIN | 220-SB | 901039136 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
CORRECT | FIN | - | 901046377 | DO | 1 | 1 | Investigate sync close of 220 kV couple K1 CB. CB Direct Closed. Angle difference <1 deg and voltage difference <0.5 kV.
BUSBAR SECTION - FINGLAS GIS 110 kV A1
TO-20-110 kV A1 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A2
TO-20-110 kV A2 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A3
TO-20-110 kV A3 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A4
TO-20-110 kV A4 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A5
TO-20-110 kV A5 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A6
TO-20-110 kV A6 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B1
TO-20-110 kV B1 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B2
TO-20-110 kV B2 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B3
TO-20-110 kV B3 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B4
TO-20-110 kV B4 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B5
TO-20-110 kV B5 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B6
TO-20-110 kV B6 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K1
TO-20-FIN GIS-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901043767 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-FIN GIS-110K1-02 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K2
TO-20-FIN GIS-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K5
TO-20-FIN GIS-110K5-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K6
TO-20-FIN GIS-110K6-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA1-2CB
TO-20-FIN GIS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA1-3CB
TO-20-FIN GIS-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA2-4CB
TO-20-FIN GIS-110SA2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA3-5CB
TO-20-FIN GIS-110SA3-5CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA4-6CB
TO-20-FIN GIS-110SA4-6CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB1-2CB
TO-20-FIN GIS-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB1-3CB
TO-20-FIN GIS-110SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB2-4CB
TO-20-FIN GIS-110SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB3-5CB
TO-20-FIN GIS-110SB3-5CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB4-6CB
TO-20-FIN GIS-110SB4-6CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
110kV FEEDER - FINGLAS GIS GLASMORE [NDCC]
TO-20-FIN GIS-GLA-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | FIN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - FINGLAS GIS T2101
TO-20-FIN GIS-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | FIN | 220 | 901038497 | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | FIN | TRAFO | 901042114 | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | FIN |  | 901080725 | DO | 2 | 2 | T2101 220KV CB Over Pressure
TRANSFORMER - FINGLAS GIS T2104
TO-20-FIN GIS-T2104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN |  | 900852318 | NS |  | 2 | Hotspot repair S phase 220KV VT connecti
TRANSFORMER - FINGLAS GIS T2106
TO-20-FIN GIS-T2106-01 ISO week: 20mo - 31mo Date: 11 May - 27 Jul Duration: 78 Days (55 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | FIN | 110 | 901129786 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CORRECT | FIN | - | 900973442 | DO | 3 | 2 | ESBI Replace faulty isolation valve on S
OPT | FIN | TRAFO | 901045418 | CLO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | FIN | 220 | 901129542 | CLO | 3 | 3 | 220kV SF6 Cubicle Operational Test
CORRECT | FIN |  | 901059907 | CLO |  | 2 | Investigate Hydran alarms not working
220kV FEEDER - FINGLAS HUNTSTOWN
TO-20-FIN-HN-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN | - | 900479248 | CANC | 3 | 2 | HUNTSTOWN 220KV DL PI IN EIRGRID WHEN DL
TO-20-FIN-HN-1-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | FIN |  | 901076401 | DO | 3 | 1 | Replace CB counter/ complete CA on VT's & SA's
CM | HUN | 220-DL | 901128554 | DO | 2 | 1 | T Phase Hotspot on T phase DL/DE disconnect DUE : 17-Jul-20
220kV FEEDER - FINGLAS NORTH WALL
TO-20-FIN-NW-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
TO-20-FIN-NW-1-02 Status: Unscheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | FIN | - | 901042333 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | FIN | 220 | 901038498 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OPT | NW | - | 901039120 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - FINGLAS SHELLYBANKS
TO-20-FIN-SHL-1-04 ISO week: 37fr - 37su Date: 11 Sep - 13 Sep Duration: 3 Days (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay
Switching to start at 18:00 11 Sept
TO-20-FIN-SHL-1-05 ISO week: 39we - 39fr Date: 23 Sep - 25 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outage required to remove scaffolding at the new Belcamp bay.
TO-20-FIN-SHL-1-01 ISO week: 11fr - 22fr Date: 13 Mar - 29 May Duration: 78 Days (52 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 10 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TRANSFORMER - FINGLAS T2103
TO-20-FIN-T2103-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN | TRAFO | 901039279 | CANC | 1 | 2 | Finglas T2103 Transformer: Drycol Replacement
TRANSFORMER - FINGLAS T2104
TO-20-FIN-T2104-01 ISO week: 38mo - 49fr Date: 14 Sep - 04 Dec Duration: 82 Days (59 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | FIN | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | FIN | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | FIN | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | FIN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRAFO | FIN | TRAFO |  | DO |  | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | FIN | TRAFO |  | DO |  | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | FIN |  | 900474794 | DO |  | 2 | 0. 1. ESBI CB - Abnormal timing results
BUSBAR SECTION - FLAGFORD 110 kV A1
TO-20-110 kV A1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-110 kV A1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-110 kV A1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-110 kV A1 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-110 kV A1 @ FLA-05 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 110 kV A2
TO-20-110 kV A2 @ FLA-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV A2 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-110 kV A2 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-110 kV A2 @ FLA-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-110 kV A2 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
BUSBAR SECTION - FLAGFORD 110 kV B1
TO-20-110 kV B1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-110 kV B1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-110 kV B1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-110 kV B1 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-110 kV B1 @ FLA-05 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 110 kV B1/B2
TO-20-110 kV B1/B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
BUSBAR SECTION - FLAGFORD 110 kV B2
TO-20-110 kV B2 @ FLA-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV B2 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-110 kV B2 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-110 kV B2 @ FLA-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-110 kV B2 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
COUPLER/SECTIONALISING CB - FLAGFORD 110K1-2
TO-20-FLA-110K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
CAPX |  |  | CP1031 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV coupler bay at flagford station
TO-20-FLA-110K1-2-03 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | FLA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | FLA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | FLA | 110-SB |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FLA | 110-SA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-FLA-110K1-2-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder
BUSBAR SECTION - FLAGFORD 220 kV A1
TO-20-220 kV A1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB
TO-20-220 kV A1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-220 kV A1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-220 kV A1 @ FLA-04 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV A2
TO-20-220 kV A2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB
TO-20-220 kV A2 @ FLA-02 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV B1
TO-20-220 kV B1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-220 kV B1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-220 kV B1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-220 kV B1 @ FLA-04 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV B1/B2
TO-20-220 kV B1/B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
BUSBAR SECTION - FLAGFORD 220 kV B2
TO-20-220 kV B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - FLAGFORD 220K1-2
TO-20-FLA-220K1-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-220K1-2-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder
TO-20-FLA-220K1-2-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
CAPX |  |  | CP1031 | DO | 34 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the 220 kV coupler bay at flagford station
TO-20-FLA-220K1-2-04 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 901068587 | DO | 3 | 1 | O1 R phase pantograph on 220kV coupler s
110kV FEEDER - FLAGFORD GILRA
TO-20-FLA-GIL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
[5 empty] | 1 |  | Extra day required for covid restrictions
OS | FLA | - | 901129904 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
220kV FEEDER - FLAGFORD LOUTH
TO-20-FLA-LOU-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the Louth 220 kV bay at flagford station
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB
TO-20-FLA-LOU-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder
TO-20-FLA-LOU-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder
TO-20-FLA-LOU-1-01 ISO week: 38mo - 41fr Date: 14 Sep - 09 Oct Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0867 | DO | 40 |  | Outage to enable refurbishment of OHL, Remove ground proximity clearances and tower reinforcements
|  | - |  |  | 13 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Outage for timber cutting. RC 3 days request
FO_MISC |  |  | 901084409 | DO | 1 | 4 | 2019HP-1[4]Bird Nests
FO_MISC |  |  | 901084410 | DO | 1 | 4 | 2019HP-1[25]Bird Nests
FO_MISC |  |  | 901084411 | DO | 1 | 4 | 2019HP-1[38]Bird Nests
FO_MISC |  |  | 901084412 | CLO | 1 | 4 | 2019HP-1[192]Bird Nests
FO_MISC |  |  | 901084915 | DO | 1 | 4 | 2019HP-1[65]Insulator Broken R/ph
FO_MISC |  |  | 901084916 | DO | 1 | 4 | 2019HP-1[156]Insulator Broken C/ph
FOMISC | FLA | - | 900566631 | DO | 4 | 1 | Install Game Guards
OS | LOU | - | 901042380 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038537 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - FLAGFORD SLIABH BAWN
TO-20-FLA-SLB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV flagford Sliabh Bawn bay at flagford station
TO-20-FLA-SLB-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-FLA-SLB-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-FLA-SLB-1-05 Status: Unscheduled
SAG6_HV | - | Line | 901160383 | DO | 2 | 1 | SPAN 1-2 of 0.98m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160384 | DO | 2 | 1 | SPAN 15-16 of 0.76m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160385 | DO | 2 | 1 | SPAN 16-17 of 1.99m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160386 | DO | 2 | 1 | SPAN 19-20 of 2.75m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160387 | DO | 2 | 1 | SPAN 31-32 of 0.92m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160388 | DO | 2 | 1 | SPAN 46-47 of 2.52m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160389 | DO | 2 | 1 | SPAN 76-77 of 2.23m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160390 | DO | 2 | 1 | SPAN 95-96 of 0.34m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160391 | DO | 2 | 1 | SPAN 1-2 of 0.43m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160392 | DO | 2 | 1 | SPAN 15-16 of 0.91m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160393 | DO | 2 | 1 | SPAN 16-17 of 2.58m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160394 | DO | 2 | 1 | SPAN 19-20 of 3.69m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160395 | DO | 2 | 1 | SPAN 31-32 of 1.63m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160396 | DO | 2 | 1 | SPAN 46-47 of 3.89m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160397 | DO | 2 | 1 | SPAN 60-61 of 0.10m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160398 | DO | 2 | 1 | SPAN 76-77 of 2.48m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160399 | DO | 2 | 1 | SPAN 95-96 of 0.90m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
TO-20-FLA-SLB-1-06 Status: Unscheduled
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 44-45
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 43-44
TO-20-FLA-SLB-1-04 ISO week: 32tu - 35fr Date: 04 Aug - 28 Aug Duration: 25 Days (19 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987019 | DO | 1 | 4 | 2018HP-1[Am 64]Bird Nests
FO_MISC |  |  | 901084413 | DO | 1 | 4 | 2019HP-1[64]Bird Nests
OS | FLA | - | 901050316 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | SLB | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - FLAGFORD SLIGO
TO-20-FLA-SLI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford sligo 110 kV bay at flagford station
OPT | SLI | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-FLA-SLI-1-05 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-FLA-SLI-1-06 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
220kV FEEDER - FLAGFORD SRANANAGH
TO-20-FLA-SRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-SRA-1-02 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 900891647 | DO | 3 | 1 | O1 Srananagh 220kV DE (R phase) earthing
OPT | FLA | - | 900942345 | DO | 3 | 2 | 220kV SF6 Cubicle Operational Test
OPT | SRA | - | 900942726 | DO | 3 | 2 | 220kV SF6 Cubicle Operational Test
TRANSFORMER - FLAGFORD T2101
TO-20-FLA-T2101-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-T2101-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 60 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the T2101 220 kV bay at flagford station
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous FLA-T2101 + FLA-T2101: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV T2101 bay at flagford station
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-FLA-T2101-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder
TO-20-FLA-T2101-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-FLA-T2101-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-FLA-T2101-07 Status: Unscheduled
CORRECT | FLA |  | 900907922 | CANC |  | 2 | Allow 1 additional week for detailed mai
TO-20-FLA-T2101-06 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 900909437 | DO | 3 | 2 | Camlin Power are to supply & install a n
OPT | FLA | 110 |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | FLA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | FLA | 220 |  | DO | 1 | 4 | 220kV MO Cubicle Operational Test
TRANSFORMER - FLAGFORD T2102
TO-20-FLA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | FLA | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | FLA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | FLA | 220 | 901080658 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-FLA-T2102-02 Status: Unscheduled
CORRECT | FLA | TRAFO | 900463619 | CANC | 1 | 2 | O 1 ESBI Replace three 220kV and 110kV b
COUPLER/SECTIONALISING CB - GALWAY 110K1-2
TO-20-GAL-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-2-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K1-3
TO-20-GAL-110K1-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K2-3
TO-20-GAL-110K2-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K2-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
110kV FEEDER - GALWAY KNOCKRANNY
TO-20-GAL-KNY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
TO-20-GAL-KNY-1-01 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GAL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
CORRECT | GAL |  | 901080915 | CLO | 1 | 1 | O1 Knockranny CB low gas
110kV FEEDER - GALWAY SALTHILL
TO-20-GAL-SAL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
TO-20-GAL-SAL-1-01 ISO week: 45mo - 45tu Date: 02 Nov - 03 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612, GRL100
OPT | GAL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | SAL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GALWAY T101 [SDCC]
TO-20-GAL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
DISTRIBUTION TRANSFORMER - GALWAY T102 [SDCC]
TO-20-GAL-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T141 [SDCC]
TO-20-GAL-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - GALWAY T142 [SDCC]
TO-20-GAL-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T143 [SDCC]
TO-20-GAL-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
COUPLER/SECTIONALISING CB - GARROW 110SA1-2CB
TO-20-GRO-110SA1-2CB-01 ISO week: 26tu - 26we Date: 23 Jun - 24 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | GRO |  | 901129711 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | GRO | 110-SA1 | 901130110 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | GRO | 110-SA2 | 901130111 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - GARROW T122 [Coomacheo CZ1]
TO-20-GRO-T122-01 ISO week: 26tu - 26we Date: 23 Jun - 24 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GRO |  | 901129713 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - GARVAGH 110 kV A1
TO-20-110 kV A1 @ GRV-01 ISO week: 24th Date: 11 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GARVAGH 110 kV B1
TO-20-110 kV B1 @ GRV-01 ISO week: 24th Date: 11 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - GARVAGH 110K1
TO-20-GRV-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ GRV: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ GRV: Busbar Changeover
TO-20-GRV-110K1-02 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Corderry-Garvagh 110 kV
DISTRIBUTION TRANSFORMER - GARVAGH T141 [SDCC]
TO-20-GRV-T141-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Corderry-Garvagh 110 kV
TSO CUSTOMER TRANSFORMER - GILRA T121 [Masonite]
TO-20-GIL-T121-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Flagford-Gilra 110 kV
COUPLER/SECTIONALISING CB - GLANAGOW 220K1-2
TO-20-GGO-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GGO | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | GGO | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | GGO | 220-SB1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GGO | 220-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
220kV FEEDER - GLANAGOW RAFFEEN
TO-20-GGO-RAF-1-01 ISO week: 35mo - 36mo Date: 24 Aug - 31 Aug Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | GGO | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | GGO | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | RAF | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | RAF | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | RAF |  | 901028746 | DO |  | 2 | O1-220kv Cable sealing ends moss build u
GENERATOR TRANSFORMER - GLANAGOW T2001 [Bord Gáis WG1]
TO-20-GGO-T2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-GGO-T2001-02 ISO week: 35we Date: 26 Aug Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | GGO | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | GGO |  | 900951244 | DO |  | 2 | O1- T2001 Protection Maintenance
GENERATOR TRANSFORMER - GLANLEE T121 [Glanlee GL1]
TO-20-GAE-T121-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | GAE | - | 900973585 | DO | 1 | 2 | AC and DC Supplies:
OPT | GAE |  | 901129611 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GLENLARA KNOCKACUMMER [Mountain Lodge ML1]
TO-20-GLE-KCR-1-01 ISO week: 34mo - 34fr Date: 17 Aug - 21 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 5 | 4 | Cable Insp. 110kV XLPE
OPT | GLE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KCR | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - GLENREE 110SA1-2CB
TO-20-GLR-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | GLR | 110-SA2 | 901130245 | CANC | 2 | 2 | 110kV Sect / Dist Ordinary Service
TO-20-GLR-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | GLR | 110-SA1 | 901130243 | CANC | 2 | 2 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - GLENREE MOY
TO-20-GLR-MOY-1-01 ISO week: 10mo - 43th Date: 02 Mar - 22 Oct Duration: 235 Days (163 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
CM | GLR | - | 901129078 | CLO | 10 | 1 | Repair SF6 leak on CB (ref. FO Mar 2019)
OPT | GLR | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | GLR |  | 901058978 | CLO | 1 | 2 | ESB EMP MO raised for PO. Stephen West.
DISTRIBUTION TRANSFORMER - GLENREE T142 [NDCC]
TO-20-GLR-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
GENERATOR TRANSFORMER - GOLAGH T101 [Golagh GOL1]
TO-20-GOL-T101-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Full tee outage for work on Golagh tee Letterkenny
110kV FEEDER - GOLAGH tee CLOGHER
TO-20-GOL,T-CLO-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CLO | - |  | DO | 1 | 4 | Cable Insp. 110kV XLPE
OPT | CLO | - | 901045434 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
110kV FEEDER - GOLAGH tee GOLAGH
TO-20-GOL,T-GOL-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GOL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
FOFAULT | GOL | - | 900955641 | DO | 1 | 1 | flicker light on SMD o/o/o
110kV FEEDER - GOLAGH tee LETTERKENNY
TO-20-GOL,T-LET-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
CM | LET | - | 900720114 | DO | 10 | 2 | 1[142] Carry out ancillary works at Mast
OS | LET | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | LET | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | LET |  | 900952946 | DO | 3 | 1 | moisture in H8 surge arrestors
BUSBAR SECTION - GORMAN 110 kV A1
TO-20-110 kV A1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV A2
TO-20-110 kV A2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV B1
TO-20-110 kV B1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV B2
TO-20-110 kV B2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - GORMAN 110K1-2
TO-20-GOR-110K1-2-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | GOR | - | 900776802 | CLO | 3 | 2 | Complete Siemens CB mod
CORRECT | GOR | - | 900693010 | DO | 1 | 2 | Install interlocking coils.
BUSBAR SECTION - GORMAN 220 kV A1
TO-20-220 kV A1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 220 kV B1
TO-20-220 kV B1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 220 kV B2
TO-20-220 kV B2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
220kV FEEDER - GORMAN LOUTH
TO-20-GOR-LOU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084278 | DO | 1 | 4 | 2019HP-1[75]Bird Nests
OPT | GOR | - | 901068548 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OS | LOU | - | 901050444 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
220kV FEEDER - GORMAN MAYNOOTH
TO-20-GOR-MAY-1-01 ISO week: 17mo - 19fr Date: 20 Apr - 08 May Duration: 19 Days (14 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819639 | DO | 2 | 3 | 2016HP-1[141]Insulator Check on gantry
TRAN |  | - | 900987259 | DO | 1 | 4 | 2018HP-1[136]Check Struct/Found/etc-Base
OS | GOR | - | 900943466 | DO | 5 | 3 | 220kV SF6 Cubicle Ordinary Service
OS | MAY | - | 900943354 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CM | MAY | - | 901076414 | CLO | 4 | 1 | Copper earths stolen from 220kV CT, VT and chokes to be reinstalled
CORRECT | MAY |  | 901080652 | CANC | 1 | 1 | Low Oil / Leak- T Phase Oil Looks Low
110kV FEEDER - GORMAN MEATH HILL
TO-20-GOR-MTH-1-01 ISO week: 12th Date: 19 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MTH |  | 901117748 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 1
TO-20-GOR-NAV-1-01 ISO week: 12we Date: 18 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | NAV |  | 901129624 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 2
TO-20-GOR-NAV-2-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GOR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | NAV |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 3
TO-20-GOR-NAV-3-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
AMCAB | GOR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | NAV | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - GORMAN PLATIN
TO-20-GOR-PLA-1-01 ISO week: 12fr Date: 20 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | PLA |  | 901129660 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - GORMAN T2101
TO-20-GOR-T2101-01 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | GOR |  | 900867380 | CLO | 2 | 1 | ESBIN01 GE are to supply replacement hyd
CORRECT | GOR |  | 900934390 | CLO | 2 | 1 | Following up the faulty sensor alarm on
CORRECT | GOR |  | 901059815 | DO | 2 | 1 | Replace hydran Sensor
SECTIONALISING DISCONNECT - GORTAWEE 110SA1
TO-20-GWE-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA2: 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-110SA1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
OS | GWE | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CORRECT | GWE |  | 900788599 | DO | 3 | 1 | Replace disconnect spindles
SECTIONALISING DISCONNECT - GORTAWEE 110SA2
TO-20-GWE-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
OS | GWE | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-GWE-110SA2-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA1: 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - GORTAWEE CAP1
TO-20-GWE-CAP1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - GORTAWEE T101 [Sean Quinn Cement]
TO-20-GWE-T101-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
| GOR |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Sean Quinn Cement]
TO-20-GWE-T102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-T102-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | GWE |  | 901073971 | DO | 2 | 1 | T102 110kV CB: SF6 Gauge corroded and ne
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GORTAWEE T142 [NDCC]
TO-20-GWE-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
BUSBAR SECTION - GREAT ISLAND 110 kV A1
TO-20-110 kV A1 @ GI-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND 110 kV A2
TO-20-110 kV A2 @ GI-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV A2 @ GI-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects.
BUSBAR SECTION - GREAT ISLAND 110 kV B1
TO-20-110 kV B1 @ GI-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND 110 kV B2
TO-20-110 kV B2 @ GI-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV B2 @ GI-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects.
COUPLER/SECTIONALISING CB - GREAT ISLAND 110K1-2
TO-20-GI-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-110K1-2-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GI | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
BUSBAR SECTION - GREAT ISLAND GIS 220 kV A1
TO-20-220 kV A1 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV A2
TO-20-220 kV A2 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV B1
TO-20-220 kV B1 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV B2
TO-20-220 kV B2 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220K1
TO-20-GI GIS-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220K2
TO-20-GI GIS-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SA1-2CB
TO-20-GI GIS-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover
TO-20-GI GIS-220SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SB1-2CB
TO-20-GI GIS-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover
220kV FEEDER - GREAT ISLAND GIS KELLIS
TO-20-GI GIS-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 901050728 | DO | 12 | 4 | Repair earth on 24 DC towers
FO_MISC |  | - | 900898107 | DO | 1 | 3 | 2017HP-1[196]Earths-Check earth bond top
FO_MISC |  | - | 900898108 | DO | 1 | 3 | 2017HP-1[207]Earths-Check earth bond top
FO_MISC |  | - | 900898109 | DO | 1 | 3 | 2017HP-1[214]Vib Damps EW damper fatigue
TRAN |  | - | 900987495 | DO | 1 | 4 | 2018HP-1[117]Insulatorbroken insulator
TRAN |  | - | 900987496 | DO | 1 | 4 | 2018HP-1[216]Insulatorbroken insulator
FO_MISC |  |  | 901085220 | DO |  | 2 | 2019HP-1[211]Vib Dampers EW VD fatigued
FO_MISC |  |  | 901085221 | DO |  | 4 | 2019HP-1[212]Vib Dampers EW VD fatigued
OS | GI | - | 901042324 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
AMCAB | GI | 220 | 901006258 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
OS | KLS | - | 901042334 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
220kV FEEDER - GREAT ISLAND GIS LODGEWOOD
TO-20-GI GIS-LWD-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FOINSHW |  | - | 900898158 | CLO | 2 | 2 | 2017HP-3[73/76]Insul & HW replace check
FO_MISC |  |  | 901084416 | CLO | 1 | 2 | 2019HP-1[39]Bird Nests remove birds nest
FO_MISC |  |  | 901084417 | CLO | 1 | 2 | 2019HP-1[67]Bird Nests remove birds nest
FO_MISC |  |  | 901084418 | CLO | 1 | 2 | 2019HP-1[68]Bird Nests remove birds nest
FOSTRHW |  |  | 901086406 | DO |  | 2 | 2019HP-1[1]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086407 | DO |  | 2 | 2019HP-1[2]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086408 | DO |  | 2 | 2019HP-1[3]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086409 | DO |  | 2 | 2019HP-1[4]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086410 | DO |  | 2 | 2019HP-1[5]Check Structure -Contact E&MP
GENERATOR TRANSFORMER - GREAT ISLAND GIS T2004 [SSE Generation Ireland GI4]
TO-20-GI GIS-T2004-01 ISO week: 40th - 41fr Date: 01 Oct - 09 Oct Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage request for Telemess 01/10-09/10
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
110kV FEEDER - GREAT ISLAND KILKENNY
TO-20-GI-KKY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 100 |  | Circuit and Bay works at Kilkenny & Great Island
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-KKY-1-04 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 1 |  | EI: Simultaneous GI-KKY-1 + GI-KKY-1: Energisation of circuit
TO-20-GI-KKY-1-05 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084415 | CLO | 1 | 2 | 2019HP-1[89]Bird Nests remove birds nest
FO_MISC |  |  | 901084980 | CLO |  | 2 | 2019HP-1[112]Off Plumb -plumb poles
FO_MISC |  |  | 901084981 | CLO |  | 2 | 2019HP-1[116]Off Plumb -plumb poles
FOSTRHW |  |  | 901086403 | CLO |  | 2 | 2019HP-1[15]Check Structure struct & HW
FOSTRHW |  |  | 901086404 | CLO |  | 2 | 2019HP-1[16]Check Structure struct & HW
FOSTRHW |  |  | 901086405 | CLO |  | 2 | 2019HP-1[129]Check Structure -Check Rot
CORRECT | GI |  | 901068754 | CLO |  | 2 | 110kV CTVTs Restest: Sphase .96% PF, TPh
CORRECT | KKY |  | 901072125 | CLO | 5 | 1 | surge counter unreadable , gas gauge rot
CORRECT | KKY |  | 901090669 | CLO | 5 | 1 | manometer needs replacing
CM | KKY |  | 901133697 | CLO | 3 | 1 | Replacement of Stolen Earths
TO-20-GI-KKY-1-07 ISO week: 41we - 42th Date: 07 Oct - 15 Oct Duration: 9 Days (7 WD) Status: Scheduled
TRAN |  | - | 900987497 | DO | 2 | 4 | 2018HP-1[10]Off Plumb
TRAN |  | - | 900987502 | DO | 2 | 4 | 2018HP-1[112]Off Plumb
TRAN |  | - | 900987503 | DO | 2 | 4 | 2018HP-1[113]Off Plumb
| GRI | - | 901160926 | DO | 3 | 1 | Follow on work to replace stolen earths after copper theft
OS | KKY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-20-GI-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
TO-20-GI-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-T141-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
DISTRIBUTION TRANSFORMER - GREAT ISLAND T142 [SDCC]
TO-20-GI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-T142-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Reference
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
TRANSFORMER - GREAT ISLAND T2101
TO-20-GI-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | GI | TRAFO | 901038643 | CANC | 2 | 2 | Camlin is to replace faulty transformer online oil DGA monitor on T2101 in Gt Island station.
CORRECT | GI | TRAFO | 901028698 | CANC | 1 | 2 | CREST Analysis of Paint Samples on T2101 220kV Station.
TO-20-GI-T2101-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | GI | 220 |  | DO | 2 | 4 | Cable Insp. 220kV Feeder XLPE
OPT | GI | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | GI | TRAFO |  | DO | 1 | 3 | 220/110 & 275/220 Trafo Operational Test
CORRECT | GI |  | 900943754 | DO |  | 2 | LOWER FAN BOX FIXING BROKEN....FIX
TRANSFORMER - GREAT ISLAND T2102
TO-20-GI-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-T2102-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GI | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | GI | TRAFO | 901039261 | CLO | 1 | 2 | Great Island T2102:Replace faulty oil level gauge Replace all fans Retest overall tan deltas Treat corrosion
110kV FEEDER - GREAT ISLAND WATERFORD 1
TO-20-GI-WAT-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727280 | CANC | 1 | 1 | 2015HP-1[37]Off Plumb Pole
TO-20-GI-WAT-1-05 Status: Unscheduled
FO_MISC |  | - | 900853147 | CANC | 3 | 2 | Check (General)-Painting Req. Tower 50 & 51
110kV FEEDER - GREAT ISLAND WATERFORD 2
TO-20-GI-WAT-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
TO-20-GI-WAT-2-03 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
TO-20-GI-WAT-2-05 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
TO-20-GI-WAT-2-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-WAT-2-04 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900650529 | CLO | 1 | 2 | 2014HP-1[8]Off Plumb
FO_MISC |  | - | 900650531 | CLO | 1 | 2 | 2014HP-1[11]Off Plumb
FO_MISC |  | - | 900650532 | CLO | 1 | 2 | 2014HP-1[14]Off Plumb
FO_MISC |  | - | 900650533 | CLO | 1 | 2 | 2014HP-1[15]Off Plumb
FO_MISC |  | - | 900650534 | CLO | 1 | 2 | 2014HP-1[16]Off Plumb
FOSTRHW |  | - | 900650536 | CLO | 1 | 2 | 2014HP-1[26]Check Structure split in RHP
FOSTRHW |  | - | 900650537 | CLO | 1 | 2 | 2014HP-1[27]Check Structure split in RHP
FO_MISC |  | - | 900683451 | CLO | 1 | 2 | 1[50] Insulators Off Plumb
FO_MISC |  |  | 901084982 | CLO |  | 2 | 2019HP-1[11]Off Plumb -plumb poles
FOINSHW |  |  | 901085556 | CLO |  | 2 | 2019HP-1[18]Insul&HW Replac check
FOINSHW |  |  | 901085557 | CLO |  | 2 | 2019HP-1[19]Insul&HW Replac check
OPT | GI | - | 901038787 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WAT | - | 901038982 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GREAT ISLAND WEXFORD
TO-20-GI-WEX-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-WEX-1-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | GI |  | 901129619 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WEX |  | 901129640 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GRIFFINRATH T141 [NDCC]
TO-20-GRI-T141-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of GRI,T-GRI-1: GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI-T141-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Reference (Tentative)
Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
110kV FEEDER - GRIFFINRATH tee GRANGE CASTLE
TO-20-GRI,T-GCA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-GCA-1-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900331371 | DO | 3 | 1 | 4[6,23,27,34]Repair damaged member
TRAN |  | - | 900987373 | DO | 2 | 4 | 2018HP-1[1]Check Struct/Found/etc-Base
TRAN |  | - | 900987374 | DO | 2 | 4 | 2018HP-1[32]Check Struct/Found/etc-Base
TRAN |  | - | 900987375 | DO | 2 | 4 | 2018HP-1[41]Check Struct/Found/etc-Base
FO_MISC |  | - | 900819656 | DO | 1 | 2 | 2016HP-39[1-39]Check-General Tower paint
AMCAB | GCA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - GRIFFINRATH tee GRIFFINRATH
TO-20-GRI,T-GRI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-GRI-1-02 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
as a consequence of: Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
110kV FEEDER - GRIFFINRATH tee MAYNOOTH
TO-20-GRI,T-MAY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-MAY-1-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
[5 empty] | 4 |  | Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MAY | - | 901039026 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - HUNTSTOWN T2002 [Viridian Power HN2]
TO-20-HN-T2002-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | HUN | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TO-20-HN-T2002-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Tentative
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
GENERATOR TRANSFORMER - HUNTSTOWN T2010/11 [Viridian Power HNC]
TO-20-HN-T2010/11-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | HUN |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - IKERRIN T141 [SDCC]
TO-20-IKE-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 2 |  | As a consequence of IKE,T-IKE-1: IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee IKERRIN
TO-20-IKE,T-IKE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-IKE-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee SHANNONBRIDGE
TO-20-IKE,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee THURLES
TO-20-IKE,T-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-IKE,T-THU-1-01 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | THU |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
TO-20-IKE,T-THU-1-03 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
BUSBAR SECTION - INCHICORE 220 kV A6
TO-20-220 kV A6 @ INC-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A6/B6 busbars in turn
BUSBAR SECTION - INCHICORE 220 kV B6
TO-20-220 kV B6 @ INC-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A6/B6 busbars in turn
COUPLER/SECTIONALISING CB - INCHICORE 220K1-2
TO-20-INC-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of ISM21
COUPLER/SECTIONALISING CB - INCHICORE 220K2-4
TO-20-INC-220K2-4-01 ISO week: 43tu - 43th Date: 20 Oct - 22 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
CORRECT | INC | - | 900977717 | DO | 2 | 2 | CB counter needs replacing
OPT | INC | 220-DEA4 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | - | 901076460 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | INC | 220-SA2-4 | 901076477 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | 220-DEB4 | 901076478 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | 220-SB2-4 | 901076479 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - INCHICORE 220K4-6
TO-20-INC-220K4-6-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | INC | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | INC | 220-DEA4 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEB6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-SA4-6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEA6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEB4 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-SB4-6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
220kV FEEDER - INCHICORE IRISHTOWN
TO-20-INC-ISH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 10 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | INC | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | ISH | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | ISH | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TO-20-INC-ISH-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Tentative
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
CORRECT | INC |  | 900390350 | DO |  | 2 | Inchicore Eirgrid RTU: MW, MVAr on the
| ISH | 110 |  | DO | 2 | 1 | Repair Sf6 leak
220kV FEEDER - INCHICORE MAYNOOTH 2
TO-20-INC-MAY-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 20 |  | Erect cable sealing ends, complete remote end works, loop-in Castlebagot Station to Inchicore-Maynooth 2 (EI will be required) - This will re-energise as CBT - May 2 and CBT - Inch 2
CAPX |  |  | CP0872 | DO | 2 |  | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | INC | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
220kV FEEDER - INCHICORE POOLBEG 1
TO-20-INC-PB-1-01 ISO week: 40mo - 41fr Date: 28 Sep - 09 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - | 901129050 | CLO | 10 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
220kV FEEDER - INCHICORE POOLBEG 2
TO-20-INC-PB-2-01 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - |  | DO | 10 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | INC | - | 901039093 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | PB | - | 901068550 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TRANSFORMER - INCHICORE T2102 [NDCC]
TO-20-INC-T2102-01 ISO week: 31fr Date: 31 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA511, R1Z23b, ISM21
TRANSFORMER - INCHICORE T2104 [NDCC]
TO-20-INC-T2104-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, 7SA511, 7UT512
TRANSFORMER - INCHICORE T2106 [NDCC]
TO-20-INC-T2106-01 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| INC |  |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | INC | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CORRECT | INC |  | 901084736 | DO | 3 | 1 | Low Gas / Leak- REPAIR SF6 LEAK
TO-20-INC-T2106-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
110kV FEEDER - INNISCARRA MACROOM
TO-20-IA-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-IA-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-IA-MAC-1-01 ISO week: 24mo - 24fr Date: 08 Jun - 12 Jun Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987656 | DO | 2 | 4 | "2018HP-4[22,24,52,58]Off Plumb-Poles"
TRAN |  | - | 900987657 | DO | 2 | 4 | "2018HP-3[59,60,64]Off PlumbPlumb poles"
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
FO_MISC |  |  | 901084983 | CLO |  | 2 | 2019HP-5[22,46,47,57,59]Off Plumb
FO_MISC |  |  | 901085222 | CLO |  | 2019 - Urgent | 2019HP-1[91]Vib Dampers Replace EW VD
OS | IA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | MAC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAC |  | 901028589 | CLO |  | 2 | 01-Surge Counter Covers Needs replacing
CORRECT | MAC |  | 901059059 | CLO |  | 2 | O1-Moisture in Inniscarra 110kv Lighteni
GENERATOR TRANSFORMER - INNISCARRA T101 [ESB GWM LE1/LE2]
TO-20-IA-T101-01 ISO week: 21mo Date: 18 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | IA |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - IRISHTOWN 220K1-2
TO-20-ISH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | ISH | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | ISH | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
| ISH | - |  | DO | 3 | 4 | 220kV GIS Busbar Assessment
OS | ISH | 220-DEB2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-SB1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | ISH | 220-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
220kV FEEDER - IRISHTOWN SHELLYBANKS
TO-20-ISH-SHL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB1
TO-20-ISH-SHL-1-03 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 5 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 110-DL |  | DO | 3 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-ISH-SHL-1-01 Status: Unscheduled
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB2
CORRECT | ISH |  | 900977047 | DO | 2 | 2 | Circuit Breaker to be timed
BUSBAR SECTION - KELLIS 110 kV A1
TO-20-110 kV A1 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV A2
TO-20-110 kV A2 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV B1
TO-20-110 kV B1 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV B2
TO-20-110 kV B2 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - KELLIS 220K1-2
TO-20-KLS-220K1-2-01 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | KLS |  | 901076101 | CLO | 2 | 1 | CB door broken
OPT | KLS |  | 901129547 | CLO | 2 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 220-SA | 901130124 | CLO | 2 | 4 | 220kV Sect / Dist Operational Test
110kV FEEDER - KELLIS KILKENNY
TO-20-KLS-KKY-1-01 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
FO_MISC |  |  | 901084984 | CLO | 2 | 4 | 2019HP-1[51]Off Plumb -plumb poles
FO_MISC |  |  | 901084985 | CLO | 2 | 4 | 2019HP-1[125]Off Plumb -plumb poles
TRAN |  | - | 900987666 | DO | 1 | 4 | 2018HP-1[144]Off Plumb
H3/H4 cubicle ordinary service
OS | KKY | - | 901042232 | CLO | 5 | 1 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KKY |  | 901072127 | CLO | 5 | 1 | surge counters wet inside , cables not s
OS | KLS | - | 901042231 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KLS |  | 901076103 | CLO | 5 | 1 | H4 moisture in surge counters
TRANSFORMER - KELLIS T2101
TO-20-KLS-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| KLS | - |  | CANC | 5 |  | Total Maintenance Outage Duration Requested
OPT | KLS | TRAFO | 901045352 | DO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
CM | KLS | - | 901134788 | DO | 2 | 1 | R,S & T Phases T2101 220kV Cubicle. R, S & T Phase CT internal links, heating appearing internally, possible corrosion/poor connection. DUE : 17-Nov-20
TO-20-KLS-T2101-03 Status: Unscheduled
CM | KLS | - | 901134787 | DO | 2 | 1 | R & S Phase T2101 110kV Bushing. R & S Phase connection hotspot DUE : IMMEDIATELY
TO-20-KLS-T2101-04 Status: Unscheduled
CORRECT | KLS | 220 | 901068451 | CANC | 1 | 1 | ABB required to overhaul CB poles for gas leak repair work
TO-20-KLS-T2101-01 ISO week: 13mo - 13fr Date: 23 Mar - 27 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | KLS |  | 901036845 | DO | 5 | 1 | Bund Leaking
OPT | KLS | 220 | 901038901 | DO | 2 | 3 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 110 | 901038905 | DO | 2 | 3 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - KELLIS T2102
TO-20-KLS-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | KLS | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KLS | 220 |  | DO | 2 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 110 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - KILBARRY 110 kV A1
TO-20-110 kV A1 @ KBY-03 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV A1 @ KBY-02 Status: Unscheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning
TO-20-110 kV A1 @ KBY-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning
BUSBAR SECTION - KILBARRY 110 kV A2
TO-20-110 kV A2 @ KBY-01 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KILBARRY 110 kV B1
TO-20-110 kV B1 @ KBY-03 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV B1 @ KBY-02 Status: Unscheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning
TO-20-110 kV B1 @ KBY-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning
BUSBAR SECTION - KILBARRY 110 kV B2
TO-20-110 kV B2 @ KBY-01 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - KILBARRY 110K1-2
TO-20-KBY-110K1-2-01 ISO week: 34mo - 35fr Date: 17 Aug - 28 Aug Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PROX |  | 10 |  | Proiximity for placement of 38kV cables (HI2192_Kilbarry_38kV Asset Replacement)
110kV FEEDER - KILBARRY KNOCKRAHA 1
TO-20-KBY-KRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 901128775 | CLO | 1 | 1 | Replace Pole No 42 due to lightening damage
TRAN |  | - | 901128776 | CLO | 1 | 1 | Replace Pole No 45 due to Lightening Damage
TO-20-KBY-KRA-1-01 ISO week: 16tu - 17tu Date: 14 Apr - 21 Apr Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
TRAN |  | - | 900987688 | DO | 2 | 4 | 2018HP-1[61]Replace Pole only
TRAN |  | - | 900987690 | DO | 1 | 4 | "2018HP-2[50,57]Off PlumbPlumb poles"
FOSTRHW |  |  | 901086433 | CLO | 1 | 1 | 2019HP-1[60]Replace Pole only -Rot
OS | KBY | - | 901050330 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | KBY | - | 901038491 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OPT | KRA | - | 900942501 | CLO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILBARRY KNOCKRAHA 2
TO-20-KBY-KRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | KBY |  | 900938041 | DO |  | 2 | O1- T lightening arrester -Arcing Horns
CORRECT | KBY |  | 901061010 | DO |  | 2 | O1-Wire P.F. to next available contact.
CORRECT | KRA |  | 901058701 | DO |  | 2 | Replace Bay Singnage
CORRECT | KRA |  | 901061013 | DO |  | 2 | O1-Change Signage on DL and DE
110kV FEEDER - KILBARRY MALLOW
TO-20-KBY-MAL-1-01 ISO week: 23th Date: 04 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | MAL |  | 901129483 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - KILBARRY MARINA 1
TO-20-KBY-MR-1-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KBY | - | 901050280 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - KILBARRY MARINA 2
TO-20-KBY-MR-2-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
DISTRIBUTION TRANSFORMER - KILBARRY T142 [SDCC]
TO-20-KBY-T142-01 ISO week: 34mo - 35fr Date: 17 Aug - 28 Aug Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | KBY |  |  |  | 10 |  | Proximity for Kilbarry K1-2
SECTIONALISING DISCONNECT - KILKENNY 110SA1
TO-20-KKY-110SA1-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of KKY-110SA2: 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - KILKENNY 110SA2
TO-20-KKY-110SA2-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
OS | KKY | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CM | KKY |  | 901133696 | CLO | 3 | 1 | Replacement of Stolen Earths
CAPACITOR/SVC/REACTOR - KILKENNY CAP2
TO-20-KKY-CAP2-03 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
CORRECT | KKY |  | 901083041 | DO | 5 | 1 | AC and DC Supplies:Carry out wiring mods
CM | KKY |  |  | DO | 3 | 1 | Replacement of Stolen Earths
DISTRIBUTION TRANSFORMER - KILKENNY T142 [SDCC]
TO-20-KKY-T142-03 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
GENERATOR TRANSFORMER - KILL HILL T131 [Kill Hill KH1]
TO-20-KHL-T131-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - KILL HILL THURLES
TO-20-KHL-THU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | THU |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - KILLONAN KNOCKRAHA
TO-20-KLN-KRA-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KLN-KRA-1-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KLN-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KLN-KRA-1-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | EI: Install base(s) for post insulator(s) Post curing time - erect steel + post insulator(s) Line transfer, and tubular uprate and civil works on Killonan bay.
TO-20-KLN-KRA-1-05 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084917 | DO | 2 | 2 | 2019HP-1[178]Insulator broken disc
TRAN |  | - | 900987776 | DO | 1 | 4 | "2018HP-3[173,174,175]Stud RailingRepair
TRAN |  | - | 900987793 | DO | 1 | 4 | 2018HP-1[40]ACGFit ACG
110kV FEEDER - KILLONAN LIMERICK 1
TO-20-KLN-LIM-1-01 ISO week: 36mo - 45fr Date: 31 Aug - 06 Nov Duration: 68 Days (49 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0624 | DO | 49 |  | EI: Line diversion work to enable construction of GIS building
CAPX |  |  | CP0624 | DO | 5 |  | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
OPT | KLN |  |  | DO | 3 | 4 | 110kV Air Blast Cubicle Operational Test
CORRECT | LIM |  | 901078074 | DO | 5 | 1 | Low Gas / Leak
OS | LIM | - | 900948291 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - KILLONAN LIMERICK 2
TO-20-KLN-LIM-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| - | Line | 901126082 | DO | 2 | 4 | 2019LP-1[25]Replace Pole - Pole Rot
TO-20-KLN-LIM-2-02 ISO week: 38fr - 39we Date: 18 Sep - 23 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0624 | DO | 5 |  | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
Fix Disconnect on Killonan Limerick 2
TO-20-KLN-LIM-2-01 ISO week: 9mo - 35fr Date: 24 Feb - 28 Aug Duration: 187 Days (129 WD) Status: Scheduled
CAPX |  |  | CP0624 | DO | 74 |  | EI: Line diversion work to enable construction of GIS building
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | LIM | - | 901042304 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | LIM | - | 901129154 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - KILLONAN NENAGH [SDCC]
TO-20-KLN-NEN-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, REL521
220kV FEEDER - KILLONAN SHANNONBRIDGE
TO-20-KLN-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Studied proximity CP1058
TO-20-KLN-SH-1-01 ISO week: 20mo - 22th Date: 11 May - 28 May Duration: 18 Days (14 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL521
FO_MISC |  |  | 901084918 | DO | 2 | 4 | 2019HP-1[22]Insulator broken insulator
FO_MISC |  |  | 901084919 | DO | 2 | 4 | 2019HP-1[240]Insulator broken insulator
FO_MISC |  | - | 900404035 | DO | 1 | 1 | 1[180]Fit anti climb device
YM03 | - | - | 900978885 | DO | 5 | 1 | 1[57]Repairs of damaged members on Tower
OS | KLN | - | 900858887 | CLO | 10 | 2 | 220kV Air Blast Cubicle Ordinary Service
CA | KLN | - | 901038533 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KLN |  | 901045697 | CLO | 2 | 1 | Pressure Vessel Statutory Inspection
OPT | KLN | 220-1 |  | DO | 1 | 4 | 220kV Air Blast Cubicle Operational Test
CA | SH | - | 900775936 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
OPT | SH | 220-1 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - KILLONAN SINGLAND
TO-20-KLN-SNG-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
Proximity outage for CA on Singland T101
OS | SNG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRANSFORMER - KILLONAN T2101
TO-20-KLN-T2101-01 ISO week: 39tu - 39th Date: 22 Sep - 24 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | KLN | 110 |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
OPT | KLN | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KLN | 220 |  | DO | 1 | 4 | 220kV Air Blast Cubicle Operational Test
TRANSFORMER - KILLONAN T2102
TO-20-KLN-T2102-01 ISO week: 33mo - 35fr Date: 10 Aug - 28 Aug Duration: 19 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | KLN | 220 |  | DO | 6 | 4 | 110kV Air Blast Cubicle Ordinary Service
OS | KLN | 110 |  | DO | 6 | 4 | 110kV Air Blast Cubicle Ordinary Service
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | KLN | Trafo |  | DO | 5 | 4 | 220/110 & 275/220 - Ordinary Service
CA | KLN | 220 |  | DO | 4 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | KLN | 110 |  | DO | 4 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | KLN | 110 |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
TRANSFORMER - KILLONAN T2103
TO-20-KLN-T2103-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7SA612, RET670
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | KLN | Trafo |  | DO | 5 | 4 | 220/110 & 275/220 - Ordinary Service
OS | KLN | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLN | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | KLN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - KILLONAN T2104
TO-20-KLN-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | KLN |  | 901078075 | CANC |  | 1 | ESB Networks Oil filtration plant was no
TO-20-KLN-T2104-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KLN | TRAFO | 901130045 | CLO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | KLN | 110 | 901129908 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLN | 220 | 901129999 | CLO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
CORRECT | KLN |  | 901090977 | DO | 3 | 1 | Replacement of faulty oil DGA monitoring
AMCAB | KLN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
220kV FEEDER - KILLONAN TARBERT
TO-20-KLN-TB-1-05 ISO week: 41tu - 41we Date: 06 Oct - 07 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-KLN-TB-1-01 ISO week: 23tu - 47we Date: 02 Jun - 18 Nov Duration: 170 Days (120 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 120 |  | Outage for diversion of line into Kilpaddoge station to cable into GIS building. Feeder will become Killonan Kilpaddoge
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987854 | DO | 2 | 4 | 2018HP-1[151]ACGFit ACG
SECTIONALISING DISCONNECT - KILLOTERAN 110SA1
TO-20-KTN-110SA1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA2: 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - KILLOTERAN 110SA2
TO-20-KTN-110SA2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA1: 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - KILLOTERAN T101 [SDCC]
TO-20-KTN-T101-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - KILLOTERAN T102 [SDCC]
TO-20-KTN-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - KILLOTERAN WATERFORD
TO-20-KTN-WAT-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
TO-20-KTN-WAT-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
BUSBAR SECTION - KILPADDOGE 110 kV A1
TO-20-110 kV A1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A2
TO-20-110 kV A2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A3
TO-20-110 kV A3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A4
TO-20-110 kV A4 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B1
TO-20-110 kV B1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B2
TO-20-110 kV B2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B3
TO-20-110 kV B3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B4
TO-20-110 kV B4 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 220 kV A1
TO-20-220 kV A1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KILPADDOGE 220 kV A2
TO-20-220 kV A2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-220 kV A2 @ KPG-03 Status: Unscheduled
Busbar changeover
TO-20-220 kV A2 @ KPG-04 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV A2 @ KPG-02 ISO week: 31mo - 33fr Date: 27 Jul - 14 Aug Duration: 19 Days (14 WD) Status: Scheduled
[5 empty] | 14 |  | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2
BUSBAR SECTION - KILPADDOGE 220 kV A3
TO-20-220 kV A3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A3 @ KPG-01 ISO week: 29tu - 30fr Date: 14 Jul - 24 Jul Duration: 11 Days (9 WD) Status: Scheduled
[5 empty] | 10 |  | A3/B3 in turn for replacement of DC contactors
BUSBAR SECTION - KILPADDOGE 220 kV A4
TO-20-220 kV A4 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A4 @ KPG-03 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV A4 @ KPG-01 ISO week: 36mo - 37fr Date: 31 Aug - 11 Sep Duration: 12 Days (10 WD) Status: Scheduled
[5 empty] | 10 |  | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler
BUSBAR SECTION - KILPADDOGE 220 kV B1
TO-20-220 kV B1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KILPADDOGE 220 kV B2
TO-20-220 kV B2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-220 kV B2 @ KPG-03 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B2 @ KPG-04 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV B2 @ KPG-02 ISO week: 31mo - 33fr Date: 27 Jul - 14 Aug Duration: 19 Days (14 WD) Status: Scheduled
| KPG |  |  |  | 14 |  | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2
BUSBAR SECTION - KILPADDOGE 220 kV B3
TO-20-220 kV B3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B3 @ KPG-01 ISO week: 29tu - 30fr Date: 14 Jul - 24 Jul Duration: 11 Days (9 WD) Status: Scheduled
[5 empty] | 10 |  | A3/B3 in turn for replacement of DC contactors
BUSBAR SECTION - KILPADDOGE 220 kV B4
TO-20-220 kV B4 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B4 @ KPG-03 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV B4 @ KPG-01 ISO week: 36mo - 37fr Date: 31 Aug - 11 Sep Duration: 12 Days (10 WD) Status: Scheduled
[5 empty] | 10 |  | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler
COUPLER/SECTIONALISING CB - KILPADDOGE 220K4
TO-20-KPG-220K4-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SA1-2CB
TO-20-KPG-220SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SA2-4CB
TO-20-KPG-220SA2-4CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SB1-2CB
TO-20-KPG-220SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-KPG-220SB1-2CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SB2-4CB
TO-20-KPG-220SB2-4CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | KPG | - |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-KPG-220SB2-4CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
110kV FEEDER - KILPADDOGE KNOCKANURE 110
TO-20-KPG-KNR-1-110-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0902 | DO | 40 |  | EI: Replacing polesets, hardware, insulators & crossarms. Foundation reinforcement required at angle masts. Towers to be painted.
TO-20-KPG-KNR-1-110-02 ISO week: 21th - 21fr Date: 21 May - 22 May Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Proximity outage for 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 (Hotspots 7 and 8 to be repaired; DC Cable Tower No. 160)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988027 | CLO | 1 | 4 | 2018HP-1[47]Insulator-strain insul
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | KNR | - | 901129707 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KPG |  | 901129517 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
220kV FEEDER - KILPADDOGE KNOCKANURE 220
TO-20-KPG-KNR-1-220-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 5 |  | Proximity outage to bore wall and pull cable
TO-20-KPG-KNR-1-220-02 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 2 |  | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder
TO-20-KPG-KNR-1-220-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 5 |  | Re-lable circuit to Kipaddoge-Knockanure No. 1
TO-20-KPG-KNR-1-220-03 Status: Unscheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
CM | KNR | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | KNR | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OPT | KPG | - | 901043819 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 1
TO-20-KPG-MP GIS-1-02 ISO week: 39mo - 40we Date: 21 Sep - 30 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 4 | Aux Relay - replace contactors
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 2
TO-20-KPG-MP GIS-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | EI: Energise the new Kilpaddoge- Knocknaure 2 cable
TO-20-KPG-MP GIS-2-02 Status: Unscheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Tarbert 2
TO-20-KPG-MP GIS-2-03 ISO week: 41th - 41fr Date: 08 Oct - 09 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Killonan
TO-20-KPG-MP GIS-2-04 ISO week: 48mo - 49we Date: 23 Nov - 02 Dec Duration: 10 Days (8 WD) Status: Tentative
|  | - |  | DO | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
110kV FEEDER - KILPADDOGE RATHKEALE
TO-20-KPG-RAT-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900989469 | CANC | 1 | 2 | 2018HP-1[125]ITSOul&HW Replace check
TRAN |  | - | 900989470 | CANC | 1 | 2 | 2018HP-1[130]ITSOul&HW Replace check
TRAN |  | - | 900989471 | CANC | 1 | 1 | 2018HP-1[134]Off Plumb
TO-20-KPG-RAT-1-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989472 | NS | 1 | 2 | 2018HP-1[135]ACG-Replace
OPT | RAT | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TRANSFORMER - KILPADDOGE T2101
TO-20-KPG-T2101-02 ISO week: 13th - 14th Date: 26 Mar - 02 Apr Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | KPG | TRAFO | 901039259 | DO | 3 | 2 | Corrosion on MR Messko Temp Gauges ( requires stainless surround to stop water from top cover) and fans Fans Q4 not working ceased
OPT | KPG | TRAFO | 901045373 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KPG | 110 | 901045439 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | KPG | 220 | 901045526 | CLO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-KPG-T2101-03 ISO week: 42mo - 43we Date: 12 Oct - 21 Oct Duration: 10 Days (8 WD) Status: Scheduled
[5 empty] | 8 |  | Total Maintenance Outage Duration Requested
CM | KPG | 220 |  | DO | 8 | 2 | Aux Relay - replace contactors
TRANSFORMER - KILPADDOGE T2102
TO-20-KPG-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 10 |  | Proximity outage of F4 bay to enable termination of cable in F6 bay.
TO-20-KPG-T2102-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OPT | KPG | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | KPG | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | KPG | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
220kV FEEDER - KILPADDOGE TARBERT 1
TO-20-KPG-TB-1-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TO-20-KPG-TB-1-02 ISO week: 22tu - 22th Date: 26 May - 28 May Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 3 |  | Proximity outage of DC mast - remove lead-in and drops, strip down the CSEs
TO-20-KPG-TB-1-03 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
AMCAB | KPG | - | 901006581 | DO | 2 | 3 | Annual Insp. 400 & 220 Feeder XLPE Cable
OPT | KPG | - | 900942471 | DO | 1 | 3 | 220kV GIS Cubicle Operational Test
OS | TB | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
OS | TB | - | 901050439 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | TB | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - KILPADDOGE TRALEE 2
TO-20-KPG-TRL-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989672 | DO | 1 | 4 | 2018HP-1[31]Off PlumbPlumb poleset
TRAN |  | - | 900989674 | DO | 1 | 4 | 2018HP-1[98]Off PlumbPlumb poleset
TRAN |  | - | 900989675 | DO | 1 | 4 | 2018HP-1[99]Off PlumbPlumb poleset
TRAN |  | - | 900989676 | DO | 1 | 4 | 2018HP-1[100]Off PlumbPlumb poleset
OPT | KPG | - | 901043757 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
AMCAB | TRL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILTEEL MAYNOOTH
TO-20-KTL-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900247574 | DO | 2 | 3 | Replace Member mast no 86 replace bent b
FO_MISC |  | - | 900897418 | DO | 1 | 2 | 2017HP-1[11]Off Plumb -Poles
OPT | KTL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILTEEL MONREAD
TO-20-KTL-MON-1-01 ISO week: 23tu - 24mo Date: 02 Jun - 08 Jun Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MON |  | 901076758 | CLO | 5 | 1 | Low Gas
OPT | MON | - | 901055117 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - KINNEGAD 110SA1-2CB
TO-20-KIN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | KIN | - | 901042251 | DO | 2 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KIN | 110-SA1 | 901042964 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-KIN-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | KIN | 110-SA2 | 901042963 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - KINNEGAD MULLINGAR
TO-20-KIN-MUL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-KIN-MUL-1-02 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KIN | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MUL | - | 901118292 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-KIN-MUL-1-01 ISO week: 30mo - 41fr Date: 20 Jul - 09 Oct Duration: 82 Days (59 WD) Status: Scheduled
CAPX |  |  | CP1054 | DO | 58 |  | EI: Install 2 new towers under the line, divert line and re-energise from remote end
TSO CUSTOMER TRANSFORMER - KINNEGAD T101 [Lagan Cement]
TO-20-KIN-T101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-KIN-T101-03 Status: Unscheduled
CORRECT | KIN |  | 901068813 | CANC |  | 1 | replacement of the CT’s in Kinnegad T101
TO-20-KIN-T101-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KIN | - | 901042268 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - KINNEGAD T102 [Lagan Cement]
TO-20-KIN-T102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | KIN | TRAFO | 901080654 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - KNOCKANURE 110 kV A1
TO-20-110 kV A1 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV A2
TO-20-110 kV A2 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV A4
TO-20-110 kV A4 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV B1
TO-20-110 kV B1 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV B2
TO-20-110 kV B2 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV A1
TO-20-220 kV A1 @ KNR-01 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV A2
TO-20-220 kV A2 @ KNR-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-220 kV A2 @ KNR-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-220 kV A2 @ KNR-03 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV B1
TO-20-220 kV B1 @ KNR-01 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV B2
TO-20-220 kV B2 @ KNR-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-220 kV B2 @ KNR-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-220 kV B2 @ KNR-03 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
COUPLER/SECTIONALISING CB - KNOCKANURE 220K1
TO-20-KNR-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220K2
TO-20-KNR-220K2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
CAPX |  |  | CP0936 | DO | 3 |  | EI: Energisation of F6 reactor inc. soft closing and 24hr cable soak
TO-20-KNR-220K2-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220K2-02 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220SA1-2CB
TO-20-KNR-220SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-KNR-220SA1-2CB-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220SA1-2CB-03 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220SB1-2CB
TO-20-KNR-220SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-KNR-220SB1-2CB-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220SB1-2CB-03 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
TRANSFORMER - KNOCKANURE T2101
TO-20-KNR-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KNR | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | KNR | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TRANSFORMER - KNOCKANURE T2102
TO-20-KNR-T2102-01 ISO week: 9we - 11th Date: 26 Feb - 12 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KNR | 110 | 901129752 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
OS | KNR | 220 | 901129806 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | TRAFO | 901129834 | CLO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | KNR | TRAFO | 901130270 | CLO | 1 | 3 | Knockanure T2101 & T2102 Transformers: Check position of fans adjacent to pumps
CORRECT | KNR |  | 900982980 | CANC |  | 2 | Low Oil / Leak. Low Oil alarm being gene
110kV FEEDER - KNOCKANURE TRIEN 1
TO-20-KNR-TRI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
TO-20-KNR-TRI-1-01 ISO week: 24we - 24th Date: 10 Jun - 11 Jun Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | TRI | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRI |  | 901129634 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KNOCKANURE TRIEN 2
TO-20-KNR-TRI-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
TO-20-KNR-TRI-2-01 ISO week: 24fr Date: 12 Jun Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TRI | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - KNOCKRAHA 110 kV A1
TO-20-110 kV A1 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-110 kV A1 @ KRA-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103
BUSBAR SECTION - KNOCKRAHA 110 kV A2
TO-20-110 kV A2 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KNOCKRAHA 110 kV B1
TO-20-110 kV B1 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-110 kV B1 @ KRA-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103
BUSBAR SECTION - KNOCKRAHA 110 kV B2
TO-20-110 kV B2 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
COUPLER/SECTIONALISING CB - KNOCKRAHA 110K1-2
TO-20-KRA-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KRA | 110-SB1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SB2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - KNOCKRAHA 220 kV A1
TO-20-220 kV A1 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A1 @ KRA-03 ISO week: 41su - 42mo Date: 11 Oct - 12 Oct Duration: 2 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
BUSBAR SECTION - KNOCKRAHA 220 kV A2
TO-20-220 kV A2 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
TO-20-220 kV A2 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A2 @ KRA-03 ISO week: 25we - 25fr Date: 17 Jun - 19 Jun Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 3 |  | Droppers to be connected, followed by EI.
BUSBAR SECTION - KNOCKRAHA 220 kV B1
TO-20-220 kV B1 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-220 kV B1 @ KRA-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections
TO-20-220 kV B1 @ KRA-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | 220 kV A1/B1 IN TURN @ KRA: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-220 kV B1 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV B1 @ KRA-05 ISO week: 41su - 42mo Date: 11 Oct - 12 Oct Duration: 2 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
BUSBAR SECTION - KNOCKRAHA 220 kV B2
TO-20-220 kV B2 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
TO-20-220 kV B2 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV B2 @ KRA-03 ISO week: 26mo - 26we Date: 22 Jun - 24 Jun Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 3 |  | Droppers to be connected, followed by EI.
COUPLER/SECTIONALISING CB - KNOCKRAHA 220K1-2
TO-20-KRA-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KRA-220K1-2-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KRA-220K1-2-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
OS | KRA | 220-SB2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 220-SB1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 110-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 110-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OPT | KRA | 220-SA1 | 901039154 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | KRA | 220-SA2 | 901039155 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
TO-20-KRA-220K1-2-04 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KRA-220K1-2-05 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KRA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | KRA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KRA |  | 901047457 | DO | 3 | 1 | O1-Hotspot 220kv SA2 T Phase on A2 Side
110kV FEEDER - KNOCKRAHA MIDLETON
TO-20-KRA-MID-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21
studied outage to move 12 day outage for CP0868
TO-20-KRA-MID-1-01 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084995 | CLO |  | 2 | 2019HP-7[7,8,9,10,11,12,13]Off Plumb
TRAN | - | Line | 901130581 | DO | 3 | 1 | Hotspot 1 (AT No.50 Span 49/50) Right phase jumper terminal (Repair by 28th August 2020)
CORRECT | KRA |  | 901059062 | CLO | 1 | 1 | O1-Repair SF6 Gauge signs of corrosion
OPT | MID | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MID |  | 901078152 | CLO | 1 | 2 | Replce Bay Signage
220kV FEEDER - KNOCKRAHA RAFFEEN
TO-20-KRA-RAF-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 90 |  | 220 kV Line refurbishment, re-sagging and foundation reinforcement works.
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2)
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
CAPX |  |  | CP0796 + CP0973 | DO | 2 |  | For Energisation of A4/B4 busbar
CAPX |  |  | CP0868 | DO | 1 |  | EI: Simultaneous KRA-RAF-1 + KRA-RAF-1: Energisation using either feeder bay CB
TO-20-KRA-RAF-1-04 ISO week: 25we - 26we Date: 17 Jun - 24 Jun Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 6 |  | EI: Outage for EI, line switched out at start of works
TO-20-KRA-RAF-1-02 ISO week: 9mo - 18th Date: 24 Feb - 30 Apr Duration: 67 Days (46 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 30 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 30 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0868 | DO | 7 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-KRA-RAF-1-01 ISO week: 9mo - 21sa Date: 24 Feb - 23 May Duration: 90 Days (61 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900727347 | DO | 3 | 3 | 2015HP-1[54]Insulator Broken str insul
FO_MISC |  | - | 900897879 | DO | 1 | 3 | 2017HP-1[DCET1]Arching Horns -Replace
FO_MISC |  | - | 900897880 | DO | 1 | 3 | 2017HP-1[DCAT5]Arching Horns -Replace
PROX |  |  | PR0001 | DO | 1 |  | Proximity outage for work on Aghada-Raffeen 220 kV
FO_MISC |  |  | 901085223 | DO |  | 4 | 2019HP-2[2,3]Vib Dampers Replace EW VD
CORRECT | KRA | - | 901129378 | CLO | 5 | 1 | Replace stolen earths
TRANSFORMER - KNOCKRAHA T2101
TO-20-KRA-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KRA-T2101-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KRA-T2101-04 ISO week: 28we - 30th Date: 08 Jul - 23 Jul Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KRA | 220 | 901042177 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | KRA | 110 | 901042315 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KRA |  | 900908018 | DO | 3 | 2 | Carry out oil regeneration, wire up PRD
OS | KRA | Trafo | 901130039 | CLO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | KRA |  | 900877126 | CLO | 2 | 2 | Spare Parts for Disconnect
CORRECT | KRA | - | 900973655 | CLO | 2 | 2 | O2-Fans 2,6,9 not working
CORRECT | KRA | - | 900959190 | CLO | 1 | 2 | O2- OLTC silica gel needs changing
TRANSFORMER - KNOCKRAHA T2102
TO-20-KRA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-KRA-T2102-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections
TO-20-KRA-T2102-02 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | KRA | 110 | 901129577 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KRA | 220 | 901129728 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KRA | TRAFO | 901129737 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - KNOCKRAHA T2103
TO-20-KRA-T2103-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7SA612, RET670
OPT | KRA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KRA | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KRA | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CORRECT | KRA | - | 900959193 | DO | 1 | 2 | O2- Low oil level on OLTC tank
TO-20-KRA-T2103-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KRA-T2103-03 ISO [year]week: 42mo - [21]9we Date: 12 Oct - 03 Mar 21 Duration: 143 Days (100 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 100 |  | Remove from system to allow for offline F9 wing coupler build
110kV FEEDER - KNOCKRAHA WOODHOUSE
TO-20-KRA-WOH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21
TO-20-KRA-WOH-1-01 ISO week: 28mo - 29mo Date: 06 Jul - 13 Jul Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | KRA | - | 901129859 | CLO | 6 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KRA |  | 901036906 | CLO |  | 2 | O1-Replace Surge Counter
OS | WOO | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - KNOCKRANNY 110 kV A1
TO-20-110 kV A1 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV A2
TO-20-110 kV A2 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV B1
TO-20-110 kV B1 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV B2
TO-20-110 kV B2 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
CAPACITOR/SVC/REACTOR - KNOCKRANNY FILTER1
TO-20-KNY-FILTER1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KNY | - | 901146372 | DO | 5 | 4 | HV Filter Ordinary Service
110kV FEEDER - KNOCKRANNY SALTHILL
TO-20-KNY-SAL-1-01 ISO week: 15tu - 15we Date: 07 Apr - 08 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CM | SAL | 110 | 901129456 | CANC | 2 | 1 | Visual inspection of HIS HV cable sealing end
TO-20-KNY-SAL-1-02 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
OPT | KNY | - | 900858560 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
AMCAB | SAL | - |  | DO | 2 | 1 | CSE Inspection, ref. Galway cubicle CSE Failure in Salthill (FO 19-26)
110kV FEEDER - KNOCKRANNY SCREEBE [SDCC]
TO-20-KNY-SCR-1-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | KNY | - | 901006383 | DO | 2 | 2 | Annual Insp. 110kV Feeder XLPE Cable
TO-20-KNY-SCR-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Reference
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KNY | - | 900942465 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
110kV FEEDER - KNOCKRANNY UGGOOL
TO-20-KNY-UGL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - LANESBORO 110SA1-2CB
TO-20-LA-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | LA | - | 901129877 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | LA | - |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | LA | - |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - LANESBORO MULLINGAR
TO-20-LA-MUL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-LA-MUL-1-03 Status: Unscheduled
YM03 | - | Line | 901110465 | CLO | 5 | 1 | R1 206 - 207 Right Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110466 | CLO | 5 | 1 | C1 206 - 207 Centre Mid span joint Replace joint within 3 months pending TSO review.
YM03 | - | Line | 901110467 | CLO | 5 | 1 | L1 206 - 207 Left Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110468 | CLO | 5 | 1 | R2 205 - 206 Right Mid span joint Replace joint within 6 months pending TSO review
YM03 | - | Line | 901110469 | CLO | 5 | 1 | L2 205 - 206 Left Mid span joint. Replace joint during the next planned outage
YM03 | - | Line | 901110514 | CLO | 5 | 1 | C2 205 - 206 Centre Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110515 | CLO | 5 | 1 | Am No.75 75 - 76 Left Dead end termination Replace joint within 1 month pending TSO review
YM03 | - | Line | 901110516 | CLO | 5 | 1 | R1 74 - 75 Right Mid span joint Replace joint during the next planned outage.
110kV FEEDER - LANESBORO RICHMOND 1 [NDCC]
TO-20-LA-RIC-1-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
110kV FEEDER - LANESBORO RICHMOND 2 [NDCC]
TO-20-LA-RIC-2-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
110kV FEEDER - LANESBORO SLIABH BAWN
TO-20-LA-SLB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | SLB | - | 901042297 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-LA-SLB-1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
GENERATOR TRANSFORMER - LANESBORO T104 [ESB GWM LR4]
TO-20-LA-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - LANESBORO T141 [NDCC]
TO-20-LA-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
COUPLER/SECTIONALISING CB - LETTERKENNY 110SA1-3CB
TO-20-LET-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-110SA1-3CB-02 Status: Unscheduled
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | LET | - | 901080653 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CAPACITOR/SVC/REACTOR - LETTERKENNY CAP2
TO-20-LET-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | LET |  | 900332304 | DO | 1 | 2 | N O 1 Misc- work not on other C
CAPACITOR/SVC/REACTOR - LETTERKENNY M/CAP1
TO-20-LET-M/CAP1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
TO-20-LET-M/CAP1-01 Status: Unscheduled
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TRANSFORMER - LETTERKENNY STRABANE PST
TO-20-LET-PST-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-PST-03 Status: Unscheduled
PROT |  |  |  | DO | 2 |  | P1 Protection maintenance of 7SA511, MX3P3A
TO-20-LET-PST-02 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OS | LET | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | LET |  | 900952919 | DO | 1 | 1 | maintenane req on "S" phase arm of mecha
CAPACITOR/SVC/REACTOR - LETTERKENNY SVC
TO-20-LET-SVC-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-SVC-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | LET | - | 900863569 | DO | 5 | 1 | Replace 10kV LV Bushing at SVC
OS | LET | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SVCAI | LET | SVC | 901006304 | DO | 2 | 4 | Annual Inspection of SVC
TO-20-LET-SVC-02 ISO week: 29mo - 34th Date: 13 Jul - 20 Aug Duration: 39 Days (28 WD) Status: Scheduled
CAPX |  |  | MC0330 | DO | 28 |  | SVC Refurbishment
DISTRIBUTION TRANSFORMER - LETTERKENNY T141 [NDCC]
TO-20-LET-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 40 |  | Facilitate the demolition of existing CT/VT supports and installation of new CT/VT and associated steelwork on T141 Bay
TO-20-LET-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
110kV FEEDER - LETTERKENNY TIEVEBRACK
TO-20-LET-TIV-1-01 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | LET | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TIV | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LETTERKENNY TRILLICK [NDCC]
TO-20-LET-TLK-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | Proximity outage to install new lightning monopole
110kV FEEDER - LIBERTY STREET MARINA 1 [SDCC]
TO-20-LIB-MR-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | MR |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
SECTIONALISING DISCONNECT - LIMERICK 110SA1
TO-20-LIM-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of LIM-110SA2: 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - LIMERICK 110SA2
TO-20-LIM-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of LIM-110SA1: 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
OS | LIM | SA2 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - LIMERICK MONETEEN
TO-20-LIM-MTN-1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900567326 | DO | 2 | 1 | 3[509,510,511] DCIMP5 badly kinked (IMP49 KIL-LIM 1)
OPT | LIM |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LIMERICK RATHKEALE
TO-20-LIM-RAT-1-01 ISO week: 42we - 42fr Date: 14 Oct - 16 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988374 | DO | 2 | 4 | 2018HP-1[42-43]Conflicts-No Guard Wire
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of R1Z23b
AMCAB | LIM | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | LIM | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | RAT |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
DISTRIBUTION TRANSFORMER - LIMERICK T141 [SDCC]
TO-20-LIM-T141-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - LIMERICK T142 [SDCC]
TO-20-LIM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
SECTIONALISING DISCONNECT - LISDRUM 110SA1
TO-20-LIS-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
OS | LIS | SA1 | 901039705 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-LIS-110SA1-02 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 1 |  | As a consequence of LIS-110SA2: 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
SECTIONALISING DISCONNECT - LISDRUM 110SA2
TO-20-LIS-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of LIS-110SA1: 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
TO-20-LIS-110SA2-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
CAPACITOR/SVC/REACTOR - LISDRUM CAP1
TO-20-LIS-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - LISDRUM CAP2
TO-20-LIS-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
TO-20-LIS-CAP2-02 ISO week: 33mo Date: 10 Aug Duration: 1 Day (1 WD) Status: Scheduled
CORRECT | LIS |  | 901078676 | CLO | 1 | 1 | Contact resistance measurement on the ci
110kV FEEDER - LISDRUM LOUTH
TO-20-LIS-LOU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
CORRECT | LOU |  |  | DO | 3 | 1 | Hotspot 1 (SC AM No.52 Span 51/52) Jumper terminal (Repair ASAP)
TO-20-LIS-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 900982920 | DO | 3 | 1 | Surge counters need replacement on R/S/T
TO-20-LIS-LOU-1-01 ISO week: 29th - 29fr Date: 16 Jul - 17 Jul Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | LIS |  | 901129596 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LISDRUM SHANKILL
TO-20-LIS-SKL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 13 |  | Total Maintenance Outage Duration Requested
TO-20-LIS-SKL-1-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
|  | - |  | CANC | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
TO-20-LIS-SKL-1-04 ISO week: 39mo - 39fr Date: 21 Sep - 25 Sep Duration: 5 Days (5 WD) Status: Proposed
OS | LIS | - | 901129864 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service. do under OD1391
OS | SKL | - | 901129823 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service.do under OD1391
TO-20-LIS-SKL-1-02 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
| SKL |  |  |  | 2 |  | Hot spot detected on Lisdrum Cubicle DA S Pha
DISTRIBUTION TRANSFORMER - LISDRUM T141 [NDCC]
TO-20-LIS-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - LISDRUM T142 [NDCC]
TO-20-LIS-T142-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
SECTIONALISING DISCONNECT - LISHEEN 110SA1-2
TO-20-LSN-110SA1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
SECTIONALISING DISCONNECT - LISHEEN 110SA2-4
TO-20-LSN-110SA2-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
GENERATOR TRANSFORMER - LISHEEN T122 [Lisheen LS1/LS2]
TO-20-LSN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-T122-01 ISO week: 28mo - 28tu Date: 06 Jul - 07 Jul Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request for 2 WD
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LSN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - LISHEEN T142 [SDCC]
TO-20-LSN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
110kV FEEDER - LISHEEN THURLES
TO-20-LSN-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-THU-1-01 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988512 | DO | 2 | 4 | 2018HP-1[25]Bird Nestsremove asap
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
TO-20-LSN-THU-1-03 Status: Unscheduled
TRAN |  | - | 900988515 | CANC | 1 | 1 | 2018HP-1[47]Bird Nestsremove asap
SECTIONALISING DISCONNECT - LODGEWOOD 110SA1
TO-20-LWD-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LWD | - | 901042978 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-LWD-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of LWD-110SA2: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
SECTIONALISING DISCONNECT - LODGEWOOD 110SA2
TO-20-LWD-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LWD |  |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-LWD-110SA2-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of LWD-110SA1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
COUPLER/SECTIONALISING CB - LODGEWOOD 220K1-2
TO-20-LWD-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | LWD | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | LWD | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | LWD | 220-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | LWD | 220-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TRANSFORMER - LODGEWOOD T2102
TO-20-LWD-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-LWD-T2102-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | LWD | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CA | LWD | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OPT | LWD | TRAFO |  | DO |  | 4 | 220/110 & 275/220 Trafo Operational Test
GENERATOR TRANSFORMER - LONG POINT T2002 [ESB GWM AD2]
TO-20-LPT-T2002-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | LPT | - | 901129020 | CLO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | LPT | 220 | 901129732 | CLO | 1 | 4 | 2200kV SF6 Cubicle Operational Test
BUSBAR SECTION - LOUTH 110 kV A1
TO-20-110 kV A1 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV A2
TO-20-110 kV A2 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV B1
TO-20-110 kV B1 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV B2
TO-20-110 kV B2 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV A1
TO-20-220 kV A1 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV A2
TO-20-220 kV A2 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV B1
TO-20-220 kV B1 @ LOU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 90 |  | Replace DB1 and coupler CB
TO-20-220 kV B1 @ LOU-02 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 2 |  | connection between new DB1 and DA1
TO-20-220 kV B1 @ LOU-03 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 1 |  | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB
CAPX |  |  | CP0799 | DO | 1 |  | Energise new coupler DB1 and coupler CB
TO-20-220 kV B1 @ LOU-04 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV B2
TO-20-220 kV B2 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
COUPLER/SECTIONALISING CB - LOUTH 220K1-2
TO-20-LOU-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 90 |  | Replacement of coupler
TO-20-LOU-220K1-2-02 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | LOU |  | 901074162 | CANC | 3 | 1 | N O 1 F00 220 Coupler Switching and Ex
OPT | LOU | - | 901038920 | DO | 1 | 3 | 220kV MO Cubicle Operational Test
TRANSFORMER - LOUTH AT1
TO-20-LOU-AT1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900821328 | CANC |  | 1 | Replace Drycol Breather
TO-20-LOU-AT1-01 ISO week: 27mo - 30we Date: 29 Jun - 22 Jul Duration: 24 Days (18 WD) Status: Scheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | LOU | 220 | 901041554 | CLO | 10 | 4 | 220kV MO Cubicle Ordinary Service
OS | LOU | 275 | 901041555 | CLO | 7 | 4 | 275kV MO Cubicle Ordinary Service
OS | LOU | Trafo | 901042117 | CLO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CA | LOU | 275 | 901129257 | CLO | 3 | 4 | 275KV CUBICLE CONDITION ASSESSMENT
TRAFO | LOU | TRAFO | 901129265 | CLO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
TRAFO | LOU | TRAFO | 901130086 | CLO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
CORRECT | LOU | TRAFO | 901039328 | DO | 1 | 2 | Louth AT1 Transformer: Drycol Replacement
TRANSFORMER - LOUTH AT2
TO-20-LOU-AT2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOFAULT | LOU | TRAFO | 900962773 | CANC | 1 | 1 | O 1 AT2 Trafo mech box Excessive conde
TO-20-LOU-AT2-01 ISO week: 31th - 34th Date: 30 Jul - 20 Aug Duration: 22 Days (15 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | LOU | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | LOU | Trafo |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | LOU | 275 |  | DO | 4 | 4 | 275kV SF6 Cubicle Ordinary Service
AMCAB | LOU | 275 |  | DO | 3 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | LOU |  | 901059811 | DO | 3 | 1 | Invesigate system fault
TRANSFORMER - LOUTH AT3
TO-20-LOU-AT3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900821331 | CANC |  | 1 | Replace Drycol Breather
CORRECT | LOU |  | 900908057 | NS |  | 1 | Replace Conservator tank supports AT3
TO-20-LOU-AT3-01 ISO week: 30th - 31we Date: 23 Jul - 29 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | LOU | 220 | 901129023 | CLO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | LOU | TRAFO | 901039329 | DO | 1 | 2 | Louth AT3 Transformer: Drycol Replacement
CORRECT | LOU |  | 901059908 | DO | 1 | 1 | Replace Sensor
CAPACITOR/SVC/REACTOR - LOUTH CAP1
TO-20-LOU-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900982921 | DO | 1 | 1 | Surge counters/Ammeters on R/S/T phases
110kV FEEDER - LOUTH MEATH HILL
TO-20-LOU-MTH-1-01 ISO week: 19tu - 19fr Date: 05 May - 08 May Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085133 | DO | 1 | 4 | 2019HP-1[72]Stays-Replace broken
CORRECT | LOU |  | 901087475 | CLO | 4 | 1 | EMP AMS: Check VT bellows on R,S and T p
110kV FEEDER - LOUTH MULLAGHARLIN
TO-20-LOU-MLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-LOU-MLN-1-03 Status: Unscheduled
CORRECT | LOU |  | 901059534 | CANC |  | 1 | N O 1 H01 Mullagharlin Switching and
TO-20-LOU-MLN-1-02 ISO week: 45fr Date: 06 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LOUTH RATRUSSAN
TO-20-LOU-RRU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084279 | CLO | 1 | 4 | 2019HP-1[123]Bird Nests
FO_MISC |  |  | 901084320 | CLO | 1 | 4 | 2019HP-1[126]Bird Nests
FO_MISC |  |  | 901084321 | CLO | 1 | 4 | 2019HP-1[128]Bird Nests
FO_MISC |  |  | 901084322 | CLO | 1 | 4 | 2019HP-1[130]Bird Nests
FO_MISC |  |  | 901084924 | CLO | 1 | 4 | 2019HP-1[197]Insulator broken aux string
OS | LOU | - | 901050323 | CLO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OPT | RRU | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-LOU-RRU-1-03 Status: Unscheduled
YM03 | - | Line | 901110486 | CLO | 5 | 1 | Am No.165 165 - 166 Right Dead end termination Replace joint within 3 months pending TSO review.
YM03 | - | Line | 901110487 | CLO | 5 | 1 | R1 107 - 108 Right Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110488 | CLO | 5 | 1 | Am No.51 51 - 52 Right Dead end termination Replace joint immediately pending TSO review.
TRANSFORMER - LOUTH T2101
TO-20-LOU-T2101-01 ISO week: 45tu - 45th Date: 03 Nov - 05 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | LOU | TRAFO | 901039288 | NS | 3 | 2 | Louth T2101 Transformer: Camlin Totus G9 Gas in Oil Monitor
OPT | LOU | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - LOUTH T2102
TO-20-LOU-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900908023 | CANC |  | 1 | Repair leak on LV bushing, bushing needs
CORRECT | LOU |  | 900908033 | CANC |  | 1 | Shot blast and treat main cover corrosio
CORRECT | LOU |  | 900950041 | NS |  | 1 | ABB to repair an oil leak on Louth T2102
TO-20-LOU-T2102-01 ISO week: 11mo - 12fr Date: 09 Mar - 20 Mar Duration: 12 Days (9 WD) Status: Scheduled
|  | - |  |  | 13 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of R1Z23b, ISM21
CORRECT | LOU | TRAFO | 901039286 | CLO | 5 | 2 | Louth T2102 Transformer: Repair leak on LV bushing, bushing needs to be removed and seals replaced by ABB Repeat tan delta and FDS tests on transformer
CORRECT | LOU |  | 900789878 | CLO | 2 | 1 | repair leak on LV bushings
CORRECT | LOU |  | 901087467 | DO | 1 | 1 | EMP AMS Replace CB Counter
OPT | LOU | 110 | 901129471 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | LOU | 220 | 901129539 | CLO | 1 | 4 | 220kV MO Cubicle Operational Test
TRANSFORMER - LOUTH T2103
TO-20-LOU-T2103-01 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | LOU | Trafo | 901042116 | DO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | LOU | 220 | 901042343 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | LOU | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
FM | LOU | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TRANSFORMER - LOUTH T2104
TO-20-LOU-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900873633 | CANC |  | 1 | ESBIN01 GE are to supply a new Hydran 20
TO-20-LOU-T2104-01 ISO week: 10we - 10fr Date: 04 Mar - 06 Mar Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA511, 7UT92
OPT | LOU | 220 | 901038922 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | LOU | 110 | 901038927 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | LOU | TRAFO | 901045371 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
275kV FEEDER - LOUTH TANDRAGEE 2
TO-20-LOU-TAN-2-01 ISO week: 31th - 34th Date: 30 Jul - 20 Aug Duration: 22 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513, LFZP111
220kV FEEDER - LOUTH WOODLAND
TO-20-LOU-WOO-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| LOU |  |  |  | 3 |  | 220kV Cubicle Condition Assessment
TO-20-LOU-WOO-1-01 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 1 |  | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB
TO-20-LOU-WOO-1-04 Status: Unscheduled
CORRECT | WOO |  | 900444614 | NS |  | 2 | O. ESBI Inspect and test all the cylind
TO-20-LOU-WOO-1-02 ISO week: 22mo - 25fr Date: 25 May - 19 Jun Duration: 26 Days (19 WD) Status: Scheduled
CAPX |  |  | MC0334 | DO | 15 |  | Uprate bay conductor on Louth - Woodland circuit
|  | - |  |  | 11 |  | Total Maintenance Outage Duration Requested
|  |  | 900944377 |  | 4 |  | 1[67] Replace all composite strain insulators with glass
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL521
|  |  | 900988605 |  | 1 |  | 2018HP-1[Am 128]Bird Nests
|  |  | 900988614 |  | 1 |  | 2018HP-1[189]Check Struct/Found/etc-base
| LOU |  |  |  | 10 |  | 220kV MO Cubicle Ordinary Service
OS | LOU | - | 901050446 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038535 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
PROT | LOU |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA612, REL521
CORRECT | LOU |  | 901081602 | DO |  | 1 | N O 1 Woodland F03 Switching and Extra
| WOO |  |  |  | 5 |  | 220kV SF6 Cubicle Ordinary Service
OS | WOO | - | 901042336 | CLO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
PROT | WOO |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA513, REL521
SECTIONALISING DISCONNECT - MACETOWN 110SA2
TO-20-MCE-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | MCE | SA2 | 901039707 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - MACETOWN SNUGBOROUGH
TO-20-MCE-SNU-1-01 ISO week: 47mo - 47we Date: 16 Nov - 18 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901068538 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | SNU | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SNU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MACETOWN T121 [IBM]
TO-20-MCE-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ511
TSO CUSTOMER TRANSFORMER - MACETOWN T124 [IBM]
TO-20-MCE-T124-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901038753 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MACROOM 110SA1
TO-20-MAC-110SA1-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 15 |  | Proximity outage (SA2)
TO-20-MAC-110SA1-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-MAC-110SA1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 32 |  | Old SA 1 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 25 |  | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-110SA1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-MAC-110SA1-05 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-MAC-110SA1-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | MAC | - | 900955833 | CLO | 2 | 2 | NO 2 -"T" missing from upright support
SECTIONALISING DISCONNECT - MACROOM 110SA2
TO-20-MAC-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 25 |  | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-MAC-110SA2-03 Status: Unscheduled
15 | [6 empty] | Proximity outage (SA1)
DISTRIBUTION TRANSFORMER - MACROOM T142 [SDCC]
TO-20-MAC-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
COUPLER/SECTIONALISING CB - MARINA 110K1-2
TO-20-MR-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
YM03 |  | - | 900981433 | DO | 2 | 4 | O1-110kv SA interlocking not working cor
GENERATOR TRANSFORMER - MARINA T107 [ESB GWM MR7]
TO-20-MR-T107-02 ISO week: 30th Date: 23 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | MR |  |  | DO | 1 | 4 | 110KV GIS Cubicle Operational Test
110kV FEEDER - MARINA TRABEG 1
TO-20-MR-TBG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
110kV FEEDER - MARINA TRABEG 2
TO-20-MR-TBG-2-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TBG | - | 901038815 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - MAYNOOTH 110 kV A1
TO-20-110 kV A1 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A2
TO-20-110 kV A2 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A3
TO-20-110 kV A3 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A4
TO-20-110 kV A4 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B1
TO-20-110 kV B1 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B2
TO-20-110 kV B2 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B3
TO-20-110 kV B3 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B4
TO-20-110 kV B4 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - MAYNOOTH 110K1-2
TO-20-MAY-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | MAY | 110-SB2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - MAYNOOTH 110K3-4
TO-20-MAY-110K3-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
OS | MAY | - | 901042253 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MAY | - | 900858412 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | MAY | 110-SA5 | 901038574 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SA6 | 901038575 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SB6 | 901038576 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SB5 | 901038577 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - MAYNOOTH 220 kV A1
TO-20-220 kV A1 @ MAY-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV
TO-20-220 kV A1 @ MAY-02 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV A2
TO-20-220 kV A2 @ MAY-01 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV B1
TO-20-220 kV B1 @ MAY-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV
TO-20-220 kV B1 @ MAY-02 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV B2
TO-20-220 kV B2 @ MAY-01 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - MAYNOOTH 220K1-2
TO-20-MAY-220K1-2-01 ISO week: 38tu - 38th Date: 15 Sep - 17 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | MAY | 220-SA1 |  | DO | 2 | 1 | Maynooth 220kV Coupler Sectionaliser SA2 All, left to right R,S & T Hotspot found on all 3 phases ofSA2 sectionaliser disconnects DUE : next available opportunity.
CM | MAY | 220-SA1 |  | DO | 2 | 1 | Maynooth 220kV Coupler Sectionaliser SA1 T Phas e Hotspot found on T phase SA1 sectionaliser disconnect DUE: next available opportunity.
OPT | MAY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | MAY | 220-SB2 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SB1 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SA2 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SA1 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
110kV FEEDER - MAYNOOTH RINAWADE
TO-20-MAY-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 220 kV K3-4
TO-20-MAY-RNW-1-03 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-MAY-RNW-1-01 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MAY | - | 901042239 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | RNW | - | 901038949 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MAYNOOTH RYEBROOK GIS
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: T132 EI - outage of feeder bay required for 2 days
TO-20-MAY-RYB GIS-1-04 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T131
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
220kV FEEDER - MAYNOOTH SHANNONBRIDGE
TO-20-MAY-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN | - | Line | 901110127 | CLO | 2 | 1 | Hotspot 1 (R1 Span 81/82) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110131 | DO | 2 | 1 | Hotspot 2 (R2 Span 255/256) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110136 | DO | 2 | 1 | Hotspot 3 (R1 Span 271/272) Right phase midspan (Repair by 17th July 2020)
TO-20-MAY-SH-1-01 ISO week: 26mo - 27th Date: 22 Jun - 02 Jul Duration: 11 Days (9 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819839 | DO | 4 | 2 | 2016HP-2[2 & 3]Insulator Fit Dups
FO_MISC |  |  | 901090694 | DO | 2 | 4 | 2019HP-1[47-48]Conflicts 10/20kV pole
FO_MISC |  |  | 901090695 | DO | 2 | 4 | 2019HP-1[51-52]Conflicts 10/20kV pole
CM | MAY | - | 901076415 | CLO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
CA | SH | - | 901038544 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TRANSFORMER - MAYNOOTH T2101
TO-20-MAY-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MAY | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | MAY | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MAY | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | MAY | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | MAY | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 - Ordinary Service
TRANSFORMER - MAYNOOTH T2102
TO-20-MAY-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | TRAFO | 900373274 | NS | 1 | 2 | O 1. ESBI Inpsect transformer (Tamini) f
CM | MAY | TRAFO | 900693054 | NS | 1 | 2 | Replace/repair rust on main cover bolts and channel on top of the tank
TO-20-MAY-T2102-01 ISO week: 29tu - 29fr Date: 14 Jul - 17 Jul Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OPT | MAY | TRAFO | 901080655 | DO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | MAY | 220 |  | DO | 1 | 4 | 220kV MO Cubicle Operational Test
OPT | MAY | 110 | 901038584 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY | TRAFO | 901039322 | DO | 1 | 2 | Maynooth T2102 Transformer: Drycol Replacement
TRANSFORMER - MAYNOOTH T2103
TO-20-MAY-T2103-01 ISO week: 37mo - 37we Date: 07 Sep - 09 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | MAY | 110 | 901128564 | DO | 2 | 1 | Hotspot 1 (110kV T-phase DB) Repair by 19th Sep 2020
OPT | MAY | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | MAY | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | MAY | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY | TRAFO | 901039289 | DO | 1 | 2 | maynooth T2103 Transformer: E6 dial stat faulty, shot blast and treat major main cover corrosion, retest CT and LV S phase bushing, repair several fans
TRANSFORMER - MAYNOOTH T2104
TO-20-MAY-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | TRAFO | 901039323 | DO | 1 | 2 | Maynooth T2104 Transformer: Drycol Replacement
TO-20-MAY-T2104-03 Status: Unscheduled
CORRECT | MAY | TRAFO | 901039290 | NS | 7 | 2 | Maynooth T2104 Transformer: Refurbish fans and treat corrosion on top cover. Can be done as part of next OS
TO-20-MAY-T2104-01 ISO week: 32tu - 32fr Date: 04 Aug - 07 Aug Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA612, RET521
OPT | MAY | 220 | 901039022 | CLO | 3 | 3 | 220kV SF6 Cubicle Operational Test
OPT | MAY | TRAFO | 901045376 | CLO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
CORRECT | MAY |  | 901080648 | CLO | 1 | 2 | Silica On T2104 To Be Replaced
220kV FEEDER - MAYNOOTH TURLOUGH HILL
TO-20-MAY-TH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900988793 | DO | 2 | 2 | 2018HP-1[5]Insulatorfit duplicate
TRAN |  | - | 900988794 | DO | 2 | 2 | 2018HP-1[6]Insulatorfit duplicate
CORRECT | TH |  | 901087476 | NS | 10 | 2 | Full overhaul of Circuit Breaker
CORRECT | TH |  | 901084687 | NS | 5 | 2 | 1.Replace R phase CB pole and drive insu
TO-20-MAY-TH-1-01 Status: Unscheduled
CAPX |  |  | CP1022 | DO | 25 |  | EI: Replacement and Commissioning of PLC Equipment
TRAN |  | - | 900988802 | DO | 2 | 2 | 2018HP-1[173]Insulatorbroken
FO_MISC |  |  | 901084925 | DO | 2 | 2 | 2019HP-1[99]Insulator Broken insulator
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
CORRECT | MAY |  | 901080651 | DO | 2 | 1 | Low Oil / Leak- CB Oil Low
AMCAB | TH | - | 901005625 | DO | 3 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
TO-20-MAY-TH-1-04 Status: Unscheduled
CM | TH | - | 901128568 | CLO | 2 | 1 | S Phase Hotspot found on S Phas HV Connection by 6th July 2020
TO-20-MAY-TH-1-03 ISO week: 28mo - 28tu Date: 06 Jul - 07 Jul Duration: 2 Days (2 WD) Status: Scheduled
| TH |  | 20CM0450 |  | 2 |  | S Phase Hotspot found on S Phase HV connection by 6th July
220kV FEEDER - MAYNOOTH WOODLAND
TO-20-MAY-WOO-1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901076417 |  | 3 |  | Copper earths stolen from 220kV CT and VT to be reinstalled
TO-20-MAY-WOO-1-02 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  | - | 900819860 | DO | 1 | 2 | 2016HP-1[5-71]Check Structure -Painting
TRAN |  | - | 900988803 | DO | 1 | 4 | 2018HP-1[5]Check Struct/Found/etc-base
CM | MAY | - | 901076417 | DO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
FM | WOO | - | 900943534 | DO | 2 | 3 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - MEENTYCAT T121 [Meentycat MCT]
TO-20-MEE-T121-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of work on Drumkeen-Meentycat 110 kV
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MEE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - MIDLETON 110SA1
TO-20-MID-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of MID-110SA2: 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MIDLETON 110SA2
TO-20-MID-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | MID | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MID-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-20-MID-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-20-MID-WHI-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988883 | DO | 2 | 4 | "2018HP-2[41,42]Sus/Dup 110kV replace"
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084330 | DO | 1 | 2 | 2019HP-1[22]Bird Nests Over Right phase
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
OPT | MID |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
SECTIONALISING DISCONNECT - MONETEEN 110SA1
TO-20-MTN-110SA1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of MTN-110SA2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MONETEEN 110SA2
TO-20-MTN-110SA2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
OS | MTN | SA2 | 901039690 | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - MONETEEN MUNGRET 1
TO-20-MTN-MUN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MTN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - MONETEEN MUNGRET 2
TO-20-MTN-MUN-2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | MTN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - MONEYPOINT 400 kV A1
TO-20-400 kV A1 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A1 / A3 BB In Turn, SA1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV A2
TO-20-400 kV A2 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A2 / A4 BB In Turn, SA2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV B1
TO-20-400 kV B1 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
B1 / B3 BB In Turn, SB1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV B2
TO-20-400 kV B2 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
B2 / B4 BB In Turn , SB2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays
COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110SA1-2CB
TO-20-MP GIS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | - |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
400kV FEEDER - MONEYPOINT GIS OLDSTREET
TO-20-MP GIS-OST-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900988931 | NS |  | 1 | 2018HP-1[166]Bird Nestsremove asap
TRAN |  | - | 900988938 | NS |  | 1 | 2018HP-1[176]Bird Nestsremove asap
TRAN |  | - | 900988946 | NS |  | 1 | 2018HP-1[191]Bird Nestsremove asap
TRAN |  | - | 900988976 | NS |  | 1 | 2018HP-1[74]Bird Nestsremove asap
TO-20-MP GIS-OST-1-04 Status: Unscheduled
studied outage for CP0824
TO-20-MP GIS-OST-1-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-MP GIS-OST-1-01 ISO week: 9mo - 14th Date: 24 Feb - 02 Apr Duration: 39 Days (28 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting
TO-20-MP GIS-OST-1-02 ISO week: 21th - 41fr Date: 21 May - 09 Oct Duration: 142 Days (100 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting (part 2)
|  |  | OD0321 |  | 5 |  | Total Maintenance Outage Duration Requested
|  | MP | 19EG23677 | CLO | 2 |  | Cable Insp. 400kV XLPE
|  |  | 20LN4755 |  | 2 |  | 2019HP-1[11]Insulator Broken
|  |  | 18LN1616 |  | 1 |  | 2017HP-1[199]Earths-Check S/W hardware
|  |  | 18LN1618 |  | 1 |  | 2017HP-1[55A]Insulator Broken
|  |  | 18LN1631 |  | 1 |  | 2017HP-1[139]Earths-Check S/W hardware
|  |  | 19LN6391 |  | 1 |  | 2018HP-3[3]Insul&HW Replace check
|  |  | 19LN6392 |  | 1 |  | 2018HP-3[8]Insul&HW Replace check
|  |  | 19LN6393 |  | 1 |  | 2018HP-2[11]Insul&HW Replace check
|  |  | 19LN6394 |  | 1 |  | 2018HP-3[15]Insul&HW Replace check
|  |  | 19LN6395 |  | 1 |  | 2018HP-1[13]Insul&HW Replace check
|  |  | 19LN6396 |  | 1 |  | 2018HP-1[27]Insul&HW Replace check
|  |  | 19LN6398 |  | 1 |  | 2018HP-1[55A]Insulator-replace
|  |  | 20LN4741 |  | 1 |  | 2019HP-1[166]Bird Nests
|  |  | 20LN4743 |  | 1 |  | 2019HP-1[175]Bird Nests
|  |  | 20LN4744 |  | 1 |  | 2019HP-1[183]Bird Nests
|  |  | 20LN4745 |  | 1 |  | 2019HP-1[191]Bird Nests
|  |  | 20LN4756 |  | 1 |  | 2019HP-1[55A]Insulator Broken
| OST |  | 18EG10486 |  | 2 |  | 400kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T121 [Moneypoint MP9]
TO-20-MP GIS-T121-01 ISO week: 30fr Date: 24 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | TRAFO | 900938612 | DO | 1 | 3 | 110KV GIS Cubicle Operational Test
TRANSFORMER - MONEYPOINT GIS T2102
TO-20-MP GIS-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MP |  | 901059126 | CANC |  | 1 | Main Tank Conservator oil level gauge is
TO-20-MP GIS-T2102-03 Status: Unscheduled
CORRECT | MP | TRAFO | 901028665 | CANC | 4 | 2 | Replacement Oil Level Indicator for Moneypoint T2102 Main OLTC Conservator. Original oil level gauge faulty contacts and activating a contsant low oil level alarm evndo the oil level when check is ok.
TO-20-MP GIS-T2102-01 ISO week: 10mo - 10fr Date: 02 Mar - 06 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MP | - | 900970626 | CLO | 4 | 1 | The minitrans unit on T2102 in Moneypoin
OPT | MP | TRAFO | 900944114 | CLO | 2 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | MP | 220 | 900944165 | CLO | 2 | 3 | 220kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T4003 [ESB GWM MP3]
TO-20-MP GIS-T4003-01 ISO week: 24we - 25we Date: 10 Jun - 17 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 | 2 | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TRANSFORMER - MONEYPOINT GIS T4201
TO-20-MP GIS-T4201-01 ISO [year]week: 1we - N/A Date: 01 Jan - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Forced outage
TO-20-MP GIS-T4201-02 Status: Unscheduled
FOFAULT | MP | TRAFO | 901028372 | CANC | 2 | 1 | Ref- T4201 Bucholz alarm
CORRECT | MP |  | 901037956 | CANC |  | 1 | As part of the Fault Investigation into
TRANSFORMER - MONEYPOINT GIS T4202
TO-20-MP GIS-T4202-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MP |  | 901067748 | CANC |  | 1 | Atlantic Projects Company were required
CORRECT | MP | 220 | 901073579 | CANC |  | 1 | Camlin Power are to install an Intego bu
TO-20-MP GIS-T4202-01 Status: Unscheduled
| MP | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | MP | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | MP | 400 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | MP | 400 |  | DO | 1 | 4 | 400kV GIS Cubicle Operational Test
OPT | MP | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - MONEYPOINT PROSPECT
TO-20-MP-PRO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | PRO | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-MP-PRO-1-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
TO-20-MP-PRO-1-03 Status: Unscheduled
AMCAB | MP | 220 | 901129060 | DO | 2 | 4 | Insp. 400 & 220 Station XLPE Cable
GENERATOR TRANSFORMER - MONEYPOINT T4001 [ESB GWM MP1]
TO-20-MP-T4001-01 ISO week: 48tu - 48th Date: 24 Nov - 26 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| MON | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | MP |  |  | DO | 2 | 1 | 400kV GIS Cubicle Operational Test
AMCAB | MP | - | 901005716 | DO | 2 | 4 | Insp. 400 & 220 Station XLPE Cable
FM | MP | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - MOUNTLUCAS T121 [Mountlucas MO1]
TO-20-MLC-T121-01 ISO week: 24we Date: 10 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLC | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CAPACITOR/SVC/REACTOR - MOY CAP1
TO-20-MOY-CAP1-02 ISO week: 11mo - 43th Date: 09 Mar - 22 Oct Duration: 228 Days (158 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | MOY | - | 901042293 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MOY | CAP | 901050225 | CLO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
CAPACITOR/SVC/REACTOR - MOY CAP2
TO-20-MOY-CAP2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | MOY | - | 901042294 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MOY | CAP | 901050226 | DO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
110kV FEEDER - MOY TAWNAGHMORE 1
TO-20-MOY-TAW-1-02 ISO week: 11mo - 43th Date: 09 Mar - 22 Oct Duration: 228 Days (158 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
CORRECT | TAW |  | 901090593 | CLO | 5 | 1 | An SF6 leak was detected on the pipework
OPT | TAW | 110 | 900942733 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MOY TAWNAGHMORE 2
TO-20-MOY-TAW-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | MOY | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | TAW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MULLAGHARLIN 110SA1
TO-20-MLN-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MLN |  | 901059536 | CANC |  | 1 | N O 1 H00 SA2 Switching and Extra hou
TO-20-MLN-110SA1-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of MLN-110SA2: 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MULLAGHARLIN 110SA2
TO-20-MLN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1101 | DO | 27 |  | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: Civil works on bay H1 and H0
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
OS | MLN | SA2 | 901039708 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MLN-110SA2-02 ISO week: 44tu - 44th Date: 27 Oct - 29 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 3 |  | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: 1 - H3-T121 Transfomer relabelling to H3-T123
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T121 [Xerox]
TO-20-MLN-T121-02 ISO week: 32th - 32fr Date: 06 Aug - 07 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Customer outage request
TO-20-MLN-T121-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
CAPX |  |  | CP1101 | DO | 2 |  | T121 Trafo Relabelling to T123
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T122 [Xerox]
TO-20-MLN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-MLN-T122-03 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request
COUPLER/SECTIONALISING CB - MULLINGAR 110SA1-2CB
TO-20-MUL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-MUL-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MUL | - | 901129883 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | MUL | SA1 | 901039452 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MUL-110SA1-2CB-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
CAPACITOR/SVC/REACTOR - MULLINGAR CAP1
TO-20-MUL-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - MULLINGAR CAP2
TO-20-MUL-CAP2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
TO-20-MUL-CAP2-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
CORRECT | MUL | - | 900869763 | CLO | 4 | 1 | Replace Densimeters on Circuit Breaker
OPT | MUL |  | 901129545 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - MULLINGAR T101 [NDCC]
TO-20-MUL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - MULLINGAR T102 [NDCC]
TO-20-MUL-T102-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
DISTRIBUTION TRANSFORMER - MULLINGAR T141 [NDCC]
TO-20-MUL-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - MULLINGAR T142 [NDCC]
TO-20-MUL-T142-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
GENERATOR TRANSFORMER - MULREAVY T131 [Mulreavy MB1/MB2]
TO-20-MRY-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | MRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - MUNGRET T101 [Irish Cement]
TO-20-MUN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer outage requestfor tap changer maintenance on incoming transformer T101
TSO CUSTOMER TRANSFORMER - MUNGRET T102 [Irish Cement]
TO-20-MUN-T102-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of MTN-MUN-2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
COUPLER/SECTIONALISING CB - NAVAN 110SA1-2CB
TO-20-NAV-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | NAV | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-NAV-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
CAPACITOR/SVC/REACTOR - NAVAN M/CAP1
TO-20-NAV-M/CAP1-01 ISO [year]week: 1we - N/A Date: 01 Jan - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
forced out
TO-20-NAV-M/CAP1-02 Status: Unscheduled
OS | NAV | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA1
TO-20-NEW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA1 | 901039710 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA2: 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA2
TO-20-NEW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA1: 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - NEWBRIDGE PORTLAOISE
TO-20-NEW-PLS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-NEW-PLS-1-01 ISO week: 10mo - 12fr Date: 02 Mar - 20 Mar Duration: 19 Days (14 WD) Status: Scheduled
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989025 | DO | 2 | 4 | 2018HP-1[106]ACGFit ACG
TRAN |  | - | 900989041 | CLO | 2 | 4 | 2018HP-1[201]Conductor Check-Top Rot
FO_MISC |  |  | 901084851 | DO | 2 | 4 | 2019HP-1[2-3]Conflicts 20kV cable pole
FOINSHW |  | - | 900973635 | DO | 1 | 3 | 1[214]Install Duplicate Suspension Insul
TRAN |  | - | 900989023 | DO | 1 | 4 | 2018HP-1[56-57]Conflicts-LV/MV pole
TRAN |  | - | 900989024 | CLO | 1 | 4 | 2018HP-2[68]Cattle Guards
TRAN |  | - | 900989035 | CLO | 1 | 4 | 2018HP-1[137]Insul&HW Replace check
TRAN |  | - | 900989036 | CLO | 1 | 4 | 2018HP-1[138]Insul&HW Replace check
TRAN |  | - | 900989037 | CLO | 1 | 4 | 2018HP-1[139]Insul&HW Replace check
TRAN |  | - | 900989038 | CLO | 1 | 4 | 2018HP-1[145]Insul&HW Replace check
FO_MISC |  |  | 901084324 | DO | 1 | 4 | 2019HP-1[106]Bird Nests -Remove
TRAN |  | - | 901146901 | CLO | 1 | 1 | Hotspot 3 (Angle Tower No. 117, span 116/117), right jumper terminal
TRAN | - | - | 901128694 | CLO | 1 | 1 | Hotspot 1 (Angle Tower No. 48, span 48/49), left Jumper Terminal
TRAN | - | - | 901146902 | CLO | 1 | 1 | Hotspot 2 (Angle Tower No. 116, span 115A/116), right deadend
CORRECT | NEW |  | 901059566 | CLO | 5 | 1 | Replace SF6 pipework
CORRECT | NEW |  | 901060158 | CLO | 5 | 1 | O1-Small SF6 piping to be changed on CB.
DISTRIBUTION TRANSFORMER - NEWBRIDGE T141 [NDCC]
TO-20-NEW-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - NEWBRIDGE T142 [NDCC]
TO-20-NEW-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
220kV FEEDER - NORTH WALL POOLBEG
TO-20-NW-PB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - | 900913186 | DO | 5 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OS | NW | 220-DA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OPT | NW | - | 901039122 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OS | PB | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | PB | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TO-20-NW-PB-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
GENERATOR TRANSFORMER - NORTH WALL T2004/5 [ESB GWM NW5]
TO-20-NW-T2004/5-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
TRANSFORMER - OLDSTREET T4202
TO-20-OST-T4202-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of OST-TY-1: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-OST-T4202-03 Status: Unscheduled
CORRECT | OST |  | 901090507 | CANC |  | 1 | Following the increase of H2 gas within
TO-20-OST-T4202-04 Status: Unscheduled
CORRECT | OST | TRAFO | 901039294 | CANC | 3 | 2 | Oldstreet T4202 Transformer: Transfix G9 Installation
TO-20-OST-T4202-02 Status: Unscheduled
|  | - |  |  | 20 |  | Total Maintenance Outage Duration Requested
[5 empty] | 2 |  | Operator approval evaluations
TRAFO | OST | TRAFO |  | DO | 5 | 1 | 400/220kV Trafo Tap Changer Inspection
OS | OST | 400 |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
TRAFO | OST | TRAFO |  | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT
OS | OST | Trafo | 901041548 | DO | 5 | 4 | 400/220kV Transformer Ordinary Service
CA | OST | 400 |  | DO | 4 | 1 | 400KV CUBICLE CONDITION ASSESSMENT
OS | OST | 220 |  | DO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | OST | 220 | 901038565 | DO | 4 | 1 | 220kV Cubicle Condition Assessment
CORRECT | OST | TRAFO | 901039331 | DO | 1 | 2 | Oldstreet T4202 Transformer: Drycol Replacement
220kV FEEDER - OLDSTREET TYNAGH
TO-20-OST-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-OST-TY-1-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
MO |  |  | 901039105 |  | 1 |  | 220kV SF6 Cubicle Operational Test
FO_MISC |  |  | 901084335 | DO | 1 | 4 | 2019HP-1[17]Bird Nests
CM | TYN | - | 901133678 | DO | 2 | 1 | 220kV SF6 Cubicle Ordinary Service DUE : 17-Jul-20
OPT | TYN | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
400kV FEEDER - OLDSTREET WOODLAND
TO-20-OST-WOO-1-01 ISO week: 42sa - 44fr Date: 17 Oct - 30 Oct Duration: 14 Days (9 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084928 | DO | 2 | 4 | 2019HP-1[103]Insulator Broken
FO_MISC |  |  | 901084929 | DO | 2 | 4 | 2019HP-1[115]Insulator Broken
FO_MISC |  |  | 901084930 | DO | 2 | 4 | 2019HP-1[272]Insulator Remove old insul
FO_STDMG |  |  | 901086387 | DO | 2 | 4 | 2019HP-1[90 ]Replace Member
FO_STDMG |  |  | 901086388 | DO | 2 | 4 | 2019HP-1[100]Replace Member
FO_STDMG |  |  | 901086389 | DO | 2 | 4 | 2019HP-1[120]Replace Member
TRAN |  | - | 900989127 | DO | 1 | 4 | 2018HP-1[99]Replace Memberrakers
TRAN |  | - | 900989128 | DO | 1 | 4 | 2018HP-1[100]Replace Memberrakers
TRAN |  | - | 900989185 | DO | 1 | 4 | 2018HP-1[115]Insulator-broken c/ph
TRAN |  | - | 900989188 | DO | 1 | 4 | 2018HP-1[162]Check(General)Remove object
FO_MISC |  |  | 901084336 | DO | 1 | 4 | 2019HP-1[76]Bird Nests
FO_MISC |  |  | 901084337 | DO | 1 | 4 | 2019HP-1[79]Bird Nests
FO_MISC |  |  | 901084338 | DO | 1 | 4 | 2019HP-1[93]Bird Nests
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SL32, FYS3L, FYG2L
OPT | OST | - | 901039088 | DO | 2 | 4 | 400kV SF6 Cubicle Operational Test
CORRECT | WOO | R4001 | 900821342 | DO | 10 | 1 | Some work done in 2014 Beltec 2 leaks HV
CORRECT | WOO |  | 900724385 | DO | 5 | 1 | O/1 Repair to leak in concrete of Bund
CORRECT | WOO |  | 901046071 | DO | 3 | 1 | SF6 leak repair
FM | WOO | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | WOO |  | 900788839 | DO |  | 2 | Misc- work not on other CORRECT counters
DISTRIBUTION TRANSFORMER - OUGHTRAGH T141 [SDCC]
TO-20-OUG-T141-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
110kV FEEDER - OUGHTRAGH tee KNOCKEARAGH
TO-20-OUG,T-KER-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA511, REL521
OPT | KER | - | 901038793 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - OUGHTRAGH tee OUGHTRAGH
TO-20-OUG,T-OUG-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989804 | DO | 1 | 4 | 2018HP-1[192-193]Re-sag conductor
FO_MISC |  |  | 901084875 | DO | 1 | 2 | 2019HP-1[227]Earths-Replace earth wire
110kV FEEDER - OUGHTRAGH tee TRALEE
TO-20-OUG,T-TRL-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
OPT | TRL | - | 901038831 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - PLATIN T105 [Irish Cement]
TO-20-PLA-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
Customer works
CORRECT | PLA |  | 901087478 | DO | 5 | 2 | Replace CB Counter
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA1
TO-20-PA-110SA1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA2
TO-20-PA-110SA2-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
GENERATOR TRANSFORMER - POLLAPHUCA T101 [ESB GWM LI1/LI2/LI4]
TO-20-PA-T101-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
As a consequence of works on Stratford tee Pollaphuca
CORRECT | PA |  | 901079398 | DO | 2 | 2 | Check the bellows of the current transfo
CORRECT | PA |  | 901079400 | DO | 2 | 2 | Change the oil in the circuit breaker
CORRECT | PA |  | 901087470 | DO | 1 | 2 | EMP AMS: Replace CB Counter
COUPLER/SECTIONALISING CB - POOLBEG 220K2-3
TO-20-PB-220K2-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | PB | - |  | DO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | PB | 220-SB2-3 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | PB | 220-SA2-3 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - POOLBEG 220K3-4
TO-20-PB-220K3-4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | PB | - | 901042163 | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | PB | 220-SA3-4 | 901039697 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | PB | 220-SB3-4 | 901039698 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-PB-220K3-4-01 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
SECTIONALISING DISCONNECT - POOLBEG 220SA1-2
TO-20-PB-220SA1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OS | PB | 110-SA1-2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-PB-220SA1-2-02 Status: Unscheduled
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
SECTIONALISING DISCONNECT - POOLBEG 220SB1-2
TO-20-PB-220SB1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
CAPACITOR/SVC/REACTOR - POOLBEG R2001
TO-20-PB-R2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | PB | - | 900942637 | DO | 2 | 3 | 220kV SF6 Cubicle Operational Test
AMCAB | PB | R2001 | 900944063 | DO | 2 | 3 | Insp. 400 & 220 Feeder XLPE Cable
OPT | PB | R2001 | 900944210 | DO | 1 | 3 | HV Reactor Operational Test
CAPACITOR/SVC/REACTOR - POOLBEG R2002
TO-20-PB-R2002-01 ISO week: 24we - 24fr Date: 10 Jun - 12 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | PB | - | 901038594 | DO | 2 | 4 | Insp. 400 & 220 Feeder XLPE Cable
OPT | PB |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | PB | R2002 | 901038596 | DO | 1 | 4 | HV Reactor Operational Test
CAPACITOR/SVC/REACTOR - POOLBEG R223-4
TO-20-PB-R223-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
CA | PB | 220-R223-4 | 900858397 | DO | 3 | 3 | 220KV REACTOR CONDITION ASSESSMENT
CA | PB | 220-BAY4 | 900858465 | DO | 3 | 3 | 220KV CUBICLE CONDITION ASSESSMENT
CA | PB | 220-BAY3 | 900858466 | DO | 3 | 3 | 220KV CUBICLE CONDITION ASSESSMENT
AMCAB | PB | Bay4 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | PB | Bay3 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | PB | 220-R223-4 | 901045341 | DO | 2 | 4 | HV Reactor Operational Test
OPT | PB | 220-BAY3 | 901038941 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | PB | 220-BAY4 | 901038945 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-PB-R223-4-02 ISO week: 48tu - 51th Date: 24 Nov - 17 Dec Duration: 24 Days (18 WD) Status: Scheduled
| PB |  |  |  | 18 |  | FS6 repair
220kV FEEDER - POOLBEG SHELLYBANKS
TO-20-PB-SHL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D1/CB3
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV D2/CB3
TO-20-PB-SHL-1-03 Status: Unscheduled
[5 empty] | 3 |  | Density Switch Replacement
TRANSFORMER - PORTAN T4301
TO-20-PRN-T4301-01 ISO week: 35th - 35fr Date: 27 Aug - 28 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | POR | 400 |  | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test
400kV FEEDER - PORTAN WOODLAND
TO-20-PRN-WOO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | 400 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | WOO | 400-1 |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CA | WOO | 400-1 |  | DO | 3 | 4 | 400kV Cubicle Condition Assessment
BUSBAR SECTION - PORTLAOISE 110 kV A1
TO-20-110 kV A1 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV A2
TO-20-110 kV A2 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV B1
TO-20-110 kV B1 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV B2
TO-20-110 kV B2 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
COUPLER/SECTIONALISING CB - PORTLAOISE 110K1-2
TO-20-PLS-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | PLS | 110-SA1 | 900859298 | DO | 2 | 2 | 110kV Sect / Dist Ordinary Service
OS | PLS | 110-SB1 | 900859306 | DO | 2 | 2 | 110kV Sect / Dist Ordinary Service
OPT | PLS | - | 901038676 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | PLS | 110-SB2 | 901042975 | DO | 2 | 4 | 110kV Sect / Dist Operational Test
OPT | PLS | 110-SA2 | 901042976 | DO | 2 | 4 | 110kV Sect / Dist Operational Test
220kV FEEDER - PROSPECT TARBERT
TO-20-PRO-TB-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Prox outage required for pipeline survey
TO-20-PRO-TB-1-04 ISO week: 31mo - 31tu Date: 27 Jul - 28 Jul Duration: 2 Days (2 WD) Status: Scheduled
Prox outage required for pipeline survey
TO-20-PRO-TB-1-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_CABLE |  | - | 900952297 | CLO | 2 | 1 | Replacement of Cathodic Protection Battery
AMCAB | TB | - | 901113198 | CLO | 2 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | TB |  | 901129537 | CLO | 1 | 4 | 220kV MO Cubicle Operational Test
COUPLER/SECTIONALISING CB - RAFFEEN 110K1-2
TO-20-RAF-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - RAFFEEN 220K1-2
TO-20-RAF-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | RAF | - | 901042176 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | RAF | 220-SB | 900942645 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | RAF | 220-SA | 901039742 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
FM | RAF | - | 901045776 | DO | 1 | 4 | HV Pressure Vessel Inspection
TO-20-RAF-220K1-2-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
CAPACITOR/SVC/REACTOR - RAFFEEN CAP2
TO-20-RAF-CAP2-01 ISO week: 41tu - 42tu Date: 06 Oct - 13 Oct Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | RAF | - | 901129961 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - RAFFEEN RINGASKIDDY [SDCC]
TO-20-RAF-RSY-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RAF | - | 900942660 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TO-20-RAF-RSY-1-02 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, GRZ100
TRANSFORMER - RAFFEEN T2101
TO-20-RAF-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | RAF | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | RAF | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | RAF | Trafo |  | DO |  | 4 | 220/110 & 275/220 Trafo Ordinary Service
TO-20-RAF-T2101-01 ISO week: 43tu - 43we Date: 20 Oct - 21 Oct Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
|  |  | PROT |  |  |  | P2 Protection maintenance of 7SA511, 7SA511, 7UT512
CORRECT | RAF |  | 900908059 | DO |  | 2 | Degas oil completely T2101
TO-20-RAF-T2101-03 ISO week: 43tu - 43th Date: 20 Oct - 22 Oct Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | RAF | - |  | DO | 2 | 1 | Replace stolen earths
TRANSFORMER - RAFFEEN T2102
TO-20-RAF-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | RAF | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | RAF | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | RAF | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
FM | RAF | 110 |  | DO | 1 | 1 | HV Pressure Vessel Inspection
CORRECT | RAF |  | 901060347 | DO | 1 | 2 | Replace Signs on Trafo's and Assoicated
TO-20-RAF-T2102-02 Status: Unscheduled
CORRECT | RAF |  | 901075226 | CANC |  | 1 | Replace Earths
110kV FEEDER - RAFFEEN TRABEG 1
TO-20-RAF-TBG-1-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
CORRECT | RAF | - |  | DO | 2 | 1 | Replace stolen earths
CORRECT | RAF |  | 901074427 | DO | 1 | 2 | Replce Bay Signage
110kV FEEDER - RAFFEEN TRABEG 2
TO-20-RAF-TBG-2-02 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901133690 | DO | 2 | 2 | Clean cable sealing ends (and stand-off insulators) at line/cable interface compound at Trabeg station.
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
TO-20-RAF-TBG-2-01 ISO week: 12mo - 13tu Date: 16 Mar - 24 Mar Duration: 9 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085002 | DO | 3 | 4 | 2019HP-3[20,22,23]Off Plumb -plumb poles
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
SECTIONALISING DISCONNECT - RATRUSSAN 110SA1
TO-20-RRU-110SA1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 2 | 4 | Total Maintenance Outage Duration Requested
OS | RAT | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-RRU-110SA1-01 ISO week: 11mo - 11tu Date: 09 Mar - 10 Mar Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RRU-110SA1-02 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of RRU-110SA2: 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - RATRUSSAN 110SA2
TO-20-RRU-110SA2-02 ISO week: 11mo - 11tu Date: 09 Mar - 10 Mar Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RRU-110SA1: 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RRU-110SA2-01 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
OS | RAT | SA2 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - RATRUSSAN SHANKILL
TO-20-RRU-SKL-1-01 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
TRAN |  | - | 900989485 | DO | 1 | 4 | 2018HP-1[48]Bird Nests
FO_MISC |  |  | 901084326 | DO | 1 | 4 | 2019HP-1[33]Bird Nests
FO_MISC |  |  | 901084327 | DO | 1 | 4 | 2019HP-1[48]Bird Nests
OPT | RRU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SKL | - | 901129889 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SKL | - | 901129196 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-RRU-SKL-1-02 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
GENERATOR TRANSFORMER - RATRUSSAN T121 [Bindoo BD1]
TO-20-RRU-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
GENERATOR TRANSFORMER - RATRUSSAN T122 [Mountain Lodge ML1]
TO-20-RRU-T122-01 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
CORRECT | RRU |  | 900990024 | CLO | 3 | 1 | Re-Test - Condition Assessment of the Cu
OPT | RRU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-RRU-T122-02 ISO week: 40tu - 40th Date: 29 Sep - 01 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 3 |  | Customer outage request
SECTIONALISING DISCONNECT - REAMORE 110SA1
TO-20-REM-110SA1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
SECTIONALISING DISCONNECT - REAMORE 110SA2
TO-20-REM-110SA2-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
DISTRIBUTION TRANSFORMER - REAMORE T142 [SDCC]
TO-20-REM-T142-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
110kV FEEDER - REAMORE TRALEE
TO-20-REM-TRL-1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | REM |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - RINAWADE 110SA1
TO-20-RNW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
OS | RNW | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-RNW-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RNW-110SA2: 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - RINAWADE 110SA2
TO-20-RNW-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RNW-110SA1: 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RNW-110SA2-01 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
| RNW |  |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | RNW | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TSO CUSTOMER TRANSFORMER - RINAWADE T121 [Hewlett Packard]
TO-20-RNW-T121-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RNW-T121-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SJ511
OPT | RNW | - | 901038951 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - RINAWADE T122 [Hewlett Packard]
TO-20-RNW-T122-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RNW | - | 901038952 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - RYEBROOK GIS 110 kV A1
TO-20-110 kV A1 @ RYB GIS-02 ISO week: 45we - 45th Date: 04 Nov - 05 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-110 kV A1 @ RYB GIS-03 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T131
TO-20-110 kV A1 @ RYB GIS-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
BUSBAR SECTION - RYEBROOK GIS 110 kV A1/A2/A4
TO-20-110 kV A1/A2/A4 @ RYB GIS-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: T132 EI - outage of feeder bay required for 2 days
BUSBAR SECTION - RYEBROOK GIS 110 kV A3
TO-20-110 kV A3 @ RYB GIS-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-110 kV A3 @ RYB GIS-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
BUSBAR SECTION - RYEBROOK GIS 110 kV B1
TO-20-110 kV B1 @ RYB GIS-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
BUSBAR SECTION - RYEBROOK GIS 110 kV B3
TO-20-110 kV B3 @ RYB GIS-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
BUSBAR SECTION - RYEBROOK GIS 110 kV B4
TO-20-110 kV B4 @ RYB GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110K3
TO-20-RYB GIS-110K3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB | - | 900942678 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110K3-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-RYB GIS-110K3-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110K4
TO-20-RYB GIS-110K4-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
TO-20-RYB GIS-110K4-01 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB | - | 900942679 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110K4-03 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA1-2CB
TO-20-RYB GIS-110SA1-2CB-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131
TO-20-RYB GIS-110SA1-2CB-03 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
TO-20-RYB GIS-110SA1-2CB-02 ISO week: 45we - 45th Date: 04 Nov - 05 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-RYB GIS-110SA1-2CB-01 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA1-3CB
TO-20-RYB GIS-110SA1-3CB-05 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
TO-20-RYB GIS-110SA1-3CB-04 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-RYB GIS-110SA1-3CB-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-RYB GIS-110SA1-3CB-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA2-4CB
TO-20-RYB GIS-110SA2-4CB-02 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB1-2CB
TO-20-RYB GIS-110SB1-2CB-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB1-3CB
TO-20-RYB GIS-110SB1-3CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110SB1-3CB-04 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
TO-20-RYB GIS-110SB1-3CB-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB2-4CB
TO-20-RYB GIS-110SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T105 [Intel]
TO-20-RYB GIS-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T106 [Intel]
TO-20-RYB GIS-T106-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TO-20-RYB GIS-T106-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T107 [Intel]
TO-20-RYB GIS-T107-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - | 900926063 | DO | 2 | 3 | INSP. 110 STATION XLPE CABLE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T108 [Intel]
TO-20-RYB GIS-T108-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | RYB | - |  | DO | 2 | 4 | INSP. 110 STATION XLPE CABLE
TO-20-RYB GIS-T108-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T109 [Intel]
TO-20-RYB GIS-T109-01 ISO week: 22tu - 23tu Date: 26 May - 02 Jun Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - | 901129747 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T131 [Intel]
TO-20-RYB GIS-T131-01 ISO week: 47mo Date: 16 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 1 |  | Intel request to test transformer oil from T131. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
COUPLER/SECTIONALISING CB - SALTHILL 110SA1-2CB
TO-20-SAL-110SA1-2CB-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ611
OS | SAL | 110-SA2 | 900944542 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service
DISTRIBUTION TRANSFORMER - SALTHILL T102 [SDCC]
TO-20-SAL-T102-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | SAL |  |  |  | 2 |  | Proximity for SA2 Maintenance
GENERATOR TRANSFORMER - SEALROCK T103 [Aughinish Alumina SK3]
TO-20-SK-T103-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-3: 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-SK-T103-03 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequence of AUG-SK-3: 110 kV A1 @ AUG
TO-20-SK-T103-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CM |  |  | 901137683 | DO | 5 | 1 | Gas Leak Repar S Phase
AMCAB | SK | 110 | 901129121 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - SEALROCK T104 [Aughinish Alumina SK4]
TO-20-SK-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | 4 day customer outage
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-4: 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
AMCAB | SK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SK |  |  | DO | 2 | 4 | 110KV SF6 Cubicle Operational Test
TO-20-SK-T104-02 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of AUG-SK-4: 110 kV
Outage start @ 14:00 07 Sept 2020, Outage end @ 15:00 10 Sept 2020
Customer outage request
SECTIONALISING DISCONNECT - SHANKILL 110SA1
TO-20-SKL-110SA1-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
DISTRIBUTION TRANSFORMER - SHANKILL T141 [NDCC]
TO-20-SKL-T141-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
BUSBAR SECTION - SHANNONBRIDGE 110 kV A1
TO-20-110 kV A1 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV A1 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV A2
TO-20-110 kV A2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV A2 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV B1
TO-20-110 kV B1 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV B1 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV B2
TO-20-110 kV B2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV B2 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110K1-2
TO-20-SH-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SH | 110-SB2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SB1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-SH-110K1-2-02 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
BUSBAR SECTION - SHANNONBRIDGE 220 kV A1
TO-20-220 kV A1 @ SH-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A1 @ SH-01 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
BUSBAR SECTION - SHANNONBRIDGE 220 kV A2
TO-20-220 kV A2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 10 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs
TO-20-220 kV A2 @ SH-03 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo).
TO-20-220 kV A2 @ SH-05 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A2 @ SH-06 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 20 |  | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs.
TO-20-220 kV A2 @ SH-04 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
TO-20-220 kV A2 @ SH-02 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1058 | DO | 20 |  | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs.
BUSBAR SECTION - SHANNONBRIDGE 220 kV B1
TO-20-220 kV B1 @ SH-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B1 @ SH-01 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
BUSBAR SECTION - SHANNONBRIDGE 220 kV B2
TO-20-220 kV B2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 10 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs
TO-20-220 kV B2 @ SH-04 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 4 |  | Installation of tube between DA, DB and to CB
TO-20-220 kV B2 @ SH-05 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo).
TO-20-220 kV B2 @ SH-02 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 3 |  | Errection and installation of circuti breaker. B2 proximity outage required
TO-20-220 kV B2 @ SH-07 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B2 @ SH-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 20 |  | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs.
TO-20-220 kV B2 @ SH-06 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
TO-20-220 kV B2 @ SH-03 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1058 | DO | 20 |  | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs.
COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220K1-2
TO-20-SH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 1 |  | Coupler outage. Testing of interlocking between new trafo and coupler (drive sharfts on pantographs removed)
TO-20-SH-220K1-2-02 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | SH |  | 900315850 | DO | 3 | 1 | O.2.esbi reqd.moving contact to be repla
OPT | SH | 220-SA1 | 901130125 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | SH | 220-SA2 | 901130126 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | SH | 220-SB1 | 901130127 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - SHANNONBRIDGE T104 [ESB GWM WO4]
TO-20-SH-T104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SH-T104-01 ISO week: 36tu - 36we Date: 01 Sep - 02 Sep Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - SHANNONBRIDGE T2101
TO-20-SH-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 2 |  | EI: Feeder outage to accmodate EI of T224 (DA, DB and trafo).
TO-20-SH-T2101-02 ISO week: 21mo - 22tu Date: 18 May - 26 May Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 9 |  | Total Maintenance Outage Duration Requested
OS | SH | 110 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | SH | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | SH | Trafo |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | SH |  | 901059910 | CLO | 1 | 1 | Replace Sensor
TRANSFORMER - SHANNONBRIDGE T2102
TO-20-SH-T2102-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | SH |  | 901059909 | CANC |  | 1 | Investigate unit fault
TO-20-SH-T2102-05 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SH-T2102-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | EI: EI to prove the new station & customer transformer T121 including 24 hour soak. Use T2102 in Shannonbridge to energise Derrycarney station on tail
TO-20-SH-T2102-01 ISO week: 22we - 24we Date: 27 May - 10 Jun Duration: 15 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | SH | TRAFO |  | DO | 6 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | SH | 110 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TRAFO | SH | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | SH | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | SH | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | SH | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | SH |  | 900867382 | CLO | 2 | 1 | ESBIN01 GE are to supply replacement hyd
TO-20-SH-T2102-04 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
Shannonbridge T2102 - VT replacement required
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB1
TO-20-SHL-D1/CB1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SHL |  |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-SHL-D1/CB1-02 ISO week: 23mo - 23we Date: 01 Jun - 03 Jun Duration: 3 Days (2 WD) Status: Tentative
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2016
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB2
TO-20-SHL-D1/CB2-01 ISO week: 34fr - 35tu Date: 21 Aug - 25 Aug Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2014
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SHL |  |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB3
TO-20-SHL-D1/CB3-01 ISO week: 34mo - 35tu Date: 17 Aug - 25 Aug Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2014
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB1
TO-20-SHL-D2/CB1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TO-20-SHL-D2/CB1-02 ISO week: 23mo - 23we Date: 01 Jun - 03 Jun Duration: 3 Days (2 WD) Status: Tentative
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2016
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB2
TO-20-SHL-D2/CB2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TO-20-SHL-D2/CB2-02 ISO week: 23fr - 23su Date: 05 Jun - 07 Jun Duration: 3 Days (1 WD) Status: Scheduled
CORRECT | SHL |  | 901079135 | DO | 3 | 2 | D5 disconnect failed to operate correctl
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB3
TO-20-SHL-D2/CB3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - SHELLYBANKS T2014 [ESB GWM PB4]
TO-20-SHL-T2014-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D1/CB3
OS | SHL | 220-DT |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
AMCAB | SHL | cable | 900838786 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
GENERATOR TRANSFORMER - SHELLYBANKS T2015 [ESB GWM PB5]
TO-20-SHL-T2015-01 ISO week: 24mo - 24th Date: 08 Jun - 11 Jun Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB2
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV D2/CB3
AMCAB | SHL | - | 901129026 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130137 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
GENERATOR TRANSFORMER - SHELLYBANKS T2016 [ESB GWM PB6]
TO-20-SHL-T2016-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
AMCAB | SHL | 220 | 901129027 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130138 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-SHL-T2016-02 ISO week: 23mo - 23th Date: 01 Jun - 04 Jun Duration: 4 Days (3 WD) Status: Scheduled
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
| SHL |  |  |  | 4 |  | Resolve DL S6 Leak
TSO CUSTOMER TRANSFORMER - SHELTON ABBEY T102 [Holfeld Plastics]
TO-20-SHE-T102-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
proximity outage to allow ESBN carry out the replacement of the corroded gantry in Shelton Abbey compound
COUPLER/SECTIONALISING CB - SINGLAND 110SA1-2CB
TO-20-SNG-110SA1-2CB-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
DSO proximity request for works on SNG T102
OPT | SNG | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | SNG | 110-SA2/DEM2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-SNG-110SA1-2CB-03 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
proximity for CA on Singland T101
TO-20-SNG-110SA1-2CB-02 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Proposed
OPT | SNG | 110-SA1/DEM1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - SINGLAND T101 [SDCC]
TO-20-SNG-T101-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CA on Singland T101
DISTRIBUTION TRANSFORMER - SINGLAND T102 [SDCC]
TO-20-SNG-T102-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO request for CA on SNG T102
BUSBAR SECTION - SLIABH BAWN 110 kV A2
TO-20-110 kV A2 @ SLB-01 ISO week: 27th Date: 02 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - SLIABH BAWN 110 kV B2
TO-20-110 kV B2 @ SLB-01 ISO week: 27th Date: 02 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - SLIGO 110SA1-2CB
TO-20-SLI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SLI | - | 901080653 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CAPACITOR/SVC/REACTOR - SLIGO CAP1
TO-20-SLI-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of SPAJ, 160C
110kV FEEDER - SLIGO SRANANAGH 1
TO-20-SLI-SRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
|  | - |  |  | 0 |  | Total Maintenance Outage Duration Requested
OPT | SLI | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | SRA | - | 901042241 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - | 901038567 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-SLI-SRA-1-01 ISO week: 43fr Date: 23 Oct Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends
110kV FEEDER - SLIGO SRANANAGH 2
TO-20-SLI-SRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | SRA |  | 901059776 | DO | 3 | 1 | Replace the pipework on the 110kV circui
CORRECT | SRA |  | 900535714 | DO | 1 | 1 | ESBI 02 non outage. Repeat online leakag
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110K2
TO-20-SNU-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | - | 901068540 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SA1-2CB
TO-20-SNU-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | 110-SA1-2 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SB1-2CB
TO-20-SNU-110SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | 110-SB1-2 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - SOMERSET T142 [SDCC]
TO-20-SOM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM-T142-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Reference
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
110kV FEEDER - SOMERSET tee CASHLA
TO-20-SOM,T-CSH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla Shannonbridge 110 kV bay at cashla station.
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-CSH-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-CSH-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084838 | DO | 2 | 4 | 2019HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900727084 | DO | 1 | 1 | 2015HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900902253 | DO | 1 | 3 | 2017CP-1[87]Off Plumb Poles
FO_STDMG |  | - | 900902255 | DO | 1 | 3 | 2017CP-1[95]Found/Site repair -Sleeper
FO_MISC |  | - | 900902263 | CLO | 1 | 3 | 2017CP-1[173]Off Plumb Poles
FO_MISC |  | - | 900902264 | CLO | 1 | 3 | 2017CP-1[175]Off Plumb Poles
FO_MISC |  | - | 900902266 | DO | 1 | 3 | 2017CP-1[184]Off Plumb Insuls
FO_MISC |  | - | 900902268 | CLO | 1 | 3 | 2017CP-1[220]Off Plumb Insuls
TRAN |  | - | 900984945 | DO | 1 | 4 | 2018HP-1[152]Foundation/Site repair-stay
FO_MISC |  |  | 901084265 | CLO | 1 | 4 | 2019HP-1[181]Bird Nests
FO_MISC |  |  | 901084266 | CLO | 1 | 4 | 2019HP-1[260]Bird Nests
CORRECT | CSH |  | 900907890 | DO | 1 | 1 | Counter not working. To be replaced.
OPT | CSH | - | 901076462 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - SOMERSET tee SHANNONBRIDGE
TO-20-SOM,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-SH-1-04 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SOM,T-SH-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL521
FO_MISC |  | - | 900902328 | DO | 1 | 3 | 2017CP-1[3]Vibration Dampers -Replace
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - SOMERSET tee SOMERSET
TO-20-SOM,T-SOM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-SOM-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-SOM-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
DISTRIBUTION TRANSFORMER - SORNE HILL T122 [NDCC]
TO-20-SOR-T122-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - SORNE HILL T124 [NDCC]
TO-20-SOR-T124-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
110kV FEEDER - SORNE HILL TRILLICK [NDCC]
TO-20-SOR-TLK-1-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA1
TO-20-SKY-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-110SA1-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA2
TO-20-SKY-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
GENERATOR TRANSFORMER - SRAHNAKILLY T131 [Srahnakilly OY1]
TO-20-SKY-T131-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-T131-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorrick - Srahnakilly
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SKY | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - SRANANAGH 110 kV A1
TO-20-110 kV A1 @ SRA-03 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV A1 @ SRA-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh
BUSBAR SECTION - SRANANAGH 110 kV A2
TO-20-110 kV A2 @ SRA-01 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - SRANANAGH 110 kV B1
TO-20-110 kV B1 @ SRA-03 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV B1 @ SRA-04 ISO week: 42we Date: 14 Oct Duration: 1 Day (1 WD) Status: Proposed
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous 110 kV B1 @ SRA + SLI-SRA-1: EI - Energise DB on Corderry bay
TO-20-110 kV B1 @ SRA-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh
TO-20-110 kV B1 @ SRA-05 ISO week: 42mo - 42th Date: 12 Oct - 15 Oct Duration: 4 Days (4 WD) Status: Proposed
CAPX |  |  | CP0942 | DO | 3 |  | Connect new Jumpers on B1 BB Section In Srananagh & energise DB on Corderry bay
BUSBAR SECTION - SRANANAGH 110 kV B2
TO-20-110 kV B2 @ SRA-01 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
SECTIONALISING DISCONNECT - SRANANAGH 220SA1
TO-20-SRA-220SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
SECTIONALISING DISCONNECT - SRANANAGH 220SA2
TO-20-SRA-220SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TRANSFORMER - SRANANAGH T2102
TO-20-SRA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-SRA-T2102-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA511, 7UT512
| SRA | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | SRA | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CM | SRA | TRAFO | 900693061 | DO | 5 | 2 | Replace timber supports
OS | SRA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SRA | Trafo |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CA | SRA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TRAFO | SRA | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CA | SRA | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TRAFO | SRA | TRAFO |  | DO | 2 | 4 | 220/110kV Trafo Tap Changer Inspection
DISTRIBUTION TRANSFORMER - STRATFORD T141 [SDCC]
TO-20-STR-T141-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Full tee out for STRATFORD tee-POLLAPHUCA out
110kV FEEDER - STRATFORD tee CARLOW
TO-20-STR,T-CLW-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086426 | DO | 2 | 1 | 2019HP-1[110]Replace Pole only -Rot
FO_MISC |  | - | 900864816 | DO | 1 | 2 | 2016CP-1[109]Off Plumb Pole & insulators
FO_STDMG |  | - | 900864817 | DO | 1 | 2 | 2016CP-1[109]Replace Pole Bolt -Bent
FO_MISC |  | - | 900864818 | DO | 1 | 2 | 2016CP-1[109]Vibration Dampers Replace
FOINSHW |  | - | 900864820 | DO | 1 | 2 | 2016CP-1[109]H-ware Susp Clamps corroded
FO_STDMG |  | - | 900864821 | DO | 1 | 2 | 2016CP-1[109]Crossarm Replacement
FOSTRHW |  | - | 900864822 | DO | 1 | 1 | 2016CP-1[110]Replace Pole only -Rotten
TRAN |  | - | 900984379 | DO | 1 | 4 | 2018HP-1[90]ACGfit ACG
TRAN |  | - | 900989809 | DO | 1 | 4 | 2018HP-1[94]Check Structure-top rot - Ch
FOSTRHW |  |  | 901086400 | DO | 1 | 4 | 2019HP-1[124]Check Structure -Check Rot
OPT | CLW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - STRATFORD tee POLLAPHUCA
TO-20-STR,T-PA-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 900864747 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
FO_STDMG |  | - | 900898188 | CLO | 2 | 3 | 2017HP-1[14]Crossarm Replacement Replace
FO_MISC |  | - | 900864747 | CLO | 1 | 2 | 2016CP-1[13]Off Plumb Poles
FOSTRHW |  | - | 900973774 | CANC | 1 | 1 | 1[33]Replace Rotten Pole
FO_MISC |  | - | 900975368 | CLO | 1 | 1 | 1[53]Install ACG on mast no. 53
TRAN |  | - | 900989394 | DO | 1 | 4 | 2018HP-1[15]Off Plumb-Poles
OS | PA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | PA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - STRATFORD tee STRATFORD
TO-20-STR,T-STR-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989656 | DO | 1 | 4 | 2018HP-1[192]ACGfit ACG on TEE tower
FOSTRHW |  |  | 901086414 | DO | 1 | 4 | 2019HP-1[2]Check Structure -Check Rot
BUSBAR SECTION - TARBERT 110 kV A1
TO-20-110 kV A1 @ TB-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2
BUSBAR SECTION - TARBERT 110 kV B1
TO-20-110 kV B1 @ TB-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2
COUPLER/SECTIONALISING CB - TARBERT 110K1-2
TO-20-TB-110K1-2-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | TB | 110-SA1 | 900859451 | DO | 4 | 3 | 110kV Sect / Dist Ordinary Service
AMCAB | TB | - |  | DO | 3 | 4 | Annual Insp. 110kV Station OF Cable
FO_CABLE | TB | - | 900973548 | DO | 1 | 1 | leak on S-Phase ( weep on CSE valve to be replaced)
COUPLER/SECTIONALISING CB - TARBERT 220K1-2
TO-20-TB-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | TB | 220-SB1 | 901134801 | DO | 1 | 1 | T Phase 220kV Coupler. Hotspot T Phase DB1 pantograph hinge DUE : next available opportunity.
TO-20-TB-220K1-2-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TB | 220-SA1 | 901039188 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - TARBERT T101 [SSE Generation Ireland TB1]
TO-20-TB-T101-01 ISO week: 15mo - 15tu Date: 06 Apr - 07 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T102 [SSE Generation Ireland TB2]
TO-20-TB-T102-01 ISO week: 14th - 14fr Date: 02 Apr - 03 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T2003 [SSE Generation Ireland TB3]
TO-20-TB-T2003-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TB |  | 901129535 | CLO | 2 | 4 | 220kV MO Cubicle Operational Test
GENERATOR TRANSFORMER - TARBERT T2004 [SSE Generation Ireland TB4]
TO-20-TB-T2004-01 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of R1Z23b, S Type Overcurrent
TRANSFORMER - TARBERT T2101
TO-20-TB-T2101-01 ISO week: 15mo - 15we Date: 06 Apr - 08 Apr Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | TB | 110 | 901005821 | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
OPT | TB | 220 | 901038969 | DO | 1 | 3 | 220kV MO Cubicle Operational Test
OPT | TB | 110 | 901038971 | DO | 1 | 3 | 110kV MO Cubicle Operational Test
OPT | TB | TRAFO | 901045378 | DO | 1 | 3 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - TARBERT T2102
TO-20-TB-T2102-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TB | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | TB | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | TB |  | 901059334 | CANC | 1 | 2 | Rust / Corrosion Station Equipment
110kV FEEDER - TARBERT TRALEE 1
TO-20-TB-TRL-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage for maps, circuit is now Kilpaddoge - Tralee
COUPLER/SECTIONALISING CB - TAWNAGHMORE 110SA1-2CB
TO-20-TAW-110SA1-2CB-01 ISO week: 42we - 42th Date: 14 Oct - 15 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
YM03 | TAW | - | 900978748 | DO | 1 | 1 | STATUS OF CONTROL SELECTOR SWITCH IS NOT
OPT | TAW | - | 901043730 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TAW | 110-SA2 | 901050340 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - TAWNAGHMORE T1/T2 [SSE Generation Ireland TP1]
TO-20-TAW-T1/T2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - TAWNAGHMORE T3 [SSE Generation Ireland TP3]
TO-20-TAW-T3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 | 901043728 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - THORNSBERRY T141 [NDCC]
TO-20-TSB-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - THORNSBERRY T142 [NDCC]
TO-20-TSB-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
COUPLER/SECTIONALISING CB - THURLES 110SA1-2CB
TO-20-THU-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
CAPACITOR/SVC/REACTOR - THURLES CAP1
TO-20-THU-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
CAPACITOR/SVC/REACTOR - THURLES CAP2
TO-20-THU-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - THURLES T142 [SDCC]
TO-20-THU-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
BUSBAR SECTION - TRABEG 110 kV A1
TO-20-110 kV A1 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | A1/A2 BB in turn
BUSBAR SECTION - TRABEG 110 kV A2
TO-20-110 kV A2 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | A1/A2 BB in turn
BUSBAR SECTION - TRABEG 110 kV B1
TO-20-110 kV B1 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | B1/B2 BB in turn
BUSBAR SECTION - TRABEG 110 kV B2
TO-20-110 kV B2 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | B1/B2 BB in turn
COUPLER/SECTIONALISING CB - TRABEG 110K1-2
TO-20-TBG-110K1-2-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
| TBG | 110-SA1 |  | DO | 2 | 1 | Clean busbar insulators (Indoor AIS)
TO-20-TBG-110K1-2-02 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
| TBG | 110-SA2 |  | DO | 2 | 1 | Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T101 [SDCC]
TO-20-TBG-T101-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T102 [SDCC]
TO-20-TBG-T102-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T141 [SDCC]
TO-20-TBG-T141-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T142 [SDCC]
TO-20-TBG-T142-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
COUPLER/SECTIONALISING CB - TRALEE 110SA1-2CB
TO-20-TRL-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TRL | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
CAPACITOR/SVC/REACTOR - TRALEE CAP2
TO-20-TRL-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
COUPLER/SECTIONALISING CB - TRIEN 110SA1-2CB
TO-20-TRI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042136 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | TRI | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | TRI | 110-SA2 | 901042289 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-2CB-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
TO-20-TRI-110SA1-2CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
COUPLER/SECTIONALISING CB - TRIEN 110SA1-3CB
TO-20-TRI-110SA1-3CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
TO-20-TRI-110SA1-3CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042137 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
OS | TRI | 110-SA3 | 901042966 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-3CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
CAPACITOR/SVC/REACTOR - TRIEN CAP1
TO-20-TRI-CAP1-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-TRI-CAP1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | TRI | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - TRIEN T141 [SDCC]
TO-20-TRI-T141-01 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
DISTRIBUTION TRANSFORMER - TRIEN T142 [SDCC]
TO-20-TRI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
DISTRIBUTION TRANSFORMER - TRIEN T143 [SDCC]
TO-20-TRI-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
DISTRIBUTION TRANSFORMER - TRILLICK T141 [NDCC]
TO-20-TLK-T141-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - TRILLICK T142 [NDCC]
TO-20-TLK-T142-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - TULLABRACK T141 [SDCC]
TO-20-TBK-T141-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | As a consequence of TBK,T-TBK-1: BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7VK611
110kV FEEDER - TULLABRACK tee BOOLTIAGH
TO-20-TBK,T-BOL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BOL | - | 901129965 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - TULLABRACK tee MONEYPOINT GIS
TO-20-TBK,T-MP GIS-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988895 | DO | 2 | 4 | 2018HP-1[98]Off PlumbPlumb poleset
FO_MISC |  |  | 901082688 | DO | 2 | 4 | 2019HP-1[99]Off Plumb -plumb poles
110kV FEEDER - TULLABRACK tee TULLABRACK
TO-20-TBK,T-TBK-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
BUSBAR SECTION - TURLOUGH HILL 220 kV B2
TO-20-220 kV B2 @ TH-01 ISO week: 39fr Date: 25 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Black Start Test
COUPLER/SECTIONALISING CB - TURLOUGH HILL 220K1-2
TO-20-TH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | TH | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
GENERATOR TRANSFORMER - TURLOUGH HILL T2001/2 [ESB GWM TH1/TH2]
TO-20-TH-T2001/2-01 ISO week: 29mo - 29tu Date: 13 Jul - 14 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 | 2 | Total Maintenance Outage Duration Requested
AMCAB | TH | - | 901005766 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
GENERATOR TRANSFORMER - TURLOUGH HILL T2003/4 [ESB GWM TH3/TH4]
TO-20-TH-T2003/4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | TH | 220 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TO-20-TH-T2003/4-03 ISO week: 39fr Date: 25 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | Black Start Test
TO-20-TH-T2003/4-01 ISO week: 27mo - 27tu Date: 29 Jun - 30 Jun Duration: 2 Days (2 WD) Status: Scheduled
AMCAB | TH | - | 901005768 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
SECTIONALISING DISCONNECT - TYNAGH 220SA1
TO-20-TY-220SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
TO-20-TY-220SA1-01 ISO week: 14mo - 14tu Date: 30 Mar - 31 Mar Duration: 2 Days (2 WD) Status: Planned
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
OS | TYN | 220-SA1 | 901039728 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
SECTIONALISING DISCONNECT - TYNAGH 220SA2
TO-20-TY-220SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OS | TYN | 220-SA2 | 901039729 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-TY-220SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
GENERATOR TRANSFORMER - TYNAGH T2001/2 [Tynagh Energy TYC]
TO-20-TY-T2001/2-01 ISO week: 14mo - 14tu Date: 30 Mar - 31 Mar Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
CORRECT | TYN |  | 900990025 | CLO | 2 | 1 | Hot spot detected on T 2001/2 220kV R phase DA
OPT | TYN |  | 901129555 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - UGGOOL 110SA1-2CB
TO-20-UGL-110SA1-2CB-01 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110-SA1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - UGGOOL T131 [Uggool]
TO-20-UGL-T131-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T131-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T132 [Seecon]
TO-20-UGL-T132-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T132-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T134 [Seecon]
TO-20-UGL-T134-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | - | 900942781 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-UGL-T134-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequnce of Knockranny - Uggool 110kV
SECTIONALISING DISCONNECT - WATERFORD 110SA1
TO-20-WAT-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | WAT | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-WAT-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WATERFORD 110SA2
TO-20-WAT-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of WAT-110SA1: 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - WATERFORD T141 [SDCC]
TO-20-WAT-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WEXFORD 110SA1
TO-20-WEX-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
SECTIONALISING DISCONNECT - WEXFORD 110SA2
TO-20-WEX-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
CAPACITOR/SVC/REACTOR - WEXFORD CAP2
TO-20-WEX-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
CAPACITOR/SVC/REACTOR - WEXFORD CAP4
TO-20-WEX-CAP4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T122 [SDCC]
TO-20-WEX-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T142 [SDCC]
TO-20-WEX-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
SECTIONALISING DISCONNECT - WHITEGATE 110SA1
TO-20-WHI-110SA1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
OS | WHI | SA1 | 901039691 | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CORRECT | WHI |  | 901059046 | DO | 5 | 2 | O1- Replace disconnect due to severe rus
CORRECT | WHI |  | 901059045 | DO |  | 1 | 01-investigate interlocking issue betwee
SECTIONALISING DISCONNECT - WHITEGATE 110SA2
TO-20-WHI-110SA2-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T101 [Irving Oil]
TO-20-WHI-CKB-T101-02 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
| WHI |  |  | DO | 5 |  | Customer outage request
OS | WHI | - | 901042301 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | WHI |  | 901039125 | DO | 1 | 2 | O1-Water in CB Mech Box.
TO-20-WHI-CKB-T101-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T102 [Irving Oil]
TO-20-WHI-CKB-T102-01 ISO week: 39mo - 39fr Date: 21 Sep - 25 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | WHI |  | 901059048 | DO | 1 | 2 | O1-Replace bird guard on CB.Severely rus
SECTIONALISING DISCONNECT - WOODHOUSE 110SA1
TO-20-WOH-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOD | 110-SA1 | 901039200 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - WOODHOUSE 110SA2
TO-20-WOH-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOD | 110-SA2 | 901039201 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - WOODHOUSE T122 [Woodhouse WS1]
TO-20-WOH-T122-02 ISO week: 41we Date: 07 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer works
TO-20-WOH-T122-01 ISO week: 26mo - 26fr Date: 22 Jun - 26 Jun Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Oil leak on grid transformer
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOO |  | 901129682 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - WOODLAND 220K1-2
TO-20-WOO-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | WOO | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | WOO | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OS | WOO | 220-SB |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | WOO | 220-SA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - WOODLAND 400K1-2
TO-20-WOO-400K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7TG17
OS | WOO | - |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CORRECT | WOO |  | 900531762 | DO | 5 | 2 | Inspect and test all the cylinders, pist
CA | WOO | - |  | DO | 3 | 4 | 400kV Cubicle Condition Assessment
OS | WOO | 400-SB |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-SA |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEB2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEB1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEA2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEA1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
TO-20-WOO-400K1-2-02 Status: Unscheduled
CORRECT | WOO |  | 900444684 | NS | 5 | 2 | O. ESBI Inspect and test all the cylind
TRANSFORMER - WOODLAND T4201
TO-20-WOO-T4201-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 25 |  | Total Maintenance Outage Duration Requested
TO-20-WOO-T4201-03 Status: Unscheduled
| WOO | - |  | DO | 25 |  | Total Maintenance Outage Duration Requested
TO-20-WOO-T4201-01 Status: Unscheduled
CM | WOO | TRAFO |  | DO | 14 | 1 | Partial Discharge Test on T4201.Use OD1392
| WOO | TRAFO |  | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1392.
TRAFO | WOO | TRAFO |  | DO | 3 | 1 | 400/220kV Trafo Tap Changer Inspection. Use OD1392.
OPT | WOO | 220 | 900942806 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test. Use OD1392.
FM | WOO | - | 901114185 | DO | 1 | 4 | HV Pressure Vessel Inspection. Use OD1392
OPT | WOO | TRAFO | 901129762 | DO | 1 | 4 | 400/220kV Transformer Operational Test. Use OD1392.
OPT | WOO | 400 | 901146366 | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test. Use OD1392.
CORRECT | WOO |  | 900801507 | DO |  | 2 | o/1 air pressure alarm req for CB. Use OD1392
TRANSFORMER - WOODLAND T4202
TO-20-WOO-T4202-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | WOO |  | 900532120 | NS | 5 | 2 | Inspect and test all the cylinders, pist
TO-20-WOO-T4202-01 ISO week: 26we - 27fr Date: 24 Jun - 03 Jul Duration: 10 Days (8 WD) Status: Scheduled
[5 empty] | 5 |  | SF6 leak on transformer bays
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | WOO |  | 901073407 | CANC | 2 | 2 | Corrective- T4202 220KV CB LOW
OPT | WOO | 400 |  | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test
OPT | WOO | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CORRECT | WOO |  | 901073092 | DO | 1 | 2 | SF6 GAUGE TO BE REPLACED AS PER ESBI
CORRECT | WOO |  | 901081577 | DO | 1 | 2 | Corrective- T4202 Surge Counters Unreada
OPT | WOO | TRAFO |  | DO |  | 4 | 400/220kV Transformer Operational Test
TRANSFORMER - WOODLAND T4204
TO-20-WOO-T4204-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | WOO | TRAFO |  | DO | 1 | 4 | 400/220kV Transformer Operational Test
OPT | WOO | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-WOO-T4204-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7SA612, RET670

## WATERFORD (Rgn)
110kV FEEDER - ANNER DOON
TO-20-ANR-DOO-1-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | DOO | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
| DOO |  |  | DO | 1 | 1 | Replacement of Stolen Earths
OPT | DOO | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - ANNER T101 [Medite]
TO-20-ANR-T101-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
TSO CUSTOMER TRANSFORMER - ANNER T103 [Medite]
TO-20-ANR-T103-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
SECTIONALISING DISCONNECT - BALLYDINE 110SA1
TO-20-BDN-110SA1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
CM | BAL |  | 901091973 | CLO | 3 | 1 | Replacement of Stolen Earths
OS | BDN | SA1 | 900782940 | CLO | 3 | 1 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BALLYDINE 110SA2
TO-20-BDN-110SA2-01 ISO week: 26we - 26fr Date: 24 Jun - 26 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BDN-110SA1: 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BALLYDINE CULLENAGH
TO-20-BDN-CUL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727019 | CANC | 3 | 1 | 2015HP-3[26,35,40]Off Plumb Poles
TO-20-BDN-CUL-1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BDN-CUL-1-02 ISO week: 37we - 37fr Date: 09 Sep - 11 Sep Duration: 3 Days (3 WD) Status: Scheduled
FO_MISC |  | - | 900649538 | DO | 4 | 1 | 2014HP-[27,35,40,48,55,56]Off Plumb
FO_MISC |  | - | 900649539 | DO | 4 | 1 | 2014HP-[58,59,60,77,97,99,107]Off Plumb
110kV FEEDER - BALLYDINE DOON
TO-20-BDN-DOO-1-01 ISO week: 31th - 32th Date: 30 Jul - 06 Aug Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983907 | CLO | 2 | 1 | 2018HP-1[2]Replace Pole only-Rot
OS | BDN | - | 901151576 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | BDN |  | 901091975 | CLO | 3 | 1 | Replacement of Stolen Earths
OPT | DOO |  | 901129614 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK1 [Merck Sharp & Dohme]
TO-20-BDN-MRK1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
Replace Stolen Earths
OPT | BDN |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK3 [Merck Sharp & Dohme]
TO-20-BDN-MRK3-01 ISO week: 29mo - 30mo Date: 13 Jul - 20 Jul Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BDN | - | 901042188 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
CM | BDN | - | 901091974 | CLO | 3 | 1 | Replace Stolen Earths
DISTRIBUTION TRANSFORMER - BALLYDINE T141 [SDCC]
TO-20-BDN-T141-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA1
TO-20-BUT-110SA1-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA2: 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA2
TO-20-BUT-110SA2-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA1: 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA2 | 901146318 | CLO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - BUTLERSTOWN CULLENAGH
TO-20-BUT-CUL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | CUL | - | 901080692 | CANC | 3 | 1 | Copper earths stolen from DL, DE, all 110kV CT’s, VT’s and surge arrestors to be reinstalled
TO-20-BUT-CUL-1-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084937 | DO | 2 | 4 | 2019HP-2[49,50]Off Plumb -plumb poles
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084678 | DO | 1 | 2 | 2019HP-1[23]Check (General) -LPh weight
OPT | BUT |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BUTLERSTOWN KILLOTERAN
TO-20-BUT-KTN-1-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL551
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BUT |  | 901129602 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KTN |  | 901129696 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T141 [SDCC]
TO-20-BUT-T141-01 ISO week: 33we - 33fr Date: 12 Aug - 14 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T142 [SDCC]
TO-20-BUT-T142-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
COUPLER/SECTIONALISING CB - CAHIR 110K1-2
TO-20-CAH-110K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | CAH | - | 901134760 | CLO | 2 | 1 | R Phase Bus coupler 110kV Cubicle. R Phase CT.DUE : 17-Aug-20
CM | CAH | - | 901134761 | CLO | 2 | 1 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA. DUE : 17-Aug-20
CM | CAH | - | 901134762 | CLO | 2 | 1 | S & T Phase Bus coupler 110kV Cubicle. S & T Phase DA & T Phase CT connection DUE : 17-Aug-20
CM | CAH | - | 901134763 | CLO | 2 | 1 | T Phase Bus coupler 110kV Cubicle. T Phase Bus coupler DB DUE : 17-Jul-20
110kV FEEDER - CAHIR DOON
TO-20-CAH-DOO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900897597 | DO | 5 | 2 | 2017HP-5[5,12,13,33,37]Off Plumb
FO_MISC |  | - | 900897598 | DO | 3 | 2 | 2017HP-4[47,56,72,75]Off Plumb
FO_MISC |  |  | 901084938 | DO | 3 | 2 | 2019HP-5[14,29,30,37,38]Off Plumb
FO_MISC |  |  | 901084939 | DO | 1 | 2 | 2019HP-3[53,56,72]Off Plumb -plumb poles
|  |  | 901132793 |  |  |  | Poles currently in crop, good chance it will be cut by 13th of July KK
CM | CAH | - | 901134764 | CLO | 2 | 1 | T Phase Doon 110kV Cubicle. TPhase CB connection DUE : 17-Nov-2 hotspot
OPT | CAH |  | 901129607 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DOO | - | 901129615 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CAHIR KILL HILL
TO-20-CAH-KHL-1-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084942 | DO | 2 | 4 | 2019HP-1[47]Off Plumb -plumb poles
TRAN |  | - | 900984365 | DO | 1 | 4 | 2018HP-1[47]Off Plumb
OPT | CAH |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CAHIR TIPPERARY
TO-20-CAH-TIP-1-01 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984368 | DO | 3 | 4 | "2018HP-5[25,26,29,34,35]Off Plumb-Poles
TRAN |  | - | 900984369 | DO | 3 | 4 | "2018HP-5[36,55,84,90,91]Off Plumb-Poles
TRAN |  | - | 900984378 | DO | 1 | 4 | 2018HP-1[2]Earths-Replace-Broken
BUSBAR SECTION - CULLENAGH 110 kV A1
TO-20-110 kV A1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV A1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV A2
TO-20-110 kV A2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV A2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV B1
TO-20-110 kV B1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV B1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 110 kV B2
TO-20-110 kV B2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 110kV K1-2
TO-20-110 kV B2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CUL: Busbar Changeover
COUPLER/SECTIONALISING CB - CULLENAGH 110K1-2
TO-20-CUL-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
110kV Sect / Dist Operational Test
TO-20-CUL-110K1-2-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CUL | 110-SB |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | CUL | 110-SA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-CUL-110K1-2-03 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ511
BUSBAR SECTION - CULLENAGH 220 kV A1
TO-20-220 kV A1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV A1 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV A2
TO-20-220 kV A2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV A2 @ CUL-01 Status: Unscheduled
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV B1
TO-20-220 kV B1 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A1/B1 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV B1 @ CUL-01 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CUL: Busbar Changeover
BUSBAR SECTION - CULLENAGH 220 kV B2
TO-20-220 kV B2 @ CUL-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 2 |  | 220 kV A2/B2 IN TURN @ CUL: Proximity outage for work on Cullenagh 220kV K1-2
TO-20-220 kV B2 @ CUL-01 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CUL: Busbar Changeover
COUPLER/SECTIONALISING CB - CULLENAGH 220K1-2
TO-20-CUL-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | CUL | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CUL | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | CUL | 220-SB |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | CUL | 220-SA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-CUL-220K1-2-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
110kV FEEDER - CULLENAGH DUNGARVAN
TO-20-CUL-DGN-1-01 ISO week: 36mo - 36we Date: 31 Aug - 02 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985985 | DO | 3 | 4 | "2018HP-4[6,25,26,77]Off Plumb-Poles"
FO_MISC |  |  | 901084969 | DO | 1 | 2 | 2019HP-2[5,6]Off Plumb -plumb poles
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CUL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DGN |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - CULLENAGH GREAT ISLAND GIS
TO-20-CUL-GI GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
TO-20-CUL-GI GIS-1-02 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
TO-20-CUL-GI GIS-1-06 Status: Unscheduled
FO_MISC |  | - | 900855588 | CANC | 3 | 2 | Line Towers 35 - Replace angle insulator
OS | CUL | - | 900943447 | CANC | 6 | 3 | 220kV SF6 Cubicle Ordinary Service
CA | CUL | - | 900943872 | CANC | 3 | 3 | 220kV Cubicle Condition Assessment
AMCAB | GI | - | 901006385 | CANC | 2 | 2 | Cable Insp. 110kV XLPE
OPT | GI | - | 900840902 | CANC | 1 | 3 | 220kV MO Cubicle Operational Test
TO-20-CUL-GI GIS-1-04 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Proposed
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
FO_MISC |  | - | 900855589 | DO | 2 | 2 | Line Towers 35 & 36 (Angle & Intermediate) - Replace intermediate insulators and measurement of existing strain insulator chain length
FOINSHW |  |  | 901086391 | DO | 2 | 2 | 2019HP-3[27,28,29]Clean Insulators
220kV FEEDER - CULLENAGH KNOCKRAHA
TO-20-CUL-KRA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 7 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-CUL-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-CUL-KRA-1-01 ISO week: 9mo - 18th Date: 24 Feb - 30 Apr Duration: 67 Days (46 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Knockraha-Raffeen 220 kV
CORRECT | KRA |  | 901081935 | CLO | 3 | 2 | Ordinary service required on DB followin
TRANSFORMER - CULLENAGH T2101
TO-20-CUL-T2101-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CUL |  | 900908056 | DO | 30 | 2 | Refurbish main cover using Megalift devi
CORRECT | CUL | - | 900807712 | CLO | 3 | 1 | Repair oil leak on tertiary bushings
TO-20-CUL-T2101-02 Status: Unscheduled
|  | - |  |  | 30 |  | Total Maintenance Outage Duration Requested
CORRECT | CUL |  | 900706946 | CANC | 30 | 2 | Replace main cover gasket
OS | CUL | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TRAFO | CUL | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | CUL | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | CUL | TRAFO |  | DO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
CA | CUL | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CA | CUL | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | CUL | Trafo |  | DO | 3 | 4 | 220/110 & 275/220 - Ordinary Service
CORRECT | CUL |  | 900794262 | DO | 1 | 2 | Power Diagnostix are to carry out PD mea
TO-20-CUL-T2101-03 Status: Unscheduled
PROT |  |  |  | DO | 2 |  | P1 Protection maintenance of 7SA511, 7SA511, 7UT512
110kV FEEDER - CULLENAGH WATERFORD
TO-20-CUL-WAT-1-01 ISO week: 45mo - 45tu Date: 02 Nov - 03 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CUL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | WAT | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - DUNGARVAN 110SA1
TO-20-DGN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | DGN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - DUNGARVAN WOODHOUSE
TO-20-DGN-WOH-1-01 ISO week: 47th - 48th Date: 19 Nov - 26 Nov Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | DGN | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | WOO | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - GREAT ISLAND WATERFORD 1
TO-20-GI-WAT-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727280 | CANC | 1 | 1 | 2015HP-1[37]Off Plumb Pole
TO-20-GI-WAT-1-05 Status: Unscheduled
FO_MISC |  | - | 900853147 | CANC | 3 | 2 | Check (General)-Painting Req. Tower 50 & 51
110kV FEEDER - GREAT ISLAND WATERFORD 2
TO-20-GI-WAT-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
TO-20-GI-WAT-2-03 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
TO-20-GI-WAT-2-05 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
TO-20-GI-WAT-2-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-WAT-2-04 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900650529 | CLO | 1 | 2 | 2014HP-1[8]Off Plumb
FO_MISC |  | - | 900650531 | CLO | 1 | 2 | 2014HP-1[11]Off Plumb
FO_MISC |  | - | 900650532 | CLO | 1 | 2 | 2014HP-1[14]Off Plumb
FO_MISC |  | - | 900650533 | CLO | 1 | 2 | 2014HP-1[15]Off Plumb
FO_MISC |  | - | 900650534 | CLO | 1 | 2 | 2014HP-1[16]Off Plumb
FOSTRHW |  | - | 900650536 | CLO | 1 | 2 | 2014HP-1[26]Check Structure split in RHP
FOSTRHW |  | - | 900650537 | CLO | 1 | 2 | 2014HP-1[27]Check Structure split in RHP
FO_MISC |  | - | 900683451 | CLO | 1 | 2 | 1[50] Insulators Off Plumb
FO_MISC |  |  | 901084982 | CLO |  | 2 | 2019HP-1[11]Off Plumb -plumb poles
FOINSHW |  |  | 901085556 | CLO |  | 2 | 2019HP-1[18]Insul&HW Replac check
FOINSHW |  |  | 901085557 | CLO |  | 2 | 2019HP-1[19]Insul&HW Replac check
OPT | GI | - | 901038787 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WAT | - | 901038982 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - KILLOTERAN 110SA1
TO-20-KTN-110SA1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA2: 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - KILLOTERAN 110SA2
TO-20-KTN-110SA2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA1: 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - KILLOTERAN T101 [SDCC]
TO-20-KTN-T101-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - KILLOTERAN T102 [SDCC]
TO-20-KTN-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - KILLOTERAN WATERFORD
TO-20-KTN-WAT-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
TO-20-KTN-WAT-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - KNOCKRAHA WOODHOUSE
TO-20-KRA-WOH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21
TO-20-KRA-WOH-1-01 ISO week: 28mo - 29mo Date: 06 Jul - 13 Jul Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | KRA | - | 901129859 | CLO | 6 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KRA |  | 901036906 | CLO |  | 2 | O1-Replace Surge Counter
OS | WOO | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - WATERFORD 110SA1
TO-20-WAT-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | WAT | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-WAT-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WATERFORD 110SA2
TO-20-WAT-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of WAT-110SA1: 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - WATERFORD T141 [SDCC]
TO-20-WAT-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WOODHOUSE 110SA1
TO-20-WOH-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOD | 110-SA1 | 901039200 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - WOODHOUSE 110SA2
TO-20-WOH-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOD | 110-SA2 | 901039201 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - WOODHOUSE T122 [Woodhouse WS1]
TO-20-WOH-T122-02 ISO week: 41we Date: 07 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer works
TO-20-WOH-T122-01 ISO week: 26mo - 26fr Date: 22 Jun - 26 Jun Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Oil leak on grid transformer
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOO |  | 901129682 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test

## TRALEE (Rgn)
COUPLER/SECTIONALISING CB - ATHEA 110SA1-2CB
TO-20-ATE-110SA1-2CB-01 ISO week: 35mo - 35tu Date: 24 Aug - 25 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATE |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | ATE | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | ATE | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - ATHEA DROMADA
TO-20-ATE-DRO-1-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATE | - | 901043693 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - ATHEA KNOCKANURE
TO-20-ATE-KNR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | ATE | - | 901042193 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | ATE | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | KNR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | KNR | - | 901043731 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - ATHEA T121 [Athea AH1]
TO-20-ATE-T121-01 ISO week: 35mo - 35th Date: 24 Aug - 27 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | ATE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | ATE | 110 | 901043038 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - AUGHINISH KILPADDOGE
TO-20-AUG-KPG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | KPG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| KPG |  |  |  | 3 |  | Outstanding issues with the AR Supervisory scheme on the bay including testing and recommissioning of the BCU and testing of new commands and PI back to NCC
TO-20-AUG-KPG-1-02 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901110437 | CLO | 2 | 1 | Hotspot 8 (DC Cable Tower No.160 Span 159/160) Lower (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110438 | CLO | 2 | 1 | Hotspot 7 (DC Cable Tower No.160 Span 159/160) Top (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110439 | CLO | 2 | 1 | Hotspot 4 (Transposition Tower No. 58 Span 57/58) Left Jumper Terminal (Repair by 24th Jul)
TRAN | - | Line | 901110456 | CLO | 2 | 1 | Hotspot 2 (Transposition Tower No. 58 Span 58/59) Centre Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110457 | CLO | 2 | 1 | Hotspot 3 (Transposition Tower No. 58 Span 58/59) Left Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110460 | CLO | 2 | 1 | Hotspot 5 (Transposition Tower No. 58 Span 57/58) Centre Jumper Terminal (Repair by 24th May)
TRAN | - | Line | 901110461 | CLO | 2 | 1 | Hotspot 6 (Transposition Tower No. 58 Span 57/58) Right Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110462 | CLO | 2 | 1 | Hotspot 1 (Transposition Tower No. 58 Span 58/59) Right Jumper Terminal (Repair by 24th Oct)
BUSBAR SECTION - BALLYNAHULLA 110 kV A1
TO-20-110 kV A1 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV A2
TO-20-110 kV A2 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV B1
TO-20-110 kV B1 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
BUSBAR SECTION - BALLYNAHULLA 110 kV B2
TO-20-110 kV B2 @ BYH-01 ISO week: 8th Date: 20 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110K1
TO-20-BYH-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110K1-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901050244 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110K2
TO-20-BYH-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110SA1-2CB
TO-20-BYH-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043737 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 110SB1-2CB
TO-20-BYH-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BYH: 110 kV A2/B2 IN TURN @ BYH: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BYH: 110 kV A1/B1 IN TURN @ BYH: Busbar Changeover
TO-20-BYH-110SB1-2CB-02 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043738 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220K1
TO-20-BYH-220K1-01 ISO week: 9th - 10tu Date: 27 Feb - 03 Mar Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BYH | - | 901129779 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | BYH |  | 901078169 | CLO | 2 | 1 | PI from DEM1 & DEM2 not working followin
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220K2
TO-20-BYH-220K2-01 ISO week: 10we - 11tu Date: 04 Mar - 10 Mar Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BYH | - | 901129804 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | BYH |  | 901078168 | CLO | 2 | 1 | PI from DEM1 & DEM2 not working followin
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220SA1-2CB
TO-20-BYH-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043813 | DO | 2 | 4 | 220kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYNAHULLA 220SB1-2CB
TO-20-BYH-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | - | 901043800 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - BALLYNAHULLA BALLYVOUSKILL
TO-20-BYH-BVK-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
Maintenance
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | BYH | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | BYH | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-BYH-BVK-1-01 ISO week: 46th - 47fr Date: 12 Nov - 20 Nov Duration: 9 Days (7 WD) Status: Scheduled
CM | BVK | - |  | DO | 6 | 2 | Aux Relay - replace contactors
CM | BYH | - |  | DO | 6 | 2 | Aux Relay - replace contactors
110kV FEEDER - BALLYNAHULLA CORDAL
TO-20-BYH-CDL-1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901128997 | DO | 3 | 3 | Insp. 110kV Feeder XLPE Cable
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CDL |  | 901129678 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALLYNAHULLA GLENLARA
TO-20-BYH-GLE-1-01 ISO week: 13th Date: 26 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| - | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH |  | 901129526 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | GLE | - | 901129703 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - BALLYNAHULLA KNOCKANURE
TO-20-BYH-KNR-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 5 |  | Proximity outage to move link box
CAPX |  |  | CP0936 | DO | 2 |  | Proximity outage to remove scaffolding
TO-20-BYH-KNR-1-02 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 2 |  | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder
TO-20-BYH-KNR-1-04 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 100 |  | Line uprate works - restringing, foundation reinforcement, hardware etc
TO-20-BYH-KNR-1-05 Status: Unscheduled
FOINSHW |  | - | 900897561 | DO | 2 | 3 | 2017HP-1[37]Susp/Dup 220kV replacement
FO_MISC |  |  | 901084882 | DO |  | 2 | 2019HP-1[80]Insulator Broken disc
OS | BYH | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
TO-20-BYH-KNR-1-01 ISO week: 44tu - 46we Date: 27 Oct - 11 Nov Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 4 |  | SF6 repairs in Knockanure
CM | BYH | - |  | DO | 6 | 2 | Aux Relay - replace contactors
AMCAB | BYH | - | 901051722 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
CM | KNR | - |  | DO | 6 | 1 | Aux Relay - replace contactors
AMCAB | KNR | - | 901051726 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
TRANSFORMER - BALLYNAHULLA T2101
TO-20-BYH-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | BYH | 110 | 901129028 | CANC | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-BYH-T2101-01 Status: Unscheduled
| BYH | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BYH | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | BYH | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TRANSFORMER - BALLYNAHULLA T2102
TO-20-BYH-T2102-01 ISO week: 36tu - 36th Date: 01 Sep - 03 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| BYH | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | BYH | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | BYH | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
CORRECT | BYH | TRAFO | 901075872 | DO | 1 | 2 | False low oil alarm & DC earth fault com
CORRECT | BYH | TRAFO | 901079981 | DO | 1 | 2 | Following the malfunction fault on oil m
BUSBAR SECTION - BALLYVOUSKILL 110 kV A1
TO-20-110 kV A1 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV A2
TO-20-110 kV A2 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV B1
TO-20-110 kV B1 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
BUSBAR SECTION - BALLYVOUSKILL 110 kV B2
TO-20-110 kV B2 @ BVK-01 ISO week: 8tu Date: 18 Feb Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110K1
TO-20-BVK-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110K2
TO-20-BVK-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110SA1-2CB
TO-20-BVK-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
TO-20-BVK-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | BVK | - | 901043740 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110SB1-2CB
TO-20-BVK-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ BVK: 110 kV A2/B2 IN TURN @ BVK: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ BVK: 110 kV A1/B1 IN TURN @ BVK: Busbar Changeover
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220K1
TO-20-BVK-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220K2
TO-20-BVK-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BVK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
220kV FEEDER - BALLYVOUSKILL CLASHAVOON
TO-20-BVK-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101
TO-20-BVK-CLA-1-02 Status: Unscheduled
CM | BVK | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TO-20-BVK-CLA-1-03 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | BVK | - | 901050433 | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | CLA | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CLA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - BALLYVOUSKILL COOMATAGGART
TO-20-BVK-COT-1-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | - | 110 | 901132973 | DO | 5 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BALLYVOUSKILL GARROW
TO-20-BVK-GRO-1-01 ISO week: 27tu - 27fr Date: 30 Jun - 03 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CM |  |  | 901056104 | DO | 3 | 1 | Water ingress into JB01 Link Box – Raise
CM |  |  | 901068796 | CANC | 3 | 2 | Visual inspection of HIS HV cable sealin
OPT | GRO |  | 901129712 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - BALLYVOUSKILL T2101
TO-20-BVK-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | BVK | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | BVK | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | BVK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | BVK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - BALLYVOUSKILL T2102
TO-20-BVK-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | BVK | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | BVK | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | BVK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | BVK | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | BVK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - CHARLEVILLE GLENLARA
TO-20-CHA-GLE-1-01 ISO week: 11tu - 11fr Date: 10 Mar - 13 Mar Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 4 |  | Total Maintenance Outage Duration Requested
OS | CHA | - | 901129798 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | GLE | - | 901116384 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLAHANE T122 [Clahane CJ1]
TO-20-CLH-T122-01 ISO week: 21tu Date: 19 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer work
110kV FEEDER - CLAHANE TRALEE
TO-20-CLH-TRL-1-02 ISO week: 42mo - 43mo Date: 12 Oct - 19 Oct Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 901038454 | DO | 1 | 4 | 2018CP-1[49]Replace/Retire pole butts
FO_STDMG |  | - | 901038455 | DO | 1 | 4 | 2018CP-1[50]Found/Site repair -Sleepers
FO_STDMG |  | - | 901038457 | DO | 1 | 4 | 2018CP-1[50]Crossarm -Repair Grid Gain
FO_STDMG |  | - | 901038464 | DO | 1 | 4 | 2018CP-1[54]Crossarm -Repair Grid Gain
FO_STDMG |  | - | 901038480 | DO | 1 | 4 | 2018CP-1[62]Crossarm -Repair Grid Gain
FO_MISC |  | - | 901038483 | DO | 1 | 4 | 2018CP-1[63]Insulator -Replace (rust)
FO_MISC |  | - | 901038484 | DO | 1 | 4 | 2018CP-1[63]Ubolts -Replace (rust)
FO_MISC |  | - | 901038487 | DO | 1 | 4 | 2018CP-1[68]Off Plumb -Poleset
FO_MISC |  | - | 901038488 | DO | 1 | 4 | 2018CP-1[69]Off Plumb -Poleset
FOSTRHW |  | - | 901045854 | CLO | 1 | 1 | 2018CP-1[64]Replace Pole only -Rotten
AMCAB | TRL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | TRL | - |  | DO | 1 | 2 | Inspect Phisterer CSE & record serial number
110kV FEEDER - CLAHANE TRIEN
TO-20-CLH-TRI-1-01 ISO week: 9tu - 10mo Date: 25 Feb - 02 Mar Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985518 | CLO | 2 | 4 | 2018HP-1[42]Insul&HW Replace check
TRAN |  | - | 900985520 | CLO | 2 | 4 | 2018HP-1[44]Insul&HW Replace check
TRAN |  | - | 900985522 | CLO | 2 | 4 | 2018HP-1[57]Insul&HW Replace check
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
FOSTRHW |  | - | 900773923 | CLO | 1 | 3 | 2015CP-1[26]Off Plumb
FOINSHW |  | - | 900819428 | CLO | 1 | 3 | 2016HP-1[29]Insul&H-ware check
PROT |  |  |  | DO |  |  | P2 Protection maintenance of REL521, GRL100
CORRECT | CLH |  | 901080639 | CANC | 1 | 1 | Water in Tech. Box in H2 Trien CB-SS.
FM | TRI | - | 901114178 | CLO | 1 | 4 | HV Pressure Vessel Inspection
110kV FEEDER - CLASHAVOON CLONKEEN
TO-20-CLA-CKN-1-01 ISO week: 9we - 22su Date: 26 Feb - 31 May Duration: 96 Days (64 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0996 | DO | 60 |  | EI: Realingment of the line to allow for the construction of the new N22 bypass. A number of new towers are being constructed and polesets moved
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084961 | CLO | 1 | 2 | 2019HP-1[131]Off Plumb -plumb poles
FO_MISC |  |  | 901084962 | CLO | 1 | 2 | 2019HP-2[91,92]Off Plumb -plumb poles
FO_MISC |  |  | 901084963 | CLO | 1 | 2 | 2019HP-2[76,77]Off Plumb -plumb poles
FO_MISC |  |  | 901084964 | DO | 1 | 2 | 2019HP-2[19,20]Off Plumb -plumb poles
AMCAB | CKN | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CKN |  | 901129659 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | CLA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA1
TO-20-CBA-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA1-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA1 | 900938714 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA2
TO-20-CBA-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | 110-SA2 |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA2-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA2 |  | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CLOGHBOOLA T122 [SDCC]
TO-20-CBA-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-T122-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Reference
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
GENERATOR TRANSFORMER - CLOGHBOOLA T131 [Cloghboola CL1]
TO-20-CBA-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-T131-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | 110 | 901068541 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHBOOLA TRIEN
TO-20-CBA-TRI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-TRI-1-01 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CBA | - | 901043718 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRI | - | 901050357 | CLO | 1 | 3 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CLONKEEN 110SA1-2CB
TO-20-CKN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CKN | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | CKN | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | CKN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CKN-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
110kV FEEDER - CLONKEEN COOMAGEARLAHY
TO-20-CKN-CGL-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129698 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CKN |  | 901129658 | CLO | 3 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLONKEEN GARROW
TO-20-CKN-GRO-1-01 ISO week: 24mo - 24fr Date: 08 Jun - 12 Jun Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of REL521, GRL100
CM |  | 110 | 901068795 | CANC | 1 | 1 | Visual inspection of HIS HV cable sealin
OS | CKN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CKN | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | GRO | - | 901129956 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | GRO | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CLONKEEN KNOCKEARAGH
TO-20-CKN-KER-1-01 ISO week: 23th - 23fr Date: 04 Jun - 05 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7SA511
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
TRAN |  | - | 900985669 | CLO | 1 | 4 | 2018HP-1[33]Off PlumbPlumb poles
FO_MISC |  |  | 901084966 | CLO | 1 | 2 | 2019HP-1[32]Off Plumb -plumb poles
OPT | CKN |  | 901129657 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | CKN | 110-DL | 901134777 | CLO | 1 | 1 | R Phase Knockearagh 110kV Cubicle. R Phase DL contact. DUE : 17-Aug-20 hotspot
110kV FEEDER - COOLNANOONAGH KILPADDOGE
TO-20-CNO-KPG-1-01 ISO week: 44we - 45mo Date: 28 Oct - 02 Nov Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage to facilitate customer's work
GENERATOR TRANSFORMER - COOLNANOONAGH T131
TO-20-CNO-T131-01 ISO week: 36mo Date: 31 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Black start testing
TO-20-CNO-T131-02 ISO week: 47fr - 48tu Date: 20 Nov - 24 Nov Duration: 5 Days (3 WD) Status: Tentative
Outage to facilitate customer's work
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA1
TO-20-CGL-110SA1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | CGL | - | 900801826 | DO | 2 | 2 | O2.Sectionaliser not working from Mimic.
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA2
TO-20-CGL-110SA2-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Prox for SA1
110kV FEEDER - COOMAGEARLAHY GLANLEE
TO-20-CGL-GAE-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129700 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T121 [Coomagearlahy CG3]
TO-20-CGL-T121-01 ISO week: 29mo - 29th Date: 13 Jul - 16 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129701 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T122 [Coomagearlahy CG1/CG2]
TO-20-CGL-T122-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129699 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - COOMATAGGART 110SA1
TO-20-COT-110SA1-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
SECTIONALISING DISCONNECT - COOMATAGGART 110SA2
TO-20-COT-110SA2-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
GENERATOR TRANSFORMER - COOMATAGGART T132 [Grousemount GD1]
TO-20-COT-T132-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
DISTRIBUTION TRANSFORMER - COOMATAGGART T141 [SDCC]
TO-20-COT-T141-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As consequence of Ballyvouskill - Coomataggart 110kV outage
SECTIONALISING DISCONNECT - CORDAL 110SA1
TO-20-CDL-110SA1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA1 | 901130105 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - CORDAL 110SA2
TO-20-CDL-110SA2-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA2 | 901146308 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - CORDAL T132
TO-20-CDL-T132-01 ISO week: 33tu - 33fr Date: 11 Aug - 14 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | CDL |  | 901074069 | DO | 2 | 1 | Replair replace bonding leads (damaged)
OPT | CDL |  | 901118391 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CORDAL T141 [SDCC]
TO-20-CDL-T141-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Ballynahulla-Cordal 110 kV circuit
GENERATOR TRANSFORMER - DROMADA T121 [Dromada DR1]
TO-20-DRO-T121-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | DRO | - | 901038511 | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
COUPLER/SECTIONALISING CB - GARROW 110SA1-2CB
TO-20-GRO-110SA1-2CB-01 ISO week: 26tu - 26we Date: 23 Jun - 24 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | GRO |  | 901129711 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | GRO | 110-SA1 | 901130110 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | GRO | 110-SA2 | 901130111 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - GARROW T122 [Coomacheo CZ1]
TO-20-GRO-T122-01 ISO week: 26tu - 26we Date: 23 Jun - 24 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GRO |  | 901129713 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - GLANLEE T121 [Glanlee GL1]
TO-20-GAE-T121-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | GAE | - | 900973585 | DO | 1 | 2 | AC and DC Supplies:
OPT | GAE |  | 901129611 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GLENLARA KNOCKACUMMER [Mountain Lodge ML1]
TO-20-GLE-KCR-1-01 ISO week: 34mo - 34fr Date: 17 Aug - 21 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 5 | 4 | Cable Insp. 110kV XLPE
OPT | GLE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KCR | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - KILLONAN TARBERT
TO-20-KLN-TB-1-05 ISO week: 41tu - 41we Date: 06 Oct - 07 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-KLN-TB-1-01 ISO week: 23tu - 47we Date: 02 Jun - 18 Nov Duration: 170 Days (120 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 120 |  | Outage for diversion of line into Kilpaddoge station to cable into GIS building. Feeder will become Killonan Kilpaddoge
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987854 | DO | 2 | 4 | 2018HP-1[151]ACGFit ACG
BUSBAR SECTION - KILPADDOGE 110 kV A1
TO-20-110 kV A1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A2
TO-20-110 kV A2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A3
TO-20-110 kV A3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV A4
TO-20-110 kV A4 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B1
TO-20-110 kV B1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B2
TO-20-110 kV B2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B3
TO-20-110 kV B3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 110 kV B4
TO-20-110 kV B4 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KILPADDOGE 220 kV A1
TO-20-220 kV A1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KILPADDOGE 220 kV A2
TO-20-220 kV A2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-220 kV A2 @ KPG-03 Status: Unscheduled
Busbar changeover
TO-20-220 kV A2 @ KPG-04 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV A2 @ KPG-02 ISO week: 31mo - 33fr Date: 27 Jul - 14 Aug Duration: 19 Days (14 WD) Status: Scheduled
[5 empty] | 14 |  | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2
BUSBAR SECTION - KILPADDOGE 220 kV A3
TO-20-220 kV A3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A3 @ KPG-01 ISO week: 29tu - 30fr Date: 14 Jul - 24 Jul Duration: 11 Days (9 WD) Status: Scheduled
[5 empty] | 10 |  | A3/B3 in turn for replacement of DC contactors
BUSBAR SECTION - KILPADDOGE 220 kV A4
TO-20-220 kV A4 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A4 @ KPG-03 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV A4 @ KPG-01 ISO week: 36mo - 37fr Date: 31 Aug - 11 Sep Duration: 12 Days (10 WD) Status: Scheduled
[5 empty] | 10 |  | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler
BUSBAR SECTION - KILPADDOGE 220 kV B1
TO-20-220 kV B1 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KILPADDOGE 220 kV B2
TO-20-220 kV B2 @ KPG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-220 kV B2 @ KPG-03 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B2 @ KPG-04 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV B2 @ KPG-02 ISO week: 31mo - 33fr Date: 27 Jul - 14 Aug Duration: 19 Days (14 WD) Status: Scheduled
| KPG |  |  |  | 14 |  | 220kV A2/B2 IN TURN DC Contactor replacement: Sect, Spare Bay, Trafo T2102, Tarbert 2
BUSBAR SECTION - KILPADDOGE 220 kV B3
TO-20-220 kV B3 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B3 @ KPG-01 ISO week: 29tu - 30fr Date: 14 Jul - 24 Jul Duration: 11 Days (9 WD) Status: Scheduled
[5 empty] | 10 |  | A3/B3 in turn for replacement of DC contactors
BUSBAR SECTION - KILPADDOGE 220 kV B4
TO-20-220 kV B4 @ KPG-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B4 @ KPG-03 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-220 kV B4 @ KPG-01 ISO week: 36mo - 37fr Date: 31 Aug - 11 Sep Duration: 12 Days (10 WD) Status: Scheduled
[5 empty] | 10 |  | 220kV A4/B4 IN TURN DC Contactor replacement: Sect, Coupler
COUPLER/SECTIONALISING CB - KILPADDOGE 220K4
TO-20-KPG-220K4-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SA1-2CB
TO-20-KPG-220SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SA2-4CB
TO-20-KPG-220SA2-4CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV A4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SB1-2CB
TO-20-KPG-220SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: 220 kV A2/B2 IN TURN @ KPG: Commission new Knockanure No.2 bay
TO-20-KPG-220SB1-2CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
COUPLER/SECTIONALISING CB - KILPADDOGE 220SB2-4CB
TO-20-KPG-220SB2-4CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | KPG | - |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-KPG-220SB2-4CB-01 ISO week: 41mo - 41we Date: 05 Oct - 07 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B2 @ KPG: Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | As a consequence of 220 kV B4 @ KPG: Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
110kV FEEDER - KILPADDOGE KNOCKANURE 110
TO-20-KPG-KNR-1-110-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0902 | DO | 40 |  | EI: Replacing polesets, hardware, insulators & crossarms. Foundation reinforcement required at angle masts. Towers to be painted.
TO-20-KPG-KNR-1-110-02 ISO week: 21th - 21fr Date: 21 May - 22 May Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Proximity outage for 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 (Hotspots 7 and 8 to be repaired; DC Cable Tower No. 160)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988027 | CLO | 1 | 4 | 2018HP-1[47]Insulator-strain insul
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | KNR | - | 901129707 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KPG |  | 901129517 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
220kV FEEDER - KILPADDOGE KNOCKANURE 220
TO-20-KPG-KNR-1-220-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 5 |  | Proximity outage to bore wall and pull cable
TO-20-KPG-KNR-1-220-02 Status: Unscheduled
CAPX |  |  | CP0883 | DO | 2 |  | EI: Simultaneous BYH-KNR-1 + KPG-KNR-1-220: Energisation of Ballynahulla-Knockanure using Kilpaddoge feeder
TO-20-KPG-KNR-1-220-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 5 |  | Re-lable circuit to Kipaddoge-Knockanure No. 1
TO-20-KPG-KNR-1-220-03 Status: Unscheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
CM | KNR | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
AMCAB | KNR | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OPT | KPG | - | 901043819 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 1
TO-20-KPG-MP GIS-1-02 ISO week: 39mo - 40we Date: 21 Sep - 30 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 4 | Aux Relay - replace contactors
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 2
TO-20-KPG-MP GIS-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | EI: Energise the new Kilpaddoge- Knocknaure 2 cable
TO-20-KPG-MP GIS-2-02 Status: Unscheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Tarbert 2
TO-20-KPG-MP GIS-2-03 ISO week: 41th - 41fr Date: 08 Oct - 09 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Killonan
TO-20-KPG-MP GIS-2-04 ISO week: 48mo - 49we Date: 23 Nov - 02 Dec Duration: 10 Days (8 WD) Status: Tentative
|  | - |  | DO | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
110kV FEEDER - KILPADDOGE RATHKEALE
TO-20-KPG-RAT-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900989469 | CANC | 1 | 2 | 2018HP-1[125]ITSOul&HW Replace check
TRAN |  | - | 900989470 | CANC | 1 | 2 | 2018HP-1[130]ITSOul&HW Replace check
TRAN |  | - | 900989471 | CANC | 1 | 1 | 2018HP-1[134]Off Plumb
TO-20-KPG-RAT-1-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989472 | NS | 1 | 2 | 2018HP-1[135]ACG-Replace
OPT | RAT | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TRANSFORMER - KILPADDOGE T2101
TO-20-KPG-T2101-02 ISO week: 13th - 14th Date: 26 Mar - 02 Apr Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | KPG | TRAFO | 901039259 | DO | 3 | 2 | Corrosion on MR Messko Temp Gauges ( requires stainless surround to stop water from top cover) and fans Fans Q4 not working ceased
OPT | KPG | TRAFO | 901045373 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KPG | 110 | 901045439 | CLO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | KPG | 220 | 901045526 | CLO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-KPG-T2101-03 ISO week: 42mo - 43we Date: 12 Oct - 21 Oct Duration: 10 Days (8 WD) Status: Scheduled
[5 empty] | 8 |  | Total Maintenance Outage Duration Requested
CM | KPG | 220 |  | DO | 8 | 2 | Aux Relay - replace contactors
TRANSFORMER - KILPADDOGE T2102
TO-20-KPG-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 10 |  | Proximity outage of F4 bay to enable termination of cable in F6 bay.
TO-20-KPG-T2102-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
OPT | KPG | 110 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | KPG | 220 |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | KPG | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
220kV FEEDER - KILPADDOGE TARBERT 1
TO-20-KPG-TB-1-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | KPG | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TO-20-KPG-TB-1-02 ISO week: 22tu - 22th Date: 26 May - 28 May Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 3 |  | Proximity outage of DC mast - remove lead-in and drops, strip down the CSEs
TO-20-KPG-TB-1-03 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
AMCAB | KPG | - | 901006581 | DO | 2 | 3 | Annual Insp. 400 & 220 Feeder XLPE Cable
OPT | KPG | - | 900942471 | DO | 1 | 3 | 220kV GIS Cubicle Operational Test
OS | TB | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
OS | TB | - | 901050439 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | TB | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - KILPADDOGE TRALEE 2
TO-20-KPG-TRL-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989672 | DO | 1 | 4 | 2018HP-1[31]Off PlumbPlumb poleset
TRAN |  | - | 900989674 | DO | 1 | 4 | 2018HP-1[98]Off PlumbPlumb poleset
TRAN |  | - | 900989675 | DO | 1 | 4 | 2018HP-1[99]Off PlumbPlumb poleset
TRAN |  | - | 900989676 | DO | 1 | 4 | 2018HP-1[100]Off PlumbPlumb poleset
OPT | KPG | - | 901043757 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
AMCAB | TRL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - KNOCKANURE 110 kV A1
TO-20-110 kV A1 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV A2
TO-20-110 kV A2 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV A4
TO-20-110 kV A4 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV B1
TO-20-110 kV B1 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 110 kV B2
TO-20-110 kV B2 @ KNR-01 ISO week: 39we Date: 23 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV A1
TO-20-220 kV A1 @ KNR-01 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV A2
TO-20-220 kV A2 @ KNR-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-220 kV A2 @ KNR-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-220 kV A2 @ KNR-03 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV B1
TO-20-220 kV B1 @ KNR-01 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - KNOCKANURE 220 kV B2
TO-20-220 kV B2 @ KNR-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-220 kV B2 @ KNR-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-220 kV B2 @ KNR-03 ISO week: 39th Date: 24 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
COUPLER/SECTIONALISING CB - KNOCKANURE 220K1
TO-20-KNR-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220K2
TO-20-KNR-220K2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
CAPX |  |  | CP0936 | DO | 3 |  | EI: Energisation of F6 reactor inc. soft closing and 24hr cable soak
TO-20-KNR-220K2-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220K2-02 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220SA1-2CB
TO-20-KNR-220SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-KNR-220SA1-2CB-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV A2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220SA1-2CB-03 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - KNOCKANURE 220SB1-2CB
TO-20-KNR-220SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0936 | DO | 10 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commissioning
TO-20-KNR-220SB1-2CB-01 Status: Unscheduled
CAPX |  |  | CP0726 | DO | 2 |  | As a consequence of 220 kV B2 @ KNR: 220 kV A2/B2 IN TURN @ KNR: Commission new Kilpaddoge No.2 bay
TO-20-KNR-220SB1-2CB-03 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KNR | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
TRANSFORMER - KNOCKANURE T2101
TO-20-KNR-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KNR | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | KNR | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TRANSFORMER - KNOCKANURE T2102
TO-20-KNR-T2102-01 ISO week: 9we - 11th Date: 26 Feb - 12 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KNR | 110 | 901129752 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
OS | KNR | 220 | 901129806 | CLO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | KNR | TRAFO | 901129834 | CLO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | KNR | TRAFO | 901130270 | CLO | 1 | 3 | Knockanure T2101 & T2102 Transformers: Check position of fans adjacent to pumps
CORRECT | KNR |  | 900982980 | CANC |  | 2 | Low Oil / Leak. Low Oil alarm being gene
110kV FEEDER - KNOCKANURE TRIEN 1
TO-20-KNR-TRI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
TO-20-KNR-TRI-1-01 ISO week: 24we - 24th Date: 10 Jun - 11 Jun Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | KNR | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | TRI | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TRI |  | 901129634 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KNOCKANURE TRIEN 2
TO-20-KNR-TRI-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
TO-20-KNR-TRI-2-01 ISO week: 24fr Date: 12 Jun Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TRI | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - OUGHTRAGH T141 [SDCC]
TO-20-OUG-T141-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
110kV FEEDER - OUGHTRAGH tee KNOCKEARAGH
TO-20-OUG,T-KER-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA511, REL521
OPT | KER | - | 901038793 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - OUGHTRAGH tee OUGHTRAGH
TO-20-OUG,T-OUG-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989804 | DO | 1 | 4 | 2018HP-1[192-193]Re-sag conductor
FO_MISC |  |  | 901084875 | DO | 1 | 2 | 2019HP-1[227]Earths-Replace earth wire
110kV FEEDER - OUGHTRAGH tee TRALEE
TO-20-OUG,T-TRL-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
OPT | TRL | - | 901038831 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - PROSPECT TARBERT
TO-20-PRO-TB-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Prox outage required for pipeline survey
TO-20-PRO-TB-1-04 ISO week: 31mo - 31tu Date: 27 Jul - 28 Jul Duration: 2 Days (2 WD) Status: Scheduled
Prox outage required for pipeline survey
TO-20-PRO-TB-1-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_CABLE |  | - | 900952297 | CLO | 2 | 1 | Replacement of Cathodic Protection Battery
AMCAB | TB | - | 901113198 | CLO | 2 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | TB |  | 901129537 | CLO | 1 | 4 | 220kV MO Cubicle Operational Test
SECTIONALISING DISCONNECT - REAMORE 110SA1
TO-20-REM-110SA1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
SECTIONALISING DISCONNECT - REAMORE 110SA2
TO-20-REM-110SA2-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
DISTRIBUTION TRANSFORMER - REAMORE T142 [SDCC]
TO-20-REM-T142-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
110kV FEEDER - REAMORE TRALEE
TO-20-REM-TRL-1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | REM |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - TARBERT 110 kV A1
TO-20-110 kV A1 @ TB-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2
BUSBAR SECTION - TARBERT 110 kV B1
TO-20-110 kV B1 @ TB-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A1/B1 @ TB: Proximity outage for work on Tarbert 110kV K1-2
COUPLER/SECTIONALISING CB - TARBERT 110K1-2
TO-20-TB-110K1-2-01 ISO week: 15mo - 15th Date: 06 Apr - 09 Apr Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | TB | 110-SA1 | 900859451 | DO | 4 | 3 | 110kV Sect / Dist Ordinary Service
AMCAB | TB | - |  | DO | 3 | 4 | Annual Insp. 110kV Station OF Cable
FO_CABLE | TB | - | 900973548 | DO | 1 | 1 | leak on S-Phase ( weep on CSE valve to be replaced)
COUPLER/SECTIONALISING CB - TARBERT 220K1-2
TO-20-TB-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | TB | 220-SB1 | 901134801 | DO | 1 | 1 | T Phase 220kV Coupler. Hotspot T Phase DB1 pantograph hinge DUE : next available opportunity.
TO-20-TB-220K1-2-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TB | 220-SA1 | 901039188 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - TARBERT T101 [SSE Generation Ireland TB1]
TO-20-TB-T101-01 ISO week: 15mo - 15tu Date: 06 Apr - 07 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T102 [SSE Generation Ireland TB2]
TO-20-TB-T102-01 ISO week: 14th - 14fr Date: 02 Apr - 03 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T2003 [SSE Generation Ireland TB3]
TO-20-TB-T2003-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TB |  | 901129535 | CLO | 2 | 4 | 220kV MO Cubicle Operational Test
GENERATOR TRANSFORMER - TARBERT T2004 [SSE Generation Ireland TB4]
TO-20-TB-T2004-01 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of R1Z23b, S Type Overcurrent
TRANSFORMER - TARBERT T2101
TO-20-TB-T2101-01 ISO week: 15mo - 15we Date: 06 Apr - 08 Apr Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | TB | 110 | 901005821 | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
OPT | TB | 220 | 901038969 | DO | 1 | 3 | 220kV MO Cubicle Operational Test
OPT | TB | 110 | 901038971 | DO | 1 | 3 | 110kV MO Cubicle Operational Test
OPT | TB | TRAFO | 901045378 | DO | 1 | 3 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - TARBERT T2102
TO-20-TB-T2102-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TB | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | TB | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | TB |  | 901059334 | CANC | 1 | 2 | Rust / Corrosion Station Equipment
110kV FEEDER - TARBERT TRALEE 1
TO-20-TB-TRL-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage for maps, circuit is now Kilpaddoge - Tralee
COUPLER/SECTIONALISING CB - TRALEE 110SA1-2CB
TO-20-TRL-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TRL | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
CAPACITOR/SVC/REACTOR - TRALEE CAP2
TO-20-TRL-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
COUPLER/SECTIONALISING CB - TRIEN 110SA1-2CB
TO-20-TRI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042136 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | TRI | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | TRI | 110-SA2 | 901042289 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-2CB-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
TO-20-TRI-110SA1-2CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
COUPLER/SECTIONALISING CB - TRIEN 110SA1-3CB
TO-20-TRI-110SA1-3CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
TO-20-TRI-110SA1-3CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042137 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
OS | TRI | 110-SA3 | 901042966 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-3CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
CAPACITOR/SVC/REACTOR - TRIEN CAP1
TO-20-TRI-CAP1-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-TRI-CAP1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | TRI | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - TRIEN T141 [SDCC]
TO-20-TRI-T141-01 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
DISTRIBUTION TRANSFORMER - TRIEN T142 [SDCC]
TO-20-TRI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
DISTRIBUTION TRANSFORMER - TRIEN T143 [SDCC]
TO-20-TRI-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)

## SLIGO (Rgn)
110kV FEEDER - ARIGNA tee CARRICK ON SHANNON
TO-20-ARI,T-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085136 | DO | 2 | 4 | 2019HP-1[188]Vib Dampers Loose
FO_STDMG |  |  | 901086390 | DO | 1 | 4 | 2019HP-2[182, 183]Replace Pole Bolt
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
110kV FEEDER - ARIGNA tee CORDERRY
TO-20-ARI,T-CDY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDY | - | 901039100 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARVA CARRICK ON SHANNON
TO-20-ARV-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | COS | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-ARV-COS-1-02 Status: Unscheduled
|  | - | 901148340 | CLO | 2 | 1 | Hotspot 1 (ET No.1, Span 1-2) Left Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148341 | CLO | 2 | 1 | Hotspot 2 (AT No.6, Span 6-7) Right Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148343 | CLO | 2 | 1 | Hotspot 4 (AT No.10, Span 10-11) Centre Deadend Terminiation (Repair by 6th June 2020)
|  | - | 901148345 | CLO | 2 | 1 | Hotspot 5 (AT No.11, Span 10-11) Right Deadend Termination (Repair by 6th Aug 2020)
|  | - | 901148346 | CLO | 2 | 1 | Hotspot 6 (AT No.154, Span 153-154) Centre Jumper Terminal (Repair by 6th Nov 2020)
|  | - | 901148348 | CLO | 2 | 1 | Hotspot 7 (R1, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148349 | CLO | 2 | 1 | Hotspot 8 (R2, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148350 | CLO | 2 | 1 | Hotspot 9 (C1, Span 204-205) Centre Midspan Joint (Repair Immediately)
|  | - | 901148351 | CLO | 2 | 1 | Hotspot 10 (C1, Span 204-205) Right Midspan Joint (Measure resistance by while repairing Hotspot 9))
|  | - | 901148352 | CLO | 2 | 1 | Hotspot 11 (R2, Span 168-169) Centre Midspan Joints (Measure resistance by 6th Aug 2020)
TO-20-ARV-COS-1-03 ISO week: 47mo - 47th Date: 16 Nov - 19 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | 901148342 | DO | 2 |  | Hotspot 3 (AT No.10, Span 9-10) Centre Deadend Terminiation (Repair by 6th Nov 2020)
SECTIONALISING DISCONNECT - BELLACORICK 110SA1
TO-20-BK-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA2: 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-110SA1-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA1 | 900942127 | DO | 1 | 2 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - BELLACORICK 110SA2
TO-20-BK-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-BK-110SA2-02 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA1: 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BELLACORICK CASTLEBAR
TO-20-BK-CBR-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-CBR-1-02 ISO week: 46th - 47th Date: 12 Nov - 19 Nov Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
YM03 | - | Line | 900979811 | DO | 3 | 1 | 2018HP-40m[59-60]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901088171 | DO | 3 | 1 | 2019HP-30m[168-169]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901060073 | DO | 2 | 1 | HAZ CNF 80m[101-102] 8-9m High Timber U
OPT | BK | - | 901050277 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | CBR | - | 901050314 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
AMCAB | CBR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BELLACORICK MOY
TO-20-BK-MOY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BK-MOY-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
| BK | - |  | DO | 2 | 4 | Cable Inspection XLPE
110kV FEEDER - BELLACORICK SRAHNAKILLY
TO-20-BK-SKY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 1 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-SKY-1-01 Status: Unscheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | CAB | 110 |  | DO | 5 | 4 | Cable Insp. 110kV XLPE
OPT | SKY |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-BK-SKY-1-03 ISO week: 29tu - 29we Date: 14 Jul - 15 Jul Duration: 2 Days (2 WD) Status: Scheduled
| BK |  | 901137803 | DO | 3 | 1 | NCC CANNOT OPERATE CB
OPT | BK |  | 901129688 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - BELLACORICK T122 [NDCC]
TO-20-BK-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0850 |  | 3 |  | Bay Outage for BZP
TO-20-BK-T122-02 Status: Reference (Unscheduled)
PROX |  |  | PR0002 | DO | 1 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - BELLACORICK T141 [NDCC]
TO-20-BK-T141-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110SA1-2CB
TO-20-COS-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
TO-20-COS-110SA1-2CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | COS | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - CARRICK ON SHANNON FLAGFORD 1
TO-20-COS-FLA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder
TO-20-COS-FLA-1-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 1 110 kV bay at flagford station
TO-20-COS-FLA-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-COS-FLA-1-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-COS-FLA-1-05 ISO week: 48th - 49tu Date: 26 Nov - 01 Dec Duration: 6 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | COS |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | FLA |  | 901053361 | DO |  | 1 | O1 Replacement coupling required on H3 d
CORRECT | FLA |  | 901053362 | DO |  | 1 | O1 Investigate control circuit including
110kV FEEDER - CARRICK ON SHANNON FLAGFORD 2
TO-20-COS-FLA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford carrick on shannon 2 110 kV Bay at flagford station
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TO-20-COS-FLA-2-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-COS-FLA-2-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-COS-FLA-2-04 Status: Unscheduled
Studied outage for potential extension of CP1031 due to CV-19
220kV FEEDER - CASHLA FLAGFORD
TO-20-CSH-FLA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at flagford station in the Cashla 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at Cashla station in the Flagford 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB
TO-20-CSH-FLA-1-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-FLA-1-06 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB
TO-20-CSH-FLA-1-07 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-08 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-10 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984858 | DO | 1 | 4 | 2018HP-1[am 247]Insulatorfit duplicates
FO_MISC |  |  | 901084304 | DO | 1 | 4 | 2019HP-1[134]Bird Nests
FO_MISC |  |  | 901084305 | DO | 1 | 4 | 2019HP-1[203]Bird Nests
FO_MISC |  |  | 901084306 | DO | 1 | 4 | 2019HP-1[210]Bird Nests
FO_MISC |  |  | 901084307 | DO | 1 | 4 | 2019HP-1[211]Bird Nests
FO_MISC |  |  | 901084308 | DO | 1 | 4 | 2019HP-1[212]Bird Nests
FO_MISC |  |  | 901084309 | DO | 1 | 4 | 2019HP-1[215]Bird Nests
FO_MISC |  |  | 901084310 | DO | 1 | 4 | 2019HP-1[240]Bird Nests
FO_MISC |  |  | 901084311 | DO | 1 | 4 | 2019HP-1[73]Bird Nests
FO_MISC |  |  | 901084312 | DO | 1 | 4 | 2019HP-1[78]Bird Nests
FO_MISC |  |  | 901084313 | CLO | 1 | 4 | 2019HP-1[80]Bird Nests
FO_MISC |  |  | 901084836 | DO | 1 | 4 | 2019HP-1[247]Insulator Fit Duplicate
OS | CSH | - | 900943133 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
OS | FLA | - | 900943176 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
TO-20-CSH-FLA-1-09 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513., REL521
TO-20-CSH-FLA-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
110kV FEEDER - CATHALEENS FALL SRANANAGH 1
TO-20-CF-SRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
FO_MISC |  | - | 900819401 | CLO | 2 | 2 | 2016HP-1[194]Check-General Ground works
FO_MISC |  | - | 900898210 | DO | 1 | 3 | 2017HP-1[30]Anti-Cl. Guard -Fit
AMCAB | CF | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CF | - | 901068533 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CATHALEENS FALL SRANANAGH 2
TO-20-CF-SRA-2-01 ISO week: 36we - 37fr Date: 02 Sep - 11 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900898213 | CLO | 7 | 3 | 2017HP-3[74,75,76]Off Plumb Poles
FO_MISC |  |  | 901084951 | CLO | 2 | 4 | 2019HP-1[77]Off Plumb -plumb poles
FO_MISC |  |  | 901084952 | CLO | 2 | 4 | 2019HP-1[185]Off Plumb -plumb poles
FO_MISC |  |  | 901084953 | CLO | 2 | 4 | 2019HP-1[186]Off Plumb -plumb poles
TRAN |  | - | 900985321 | CLO | 1 | 4 | 2018HP-1[44]Check(General)-old Xarm
TRAN |  | - | 900985335 | CLO | 1 | 4 | 2018HP-1[93]Check(General)rusty crossarm
FO_MISC |  |  | 901084269 | DO | 1 | 4 | 2019HP-1[247]Bird Nests
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511, REL521
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
SECTIONALISING DISCONNECT - CORDERRY 110SA1
TO-20-CDY-110SA1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA1-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
SECTIONALISING DISCONNECT - CORDERRY 110SA2
TO-20-CDY-110SA2-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA2-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
110kV FEEDER - CORDERRY GARVAGH
TO-20-CDY-GRV-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRAN | - | Line | 900985802 | NS | 1 | 4 | 2018HP-1[Am11]Bird Nests
| CDY | - | 901129384 | CLO | 5 | 1 | Leak detection on CB & repair if required
OPT | CDY |  | 901129706 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDERRY SRANANAGH
TO-20-CDY-SRA-1-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends
TO-20-CDY-SRA-1-01 ISO week: 9mo - 43fr Date: 24 Feb - 23 Oct Duration: 243 Days (169 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 170 |  | 110 kV OHL outage
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
FOSTRHW |  | - | 900725307 | DO | 8 | 1 | 2015CP-3[16,19,30]Replace Pole only
FOSTRHW |  | - | 900725308 | DO | 1 | 1 | 2015CP-1[28]Check Structure Worm Holes
P1 Protection maintenance of REL521, REL551
OPT | CDY | - | 901039099 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
DISTRIBUTION TRANSFORMER - CORDERRY T122 [NDCC]
TO-20-CDY-T122-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-T122-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
SECTIONALISING DISCONNECT - CUNGHILL 110SA1
TO-20-CUN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CUN-110SA2: 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CUNGHILL 110SA2
TO-20-CUN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
OS | CUN | SA2 | 901039702 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CUNGHILL GLENREE
TO-20-CUN-GLR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUN | - | 901042223 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | GLR | - | 901068536 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUN-GLR-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CUN: Proximity outage for work on Cunghill 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - CUNGHILL SLIGO
TO-20-CUN-SLI-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CUN | - | 901042227 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CUN-SLI-1-01 Status: Unscheduled
OPT | SLI | - | 901038824 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUNGHILL T121 [Kingsmountain KGM/KG2]
TO-20-CUN-T121-01 ISO week: 25tu - 25we Date: 16 Jun - 17 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
BUSBAR SECTION - FLAGFORD 110 kV A1
TO-20-110 kV A1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-110 kV A1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-110 kV A1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-110 kV A1 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-110 kV A1 @ FLA-05 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 110 kV A2
TO-20-110 kV A2 @ FLA-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV A2 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-110 kV A2 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-110 kV A2 @ FLA-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-110 kV A2 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
BUSBAR SECTION - FLAGFORD 110 kV B1
TO-20-110 kV B1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-110 kV B1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-110 kV B1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remove droppers (COS -FLA 1)
TO-20-110 kV B1 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + COS-FLA-1: Remake droppers (COS -FLA 1)
TO-20-110 kV B1 @ FLA-05 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 110 kV B1/B2
TO-20-110 kV B1/B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
BUSBAR SECTION - FLAGFORD 110 kV B2
TO-20-110 kV B2 @ FLA-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV B2 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remove droppers (COS -FLA 2)
TO-20-110 kV B2 @ FLA-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + COS-FLA-2: Remake droppers (COS -FLA 2)
TO-20-110 kV B2 @ FLA-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-110 kV B2 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
COUPLER/SECTIONALISING CB - FLAGFORD 110K1-2
TO-20-FLA-110K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ FLA + FLA-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
CAPX |  |  | CP1031 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV coupler bay at flagford station
TO-20-FLA-110K1-2-03 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | FLA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | FLA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | FLA | 110-SB |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FLA | 110-SA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-FLA-110K1-2-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous COS-FLA-1 + FLA-110K1-2: Energise new Circuit Breaker replacement via the 110 kV flagford carrick on shannon 1 remote end feeder
BUSBAR SECTION - FLAGFORD 220 kV A1
TO-20-220 kV A1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB
TO-20-220 kV A1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-220 kV A1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-220 kV A1 @ FLA-04 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV A2
TO-20-220 kV A2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB
TO-20-220 kV A2 @ FLA-02 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV B1
TO-20-220 kV B1 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-220 kV B1 @ FLA-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-220 kV B1 @ FLA-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-220 kV B1 @ FLA-04 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - FLAGFORD 220 kV B1/B2
TO-20-220 kV B1/B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
BUSBAR SECTION - FLAGFORD 220 kV B2
TO-20-220 kV B2 @ FLA-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - FLAGFORD 220K1-2
TO-20-FLA-220K1-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-220K1-2-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder
TO-20-FLA-220K1-2-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ FLA + FLA-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
CAPX |  |  | CP1031 | DO | 34 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the 220 kV coupler bay at flagford station
TO-20-FLA-220K1-2-04 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 901068587 | DO | 3 | 1 | O1 R phase pantograph on 220kV coupler s
110kV FEEDER - FLAGFORD GILRA
TO-20-FLA-GIL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
[5 empty] | 1 |  | Extra day required for covid restrictions
OS | FLA | - | 901129904 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
220kV FEEDER - FLAGFORD LOUTH
TO-20-FLA-LOU-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the Louth 220 kV bay at flagford station
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB
TO-20-FLA-LOU-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder
TO-20-FLA-LOU-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder
TO-20-FLA-LOU-1-01 ISO week: 38mo - 41fr Date: 14 Sep - 09 Oct Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0867 | DO | 40 |  | Outage to enable refurbishment of OHL, Remove ground proximity clearances and tower reinforcements
|  | - |  |  | 13 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Outage for timber cutting. RC 3 days request
FO_MISC |  |  | 901084409 | DO | 1 | 4 | 2019HP-1[4]Bird Nests
FO_MISC |  |  | 901084410 | DO | 1 | 4 | 2019HP-1[25]Bird Nests
FO_MISC |  |  | 901084411 | DO | 1 | 4 | 2019HP-1[38]Bird Nests
FO_MISC |  |  | 901084412 | CLO | 1 | 4 | 2019HP-1[192]Bird Nests
FO_MISC |  |  | 901084915 | DO | 1 | 4 | 2019HP-1[65]Insulator Broken R/ph
FO_MISC |  |  | 901084916 | DO | 1 | 4 | 2019HP-1[156]Insulator Broken C/ph
FOMISC | FLA | - | 900566631 | DO | 4 | 1 | Install Game Guards
OS | LOU | - | 901042380 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038537 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
110kV FEEDER - FLAGFORD SLIABH BAWN
TO-20-FLA-SLB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV flagford Sliabh Bawn bay at flagford station
TO-20-FLA-SLB-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-FLA-SLB-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-FLA-SLB-1-05 Status: Unscheduled
SAG6_HV | - | Line | 901160383 | DO | 2 | 1 | SPAN 1-2 of 0.98m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160384 | DO | 2 | 1 | SPAN 15-16 of 0.76m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160385 | DO | 2 | 1 | SPAN 16-17 of 1.99m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160386 | DO | 2 | 1 | SPAN 19-20 of 2.75m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160387 | DO | 2 | 1 | SPAN 31-32 of 0.92m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160388 | DO | 2 | 1 | SPAN 46-47 of 2.52m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160389 | DO | 2 | 1 | SPAN 76-77 of 2.23m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160390 | DO | 2 | 1 | SPAN 95-96 of 0.34m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160391 | DO | 2 | 1 | SPAN 1-2 of 0.43m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160392 | DO | 2 | 1 | SPAN 15-16 of 0.91m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160393 | DO | 2 | 1 | SPAN 16-17 of 2.58m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160394 | DO | 2 | 1 | SPAN 19-20 of 3.69m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160395 | DO | 2 | 1 | SPAN 31-32 of 1.63m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160396 | DO | 2 | 1 | SPAN 46-47 of 3.89m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160397 | DO | 2 | 1 | SPAN 60-61 of 0.10m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160398 | DO | 2 | 1 | SPAN 76-77 of 2.48m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160399 | DO | 2 | 1 | SPAN 95-96 of 0.90m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
TO-20-FLA-SLB-1-06 Status: Unscheduled
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 44-45
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 43-44
TO-20-FLA-SLB-1-04 ISO week: 32tu - 35fr Date: 04 Aug - 28 Aug Duration: 25 Days (19 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987019 | DO | 1 | 4 | 2018HP-1[Am 64]Bird Nests
FO_MISC |  |  | 901084413 | DO | 1 | 4 | 2019HP-1[64]Bird Nests
OS | FLA | - | 901050316 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | SLB | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - FLAGFORD SLIGO
TO-20-FLA-SLI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the flagford sligo 110 kV bay at flagford station
OPT | SLI | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-FLA-SLI-1-05 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remove droppers (FLA-SLI)
TO-20-FLA-SLI-1-06 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ FLA + FLA-SLI-1: Remake droppers (FLA-SLI)
220kV FEEDER - FLAGFORD SRANANAGH
TO-20-FLA-SRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-SRA-1-02 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 900891647 | DO | 3 | 1 | O1 Srananagh 220kV DE (R phase) earthing
OPT | FLA | - | 900942345 | DO | 3 | 2 | 220kV SF6 Cubicle Operational Test
OPT | SRA | - | 900942726 | DO | 3 | 2 | 220kV SF6 Cubicle Operational Test
TRANSFORMER - FLAGFORD T2101
TO-20-FLA-T2101-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-FLA-T2101-01 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 60 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the T2101 220 kV bay at flagford station
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous FLA-T2101 + FLA-T2101: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV T2101 bay at flagford station
CAPX |  |  | CP1031 | DO | 60 |  | Simultaneous 220 kV B1 @ FLA + FLA-T2101: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-FLA-T2101-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder
TO-20-FLA-T2101-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remove droppers (FLA T2101)
TO-20-FLA-T2101-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1/B1 IN TURN @ FLA + FLA-T2101: Remake droppers (FLA T2101)
TO-20-FLA-T2101-07 Status: Unscheduled
CORRECT | FLA |  | 900907922 | CANC |  | 2 | Allow 1 additional week for detailed mai
TO-20-FLA-T2101-06 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | FLA |  | 900909437 | DO | 3 | 2 | Camlin Power are to supply & install a n
OPT | FLA | 110 |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | FLA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | FLA | 220 |  | DO | 1 | 4 | 220kV MO Cubicle Operational Test
TRANSFORMER - FLAGFORD T2102
TO-20-FLA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | FLA | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | FLA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | FLA | 220 | 901080658 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-FLA-T2102-02 Status: Unscheduled
CORRECT | FLA | TRAFO | 900463619 | CANC | 1 | 2 | O 1 ESBI Replace three 220kV and 110kV b
BUSBAR SECTION - GARVAGH 110 kV A1
TO-20-110 kV A1 @ GRV-01 ISO week: 24th Date: 11 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GARVAGH 110 kV B1
TO-20-110 kV B1 @ GRV-01 ISO week: 24th Date: 11 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - GARVAGH 110K1
TO-20-GRV-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ GRV: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ GRV: Busbar Changeover
TO-20-GRV-110K1-02 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Corderry-Garvagh 110 kV
DISTRIBUTION TRANSFORMER - GARVAGH T141 [SDCC]
TO-20-GRV-T141-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Corderry-Garvagh 110 kV
TSO CUSTOMER TRANSFORMER - GILRA T121 [Masonite]
TO-20-GIL-T121-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Flagford-Gilra 110 kV
COUPLER/SECTIONALISING CB - GLENREE 110SA1-2CB
TO-20-GLR-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | GLR | 110-SA2 | 901130245 | CANC | 2 | 2 | 110kV Sect / Dist Ordinary Service
TO-20-GLR-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | GLR | 110-SA1 | 901130243 | CANC | 2 | 2 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - GLENREE MOY
TO-20-GLR-MOY-1-01 ISO week: 10mo - 43th Date: 02 Mar - 22 Oct Duration: 235 Days (163 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
CM | GLR | - | 901129078 | CLO | 10 | 1 | Repair SF6 leak on CB (ref. FO Mar 2019)
OPT | GLR | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | GLR |  | 901058978 | CLO | 1 | 2 | ESB EMP MO raised for PO. Stephen West.
DISTRIBUTION TRANSFORMER - GLENREE T142 [NDCC]
TO-20-GLR-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
CAPACITOR/SVC/REACTOR - MOY CAP1
TO-20-MOY-CAP1-02 ISO week: 11mo - 43th Date: 09 Mar - 22 Oct Duration: 228 Days (158 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | MOY | - | 901042293 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MOY | CAP | 901050225 | CLO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
CAPACITOR/SVC/REACTOR - MOY CAP2
TO-20-MOY-CAP2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | MOY | - | 901042294 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MOY | CAP | 901050226 | DO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
110kV FEEDER - MOY TAWNAGHMORE 1
TO-20-MOY-TAW-1-02 ISO week: 11mo - 43th Date: 09 Mar - 22 Oct Duration: 228 Days (158 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
CORRECT | TAW |  | 901090593 | CLO | 5 | 1 | An SF6 leak was detected on the pipework
OPT | TAW | 110 | 900942733 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MOY TAWNAGHMORE 2
TO-20-MOY-TAW-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | MOY | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | TAW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SLIGO 110SA1-2CB
TO-20-SLI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SLI | - | 901080653 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CAPACITOR/SVC/REACTOR - SLIGO CAP1
TO-20-SLI-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of SPAJ, 160C
110kV FEEDER - SLIGO SRANANAGH 1
TO-20-SLI-SRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
|  | - |  |  | 0 |  | Total Maintenance Outage Duration Requested
OPT | SLI | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | SRA | - | 901042241 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - | 901038567 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-SLI-SRA-1-01 ISO week: 43fr Date: 23 Oct Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous CDY-SRA-1 + SLI-SRA-1: EI - Energise Corderry Srananagh CT-VTs at both ends
110kV FEEDER - SLIGO SRANANAGH 2
TO-20-SLI-SRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | SRA |  | 901059776 | DO | 3 | 1 | Replace the pipework on the 110kV circui
CORRECT | SRA |  | 900535714 | DO | 1 | 1 | ESBI 02 non outage. Repeat online leakag
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA1
TO-20-SKY-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-110SA1-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA2
TO-20-SKY-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
GENERATOR TRANSFORMER - SRAHNAKILLY T131 [Srahnakilly OY1]
TO-20-SKY-T131-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-T131-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorrick - Srahnakilly
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SKY | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - SRANANAGH 110 kV A1
TO-20-110 kV A1 @ SRA-03 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV A1 @ SRA-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh
BUSBAR SECTION - SRANANAGH 110 kV A2
TO-20-110 kV A2 @ SRA-01 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - SRANANAGH 110 kV B1
TO-20-110 kV B1 @ SRA-03 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV B1 @ SRA-04 ISO week: 42we Date: 14 Oct Duration: 1 Day (1 WD) Status: Proposed
CAPX |  |  | CP0942 | DO | 1 |  | EI: Simultaneous 110 kV B1 @ SRA + SLI-SRA-1: EI - Energise DB on Corderry bay
TO-20-110 kV B1 @ SRA-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SRA: Remove Jumpers on A1/B1 BB Section In Srananagh
TO-20-110 kV B1 @ SRA-05 ISO week: 42mo - 42th Date: 12 Oct - 15 Oct Duration: 4 Days (4 WD) Status: Proposed
CAPX |  |  | CP0942 | DO | 3 |  | Connect new Jumpers on B1 BB Section In Srananagh & energise DB on Corderry bay
BUSBAR SECTION - SRANANAGH 110 kV B2
TO-20-110 kV B2 @ SRA-01 ISO week: 28th Date: 09 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
SECTIONALISING DISCONNECT - SRANANAGH 220SA1
TO-20-SRA-220SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
SECTIONALISING DISCONNECT - SRANANAGH 220SA2
TO-20-SRA-220SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TRANSFORMER - SRANANAGH T2102
TO-20-SRA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | As a consequence of FLA-SRA-1: 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-SRA-T2102-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA511, 7UT512
| SRA | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | SRA | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CM | SRA | TRAFO | 900693061 | DO | 5 | 2 | Replace timber supports
OS | SRA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SRA | Trafo |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CA | SRA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TRAFO | SRA | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CA | SRA | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TRAFO | SRA | TRAFO |  | DO | 2 | 4 | 220/110kV Trafo Tap Changer Inspection
COUPLER/SECTIONALISING CB - TAWNAGHMORE 110SA1-2CB
TO-20-TAW-110SA1-2CB-01 ISO week: 42we - 42th Date: 14 Oct - 15 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
YM03 | TAW | - | 900978748 | DO | 1 | 1 | STATUS OF CONTROL SELECTOR SWITCH IS NOT
OPT | TAW | - | 901043730 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TAW | 110-SA2 | 901050340 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - TAWNAGHMORE T1/T2 [SSE Generation Ireland TP1]
TO-20-TAW-T1/T2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - TAWNAGHMORE T3 [SSE Generation Ireland TP3]
TO-20-TAW-T3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 | 901043728 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test

## SDCC (Rgn)
110kV FEEDER - AHANE KILLONAN 2 [SDCC]
TO-20-AHA-KLN-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA513
COUPLER/SECTIONALISING CB - ATHLONE 110SA1-2CB
TO-20-ATH-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATH | - | 901039013 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
OPT | ATH | 110-SA1 | 901039204 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | ATH | 110-SA2 | 901039205 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
TO-20-ATH-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - ATHLONE T141 [SDCC]
TO-20-ATH-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - ATHLONE T142 [SDCC]
TO-20-ATH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
SECTIONALISING DISCONNECT - ATHY 110SA1
TO-20-ATY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 3 |  | Total Maintenance Outage Duration Requested
OS | ATY | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-ATY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - ATHY 110SA2
TO-20-ATY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of ATY-110SA1: 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - ATHY T101 [SDCC]
TO-20-ATY-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - BALLYBEG 110SA2
TO-20-BEG-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | BEG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - BALLYDINE T141 [SDCC]
TO-20-BDN-T141-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BALLYLICKEY DUNMANWAY [SDCC]
TO-20-BLI-DMY-1-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-DMY-1-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BALLYLICKEY T142 [SDCC]
TO-20-BLI-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-T142-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-T142-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-T142-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BALLYNAHULLA CORDAL
TO-20-BYH-CDL-1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901128997 | DO | 3 | 3 | Insp. 110kV Feeder XLPE Cable
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CDL |  | 901129678 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - BANDON 110SA1
TO-20-BAN-110SA1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OS | BAN | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BANDON 110SA2
TO-20-BAN-110SA2-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-110SA1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BANDON T101 [SDCC]
TO-20-BAN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BANDON T141 [SDCC]
TO-20-BAN-T141-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BARNAHELY RAFFEEN 1 [SDCC]
TO-20-BRY-RAF-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
110kV FEEDER - BARNAHELY RAFFEEN 2 [SDCC]
TO-20-BRY-RAF-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
DISTRIBUTION TRANSFORMER - BOGGERAGH T142 [SDCC]
TO-20-BGH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T142-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Reference
As a consequence of work on Boggeragh-Clashavoon 110 kV
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA1
TO-20-BUT-110SA1-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA2: 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BUTLERSTOWN 110SA2
TO-20-BUT-110SA2-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of BUT-110SA1: 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
OS | BUT | SA2 | 901146318 | CLO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T141 [SDCC]
TO-20-BUT-T141-01 ISO week: 33we - 33fr Date: 12 Aug - 14 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BUTLERSTOWN T142 [SDCC]
TO-20-BUT-T142-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ BUT: Proximity outage for work on Butlerstown 110kV Sect / Dist Ordinary Service (SA2)
BUSBAR SECTION - CARLOW 110 kV A1
TO-20-110 kV A1 @ CLW-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLW |  | PROX |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
DISTRIBUTION TRANSFORMER - CARLOW T141 [SDCC]
TO-20-CLW-T141-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
110kV FEEDER - CARROWBEG CASTLEBAR [SDCC]
TO-20-CBG-CBR-1-01 ISO week: 41fr Date: 09 Oct Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
XLPE inspection
DISTRIBUTION TRANSFORMER - CARROWBEG T142 [SDCC]
TO-20-CBG-T142-01 ISO week: 41mo - 42fr Date: 05 Oct - 16 Oct Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO maintenance
As a consequence of work on Carrowbeg-Castlebar 110 kV
COUPLER/SECTIONALISING CB - CASTLEBAR 110SA1-2CB
TO-20-CBR-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CBR | - | 901039130 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA1
TO-20-CVW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA2
TO-20-CVW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA2 | 901038579 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - CAUTEEN 110SA1
TO-20-CTN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CTN-110SA2: 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CAUTEEN 110SA2
TO-20-CTN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
OPT | CTN | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - CAUTEEN T142 [SDCC]
TO-20-CTN-T142-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-T142-01 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
DISTRIBUTION TRANSFORMER - CAUTEEN T144 [SDCC]
TO-20-CTN-T144-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - CLOGHBOOLA T122 [SDCC]
TO-20-CBA-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-T122-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Reference
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
BUSBAR SECTION - CLOON 110 kV A2
TO-20-110 kV A2 @ CLN-01 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PR0001 |  | 2 |  | Proximity for EI of CLN T142
SECTIONALISING DISCONNECT - CLOON 110SA1
TO-20-CLN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CLN-110SA2: 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CLOON 110SA2
TO-20-CLN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
OS | CLN | SA2 | 901039700 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - CLOON T142 [SDCC]
TO-20-CLN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-T142-02 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Reference (Tentative)
|  |  | PR0001 |  | 2 |  | EI of CLN T142 request from RC
SECTIONALISING DISCONNECT - CORDAL 110SA1
TO-20-CDL-110SA1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA1 | 901130105 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - CORDAL 110SA2
TO-20-CDL-110SA2-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA2 | 901146308 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - CORDAL T141 [SDCC]
TO-20-CDL-T141-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Ballynahulla-Cordal 110 kV circuit
110kV FEEDER - COW CROSS OLDCOURT 2 [SDCC]
TO-20-COW-OLD-2-01 ISO week: 9tu Date: 25 Feb Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
110kV FEEDER - CRORY LODGEWOOD [SDCC]
TO-20-CRY-LWD-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA611, 7SJ804
OS | LWD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - CRORY T121 [SDCC]
TO-20-CRY-T121-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CRY-LWD-1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - DALLOW T141 [SDCC]
TO-20-DAL-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 37 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 21 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL-T141-04 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 10 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL-T141-09 Status: Reference (Unscheduled)
CAPX |  |  | CP1057_OS | DO | 47 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL-T141-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 3 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL-T141-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL-T141-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL-T141-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 20 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee DALLOW
TO-20-DAL,T-DAL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-04 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-DAL-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-09 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL,T-DAL-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-DAL-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-DAL-1-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-DAL-1-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
SECTIONALISING DISCONNECT - DUNGARVAN 110SA1
TO-20-DGN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | DGN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
COUPLER/SECTIONALISING CB - DUNMANWAY 110SA1-2CB
TO-20-DMY-110SA1-2CB-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-110SA1-2CB-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-110SA1-2CB-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-DMY-110SA1-2CB-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-110SA1-2CB-02 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
OS | DMY | 110-SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
DISTRIBUTION TRANSFORMER - DUNMANWAY T141 [SDCC]
TO-20-DMY-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-T141-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-T141-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-T141-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DUNMANWAY T142 [SDCC]
TO-20-DMY-T142-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
COUPLER/SECTIONALISING CB - ENNIS 110SA1-2CB
TO-20-ENN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
TO-20-ENN-110SA1-2CB-02 Status: Unscheduled
CORRECT | ENN | - | 901045923 | CANC | 0 | 1 | Investigate CB gas leak & repair if possible
DISTRIBUTION TRANSFORMER - ENNIS T142 [SDCC]
TO-20-ENN-T142-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage requested by ESBN. DOF required following CA on T142 110kV cubicle
COUPLER/SECTIONALISING CB - GALWAY 110K1-2
TO-20-GAL-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-2-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K1-3
TO-20-GAL-110K1-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K2-3
TO-20-GAL-110K2-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K2-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T101 [SDCC]
TO-20-GAL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
DISTRIBUTION TRANSFORMER - GALWAY T102 [SDCC]
TO-20-GAL-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T141 [SDCC]
TO-20-GAL-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - GALWAY T142 [SDCC]
TO-20-GAL-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T143 [SDCC]
TO-20-GAL-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-20-GI-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
TO-20-GI-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-T141-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
DISTRIBUTION TRANSFORMER - GREAT ISLAND T142 [SDCC]
TO-20-GI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-T142-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Reference
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
DISTRIBUTION TRANSFORMER - IKERRIN T141 [SDCC]
TO-20-IKE-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 2 |  | As a consequence of IKE,T-IKE-1: IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee IKERRIN
TO-20-IKE,T-IKE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-IKE-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
DISTRIBUTION TRANSFORMER - KILBARRY T142 [SDCC]
TO-20-KBY-T142-01 ISO week: 34mo - 35fr Date: 17 Aug - 28 Aug Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | KBY |  |  |  | 10 |  | Proximity for Kilbarry K1-2
SECTIONALISING DISCONNECT - KILKENNY 110SA1
TO-20-KKY-110SA1-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of KKY-110SA2: 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - KILKENNY 110SA2
TO-20-KKY-110SA2-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
OS | KKY | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CM | KKY |  | 901133696 | CLO | 3 | 1 | Replacement of Stolen Earths
DISTRIBUTION TRANSFORMER - KILKENNY T142 [SDCC]
TO-20-KKY-T142-03 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - KILLONAN NENAGH [SDCC]
TO-20-KLN-NEN-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, REL521
SECTIONALISING DISCONNECT - KILLOTERAN 110SA1
TO-20-KTN-110SA1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA2: 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - KILLOTERAN 110SA2
TO-20-KTN-110SA2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of KTN-110SA1: 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
OS | KTN | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - KILLOTERAN T101 [SDCC]
TO-20-KTN-T101-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - KILLOTERAN T102 [SDCC]
TO-20-KTN-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ KTN: Proximity outage for work on Killoteran 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - LIBERTY STREET MARINA 1 [SDCC]
TO-20-LIB-MR-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | MR |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
SECTIONALISING DISCONNECT - LIMERICK 110SA1
TO-20-LIM-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of LIM-110SA2: 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - LIMERICK 110SA2
TO-20-LIM-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of LIM-110SA1: 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
OS | LIM | SA2 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
DISTRIBUTION TRANSFORMER - LIMERICK T141 [SDCC]
TO-20-LIM-T141-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - LIMERICK T142 [SDCC]
TO-20-LIM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
DISTRIBUTION TRANSFORMER - LISHEEN T142 [SDCC]
TO-20-LSN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - MACROOM T142 [SDCC]
TO-20-MAC-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
SECTIONALISING DISCONNECT - MIDLETON 110SA1
TO-20-MID-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of MID-110SA2: 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MIDLETON 110SA2
TO-20-MID-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | MID | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MID-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-20-MID-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - OUGHTRAGH T141 [SDCC]
TO-20-OUG-T141-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
110kV FEEDER - OUGHTRAGH tee OUGHTRAGH
TO-20-OUG,T-OUG-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989804 | DO | 1 | 4 | 2018HP-1[192-193]Re-sag conductor
FO_MISC |  |  | 901084875 | DO | 1 | 2 | 2019HP-1[227]Earths-Replace earth wire
110kV FEEDER - RAFFEEN RINGASKIDDY [SDCC]
TO-20-RAF-RSY-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RAF | - | 900942660 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TO-20-RAF-RSY-1-02 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, GRZ100
DISTRIBUTION TRANSFORMER - REAMORE T142 [SDCC]
TO-20-REM-T142-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
110kV FEEDER - REAMORE TRALEE
TO-20-REM-TRL-1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | REM |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SALTHILL 110SA1-2CB
TO-20-SAL-110SA1-2CB-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ611
OS | SAL | 110-SA2 | 900944542 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service
DISTRIBUTION TRANSFORMER - SALTHILL T102 [SDCC]
TO-20-SAL-T102-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | SAL |  |  |  | 2 |  | Proximity for SA2 Maintenance
COUPLER/SECTIONALISING CB - SINGLAND 110SA1-2CB
TO-20-SNG-110SA1-2CB-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
DSO proximity request for works on SNG T102
OPT | SNG | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | SNG | 110-SA2/DEM2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-SNG-110SA1-2CB-03 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
proximity for CA on Singland T101
TO-20-SNG-110SA1-2CB-02 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Proposed
OPT | SNG | 110-SA1/DEM1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - SINGLAND T101 [SDCC]
TO-20-SNG-T101-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CA on Singland T101
DISTRIBUTION TRANSFORMER - SINGLAND T102 [SDCC]
TO-20-SNG-T102-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO request for CA on SNG T102
DISTRIBUTION TRANSFORMER - SOMERSET T142 [SDCC]
TO-20-SOM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM-T142-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Reference
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
110kV FEEDER - SOMERSET tee SOMERSET
TO-20-SOM,T-SOM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-SOM-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-SOM-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
DISTRIBUTION TRANSFORMER - STRATFORD T141 [SDCC]
TO-20-STR-T141-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Full tee out for STRATFORD tee-POLLAPHUCA out
110kV FEEDER - STRATFORD tee STRATFORD
TO-20-STR,T-STR-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989656 | DO | 1 | 4 | 2018HP-1[192]ACGfit ACG on TEE tower
FOSTRHW |  |  | 901086414 | DO | 1 | 4 | 2019HP-1[2]Check Structure -Check Rot
COUPLER/SECTIONALISING CB - THURLES 110SA1-2CB
TO-20-THU-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - THURLES T142 [SDCC]
TO-20-THU-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - TRABEG T101 [SDCC]
TO-20-TBG-T101-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T102 [SDCC]
TO-20-TBG-T102-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T141 [SDCC]
TO-20-TBG-T141-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T142 [SDCC]
TO-20-TBG-T142-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
COUPLER/SECTIONALISING CB - TRALEE 110SA1-2CB
TO-20-TRL-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TRL | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | TRL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - TRIEN 110SA1-2CB
TO-20-TRI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042136 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | TRI | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | TRI | 110-SA2 | 901042289 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-2CB-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
TO-20-TRI-110SA1-2CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
COUPLER/SECTIONALISING CB - TRIEN 110SA1-3CB
TO-20-TRI-110SA1-3CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
TO-20-TRI-110SA1-3CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | TRI | - | 901042137 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
OS | TRI | 110-SA3 | 901042966 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-TRI-110SA1-3CB-02 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
DISTRIBUTION TRANSFORMER - TRIEN T141 [SDCC]
TO-20-TRI-T141-01 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
DISTRIBUTION TRANSFORMER - TRIEN T142 [SDCC]
TO-20-TRI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA2)
DISTRIBUTION TRANSFORMER - TRIEN T143 [SDCC]
TO-20-TRI-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
DISTRIBUTION TRANSFORMER - TULLABRACK T141 [SDCC]
TO-20-TBK-T141-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | As a consequence of TBK,T-TBK-1: BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7VK611
110kV FEEDER - TULLABRACK tee TULLABRACK
TO-20-TBK,T-TBK-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
SECTIONALISING DISCONNECT - WATERFORD 110SA1
TO-20-WAT-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | WAT | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-WAT-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WATERFORD 110SA2
TO-20-WAT-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of WAT-110SA1: 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - WATERFORD T141 [SDCC]
TO-20-WAT-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - WEXFORD 110SA1
TO-20-WEX-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
SECTIONALISING DISCONNECT - WEXFORD 110SA2
TO-20-WEX-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T122 [SDCC]
TO-20-WEX-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T142 [SDCC]
TO-20-WEX-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment

## PORTLAOISE (Rgn)
SECTIONALISING DISCONNECT - ATHY 110SA1
TO-20-ATY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 3 |  | Total Maintenance Outage Duration Requested
OS | ATY | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-ATY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - ATHY 110SA2
TO-20-ATY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of ATY-110SA1: 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - ATHY CARLOW
TO-20-ATY-CLW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
TO-20-ATY-CLW-1-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
TO-20-ATY-CLW-1-01 ISO week: 9mo - 9fr Date: 24 Feb - 28 Feb Duration: 5 Days (5 WD) Status: Scheduled
FO_MISC |  |  | 901074611 |  | 5 |  | End Tower 122 - Station Gantry in Carlow Replace insulators. Fit corona rings
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084078 |  | 2 |  | 2019HP-1[122]Anti-Cl. Guard -Replace. Wrong type fitted
OPT | CLW |  | 901128701 | CLO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ATHY PORTLAOISE
TO-20-ATY-PLS-1-02 ISO week: 18mo - 18fr Date: 27 Apr - 01 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  | - | 900606197 | CLO | 2 | 1 | 1[57] Replace pole - wayleave issue
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
TRAN |  | - | 900989777 | DO | 1 | 4 | 2018HP-1[128]Check Structure-top rot
FOSTRHW |  |  | 901086377 | DO | 1 | 4 | 2019HP-1[129]Check Structure -Check Rot
FOSTRHW |  |  | 901086378 | DO | 1 | 4 | 2019HP-1[130]Check Structure -Check Rot
H7 cubicle ordinary service
OS | ATY | - | 901042196 | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | ATY | - | 901038563 | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | PLS | - | 901050572 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | PLS |  | 901146375 | CLO | 3 | 1 | Replacement of Stolen Earths
CORRECT | PLS |  | 901072095 | DO | 1 | 2 | lamp in mech box o/o/o , corrision on wa
CORRECT | PLS |  | 901087221 | DO | 1 | 1 | moisture in surge counters
DISTRIBUTION TRANSFORMER - ATHY T101 [SDCC]
TO-20-ATY-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ ATY: Proximity outage for work on Athy 110kV Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - BARODA 110SA1-2CB
TO-20-BDA-110SA1-2CB-01 ISO week: 30mo - 30we Date: 20 Jul - 22 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CORRECT | BDA |  | 901087481 | DO | 2 | 1 | Arrange outage to complete testing of Ci
110kV FEEDER - BARODA MONREAD
TO-20-BDA-MON-1-01 ISO week: 13mo - 13fr Date: 23 Mar - 27 Mar Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | BDA | - | 901129957 | CLO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | BDA | - | 900567665 | DO | 2 | 4 | Repair Mid-Point Link Box
CA | BDA | - | 901129183 | CLO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | BDA | - | 900567665 | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CORRECT | BDA |  | 901076771 | DO | 1 | 1 | Reclosing sw protection panel : while tu
OS | MON | - | 901129932 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | MON |  | 901076757 | DO | 1 | 1 | PI on DL/DE o/o/o
CORRECT | MON |  | 901076765 | DO | 1 | 1 | CT T-phase insulator damaged
110kV FEEDER - BARODA NEWBRIDGE
TO-20-BDA-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BDA-NEW-1-01 Status: Unscheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | BDA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | BDA | - |  | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CA | NEW | - |  | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | NEW | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | DO | 3 | 1 | surge counter illigable
TSO CUSTOMER TRANSFORMER - BARODA T101 [Pfizer]
TO-20-BDA-T101-01 ISO week: 35mo - 36we Date: 24 Aug - 02 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - |  | DO | 4 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | BDA |  | 900796245 | DO | 1 | 1 | Fire alarm to be certafied
TSO CUSTOMER TRANSFORMER - BARODA T102 [Pfizer]
TO-20-BDA-T102-01 ISO week: 30mo - 31we Date: 20 Jul - 29 Jul Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - | 901129202 | CLO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - | 901129127 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
DISTRIBUTION TRANSFORMER - BLAKE T142 [NDCC]
TO-20-BLK-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
110kV FEEDER - BLAKE tee BLAKE
TO-20-BLK,T-BLK-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
TO-20-BLK,T-BLK-1-01 Status: Unscheduled
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
110kV FEEDER - BLAKE tee NEWBRIDGE
TO-20-BLK,T-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BLK,T-NEW-1-03 Status: Unscheduled
[5 empty] | 1 |  | Break jumpers for maintenance on Blake Tee Maynooth
TO-20-BLK,T-NEW-1-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 1 |  | Remake jumpers following maintenance on Blake Tee Maynooth & Blake Tee Newbridge
TRAN |  | - | 900989018 | DO | 1 | 4 | 2018HP-1[171]Off Plumbplumb poles
TRAN |  | - | 900989019 | DO | 1 | 4 | 2018HP-1[171]Earths-Replace-E/W broken
TRAN |  | - | 900989020 | DO | 1 | 4 | 2018HP-1[180]Off Plumbplumb poles
TRAN |  | - | 900989021 | DO | 1 | 4 | 2018HP-1[181]Off Plumbplumb poles
FO_MISC |  | - | 901038281 | DO | 1 | 4 | 2018CP-1[171]Vibration Dampers -rusty
FO_MISC |  | - | 901038283 | DO | 1 | 4 | 2018CP-1[171]Stays - Replace
FO_MISC |  | - | 901038284 | DO | 1 | 4 | 2018CP-1[171]Earths - Replace (E strap)
FO_MISC |  | - | 901038290 | DO | 1 | 4 | 2018CP-1[168]Earths - Replace (HW Rusty)
FO_MISC |  |  | 901084873 | DO | 1 | 4 | 2019HP-1[170]Earths-Replace broken x2
FO_MISC |  |  | 901084874 | DO | 1 | 4 | 2019HP-1[171]Earths-Replace broken x2
OS | NEW | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | 20CM0255 | 3 | 1 | surge counter illigable
CA | NEW | - |  | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
BUSBAR SECTION - CARLOW 110 kV A1
TO-20-110 kV A1 @ CLW-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLW |  | PROX |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
110kV FEEDER - CARLOW KELLIS 1
TO-20-CLW-KLS-1-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | CLW |  | 901075041 | DO | 2 | 1 | busbar disconnect seized at top , bird c
OPT | KLS | - | 901038904 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CARLOW KELLIS 2
TO-20-CLW-KLS-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084945 | DO | 2 | 4 | 2019HP-1[16]Off Plumb -plumb poles
FO_MISC |  |  | 901084946 | DO | 2 | 4 | 2019HP-1[17]Off Plumb -plumb poles
OS | CLW | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CLW-KLS-2-01 ISO week: 13tu - 14th Date: 24 Mar - 02 Apr Duration: 10 Days (8 WD) Status: Forced Out
PROT |  |  |  | DO | 1 |  | P1 Protection maintenance of 7SA511
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
DISTRIBUTION TRANSFORMER - CARLOW T141 [SDCC]
TO-20-CLW-T141-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
COUPLER/SECTIONALISING CB - CUSHALING 110SA1-2CB
TO-20-CUS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS | SA1 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUS | SA2 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUS | - | 901038992 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUS-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ611
110kV FEEDER - CUSHALING MOUNTLUCAS
TO-20-CUS-MLC-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MLC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CUSHALING NEWBRIDGE
TO-20-CUS-NEW-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-CUS-NEW-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-CUS-NEW-1-03 Status: Unscheduled
[5 empty] | 2 |  | Timber Cutting
110kV FEEDER - CUSHALING PORTLAOISE
TO-20-CUS-PLS-1-01 ISO week: 24fr - 27we Date: 12 Jun - 01 Jul Duration: 20 Days (14 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 900898064 | DO | 2 | 1 | 2019HP-1[200]Replace Pole only -Rot
FO_STDMG |  | - | 900876709 | DO | 1 | 3 | 2017CP-1[28]Found/Site repair Fill base
FO_MISC |  | - | 900876727 | CLO | 1 | 3 | 2017CP-1[71]Off Plumb Poles
FO_STDMG |  | - | 900876728 | CLO | 1 | 3 | 2017CP-1[71]Found/Site repair Fill base
FO_MISC |  | - | 900876729 | CLO | 1 | 3 | 2017CP-1[73]Shear Block Repair all
FO_STDMG |  | - | 900876730 | CLO | 1 | 3 | 2017CP-1[73]Replace Member -Bent
FO_STDMG |  | - | 900876741 | CLO | 1 | 3 | 2017CP-1[89]Found/Site repair Sleepers
FO_MISC |  | - | 900876757 | CLO | 1 | 3 | 2017CP-2[102,103]Off Plumb Poles
FO_MISC |  | - | 900876759 | CLO | 1 | 3 | 2017CP-1[103]Off Plumb Insulator
FO_MISC |  | - | 900876760 | DO | 1 | 3 | 2017CP-1[104]Replace/Retire pole butts
FO_MISC |  | - | 900876761 | DO | 1 | 3 | 2017CP-1[105]Shear Block Repair all
FO_MISC |  | - | 900876791 | CLO | 1 | 3 | 2017CP-1[134]Off Plumb Poles
FO_MISC |  | - | 900876804 | DO | 1 | 3 | 2017CP-1[147]Shear Block Repair
FO_MISC |  | - | 900876809 | DO | 1 | 3 | 2017CP-1[150]Replace/Retire pole butts
FO_MISC |  | - | 900876833 | DO | 1 | 3 | 2017CP-1[167]Shear Block Repair all
FO_MISC |  | - | 900876864 | CLO | 1 | 3 | 2017CP-1[181]Shear Block Clear base
FO_MISC |  | - | 900876869 | DO | 1 | 3 | 2017CP-1[185]Off Plumb Pole & Insulator
FO_STDMG |  | - | 900876871 | DO | 1 | 3 | 2017CP-1[185]Found/Site repair Fill base
FO_MISC |  | - | 900876877 | CLO | 1 | 3 | 2017CP-1[190]Off Plumb Pole & Insulator
FO_STDMG |  | - | 900876881 | CLO | 1 | 3 | 2017CP-1[194]Found/Site repair Fill base
FO_MISC |  | - | 900876891 | CLO | 1 | 3 | 2017CP-1[204]Shear Block Clear base
FO_STDMG |  | - | 900876926 | DO | 1 | 3 | 2017CP-1[4]Pole Bolt Loose-Tighten
FO_STDMG |  | - | 900876929 | DO | 1 | 3 | 2017CP-1[103]Pole Bolt Loose-Tighten
FO_MISC |  | - | 900876937 | CLO | 1 | 3 | 2017CP-1[105]Stepbolts Missing-Fit
FO_MISC |  | - | 900876938 | CLO | 1 | 3 | 2017CP-1[110]Stepbolts Missing-Fit
FO_MISC |  | - | 900876939 | CLO | 1 | 3 | 2017CP-1[111]Stepbolts Missing-Fit
FO_MISC |  | - | 900876940 | CLO | 1 | 3 | 2017CP-1[130]Stepbolts Missing-Fit
FO_MISC |  | - | 900876941 | CLO | 1 | 3 | 2017CP-1[147]Stepbolts Missing-Fit
FO_MISC |  | - | 900876942 | CLO | 1 | 3 | 2017CP-1[167]Stepbolts Missing-Fit
FO_MISC |  | - | 900876943 | CLO | 1 | 3 | 2017CP-1[181]Stepbolts Missing-Fit
FO_MISC |  | - | 900876947 | DO | 1 | 3 | 2017CP-1[4]Earths Repair attach. point
FO_MISC |  | - | 900876948 | CLO | 1 | 3 | 2017CP-1[7]Off Plumb -Earth attach point
FO_MISC |  | - | 900876949 | DO | 1 | 3 | 2017CP-1[4]Earths Repair earth straps
FO_MISC |  | - | 900876950 | DO | 1 | 3 | 2017CP-1[6]Earths Reclip oxlip
FO_MISC |  | - | 900876951 | DO | 1 | 3 | 2017CP-1[7]Earths Reclip oxlip
FOSTRHW |  | - | 900898062 | DO | 1 | 3 | 2017HP-2[92]Check Structure Top Rot
FOSTRHW |  | - | 900898064 | DO | 1 | 3 | 2017HP-2[200]Check Structure Top Rot
FOINSHW |  |  | 901085553 | CLO | 1 | 4 | 2019HP-1[199]Insul&HW Replac check
OS | CUS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CUS | - |  | DO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CUSHALING T101 [Edenderry Power ED1]
TO-20-CUS-T101-01 ISO week: 28tu Date: 07 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUSHALING T103/5 [Edenderry Power ED3/ED5]
TO-20-CUS-T103/5-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - DALLOW tee DALLOW
TO-20-DAL,T-DAL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-04 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-DAL-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-09 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL,T-DAL-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-DAL-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-DAL-1-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-DAL-1-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee PORTLAOISE
TO-20-DAL,T-PLS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-08 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | PLS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | PLS |  | 900965558 | DO | 3 | 1 | Moisture in LAs
CORRECT | PLS |  | 901072096 | DO | 3 | 1 | H6 , loose stripped cores in mech box ,
TO-20-DAL,T-PLS-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-PLS-1-03 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-PLS-1-01 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-PLS-1-04 ISO week: 39tu - 41mo Date: 22 Sep - 05 Oct Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-PLS-1-13 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee SHANNONBRIDGE
TO-20-DAL,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-SH-1-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-DAL,T-SH-1-11 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
TO-20-DAL,T-SH-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-SH-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-SH-1-04 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-SH-1-12 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
TO-20-DAL,T-SH-1-03 ISO week: 34mo - 38mo Date: 17 Aug - 14 Sep Duration: 29 Days (21 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-SH-1-06 ISO week: 41we - 48fr Date: 07 Oct - 27 Nov Duration: 52 Days (37 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084339 | DO | 1 | 4 | 2019HP-1[252]Bird Nests -Remove
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | SH | - | 901133675 | DO | 2 | 1 | T Phase DA Disconnect DUE: 17-Jul-20
110kV FEEDER - DERRYIRON MAYNOOTH
TO-20-DER-MAY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | - | 901045929 | CANC | 3 | 1 | Investigate CB gas leak & repair if possible
TO-20-DER-MAY-1-01 ISO week: 39mo - 42fr Date: 21 Sep - 16 Oct Duration: 26 Days (20 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  |  |  | 2 |  | proximity needed of Derryiron - Maynooth for maintenance on Dunstown - Maynooth 2
FO_MISC |  |  | 901084970 | DO | 2 | 4 | 2019HP-1[4]Off Plumb -plumb poles
FO_MISC |  |  | 901084971 | DO | 2 | 4 | 2019HP-1[28]Off Plumb -plumb poles
FO_MISC |  |  | 901084972 | DO | 2 | 4 | 2019HP-1[29]Off Plumb -plumb poles
FO_MISC |  |  | 901084973 | DO | 2 | 4 | 2019HP-1[160]Off Plumb -plumb poles
FO_MISC |  |  | 901084974 | DO | 2 | 4 | 2019HP-1[161]Off Plumb -plumb poles
FO_MISC |  |  | 901084975 | DO | 2 | 4 | 2019HP-1[164]Off Plumb -plumb poles
FO_MISC |  |  | 901084976 | DO | 2 | 4 | 2019HP-1[181]Off Plumb -plumb poles
FO_MISC |  |  | 901084977 | DO | 2 | 4 | 2019HP-1[182]Off Plumb -plumb poles
FO_MISC |  |  | 901084978 | DO | 2 | 4 | 2019HP-1[183]Off Plumb -plumb poles
FOSTRHW |  |  | 901086429 | DO | 2 | 1 | 2019HP-1[75]Replace Pole only -Rot
FOSTRHW |  |  | 901086430 | DO | 2 | 1 | 2019HP-1[106]Replace Pole only -Rot
FOSTRHW |  |  | 901086431 | DO | 2 | 1 | 2019HP-1[124]Replace Pole only -Rot
PROX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Dunstown-Maynooth-2 220 kV
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
| - | Line | 901150823 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 116 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150824 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 117 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150825 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 118 need to be replaced by the autumn 2020 before winter storms commence.
OPT | DER |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY |  | 901080694 | DO | 3 | 2 | Missing Earths on Earths on CB
AMCAB | MAY | - | 900944029 | DO | 2 | 3 | Annual Insp. 110 Feeder OF Cable
220kV FEEDER - DUNSTOWN KELLIS
TO-20-DSN-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1017 | DO | 7 |  | Proximity outage for stringing of Donard Test Line
TO-20-DSN-KLS-1-03 Status: Unscheduled
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Great Island-Kellis 220 kV
TO-20-DSN-KLS-1-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Replace stolen earths
FO_MISC |  |  | 901084901 | DO | 2 | 4 | 2019HP-1[39]Insulator Strain insul
FOINSHW |  |  |  |  | 1 |  | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  |  |  |  | 1 |  | 2017HP-1[103]Anti-Cl. Guard fit
FOINSHW |  | - | 900819574 | DO | 1 | 2 | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  | - | 900898068 | DO | 1 | 3 | 2017HP-1[103]Anti-Cl. Guard fit
TRAN |  | - | 900986534 | DO | 1 | 4 | 2018HP-1[39]Insulatorbroken insulator
TRAN |  | - | 900986536 | DO | 1 | 4 | 2018HP-1[173]Earths-Replace-Earth Strap
TRAN |  | - | 900986537 | DO | 1 | 4 | 2018HP-1[174]Earths-Replace-Earth Strap
TRAN |  | - | 900986538 | DO | 1 | 4 | 2018HP-1[176-177]Vib Dampers-EW damper
TRAN |  | - | 900986539 | DO | 1 | 4 | 2018HP-1[178-179]Vib Dampers-EW damper
CORRECT | DSN |  | 900444600 | DO | 5 | 2 | O. ESBI Inspect and test all the cylind
CORRECT | DSN |  | 900566652 | DO | 2 | 2 | ESBI 01. VT Insulation retest Important
CM | DSN | - | 900719181 | DO | 2 | 2 | 2[140,143] Replace bent/damaged steel member
FM | DSN | - | 901045782 | DO | 2 | 4 | HV Pressure Vessel Inspection
OPT | DSN | - | 900955895 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
OPT | KLS | - | 900955894 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - GREAT ISLAND GIS KELLIS
TO-20-GI GIS-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 901050728 | DO | 12 | 4 | Repair earth on 24 DC towers
FO_MISC |  | - | 900898107 | DO | 1 | 3 | 2017HP-1[196]Earths-Check earth bond top
FO_MISC |  | - | 900898108 | DO | 1 | 3 | 2017HP-1[207]Earths-Check earth bond top
FO_MISC |  | - | 900898109 | DO | 1 | 3 | 2017HP-1[214]Vib Damps EW damper fatigue
TRAN |  | - | 900987495 | DO | 1 | 4 | 2018HP-1[117]Insulatorbroken insulator
TRAN |  | - | 900987496 | DO | 1 | 4 | 2018HP-1[216]Insulatorbroken insulator
FO_MISC |  |  | 901085220 | DO |  | 2 | 2019HP-1[211]Vib Dampers EW VD fatigued
FO_MISC |  |  | 901085221 | DO |  | 4 | 2019HP-1[212]Vib Dampers EW VD fatigued
OS | GI | - | 901042324 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
AMCAB | GI | 220 | 901006258 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
OS | KLS | - | 901042334 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
110kV FEEDER - GREAT ISLAND KILKENNY
TO-20-GI-KKY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 100 |  | Circuit and Bay works at Kilkenny & Great Island
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-KKY-1-04 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 1 |  | EI: Simultaneous GI-KKY-1 + GI-KKY-1: Energisation of circuit
TO-20-GI-KKY-1-05 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084415 | CLO | 1 | 2 | 2019HP-1[89]Bird Nests remove birds nest
FO_MISC |  |  | 901084980 | CLO |  | 2 | 2019HP-1[112]Off Plumb -plumb poles
FO_MISC |  |  | 901084981 | CLO |  | 2 | 2019HP-1[116]Off Plumb -plumb poles
FOSTRHW |  |  | 901086403 | CLO |  | 2 | 2019HP-1[15]Check Structure struct & HW
FOSTRHW |  |  | 901086404 | CLO |  | 2 | 2019HP-1[16]Check Structure struct & HW
FOSTRHW |  |  | 901086405 | CLO |  | 2 | 2019HP-1[129]Check Structure -Check Rot
CORRECT | GI |  | 901068754 | CLO |  | 2 | 110kV CTVTs Restest: Sphase .96% PF, TPh
CORRECT | KKY |  | 901072125 | CLO | 5 | 1 | surge counter unreadable , gas gauge rot
CORRECT | KKY |  | 901090669 | CLO | 5 | 1 | manometer needs replacing
CM | KKY |  | 901133697 | CLO | 3 | 1 | Replacement of Stolen Earths
TO-20-GI-KKY-1-07 ISO week: 41we - 42th Date: 07 Oct - 15 Oct Duration: 9 Days (7 WD) Status: Scheduled
TRAN |  | - | 900987497 | DO | 2 | 4 | 2018HP-1[10]Off Plumb
TRAN |  | - | 900987502 | DO | 2 | 4 | 2018HP-1[112]Off Plumb
TRAN |  | - | 900987503 | DO | 2 | 4 | 2018HP-1[113]Off Plumb
| GRI | - | 901160926 | DO | 3 | 1 | Follow on work to replace stolen earths after copper theft
OS | KKY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - KELLIS 110 kV A1
TO-20-110 kV A1 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV A2
TO-20-110 kV A2 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV B1
TO-20-110 kV B1 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KELLIS 110 kV B2
TO-20-110 kV B2 @ KLS-01 ISO week: 31th Date: 30 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - KELLIS 220K1-2
TO-20-KLS-220K1-2-01 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | KLS |  | 901076101 | CLO | 2 | 1 | CB door broken
OPT | KLS |  | 901129547 | CLO | 2 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 220-SA | 901130124 | CLO | 2 | 4 | 220kV Sect / Dist Operational Test
110kV FEEDER - KELLIS KILKENNY
TO-20-KLS-KKY-1-01 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
FO_MISC |  |  | 901084984 | CLO | 2 | 4 | 2019HP-1[51]Off Plumb -plumb poles
FO_MISC |  |  | 901084985 | CLO | 2 | 4 | 2019HP-1[125]Off Plumb -plumb poles
TRAN |  | - | 900987666 | DO | 1 | 4 | 2018HP-1[144]Off Plumb
H3/H4 cubicle ordinary service
OS | KKY | - | 901042232 | CLO | 5 | 1 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KKY |  | 901072127 | CLO | 5 | 1 | surge counters wet inside , cables not s
OS | KLS | - | 901042231 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KLS |  | 901076103 | CLO | 5 | 1 | H4 moisture in surge counters
TRANSFORMER - KELLIS T2101
TO-20-KLS-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| KLS | - |  | CANC | 5 |  | Total Maintenance Outage Duration Requested
OPT | KLS | TRAFO | 901045352 | DO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
CM | KLS | - | 901134788 | DO | 2 | 1 | R,S & T Phases T2101 220kV Cubicle. R, S & T Phase CT internal links, heating appearing internally, possible corrosion/poor connection. DUE : 17-Nov-20
TO-20-KLS-T2101-03 Status: Unscheduled
CM | KLS | - | 901134787 | DO | 2 | 1 | R & S Phase T2101 110kV Bushing. R & S Phase connection hotspot DUE : IMMEDIATELY
TO-20-KLS-T2101-04 Status: Unscheduled
CORRECT | KLS | 220 | 901068451 | CANC | 1 | 1 | ABB required to overhaul CB poles for gas leak repair work
TO-20-KLS-T2101-01 ISO week: 13mo - 13fr Date: 23 Mar - 27 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | KLS |  | 901036845 | DO | 5 | 1 | Bund Leaking
OPT | KLS | 220 | 901038901 | DO | 2 | 3 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 110 | 901038905 | DO | 2 | 3 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - KELLIS T2102
TO-20-KLS-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | KLS | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KLS | 220 |  | DO | 2 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KLS | 110 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - KILKENNY 110SA1
TO-20-KKY-110SA1-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of KKY-110SA2: 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - KILKENNY 110SA2
TO-20-KKY-110SA2-05 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
OS | KKY | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CM | KKY |  | 901133696 | CLO | 3 | 1 | Replacement of Stolen Earths
CAPACITOR/SVC/REACTOR - KILKENNY CAP2
TO-20-KKY-CAP2-03 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
CORRECT | KKY |  | 901083041 | DO | 5 | 1 | AC and DC Supplies:Carry out wiring mods
CM | KKY |  |  | DO | 3 | 1 | Replacement of Stolen Earths
DISTRIBUTION TRANSFORMER - KILKENNY T142 [SDCC]
TO-20-KKY-T142-03 ISO week: 22mo - 22we Date: 25 May - 27 May Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - KILTEEL MONREAD
TO-20-KTL-MON-1-01 ISO week: 23tu - 24mo Date: 02 Jun - 08 Jun Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MON |  | 901076758 | CLO | 5 | 1 | Low Gas
OPT | MON | - | 901055117 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - MAYNOOTH SHANNONBRIDGE
TO-20-MAY-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN | - | Line | 901110127 | CLO | 2 | 1 | Hotspot 1 (R1 Span 81/82) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110131 | DO | 2 | 1 | Hotspot 2 (R2 Span 255/256) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110136 | DO | 2 | 1 | Hotspot 3 (R1 Span 271/272) Right phase midspan (Repair by 17th July 2020)
TO-20-MAY-SH-1-01 ISO week: 26mo - 27th Date: 22 Jun - 02 Jul Duration: 11 Days (9 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819839 | DO | 4 | 2 | 2016HP-2[2 & 3]Insulator Fit Dups
FO_MISC |  |  | 901090694 | DO | 2 | 4 | 2019HP-1[47-48]Conflicts 10/20kV pole
FO_MISC |  |  | 901090695 | DO | 2 | 4 | 2019HP-1[51-52]Conflicts 10/20kV pole
CM | MAY | - | 901076415 | CLO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
CA | SH | - | 901038544 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA1
TO-20-NEW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA1 | 901039710 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA2: 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA2
TO-20-NEW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA1: 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - NEWBRIDGE PORTLAOISE
TO-20-NEW-PLS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-NEW-PLS-1-01 ISO week: 10mo - 12fr Date: 02 Mar - 20 Mar Duration: 19 Days (14 WD) Status: Scheduled
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989025 | DO | 2 | 4 | 2018HP-1[106]ACGFit ACG
TRAN |  | - | 900989041 | CLO | 2 | 4 | 2018HP-1[201]Conductor Check-Top Rot
FO_MISC |  |  | 901084851 | DO | 2 | 4 | 2019HP-1[2-3]Conflicts 20kV cable pole
FOINSHW |  | - | 900973635 | DO | 1 | 3 | 1[214]Install Duplicate Suspension Insul
TRAN |  | - | 900989023 | DO | 1 | 4 | 2018HP-1[56-57]Conflicts-LV/MV pole
TRAN |  | - | 900989024 | CLO | 1 | 4 | 2018HP-2[68]Cattle Guards
TRAN |  | - | 900989035 | CLO | 1 | 4 | 2018HP-1[137]Insul&HW Replace check
TRAN |  | - | 900989036 | CLO | 1 | 4 | 2018HP-1[138]Insul&HW Replace check
TRAN |  | - | 900989037 | CLO | 1 | 4 | 2018HP-1[139]Insul&HW Replace check
TRAN |  | - | 900989038 | CLO | 1 | 4 | 2018HP-1[145]Insul&HW Replace check
FO_MISC |  |  | 901084324 | DO | 1 | 4 | 2019HP-1[106]Bird Nests -Remove
TRAN |  | - | 901146901 | CLO | 1 | 1 | Hotspot 3 (Angle Tower No. 117, span 116/117), right jumper terminal
TRAN | - | - | 901128694 | CLO | 1 | 1 | Hotspot 1 (Angle Tower No. 48, span 48/49), left Jumper Terminal
TRAN | - | - | 901146902 | CLO | 1 | 1 | Hotspot 2 (Angle Tower No. 116, span 115A/116), right deadend
CORRECT | NEW |  | 901059566 | CLO | 5 | 1 | Replace SF6 pipework
CORRECT | NEW |  | 901060158 | CLO | 5 | 1 | O1-Small SF6 piping to be changed on CB.
DISTRIBUTION TRANSFORMER - NEWBRIDGE T141 [NDCC]
TO-20-NEW-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - NEWBRIDGE T142 [NDCC]
TO-20-NEW-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
BUSBAR SECTION - PORTLAOISE 110 kV A1
TO-20-110 kV A1 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV A2
TO-20-110 kV A2 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV B1
TO-20-110 kV B1 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
BUSBAR SECTION - PORTLAOISE 110 kV B2
TO-20-110 kV B2 @ PLS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ PLS: Proximity outage for work on Portlaoise 110kV K1-2
COUPLER/SECTIONALISING CB - PORTLAOISE 110K1-2
TO-20-PLS-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | PLS | 110-SA1 | 900859298 | DO | 2 | 2 | 110kV Sect / Dist Ordinary Service
OS | PLS | 110-SB1 | 900859306 | DO | 2 | 2 | 110kV Sect / Dist Ordinary Service
OPT | PLS | - | 901038676 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | PLS | 110-SB2 | 901042975 | DO | 2 | 4 | 110kV Sect / Dist Operational Test
OPT | PLS | 110-SA2 | 901042976 | DO | 2 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - STRATFORD T141 [SDCC]
TO-20-STR-T141-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Full tee out for STRATFORD tee-POLLAPHUCA out
110kV FEEDER - STRATFORD tee CARLOW
TO-20-STR,T-CLW-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086426 | DO | 2 | 1 | 2019HP-1[110]Replace Pole only -Rot
FO_MISC |  | - | 900864816 | DO | 1 | 2 | 2016CP-1[109]Off Plumb Pole & insulators
FO_STDMG |  | - | 900864817 | DO | 1 | 2 | 2016CP-1[109]Replace Pole Bolt -Bent
FO_MISC |  | - | 900864818 | DO | 1 | 2 | 2016CP-1[109]Vibration Dampers Replace
FOINSHW |  | - | 900864820 | DO | 1 | 2 | 2016CP-1[109]H-ware Susp Clamps corroded
FO_STDMG |  | - | 900864821 | DO | 1 | 2 | 2016CP-1[109]Crossarm Replacement
FOSTRHW |  | - | 900864822 | DO | 1 | 1 | 2016CP-1[110]Replace Pole only -Rotten
TRAN |  | - | 900984379 | DO | 1 | 4 | 2018HP-1[90]ACGfit ACG
TRAN |  | - | 900989809 | DO | 1 | 4 | 2018HP-1[94]Check Structure-top rot - Ch
FOSTRHW |  |  | 901086400 | DO | 1 | 4 | 2019HP-1[124]Check Structure -Check Rot
OPT | CLW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - STRATFORD tee POLLAPHUCA
TO-20-STR,T-PA-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 900864747 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
FO_STDMG |  | - | 900898188 | CLO | 2 | 3 | 2017HP-1[14]Crossarm Replacement Replace
FO_MISC |  | - | 900864747 | CLO | 1 | 2 | 2016CP-1[13]Off Plumb Poles
FOSTRHW |  | - | 900973774 | CANC | 1 | 1 | 1[33]Replace Rotten Pole
FO_MISC |  | - | 900975368 | CLO | 1 | 1 | 1[53]Install ACG on mast no. 53
TRAN |  | - | 900989394 | DO | 1 | 4 | 2018HP-1[15]Off Plumb-Poles
OS | PA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | PA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - STRATFORD tee STRATFORD
TO-20-STR,T-STR-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989656 | DO | 1 | 4 | 2018HP-1[192]ACGfit ACG on TEE tower
FOSTRHW |  |  | 901086414 | DO | 1 | 4 | 2019HP-1[2]Check Structure -Check Rot

## OUTTURN - TSO (Rgn)
110kV FEEDER - AGANNYGAL DERRYBRIEN [Derrybrien DY1]
TO-20-AGL-DYN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-AGL-DYN-1-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-AGL-DYN-1-02 ISO week: 37mo - 37sa Date: 07 Sep - 12 Sep Duration: 6 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | AGL | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | AGL | - | 900713712 | DO | 3 | 2 | CB - Siemens 3AP mod required to prevent spring charging lockout with loss of AC.
220kV FEEDER - AGHADA LONG POINT
TO-20-AD-LPT-1-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
GENERATOR TRANSFORMER - AGHADA T2011/12 [ESB GWM AT11/AT12]
TO-20-AD-T2011/12-02 ISO week: 9mo - 23tu Date: 24 Feb - 02 Jun Duration: 100 Days (67 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | AD | - | 901130028 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | AD | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
AMCAB | AD | - | 901129053 | CLO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
FM | AD | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - AGHADA T2014 [ESB GWM AT4]
TO-20-AD-T2014-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-AD-T2014-02 ISO week: 32we - 32th Date: 05 Aug - 06 Aug Duration: 2 Days (2 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7UT92
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | AD | - |  | DO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T101 [ESB GWM AA1]
TO-20-AA GIS-T101-01 ISO week: 25tu Date: 16 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 0 |  | Total Maintenance Outage Duration Requested
OPT | AA | - | 901050256 | DO | 1 | 4 | 110KV MO Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T103 [ESB GWM AA3]
TO-20-AA GIS-T103-01 ISO week: 17mo Date: 20 Apr Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| AA |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | AA | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T104 [ESB GWM AA4]
TO-20-AA GIS-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 38 |  | Outage of transformer to faciliatet trafo replacement (IPP request)
110kV FEEDER - ATHEA DROMADA
TO-20-ATE-DRO-1-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATE | - | 901043693 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - ATHEA KNOCKANURE
TO-20-ATE-KNR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | ATE | - | 901042193 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | ATE | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | KNR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | KNR | - | 901043731 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - ATHEA T121 [Athea AH1]
TO-20-ATE-T121-01 ISO week: 35mo - 35th Date: 24 Aug - 27 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | ATE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | ATE | 110 | 901043038 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - AUGHINISH SEALROCK 3
TO-20-AUG-SK-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | AUG |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-AUG-SK-3-02 Status: Unscheduled
OPT | AUG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-AUG-SK-3-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - | 901129109 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - AUGHINISH SEALROCK 4
TO-20-AUG-SK-4-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-SK-4-02 Status: Unscheduled
Outage start @ 06:00 09 Nov 2020, Outage end @ 18:00 12 Nov 2020
Customer outage request
TO-20-AUG-SK-4-01 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALLYNAHULLA CORDAL
TO-20-BYH-CDL-1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901128997 | DO | 3 | 3 | Insp. 110kV Feeder XLPE Cable
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CDL |  | 901129678 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALLYWATER CRANE [Ballywater BW1]
TO-20-BWR-CRA-1-01 ISO week: 23tu Date: 02 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CRA |  | 901129684 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - BOGGERAGH 110SA1
TO-20-BGH-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
SECTIONALISING DISCONNECT - BOGGERAGH 110SA2
TO-20-BGH-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA2-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BGH | 110-SA2 | 901130115 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - BOGGERAGH CLASHAVOON
TO-20-BGH-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-CLA-1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - | 901129114 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | CLA |  | 900989872 | CLO | 2 | 1 | O1- Hotspot Boggeragh CT T Phase.
CORRECT | CLA |  | 900973236 | CLO |  | 1 | O1-Main ON sign in c.b. chassis is very
GENERATOR TRANSFORMER - BOGGERAGH T121 [Boggeragh BG1]
TO-20-BGH-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T121-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
GENERATOR TRANSFORMER - BOGGERAGH T132 [Boggeragh BG2]
TO-20-BGH-T132-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T132-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
GENERATOR TRANSFORMER - BOOLTIAGH T121 [Booltiagh BT1/BT2]
TO-20-BOL-T121-01 ISO week: 30mo - 30th Date: 20 Jul - 23 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BOL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - CARRIGADROHID T103 [ESB GWM LE3]
TO-20-CD-T103-01 ISO week: 25tu - 26tu Date: 16 Jun - 23 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CD |  | 901129579 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
110kV FEEDER - CASTLEDOCKRELL LODGEWOOD [Castledockrell CK1]
TO-20-CDK-LWD-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-CDK-LWD-1-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
OS | LWD | - | 901129863 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | LWD | - | 901129181 | CLO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CATHALEENS FALL CLIFF
TO-20-CF-CL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
GENERATOR TRANSFORMER - CATHALEENS FALL T103 [ESB GWM ER3]
TO-20-CF-T103-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Extra work day for IPP works on
OS | CF | - | 901129790 | CLO | 4 | 4 | 110KV SF6 Cubicle Ordinary Service
SECTIONALISING DISCONNECT - CAUTEEN 110SA1
TO-20-CTN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CTN-110SA2: 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CAUTEEN 110SA2
TO-20-CTN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
OPT | CTN | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - CLAHANE T122 [Clahane CJ1]
TO-20-CLH-T122-01 ISO week: 21tu Date: 19 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer work
GENERATOR TRANSFORMER - CLIFF T101 [ESB GWM ER1]
TO-20-CL-T101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CL |  | 901129648 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLIFF T102 [ESB GWM ER2]
TO-20-CL-T102-01 ISO week: 35tu Date: 25 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
OPT | CL |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA1
TO-20-CBA-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA1-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA1 | 900938714 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CLOGHBOOLA 110SA2
TO-20-CBA-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | 110-SA2 |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-110SA2-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | SA2 |  | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLOGHBOOLA T131 [Cloghboola CL1]
TO-20-CBA-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CBA-TRI-1: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TO-20-CBA-T131-02 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
OPT | CBA | 110 | 901068541 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHBOOLA TRIEN
TO-20-CBA-TRI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
TO-20-CBA-TRI-1-01 ISO week: 26mo - 26tu Date: 22 Jun - 23 Jun Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CBA | - | 901043718 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRI | - | 901050357 | CLO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHER MULREAVY
TO-20-CLO-MRY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - CLONKEEN COOMAGEARLAHY
TO-20-CKN-CGL-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129698 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CKN |  | 901129658 | CLO | 3 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - COOLNANOONAGH KILPADDOGE
TO-20-CNO-KPG-1-01 ISO week: 44we - 45mo Date: 28 Oct - 02 Nov Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage to facilitate customer's work
GENERATOR TRANSFORMER - COOLNANOONAGH T131
TO-20-CNO-T131-01 ISO week: 36mo Date: 31 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Black start testing
TO-20-CNO-T131-02 ISO week: 47fr - 48tu Date: 20 Nov - 24 Nov Duration: 5 Days (3 WD) Status: Tentative
Outage to facilitate customer's work
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA1
TO-20-CGL-110SA1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | CGL | - | 900801826 | DO | 2 | 2 | O2.Sectionaliser not working from Mimic.
SECTIONALISING DISCONNECT - COOMAGEARLAHY 110SA2
TO-20-CGL-110SA2-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Prox for SA1
110kV FEEDER - COOMAGEARLAHY GLANLEE
TO-20-CGL-GAE-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129700 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T121 [Coomagearlahy CG3]
TO-20-CGL-T121-01 ISO week: 29mo - 29th Date: 13 Jul - 16 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129701 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - COOMAGEARLAHY T122 [Coomagearlahy CG1/CG2]
TO-20-CGL-T122-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CGL |  | 901129699 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - CORDAL 110SA1
TO-20-CDL-110SA1-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA1 | 901130105 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - CORDAL 110SA2
TO-20-CDL-110SA2-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDL | 110-SA2 | 901146308 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - CORDAL T132
TO-20-CDL-T132-01 ISO week: 33tu - 33fr Date: 11 Aug - 14 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | CDL |  | 901074069 | DO | 2 | 1 | Replair replace bonding leads (damaged)
OPT | CDL |  | 901118391 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDERRY GARVAGH
TO-20-CDY-GRV-1-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRAN | - | Line | 900985802 | NS | 1 | 4 | 2018HP-1[Am11]Bird Nests
| CDY | - | 901129384 | CLO | 5 | 1 | Leak detection on CB & repair if required
OPT | CDY |  | 901129706 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - CORDUFF HUNTSTOWN
TO-20-CDU-HN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 5 | 4 | Cable Insp. 220kV Feeder XLPE
GENERATOR TRANSFORMER - CUNGHILL T121 [Kingsmountain KGM/KG2]
TO-20-CUN-T121-01 ISO week: 25tu - 25we Date: 16 Jun - 17 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
110kV FEEDER - CUSHALING MOUNTLUCAS
TO-20-CUS-MLC-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MLC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUSHALING T101 [Edenderry Power ED1]
TO-20-CUS-T101-01 ISO week: 28tu Date: 07 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CUSHALING T103/5 [Edenderry Power ED3/ED5]
TO-20-CUS-T103/5-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CUS | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - DERRYIRON RHODE T1/T2 [SSE Generation RP1/RP2]
TO-20-DER-T1/T2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
|  |  | PROT |  |  |  | P2 Protection maintenance of 7SA513
OPT | DER |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - DROMADA T121 [Dromada DR1]
TO-20-DRO-T121-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | DRO | - | 901038511 | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - DRUMKEEN MEENTYCAT
TO-20-DRM-MEE-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
OS | DRM | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ENNIS SLIEVECALLAN
TO-20-ENN-SLC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | ENN | - | 901134782 | CLO | 2 | 1 | S Phase Slievecallan 110kv Cubicle. S phase se connectio hotspot n DUE : IMMEDIATELY
AMCAB | ENN | - | 901076133 | NS | 0 | 4 | Cable Insp. 110kV XLPE
TO-20-ENN-SLC-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CM | SLC | - | 901134796 | CLO | 2 | 1 | S Phase Ennis 110kv Cubicle. S Phase cable end bushing connectio hotspot DUE : 17-Jul-20 hotspot
CM | SLC | 110-DL/DE | 901134797 | CLO | 2 | 1 | R & S Phases Ennis 110kV cubicle. R & S Phase DL/DE DUE : 17-Aug-20hotspot
220kV FEEDER - FINGLAS HUNTSTOWN
TO-20-FIN-HN-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN | - | 900479248 | CANC | 3 | 2 | HUNTSTOWN 220KV DL PI IN EIRGRID WHEN DL
TO-20-FIN-HN-1-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | FIN |  | 901076401 | DO | 3 | 1 | Replace CB counter/ complete CA on VT's & SA's
CM | HUN | 220-DL | 901128554 | DO | 2 | 1 | T Phase Hotspot on T phase DL/DE disconnect DUE : 17-Jul-20
GENERATOR TRANSFORMER - GARROW T122 [Coomacheo CZ1]
TO-20-GRO-T122-01 ISO week: 26tu - 26we Date: 23 Jun - 24 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GRO |  | 901129713 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - GLANAGOW T2001 [Bord Gáis WG1]
TO-20-GGO-T2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-GGO-T2001-02 ISO week: 35we Date: 26 Aug Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | GGO | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | GGO |  | 900951244 | DO |  | 2 | O1- T2001 Protection Maintenance
GENERATOR TRANSFORMER - GLANLEE T121 [Glanlee GL1]
TO-20-GAE-T121-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | GAE | - | 900973585 | DO | 1 | 2 | AC and DC Supplies:
OPT | GAE |  | 901129611 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GLENLARA KNOCKACUMMER [Mountain Lodge ML1]
TO-20-GLE-KCR-1-01 ISO week: 34mo - 34fr Date: 17 Aug - 21 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 5 | 4 | Cable Insp. 110kV XLPE
OPT | GLE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KCR | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - GREAT ISLAND GIS T2004 [SSE Generation Ireland GI4]
TO-20-GI GIS-T2004-01 ISO week: 40th - 41fr Date: 01 Oct - 09 Oct Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage request for Telemess 01/10-09/10
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
GENERATOR TRANSFORMER - HUNTSTOWN T2002 [Viridian Power HN2]
TO-20-HN-T2002-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | HUN | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TO-20-HN-T2002-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Tentative
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
GENERATOR TRANSFORMER - HUNTSTOWN T2010/11 [Viridian Power HNC]
TO-20-HN-T2010/11-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | HUN |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - IKERRIN tee SHANNONBRIDGE
TO-20-IKE,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee THURLES
TO-20-IKE,T-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-IKE,T-THU-1-01 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | THU |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
TO-20-IKE,T-THU-1-03 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
GENERATOR TRANSFORMER - INNISCARRA T101 [ESB GWM LE1/LE2]
TO-20-IA-T101-01 ISO week: 21mo Date: 18 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | IA |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - KILL HILL T131 [Kill Hill KH1]
TO-20-KHL-T131-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - KNOCKRANNY UGGOOL
TO-20-KNY-UGL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - LANESBORO T104 [ESB GWM LR4]
TO-20-LA-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
SECTIONALISING DISCONNECT - LISHEEN 110SA2-4
TO-20-LSN-110SA2-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
GENERATOR TRANSFORMER - LISHEEN T122 [Lisheen LS1/LS2]
TO-20-LSN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-T122-01 ISO week: 28mo - 28tu Date: 06 Jul - 07 Jul Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request for 2 WD
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LSN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LISHEEN THURLES
TO-20-LSN-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-THU-1-01 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988512 | DO | 2 | 4 | 2018HP-1[25]Bird Nestsremove asap
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
TO-20-LSN-THU-1-03 Status: Unscheduled
TRAN |  | - | 900988515 | CANC | 1 | 1 | 2018HP-1[47]Bird Nestsremove asap
SECTIONALISING DISCONNECT - LODGEWOOD 110SA1
TO-20-LWD-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LWD | - | 901042978 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-LWD-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of LWD-110SA2: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
GENERATOR TRANSFORMER - LONG POINT T2002 [ESB GWM AD2]
TO-20-LPT-T2002-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | LPT | - | 901129020 | CLO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | LPT | 220 | 901129732 | CLO | 1 | 4 | 2200kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MACROOM 110SA2
TO-20-MAC-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 25 |  | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-MAC-110SA2-03 Status: Unscheduled
15 | [6 empty] | Proximity outage (SA1)
GENERATOR TRANSFORMER - MEENTYCAT T121 [Meentycat MCT]
TO-20-MEE-T121-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of work on Drumkeen-Meentycat 110 kV
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MEE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110SA1-2CB
TO-20-MP GIS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | - |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T121 [Moneypoint MP9]
TO-20-MP GIS-T121-01 ISO week: 30fr Date: 24 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | TRAFO | 900938612 | DO | 1 | 3 | 110KV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T4003 [ESB GWM MP3]
TO-20-MP GIS-T4003-01 ISO week: 24we - 25we Date: 10 Jun - 17 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 | 2 | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
GENERATOR TRANSFORMER - MONEYPOINT T4001 [ESB GWM MP1]
TO-20-MP-T4001-01 ISO week: 48tu - 48th Date: 24 Nov - 26 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| MON | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | MP |  |  | DO | 2 | 1 | 400kV GIS Cubicle Operational Test
AMCAB | MP | - | 901005716 | DO | 2 | 4 | Insp. 400 & 220 Station XLPE Cable
FM | MP | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - MOUNTLUCAS T121 [Mountlucas MO1]
TO-20-MLC-T121-01 ISO week: 24we Date: 10 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLC | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - MULREAVY T131 [Mulreavy MB1/MB2]
TO-20-MRY-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | MRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - NORTH WALL T2004/5 [ESB GWM NW5]
TO-20-NW-T2004/5-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA1
TO-20-PA-110SA1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA2
TO-20-PA-110SA2-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
GENERATOR TRANSFORMER - POLLAPHUCA T101 [ESB GWM LI1/LI2/LI4]
TO-20-PA-T101-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
As a consequence of works on Stratford tee Pollaphuca
CORRECT | PA |  | 901079398 | DO | 2 | 2 | Check the bellows of the current transfo
CORRECT | PA |  | 901079400 | DO | 2 | 2 | Change the oil in the circuit breaker
CORRECT | PA |  | 901087470 | DO | 1 | 2 | EMP AMS: Replace CB Counter
GENERATOR TRANSFORMER - RATRUSSAN T121 [Bindoo BD1]
TO-20-RRU-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
GENERATOR TRANSFORMER - RATRUSSAN T122 [Mountain Lodge ML1]
TO-20-RRU-T122-01 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
CORRECT | RRU |  | 900990024 | CLO | 3 | 1 | Re-Test - Condition Assessment of the Cu
OPT | RRU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-RRU-T122-02 ISO week: 40tu - 40th Date: 29 Sep - 01 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 3 |  | Customer outage request
SECTIONALISING DISCONNECT - REAMORE 110SA1
TO-20-REM-110SA1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
SECTIONALISING DISCONNECT - REAMORE 110SA2
TO-20-REM-110SA2-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
110kV FEEDER - REAMORE TRALEE
TO-20-REM-TRL-1-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | REM |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TRL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - SEALROCK T103 [Aughinish Alumina SK3]
TO-20-SK-T103-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-3: 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-SK-T103-03 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequence of AUG-SK-3: 110 kV A1 @ AUG
TO-20-SK-T103-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CM |  |  | 901137683 | DO | 5 | 1 | Gas Leak Repar S Phase
AMCAB | SK | 110 | 901129121 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - SEALROCK T104 [Aughinish Alumina SK4]
TO-20-SK-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | 4 day customer outage
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-4: 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
AMCAB | SK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SK |  |  | DO | 2 | 4 | 110KV SF6 Cubicle Operational Test
TO-20-SK-T104-02 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of AUG-SK-4: 110 kV
Outage start @ 14:00 07 Sept 2020, Outage end @ 15:00 10 Sept 2020
Customer outage request
GENERATOR TRANSFORMER - SHANNONBRIDGE T104 [ESB GWM WO4]
TO-20-SH-T104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SH-T104-01 ISO week: 36tu - 36we Date: 01 Sep - 02 Sep Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - SHELLYBANKS T2014 [ESB GWM PB4]
TO-20-SHL-T2014-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D1/CB3
OS | SHL | 220-DT |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
AMCAB | SHL | cable | 900838786 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
GENERATOR TRANSFORMER - SHELLYBANKS T2015 [ESB GWM PB5]
TO-20-SHL-T2015-01 ISO week: 24mo - 24th Date: 08 Jun - 11 Jun Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB2
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV D2/CB3
AMCAB | SHL | - | 901129026 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130137 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
GENERATOR TRANSFORMER - SHELLYBANKS T2016 [ESB GWM PB6]
TO-20-SHL-T2016-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
AMCAB | SHL | 220 | 901129027 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130138 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-SHL-T2016-02 ISO week: 23mo - 23th Date: 01 Jun - 04 Jun Duration: 4 Days (3 WD) Status: Scheduled
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
| SHL |  |  |  | 4 |  | Resolve DL S6 Leak
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA1
TO-20-SKY-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-110SA1-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
SECTIONALISING DISCONNECT - SRAHNAKILLY 110SA2
TO-20-SKY-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
GENERATOR TRANSFORMER - SRAHNAKILLY T131 [Srahnakilly OY1]
TO-20-SKY-T131-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of Bellacorick - Srahnakilly
TO-20-SKY-T131-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | As a consequence of Bellacorrick - Srahnakilly
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SKY | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - STRATFORD tee CARLOW
TO-20-STR,T-CLW-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086426 | DO | 2 | 1 | 2019HP-1[110]Replace Pole only -Rot
FO_MISC |  | - | 900864816 | DO | 1 | 2 | 2016CP-1[109]Off Plumb Pole & insulators
FO_STDMG |  | - | 900864817 | DO | 1 | 2 | 2016CP-1[109]Replace Pole Bolt -Bent
FO_MISC |  | - | 900864818 | DO | 1 | 2 | 2016CP-1[109]Vibration Dampers Replace
FOINSHW |  | - | 900864820 | DO | 1 | 2 | 2016CP-1[109]H-ware Susp Clamps corroded
FO_STDMG |  | - | 900864821 | DO | 1 | 2 | 2016CP-1[109]Crossarm Replacement
FOSTRHW |  | - | 900864822 | DO | 1 | 1 | 2016CP-1[110]Replace Pole only -Rotten
TRAN |  | - | 900984379 | DO | 1 | 4 | 2018HP-1[90]ACGfit ACG
TRAN |  | - | 900989809 | DO | 1 | 4 | 2018HP-1[94]Check Structure-top rot - Ch
FOSTRHW |  |  | 901086400 | DO | 1 | 4 | 2019HP-1[124]Check Structure -Check Rot
OPT | CLW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - STRATFORD tee POLLAPHUCA
TO-20-STR,T-PA-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 900864747 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
FO_STDMG |  | - | 900898188 | CLO | 2 | 3 | 2017HP-1[14]Crossarm Replacement Replace
FO_MISC |  | - | 900864747 | CLO | 1 | 2 | 2016CP-1[13]Off Plumb Poles
FOSTRHW |  | - | 900973774 | CANC | 1 | 1 | 1[33]Replace Rotten Pole
FO_MISC |  | - | 900975368 | CLO | 1 | 1 | 1[53]Install ACG on mast no. 53
TRAN |  | - | 900989394 | DO | 1 | 4 | 2018HP-1[15]Off Plumb-Poles
OS | PA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | PA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - TARBERT T101 [SSE Generation Ireland TB1]
TO-20-TB-T101-01 ISO week: 15mo - 15tu Date: 06 Apr - 07 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T102 [SSE Generation Ireland TB2]
TO-20-TB-T102-01 ISO week: 14th - 14fr Date: 02 Apr - 03 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
AMCAB | TB | - |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
GENERATOR TRANSFORMER - TARBERT T2003 [SSE Generation Ireland TB3]
TO-20-TB-T2003-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | TB |  | 901129535 | CLO | 2 | 4 | 220kV MO Cubicle Operational Test
GENERATOR TRANSFORMER - TARBERT T2004 [SSE Generation Ireland TB4]
TO-20-TB-T2004-01 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of R1Z23b, S Type Overcurrent
GENERATOR TRANSFORMER - TAWNAGHMORE T1/T2 [SSE Generation Ireland TP1]
TO-20-TAW-T1/T2-01 ISO week: 33mo - 33we Date: 10 Aug - 12 Aug Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - TAWNAGHMORE T3 [SSE Generation Ireland TP3]
TO-20-TAW-T3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | TAW | 110 | 901043728 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - TURLOUGH HILL T2001/2 [ESB GWM TH1/TH2]
TO-20-TH-T2001/2-01 ISO week: 29mo - 29tu Date: 13 Jul - 14 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 | 2 | Total Maintenance Outage Duration Requested
AMCAB | TH | - | 901005766 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
GENERATOR TRANSFORMER - TURLOUGH HILL T2003/4 [ESB GWM TH3/TH4]
TO-20-TH-T2003/4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | TH | 220 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TO-20-TH-T2003/4-03 ISO week: 39fr Date: 25 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | Black Start Test
TO-20-TH-T2003/4-01 ISO week: 27mo - 27tu Date: 29 Jun - 30 Jun Duration: 2 Days (2 WD) Status: Scheduled
AMCAB | TH | - | 901005768 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
GENERATOR TRANSFORMER - TYNAGH T2001/2 [Tynagh Energy TYC]
TO-20-TY-T2001/2-01 ISO week: 14mo - 14tu Date: 30 Mar - 31 Mar Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
CORRECT | TYN |  | 900990025 | CLO | 2 | 1 | Hot spot detected on T 2001/2 220kV R phase DA
OPT | TYN |  | 901129555 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - UGGOOL 110SA1-2CB
TO-20-UGL-110SA1-2CB-01 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110-SA1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - UGGOOL T131 [Uggool]
TO-20-UGL-T131-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T131-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T132 [Seecon]
TO-20-UGL-T132-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T132-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T134 [Seecon]
TO-20-UGL-T134-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | - | 900942781 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-UGL-T134-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - WOODHOUSE T122 [Woodhouse WS1]
TO-20-WOH-T122-02 ISO week: 41we Date: 07 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer works
TO-20-WOH-T122-01 ISO week: 26mo - 26fr Date: 22 Jun - 26 Jun Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Oil leak on grid transformer
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | WOO |  | 901129682 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test

## OUTTURN - DSO (Rgn)
110kV FEEDER - BALLYLICKEY DUNMANWAY [SDCC]
TO-20-BLI-DMY-1-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-DMY-1-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - CARLOW T141 [SDCC]
TO-20-CLW-T141-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | CLW |  |  |  | 4 |  | Proximity for Carlow Kellis 1 110 kV
DISTRIBUTION TRANSFORMER - CAUTEEN T142 [SDCC]
TO-20-CTN-T142-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-T142-01 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
DISTRIBUTION TRANSFORMER - CAUTEEN T144 [SDCC]
TO-20-CTN-T144-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - CORDAL T141 [SDCC]
TO-20-CDL-T141-01 ISO week: 33tu - 33th Date: 11 Aug - 13 Aug Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Ballynahulla-Cordal 110 kV circuit
110kV FEEDER - CRORY LODGEWOOD [SDCC]
TO-20-CRY-LWD-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA611, 7SJ804
OS | LWD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - DRYBRIDGE T141 [NDCC]
TO-20-DRY-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - GLENREE T142 [NDCC]
TO-20-GLR-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - IKERRIN T141 [SDCC]
TO-20-IKE-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 2 |  | As a consequence of IKE,T-IKE-1: IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee IKERRIN
TO-20-IKE,T-IKE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-IKE-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - LETTERKENNY TRILLICK [NDCC]
TO-20-LET-TLK-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - LISHEEN T142 [SDCC]
TO-20-LSN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - MACROOM T142 [SDCC]
TO-20-MAC-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
DISTRIBUTION TRANSFORMER - REAMORE T142 [SDCC]
TO-20-REM-T142-02 ISO week: 45tu - 45we Date: 03 Nov - 04 Nov Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of Reamore Tralee 110kV Circuit
DISTRIBUTION TRANSFORMER - THURLES T142 [SDCC]
TO-20-THU-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - TRIEN T143 [SDCC]
TO-20-TRI-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A1 @ TRI: Proximity outage for work on Trien 110kV SA1-2 Coupler/Sectionalising CB (SA1)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of TRI-110SA1-3CB: 110 kV A3 @ TRI: Proximity outage for work on Trien 110kV SA1-3 Coupler/Sectionalising CB (SA3)
DISTRIBUTION TRANSFORMER - WATERFORD T141 [SDCC]
TO-20-WAT-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - WEXFORD T142 [SDCC]
TO-20-WEX-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment

## NDCC (Rgn)
SECTIONALISING DISCONNECT - BELLACORICK 110SA1
TO-20-BK-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA2: 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-110SA1-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA1 | 900942127 | DO | 1 | 2 | 110kV Sect / Dist Operational Test
SECTIONALISING DISCONNECT - BELLACORICK 110SA2
TO-20-BK-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BK | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-BK-110SA2-02 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Proposed
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BK-110SA1: 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BELLACORICK T122 [NDCC]
TO-20-BK-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0850 |  | 3 |  | Bay Outage for BZP
TO-20-BK-T122-02 Status: Reference (Unscheduled)
PROX |  |  | PR0002 | DO | 1 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - BELLACORICK T141 [NDCC]
TO-20-BK-T141-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - BINBANE 110SA1
TO-20-BIN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | As a consequence of BIN-110SA2: Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
SECTIONALISING DISCONNECT - BINBANE 110SA2
TO-20-BIN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T141 [NDCC]
TO-20-BIN-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T142 [NDCC]
TO-20-BIN-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T142-01 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
TO-20-BIN-T142-05 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
TO-20-BIN-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
TO-20-BIN-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
TO-20-BIN-T142-04 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T143 [NDCC]
TO-20-BIN-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T143-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BLAKE T142 [NDCC]
TO-20-BLK-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
110kV FEEDER - BLAKE tee BLAKE
TO-20-BLK,T-BLK-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | As a consequence: Break jumpers for maintenance on Blake Tee Maynooth
TO-20-BLK,T-BLK-1-01 Status: Unscheduled
[5 empty] | 5 |  | As a conequence of maintenance at Blake Tee Newbridge & Blake Tee Maynooth
COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110SA1-2CB
TO-20-COS-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
TO-20-COS-110SA1-2CB-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | COS | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TRANSFORMER - CARRICKMINES T2102 [NDCC]
TO-20-CKM-T2102-01 ISO week: 31we Date: 29 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
COUPLER/SECTIONALISING CB - COLLEGE PARK 110SA1-2CB
TO-20-COL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS_LO | COL | 110-DEA1(Q13) | 900744240 | DO | 3 | 3 | 110kV Sect / Dist Ordinary Service
OPT | COL | - | 900839239 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
OPT_LO | COL | 110-SA1/DEM1 | 900859195 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT_LO | COL | 110-SA2/DEM2 | 900859196 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | COL | 110-DEA2(Q14) | 900859226 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-COL-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - COLLEGE PARK T101 [NDCC]
TO-20-COL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - COLLEGE PARK T103 [NDCC]
TO-20-COL-T103-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - CORDERRY 110SA1
TO-20-CDY-110SA1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA1-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | As a consequence of CDY-110SA2: 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
SECTIONALISING DISCONNECT - CORDERRY 110SA2
TO-20-CDY-110SA2-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-110SA2-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
DISTRIBUTION TRANSFORMER - CORDERRY T122 [NDCC]
TO-20-CDY-T122-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Remove BB dropper
TO-20-CDY-T122-02 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP0942 | DO | 2 |  | 110 kV A2 @ CDY: Uprate Bay Conductor in Corderry station & connect BB dropper
110kV FEEDER - DERRYIRON THORNSBERRY
TO-20-DER-TSB-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DER-TSB-1-01 Status: Unscheduled
PROT |  |  |  | DO |  |  | P3 Protection maintenance of REL521
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
| - | 110 |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | DER | - | 900775276 | DO | 4 | 1 | 110kV SF6 Cubicle Ordinary Service
CA | DER | - | 900775914 | DO | 3 | 1 | 110KV CUBICLE CONDITION ASSESSMENT
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA1
TO-20-DRY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
OS | DRY | SA1 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-DRY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA2
TO-20-DRY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of DRY-110SA1: 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DRYBRIDGE T141 [NDCC]
TO-20-DRY-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DUNFIRTH T122 [NDCC]
TO-20-DFR-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR-T122-02 Status: Reference (Unscheduled)
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee DUNFIRTH
TO-20-DFR,T-DFR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR,T-DFR-1-02 Status: Unscheduled
[5 empty] | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
BUSBAR SECTION - FINGLAS 110 kV A1
TO-20-110 kV A1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A2
TO-20-110 kV A2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A3
TO-20-110 kV A3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B1
TO-20-110 kV B1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B2
TO-20-110 kV B2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B3
TO-20-110 kV B3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
110kV FEEDER - FINGLAS GIS GLASMORE [NDCC]
TO-20-FIN GIS-GLA-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | FIN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GARVAGH T141 [SDCC]
TO-20-GRV-T141-01 ISO week: 29mo - 29we Date: 13 Jul - 15 Jul Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Corderry-Garvagh 110 kV
DISTRIBUTION TRANSFORMER - GLENREE T142 [NDCC]
TO-20-GLR-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GLR: Proximity outage for work on Glenree 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
SECTIONALISING DISCONNECT - GORTAWEE 110SA1
TO-20-GWE-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA2: 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-110SA1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
OS | GWE | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CORRECT | GWE |  | 900788599 | DO | 3 | 1 | Replace disconnect spindles
SECTIONALISING DISCONNECT - GORTAWEE 110SA2
TO-20-GWE-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
OS | GWE | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-GWE-110SA2-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA1: 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - GORTAWEE T142 [NDCC]
TO-20-GWE-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GRIFFINRATH T141 [NDCC]
TO-20-GRI-T141-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of GRI,T-GRI-1: GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI-T141-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Reference (Tentative)
Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
110kV FEEDER - GRIFFINRATH tee GRIFFINRATH
TO-20-GRI,T-GRI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-GRI-1-02 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
as a consequence of: Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
TRANSFORMER - INCHICORE T2102 [NDCC]
TO-20-INC-T2102-01 ISO week: 31fr Date: 31 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA511, R1Z23b, ISM21
TRANSFORMER - INCHICORE T2104 [NDCC]
TO-20-INC-T2104-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, 7SA511, 7UT512
TRANSFORMER - INCHICORE T2106 [NDCC]
TO-20-INC-T2106-01 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| INC |  |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | INC | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CORRECT | INC |  | 901084736 | DO | 3 | 1 | Low Gas / Leak- REPAIR SF6 LEAK
TO-20-INC-T2106-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
COUPLER/SECTIONALISING CB - KINNEGAD 110SA1-2CB
TO-20-KIN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | KIN | - | 901042251 | DO | 2 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KIN | 110-SA1 | 901042964 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-KIN-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | KIN | 110-SA2 | 901042963 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - LANESBORO RICHMOND 1 [NDCC]
TO-20-LA-RIC-1-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
110kV FEEDER - LANESBORO RICHMOND 2 [NDCC]
TO-20-LA-RIC-2-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - LANESBORO T141 [NDCC]
TO-20-LA-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - LETTERKENNY T141 [NDCC]
TO-20-LET-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 40 |  | Facilitate the demolition of existing CT/VT supports and installation of new CT/VT and associated steelwork on T141 Bay
TO-20-LET-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
110kV FEEDER - LETTERKENNY TRILLICK [NDCC]
TO-20-LET-TLK-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | Proximity outage to install new lightning monopole
SECTIONALISING DISCONNECT - LISDRUM 110SA1
TO-20-LIS-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
OS | LIS | SA1 | 901039705 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-LIS-110SA1-02 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 1 |  | As a consequence of LIS-110SA2: 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
SECTIONALISING DISCONNECT - LISDRUM 110SA2
TO-20-LIS-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of LIS-110SA1: 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
TO-20-LIS-110SA2-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
DISTRIBUTION TRANSFORMER - LISDRUM T141 [NDCC]
TO-20-LIS-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - LISDRUM T142 [NDCC]
TO-20-LIS-T142-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
SECTIONALISING DISCONNECT - MACETOWN 110SA2
TO-20-MCE-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | MCE | SA2 | 901039707 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
COUPLER/SECTIONALISING CB - MULLINGAR 110SA1-2CB
TO-20-MUL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-MUL-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MUL | - | 901129883 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | MUL | SA1 | 901039452 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MUL-110SA1-2CB-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
DISTRIBUTION TRANSFORMER - MULLINGAR T101 [NDCC]
TO-20-MUL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - MULLINGAR T102 [NDCC]
TO-20-MUL-T102-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
DISTRIBUTION TRANSFORMER - MULLINGAR T142 [NDCC]
TO-20-MUL-T142-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
COUPLER/SECTIONALISING CB - NAVAN 110SA1-2CB
TO-20-NAV-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | NAV | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-NAV-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA1
TO-20-NEW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA1 | 901039710 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA2: 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - NEWBRIDGE 110SA2
TO-20-NEW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | NEW | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-NEW-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of NEW-110SA1: 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - NEWBRIDGE T141 [NDCC]
TO-20-NEW-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - NEWBRIDGE T142 [NDCC]
TO-20-NEW-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - SHANKILL 110SA1
TO-20-SKL-110SA1-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
DISTRIBUTION TRANSFORMER - SHANKILL T141 [NDCC]
TO-20-SKL-T141-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
COUPLER/SECTIONALISING CB - SLIGO 110SA1-2CB
TO-20-SLI-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SLI | - | 901080653 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - SORNE HILL T122 [NDCC]
TO-20-SOR-T122-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - SORNE HILL T124 [NDCC]
TO-20-SOR-T124-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
110kV FEEDER - SORNE HILL TRILLICK [NDCC]
TO-20-SOR-TLK-1-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - THORNSBERRY T141 [NDCC]
TO-20-TSB-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - THORNSBERRY T142 [NDCC]
TO-20-TSB-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - TRILLICK T141 [NDCC]
TO-20-TLK-T141-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - TRILLICK T142 [NDCC]
TO-20-TLK-T142-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole

## LIMERICK (Rgn)
110kV FEEDER - AGANNYGAL ENNIS
TO-20-AGL-ENN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | ENN | - | 901129481 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-AGL-ENN-1-01 ISO week: 25mo - 25fr Date: 15 Jun - 19 Jun Duration: 5 Days (5 WD) Status: Scheduled
TRAN |  | - | 900982973 | DO | 1 | 4 | 2018HP-1[124]Off PlumbPlumb insulators
OS | AGL | - | 901129954 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AHANE KILLONAN 2 [SDCC]
TO-20-AHA-KLN-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA513
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV A3
TO-20-110 kV A3 @ AA GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | Energisation of T104 from Drumline
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV B1
TO-20-110 kV B1 @ AA GIS-02 ISO week: 33we Date: 12 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PROX |  | 1 |  | Proximity for T103 black start
BUSBAR SECTION - ARDNACRUSHA GIS 110 kV B3
TO-20-110 kV B3 @ AA GIS-02 ISO week: 33we Date: 12 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 1 |  | Proximity for T103 black start
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110K3
TO-20-AA GIS-110K3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | AA | - | 901076456 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
TO-20-AA GIS-110K3-01 Status: Unscheduled
CAPX |  |  | CP1065 | DO | 2 |  | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline
TO-20-AA GIS-110K3-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SA1-3CB
TO-20-AA GIS-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | As a consequence of 110 kV A3 @ AA GIS: Energisation of T104 from Drumline
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SB1-2CB
TO-20-AA GIS-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ AA GIS: 110 kV A2/B2 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover
TO-20-AA GIS-110SB1-2CB-02 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | AA |  | 901053225 | DO | 4 | 1 | OEM Fault Investigation / Repair on SB2.
COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110SB1-3CB
TO-20-AA GIS-110SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B3 @ AA GIS: 110 kV A3/B3 IN TURN @ AA GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ AA GIS: 110 kV A1/B1 IN TURN @ AA GIS: Busbar Changeover
110kV FEEDER - ARDNACRUSHA GIS DRUMLINE
TO-20-AA GIS-DRU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 2 |  | Energisation of T104 from Drumline
TO-20-AA GIS-DRU-1-02 ISO week: 45tu - 45fr Date: 03 Nov - 06 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | DRU | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARDNACRUSHA GIS ENNIS
TO-20-AA GIS-ENN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | CANC |  |  | Total Maintenance Outage Duration Requested
TO-20-AA GIS-ENN-1-03 ISO week: 46tu Date: 10 Nov Duration: 1 Day (1 WD) Status: Scheduled
operator training
TO-20-AA GIS-ENN-1-01 ISO week: 11mo - 11fr Date: 09 Mar - 13 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900725270 | DO | 1 | 1 | 2015CP-1[132]Off Plumb Poles
FO_MISC |  | - | 900725277 | DO | 1 | 1 | 2015CP-1[149]Off Plumb Poles
OPT | AA | - | 901045735 | CLO | 2 | 4 | 110kV GIS Cubicle Operational Test
AMCAB | AA | - | 901129157 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
OS | ENN | - | 901129840 | CLO | 4 | 4 | 110kV MO Cubicle Ordinary Service
110kV FEEDER - ARDNACRUSHA GIS LIMERICK
TO-20-AA GIS-LIM-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-AA GIS-LIM-1-01 Status: Unscheduled
FO_MISC |  | - | 900816798 | CANC | 1 | 2 | 2016CP-1[32]Off Plumb Poles leaning
FO_MISC |  | - | 900816810 | CANC | 1 | 2 | 2016CP-1[72]Off Plumb Insulators
OPT | LIM |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARDNACRUSHA GIS SINGLAND
TO-20-AA GIS-SNG-1-01 ISO week: 30mo - 30th Date: 20 Jul - 23 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | AA | - | 901018827 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
TO-20-AA GIS-SNG-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Proposed
DSO request for CA on SNG T102
OPT | SNG | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T101 [ESB GWM AA1]
TO-20-AA GIS-T101-01 ISO week: 25tu Date: 16 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 0 |  | Total Maintenance Outage Duration Requested
OPT | AA | - | 901050256 | DO | 1 | 4 | 110KV MO Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T103 [ESB GWM AA3]
TO-20-AA GIS-T103-01 ISO week: 17mo Date: 20 Apr Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| AA |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | AA | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - ARDNACRUSHA GIS T104 [ESB GWM AA4]
TO-20-AA GIS-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1065 | DO | 38 |  | Outage of transformer to faciliatet trafo replacement (IPP request)
COUPLER/SECTIONALISING CB - AUGHINISH 110SA1-2CB
TO-20-AUG-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
OS | AUG | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-AUG-110SA1-2CB-01 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO | 1 |  | P1 Protection maintenance of ISM21
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | AUG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - AUGHINISH CASTLEFARM 1
TO-20-AUG-CFM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
OS | AUG | - | 901129898 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | AUG | - | 901129107 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-AUG-CFM-1-02 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Scheduled
1[EM 48] replacement of 110kV strain/duplicate insulator
Customer outage request
As a consequence of CFM T101
110kV FEEDER - AUGHINISH CASTLEFARM 2
TO-20-AUG-CFM-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-CFM-2-03 Status: Unscheduled
CORRECT | AUG |  | 901030139 | CANC | 1 | 2 | Assist with Relay Testing
TO-20-AUG-CFM-2-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SJ611, RADSB
901158967 | [6 empty] | Paint 110kV Tower
901158971 | [6 empty] | Replacement of Insulators
As a consequence of CFM-T102
Customer outage 14 @ CFM T102 14 Sept - 02 Oct
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AUGHINISH KILPADDOGE
TO-20-AUG-KPG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | KPG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| KPG |  |  |  | 3 |  | Outstanding issues with the AR Supervisory scheme on the bay including testing and recommissioning of the BCU and testing of new commands and PI back to NCC
TO-20-AUG-KPG-1-02 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901110437 | CLO | 2 | 1 | Hotspot 8 (DC Cable Tower No.160 Span 159/160) Lower (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110438 | CLO | 2 | 1 | Hotspot 7 (DC Cable Tower No.160 Span 159/160) Top (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110439 | CLO | 2 | 1 | Hotspot 4 (Transposition Tower No. 58 Span 57/58) Left Jumper Terminal (Repair by 24th Jul)
TRAN | - | Line | 901110456 | CLO | 2 | 1 | Hotspot 2 (Transposition Tower No. 58 Span 58/59) Centre Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110457 | CLO | 2 | 1 | Hotspot 3 (Transposition Tower No. 58 Span 58/59) Left Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110460 | CLO | 2 | 1 | Hotspot 5 (Transposition Tower No. 58 Span 57/58) Centre Jumper Terminal (Repair by 24th May)
TRAN | - | Line | 901110461 | CLO | 2 | 1 | Hotspot 6 (Transposition Tower No. 58 Span 57/58) Right Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110462 | CLO | 2 | 1 | Hotspot 1 (Transposition Tower No. 58 Span 58/59) Right Jumper Terminal (Repair by 24th Oct)
110kV FEEDER - AUGHINISH MONETEEN
TO-20-AUG-MTN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
FO_MISC |  |  | 901084931 | DO | 1 | 4 | 2019HP-1[19]Off Plumb -plumb poles
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MTN |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - AUGHINISH SEALROCK 3
TO-20-AUG-SK-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | AUG |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-AUG-SK-3-02 Status: Unscheduled
OPT | AUG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-AUG-SK-3-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - | 901129109 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - AUGHINISH SEALROCK 4
TO-20-AUG-SK-4-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-SK-4-02 Status: Unscheduled
Outage start @ 06:00 09 Nov 2020, Outage end @ 18:00 12 Nov 2020
Customer outage request
TO-20-AUG-SK-4-01 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | AUG | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BOOLTIAGH ENNIS
TO-20-BOL-ENN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OPT | BOL |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OS | ENN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - BOOLTIAGH T121 [Booltiagh BT1/BT2]
TO-20-BOL-T121-01 ISO week: 30mo - 30th Date: 20 Jul - 23 Jul Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BOL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CAHIR KILL HILL
TO-20-CAH-KHL-1-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084942 | DO | 2 | 4 | 2019HP-1[47]Off Plumb -plumb poles
TRAN |  | - | 900984365 | DO | 1 | 4 | 2018HP-1[47]Off Plumb
OPT | CAH |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CAHIR TIPPERARY
TO-20-CAH-TIP-1-01 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984368 | DO | 3 | 4 | "2018HP-5[25,26,29,34,35]Off Plumb-Poles
TRAN |  | - | 900984369 | DO | 3 | 4 | "2018HP-5[36,55,84,90,91]Off Plumb-Poles
TRAN |  | - | 900984378 | DO | 1 | 4 | 2018HP-1[2]Earths-Replace-Broken
110kV FEEDER - CASHLA ENNIS
TO-20-CSH-ENN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-ENN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-CSH-ENN-1-02 ISO week: 25th - 26fr Date: 18 Jun - 26 Jun Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | CSH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | ENN | - |  | DO | 5 | 4 | 110kV MO Cubicle Ordinary Service
CA | ENN | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
220kV FEEDER - CASHLA PROSPECT
TO-20-CSH-PRO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TSO CUSTOMER TRANSFORMER - CASTLEFARM T101 [Aughinish Alumina]
TO-20-CFM-T101-01 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of AUG-CFM-1
| CFM |  |  |  | 15 |  | Customer works
TSO CUSTOMER TRANSFORMER - CASTLEFARM T102 [Aughinish Alumina]
TO-20-CFM-T102-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | As a consequence of AUG-CFM-2
| CFM |  |  |  | 15 |  | Customer works
SECTIONALISING DISCONNECT - CAUTEEN 110SA1
TO-20-CTN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CTN-110SA2: 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CAUTEEN 110SA2
TO-20-CTN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
OPT | CTN | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - CAUTEEN KILLONAN
TO-20-CTN-KLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987741 | DO | 6 | 4 | "2018HP-6[5,15,47,48,51,64]Off Plumb"
TRAN |  | - | 900987742 | DO | 5 | 4 | "2018HP-5[72,85,102,105,121]Off Plumb"
TRAN |  | - | 900987743 | DO | 4 | 4 | "2018HP-4[122,123,127,128]Off Plumb"
TRAN |  | - | 900987744 | DO | 4 | 4 | "2018HP-4[134,135,136,137]Off Plumb"
TRAN |  | - | 900987748 | DO | 1 | 4 | 2018HP-1[AT11]Bird NestsCentre phase
OPT | CTN | - | 901038731 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KLN |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - CAUTEEN T142 [SDCC]
TO-20-CTN-T142-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-T142-01 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
DISTRIBUTION TRANSFORMER - CAUTEEN T144 [SDCC]
TO-20-CTN-T144-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - CAUTEEN TIPPERARY
TO-20-CTN-TIP-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CTN: Proximity outage for work on Cauteen 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CTN-TIP-1-01 ISO week: 41tu - 42th Date: 06 Oct - 15 Oct Duration: 10 Days (8 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985386 | DO | 2 | 4 | "2018HP-2[3,19]Off PlumbPlumb poles"
FO_MISC |  |  | 901084954 | DO | 2 | 4 | 2019HP-1[3]Off Plumb -plumb poles
FO_MISC |  |  | 901084270 | DO | 1 | 4 | 2019HP-1[4]Bird Nests Over Right phase
OS | CTN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | CTN | 110-DL | 901134773 | DO | 2 | 1 | R,S & T Phases Tipperary 110kV Cubicle.R,S & T Phase Dlconnections DUE : 17-Nov-20
OS | TIP | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CHARLEVILLE GLENLARA
TO-20-CHA-GLE-1-01 ISO week: 11tu - 11fr Date: 10 Mar - 13 Mar Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 4 |  | Total Maintenance Outage Duration Requested
OS | CHA | - | 901129798 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | GLE | - | 901116384 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CHARLEVILLE KILLONAN
TO-20-CHA-KLN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0624 | DO | 60 |  | EI: Line diversion work to enable construction of GIS building
TO-20-CHA-KLN-1-01 ISO week: 46tu - 47mo Date: 10 Nov - 16 Nov Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084958 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
TRAN |  | - | 900985430 | DO | 1 | 4 | 2018HP-1[68]Bird NestsRight phase
OPT | CHA |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
CM | CHA | 110-DL/DE | 901134774 | DO | 2 | 1 | T Phase Killonan 110kV cubicle. Tphase DL/DE connection DUE : 17-Aug-20
110kV FEEDER - CHARLEVILLE MALLOW
TO-20-CHA-MAL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985441 | CLO | 4 | 4 | "2018HP-6[16,19,62,72,81,92]Off Plumb"
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084959 | CLO | 1 | 2 | 2019HP-2[61,62]Off Plumb -plumb poles
OPT | CHA | - |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MAL | - | 901076481 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - DALLOW T141 [SDCC]
TO-20-DAL-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 37 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 21 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL-T141-04 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 10 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL-T141-09 Status: Reference (Unscheduled)
CAPX |  |  | CP1057_OS | DO | 47 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL-T141-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 3 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL-T141-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL-T141-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 5 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL-T141-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Reference
CAPX |  |  | CP1057 | DO | 20 |  | As a consequence of DAL,T-DAL-1: DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee DALLOW
TO-20-DAL,T-DAL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-04 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-DAL-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-09 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL,T-DAL-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-DAL-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-DAL-1-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-DAL-1-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee SHANNONBRIDGE
TO-20-DAL,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-SH-1-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-DAL,T-SH-1-11 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
TO-20-DAL,T-SH-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-SH-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-SH-1-04 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-SH-1-12 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
TO-20-DAL,T-SH-1-03 ISO week: 34mo - 38mo Date: 17 Aug - 14 Sep Duration: 29 Days (21 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-SH-1-06 ISO week: 41we - 48fr Date: 07 Oct - 27 Nov Duration: 52 Days (37 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084339 | DO | 1 | 4 | 2019HP-1[252]Bird Nests -Remove
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | SH | - | 901133675 | DO | 2 | 1 | T Phase DA Disconnect DUE: 17-Jul-20
110kV FEEDER - DRUMLINE ENNIS
TO-20-DRU-ENN-1-02 ISO week: 46tu Date: 10 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Operator training
TO-20-DRU-ENN-1-01 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA511
TRAN |  | - | 900986381 | DO | 1 | 4 | 2018HP-1[18]Off PlumbPlumb poleset
TRAN |  | - | 900986388 | DO | 1 | 4 | 2018HP-1[75]Off PlumbPlumb poleset
400kV FEEDER - DUNSTOWN MONEYPOINT GIS
TO-20-DSN-MP GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0873 | DO | 50 |  | EI: Line refurb works
CORRECT | DSN |  | 900531814 | DO | 5 | 2 | Inspect and test all the cylinders, pist
TO-20-DSN-MP GIS-1-03 Status: Unscheduled
FO_MISC |  |  | 901084904 | DO | 2 | 4 | 2019HP-1[361]Insulator Broken
FO_MISC |  |  | 901084905 | DO | 2 | 4 | 2019HP-1[371]Insulator Broken
FO_MISC |  |  | 901084906 | DO | 2 | 4 | 2019HP-1[396]Insulator Broken
FO_MISC |  |  | 901084907 | DO | 2 | 4 | 2019HP-1[402]Insulator Broken
FO_MISC |  |  | 901084908 | DO | 2 | 4 | 2019HP-1[410]Insulator Broken
FO_MISC |  |  | 901084909 | DO | 2 | 4 | 2019HP-1[486]Insulator Broken
FO_MISC |  |  | 901084910 | DO | 2 | 4 | 2019HP-1[563]Insulator Broken
FO_MISC |  |  | 901084911 | DO | 2 | 4 | 2019HP-1[564]Insulator Broken
TRAN |  | - | 900986826 | DO | 1 | 4 | 2018HP-1[214]ACGFit ACG
FO_MISC |  |  | 901084407 | DO | 1 | 4 | 2019HP-1[331]Bird Nests
FO_MISC |  |  | 901084408 | DO | 1 | 4 | 2019HP-1[567]Bird Nests
TRAN |  | - | 900986733 | NS |  | 1 | 2018HP-1[371]Bird Nestsremove asap
TRAN |  | - | 900986835 | NS |  | 1 | 2018HP-1[238]Bird Nestsremove asap
CORRECT | DSN | - | 901038719 | DO | 21 | 2 | Dunstown R4001 Reactor: Refurbush Reactor, regasket & paint
CORRECT | DSN |  | 900444627 | NS |  | 2 | O. ESBI Inspect and test all the cylinde
CORRECT | DSN |  | 900489556 | NS |  | 2 | O. ESBI Inspect and test all the cylind
CM | DSN | 400-R4001 | 900690047 | NS |  | 1 | O/1 R4001 DRYCOL INTERNAL FAULT
FM | MP | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TO-20-DSN-MP GIS-1-02 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Tentative
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FM | DSN | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
COUPLER/SECTIONALISING CB - ENNIS 110SA1-2CB
TO-20-ENN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | ENN | 110-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Operational Test
TO-20-ENN-110SA1-2CB-02 Status: Unscheduled
CORRECT | ENN | - | 901045923 | CANC | 0 | 1 | Investigate CB gas leak & repair if possible
110kV FEEDER - ENNIS SLIEVECALLAN
TO-20-ENN-SLC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | ENN | - | 901134782 | CLO | 2 | 1 | S Phase Slievecallan 110kv Cubicle. S phase se connectio hotspot n DUE : IMMEDIATELY
AMCAB | ENN | - | 901076133 | NS | 0 | 4 | Cable Insp. 110kV XLPE
TO-20-ENN-SLC-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CM | SLC | - | 901134796 | CLO | 2 | 1 | S Phase Ennis 110kv Cubicle. S Phase cable end bushing connectio hotspot DUE : 17-Jul-20 hotspot
CM | SLC | 110-DL/DE | 901134797 | CLO | 2 | 1 | R & S Phases Ennis 110kV cubicle. R & S Phase DL/DE DUE : 17-Aug-20hotspot
DISTRIBUTION TRANSFORMER - ENNIS T142 [SDCC]
TO-20-ENN-T142-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Outage requested by ESBN. DOF required following CA on T142 110kV cubicle
DISTRIBUTION TRANSFORMER - IKERRIN T141 [SDCC]
TO-20-IKE-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1057 | DO | 2 |  | As a consequence of IKE,T-IKE-1: IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee IKERRIN
TO-20-IKE,T-IKE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-IKE-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee SHANNONBRIDGE
TO-20-IKE,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
110kV FEEDER - IKERRIN tee THURLES
TO-20-IKE,T-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-IKE,T-THU-1-01 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | THU |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
TO-20-IKE,T-THU-1-03 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
GENERATOR TRANSFORMER - KILL HILL T131 [Kill Hill KH1]
TO-20-KHL-T131-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - KILL HILL THURLES
TO-20-KHL-THU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | KHL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | THU |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - KILLONAN KNOCKRAHA
TO-20-KLN-KRA-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KLN-KRA-1-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KLN-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KLN-KRA-1-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | EI: Install base(s) for post insulator(s) Post curing time - erect steel + post insulator(s) Line transfer, and tubular uprate and civil works on Killonan bay.
TO-20-KLN-KRA-1-05 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084917 | DO | 2 | 2 | 2019HP-1[178]Insulator broken disc
TRAN |  | - | 900987776 | DO | 1 | 4 | "2018HP-3[173,174,175]Stud RailingRepair
TRAN |  | - | 900987793 | DO | 1 | 4 | 2018HP-1[40]ACGFit ACG
110kV FEEDER - KILLONAN LIMERICK 1
TO-20-KLN-LIM-1-01 ISO week: 36mo - 45fr Date: 31 Aug - 06 Nov Duration: 68 Days (49 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0624 | DO | 49 |  | EI: Line diversion work to enable construction of GIS building
CAPX |  |  | CP0624 | DO | 5 |  | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
OPT | KLN |  |  | DO | 3 | 4 | 110kV Air Blast Cubicle Operational Test
CORRECT | LIM |  | 901078074 | DO | 5 | 1 | Low Gas / Leak
OS | LIM | - | 900948291 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - KILLONAN LIMERICK 2
TO-20-KLN-LIM-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| - | Line | 901126082 | DO | 2 | 4 | 2019LP-1[25]Replace Pole - Pole Rot
TO-20-KLN-LIM-2-02 ISO week: 38fr - 39we Date: 18 Sep - 23 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0624 | DO | 5 |  | Simultaneous KLN-LIM-1 + KLN-LIM-2: Proximity outage
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
Fix Disconnect on Killonan Limerick 2
TO-20-KLN-LIM-2-01 ISO week: 9mo - 35fr Date: 24 Feb - 28 Aug Duration: 187 Days (129 WD) Status: Scheduled
CAPX |  |  | CP0624 | DO | 74 |  | EI: Line diversion work to enable construction of GIS building
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | LIM | - | 901042304 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | LIM | - | 901129154 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - KILLONAN NENAGH [SDCC]
TO-20-KLN-NEN-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, REL521
220kV FEEDER - KILLONAN SHANNONBRIDGE
TO-20-KLN-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Studied proximity CP1058
TO-20-KLN-SH-1-01 ISO week: 20mo - 22th Date: 11 May - 28 May Duration: 18 Days (14 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL521
FO_MISC |  |  | 901084918 | DO | 2 | 4 | 2019HP-1[22]Insulator broken insulator
FO_MISC |  |  | 901084919 | DO | 2 | 4 | 2019HP-1[240]Insulator broken insulator
FO_MISC |  | - | 900404035 | DO | 1 | 1 | 1[180]Fit anti climb device
YM03 | - | - | 900978885 | DO | 5 | 1 | 1[57]Repairs of damaged members on Tower
OS | KLN | - | 900858887 | CLO | 10 | 2 | 220kV Air Blast Cubicle Ordinary Service
CA | KLN | - | 901038533 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KLN |  | 901045697 | CLO | 2 | 1 | Pressure Vessel Statutory Inspection
OPT | KLN | 220-1 |  | DO | 1 | 4 | 220kV Air Blast Cubicle Operational Test
CA | SH | - | 900775936 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
OPT | SH | 220-1 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - KILLONAN SINGLAND
TO-20-KLN-SNG-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
Proximity outage for CA on Singland T101
OS | SNG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRANSFORMER - KILLONAN T2101
TO-20-KLN-T2101-01 ISO week: 39tu - 39th Date: 22 Sep - 24 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | KLN | 110 |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
OPT | KLN | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KLN | 220 |  | DO | 1 | 4 | 220kV Air Blast Cubicle Operational Test
TRANSFORMER - KILLONAN T2102
TO-20-KLN-T2102-01 ISO week: 33mo - 35fr Date: 10 Aug - 28 Aug Duration: 19 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | KLN | 220 |  | DO | 6 | 4 | 110kV Air Blast Cubicle Ordinary Service
OS | KLN | 110 |  | DO | 6 | 4 | 110kV Air Blast Cubicle Ordinary Service
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | KLN | Trafo |  | DO | 5 | 4 | 220/110 & 275/220 - Ordinary Service
CA | KLN | 220 |  | DO | 4 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | KLN | 110 |  | DO | 4 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | KLN | 110 |  | DO | 2 | 4 | Annual Insp. 110kV Station OF Cable
TRANSFORMER - KILLONAN T2103
TO-20-KLN-T2103-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7SA612, RET670
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | KLN | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | KLN | Trafo |  | DO | 5 | 4 | 220/110 & 275/220 - Ordinary Service
OS | KLN | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLN | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | KLN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - KILLONAN T2104
TO-20-KLN-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | KLN |  | 901078075 | CANC |  | 1 | ESB Networks Oil filtration plant was no
TO-20-KLN-T2104-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KLN | TRAFO | 901130045 | CLO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | KLN | 110 | 901129908 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KLN | 220 | 901129999 | CLO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
CORRECT | KLN |  | 901090977 | DO | 3 | 1 | Replacement of faulty oil DGA monitoring
AMCAB | KLN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
220kV FEEDER - KILLONAN TARBERT
TO-20-KLN-TB-1-05 ISO week: 41tu - 41we Date: 06 Oct - 07 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A2/B2 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
CAPX |  |  | CP0647 | DO | 2 |  | Simultaneous 220 kV A4/B4 IN TURN @ KPG + KLN-TB-1: Commissioning and removal of earths
TO-20-KLN-TB-1-01 ISO week: 23tu - 47we Date: 02 Jun - 18 Nov Duration: 170 Days (120 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 120 |  | Outage for diversion of line into Kilpaddoge station to cable into GIS building. Feeder will become Killonan Kilpaddoge
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987854 | DO | 2 | 4 | 2018HP-1[151]ACGFit ACG
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 1
TO-20-KPG-MP GIS-1-02 ISO week: 39mo - 40we Date: 21 Sep - 30 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 4 | Aux Relay - replace contactors
220kV FEEDER - KILPADDOGE MONEYPOINT GIS 2
TO-20-KPG-MP GIS-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0726 | DO | 2 |  | EI: Energise the new Kilpaddoge- Knocknaure 2 cable
TO-20-KPG-MP GIS-2-02 Status: Unscheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Tarbert 2
TO-20-KPG-MP GIS-2-03 ISO week: 41th - 41fr Date: 08 Oct - 09 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0647 | DO | 2 |  | EI: EI of Kilpaddoge - Killonan
TO-20-KPG-MP GIS-2-04 ISO week: 48mo - 49we Date: 23 Nov - 02 Dec Duration: 10 Days (8 WD) Status: Tentative
|  | - |  | DO | 6 |  | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
110kV FEEDER - KILPADDOGE RATHKEALE
TO-20-KPG-RAT-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900989469 | CANC | 1 | 2 | 2018HP-1[125]ITSOul&HW Replace check
TRAN |  | - | 900989470 | CANC | 1 | 2 | 2018HP-1[130]ITSOul&HW Replace check
TRAN |  | - | 900989471 | CANC | 1 | 1 | 2018HP-1[134]Off Plumb
TO-20-KPG-RAT-1-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900989472 | NS | 1 | 2 | 2018HP-1[135]ACG-Replace
OPT | RAT | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
SECTIONALISING DISCONNECT - LIMERICK 110SA1
TO-20-LIM-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of LIM-110SA2: 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - LIMERICK 110SA2
TO-20-LIM-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of LIM-110SA1: 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
TO-20-LIM-110SA2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
OS | LIM | SA2 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - LIMERICK MONETEEN
TO-20-LIM-MTN-1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900567326 | DO | 2 | 1 | 3[509,510,511] DCIMP5 badly kinked (IMP49 KIL-LIM 1)
OPT | LIM |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LIMERICK RATHKEALE
TO-20-LIM-RAT-1-01 ISO week: 42we - 42fr Date: 14 Oct - 16 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988374 | DO | 2 | 4 | 2018HP-1[42-43]Conflicts-No Guard Wire
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of R1Z23b
AMCAB | LIM | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | LIM | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | RAT |  |  | DO | 2 | 4 | 110kV MO Cubicle Operational Test
DISTRIBUTION TRANSFORMER - LIMERICK T141 [SDCC]
TO-20-LIM-T141-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - LIMERICK T142 [SDCC]
TO-20-LIM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A1 @ LIM: Proximity outage for work on Killonan-Limerick1 110 kV
SECTIONALISING DISCONNECT - LISHEEN 110SA1-2
TO-20-LSN-110SA1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
SECTIONALISING DISCONNECT - LISHEEN 110SA2-4
TO-20-LSN-110SA2-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
GENERATOR TRANSFORMER - LISHEEN T122 [Lisheen LS1/LS2]
TO-20-LSN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-T122-01 ISO week: 28mo - 28tu Date: 06 Jul - 07 Jul Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request for 2 WD
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LSN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - LISHEEN T142 [SDCC]
TO-20-LSN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | As a consequence of LSN-THU-1: 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
110kV FEEDER - LISHEEN THURLES
TO-20-LSN-THU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
TO-20-LSN-THU-1-01 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988512 | DO | 2 | 4 | 2018HP-1[25]Bird Nestsremove asap
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
TO-20-LSN-THU-1-03 Status: Unscheduled
TRAN |  | - | 900988515 | CANC | 1 | 1 | 2018HP-1[47]Bird Nestsremove asap
SECTIONALISING DISCONNECT - MONETEEN 110SA1
TO-20-MTN-110SA1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of MTN-110SA2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MONETEEN 110SA2
TO-20-MTN-110SA2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
OS | MTN | SA2 | 901039690 | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - MONETEEN MUNGRET 1
TO-20-MTN-MUN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MTN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - MONETEEN MUNGRET 2
TO-20-MTN-MUN-2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | MTN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - MONEYPOINT 400 kV A1
TO-20-400 kV A1 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A1 / A3 BB In Turn, SA1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV A2
TO-20-400 kV A2 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A2 / A4 BB In Turn, SA2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV B1
TO-20-400 kV B1 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
B1 / B3 BB In Turn, SB1-3, K3 DC Contactor Replacement work on Sect, Coupler, Spare Bays
BUSBAR SECTION - MONEYPOINT 400 kV B2
TO-20-400 kV B2 @ MP-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
B2 / B4 BB In Turn , SB2-4, K4 DC Contactor Replacement work on Sect, Coupler, Spare Bays
COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110SA1-2CB
TO-20-MP GIS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | - |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
400kV FEEDER - MONEYPOINT GIS OLDSTREET
TO-20-MP GIS-OST-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900988931 | NS |  | 1 | 2018HP-1[166]Bird Nestsremove asap
TRAN |  | - | 900988938 | NS |  | 1 | 2018HP-1[176]Bird Nestsremove asap
TRAN |  | - | 900988946 | NS |  | 1 | 2018HP-1[191]Bird Nestsremove asap
TRAN |  | - | 900988976 | NS |  | 1 | 2018HP-1[74]Bird Nestsremove asap
TO-20-MP GIS-OST-1-04 Status: Unscheduled
studied outage for CP0824
TO-20-MP GIS-OST-1-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-MP GIS-OST-1-01 ISO week: 9mo - 14th Date: 24 Feb - 02 Apr Duration: 39 Days (28 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting
TO-20-MP GIS-OST-1-02 ISO week: 21th - 41fr Date: 21 May - 09 Oct Duration: 142 Days (100 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting (part 2)
|  |  | OD0321 |  | 5 |  | Total Maintenance Outage Duration Requested
|  | MP | 19EG23677 | CLO | 2 |  | Cable Insp. 400kV XLPE
|  |  | 20LN4755 |  | 2 |  | 2019HP-1[11]Insulator Broken
|  |  | 18LN1616 |  | 1 |  | 2017HP-1[199]Earths-Check S/W hardware
|  |  | 18LN1618 |  | 1 |  | 2017HP-1[55A]Insulator Broken
|  |  | 18LN1631 |  | 1 |  | 2017HP-1[139]Earths-Check S/W hardware
|  |  | 19LN6391 |  | 1 |  | 2018HP-3[3]Insul&HW Replace check
|  |  | 19LN6392 |  | 1 |  | 2018HP-3[8]Insul&HW Replace check
|  |  | 19LN6393 |  | 1 |  | 2018HP-2[11]Insul&HW Replace check
|  |  | 19LN6394 |  | 1 |  | 2018HP-3[15]Insul&HW Replace check
|  |  | 19LN6395 |  | 1 |  | 2018HP-1[13]Insul&HW Replace check
|  |  | 19LN6396 |  | 1 |  | 2018HP-1[27]Insul&HW Replace check
|  |  | 19LN6398 |  | 1 |  | 2018HP-1[55A]Insulator-replace
|  |  | 20LN4741 |  | 1 |  | 2019HP-1[166]Bird Nests
|  |  | 20LN4743 |  | 1 |  | 2019HP-1[175]Bird Nests
|  |  | 20LN4744 |  | 1 |  | 2019HP-1[183]Bird Nests
|  |  | 20LN4745 |  | 1 |  | 2019HP-1[191]Bird Nests
|  |  | 20LN4756 |  | 1 |  | 2019HP-1[55A]Insulator Broken
| OST |  | 18EG10486 |  | 2 |  | 400kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T121 [Moneypoint MP9]
TO-20-MP GIS-T121-01 ISO week: 30fr Date: 24 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MP | TRAFO | 900938612 | DO | 1 | 3 | 110KV GIS Cubicle Operational Test
TRANSFORMER - MONEYPOINT GIS T2102
TO-20-MP GIS-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MP |  | 901059126 | CANC |  | 1 | Main Tank Conservator oil level gauge is
TO-20-MP GIS-T2102-03 Status: Unscheduled
CORRECT | MP | TRAFO | 901028665 | CANC | 4 | 2 | Replacement Oil Level Indicator for Moneypoint T2102 Main OLTC Conservator. Original oil level gauge faulty contacts and activating a contsant low oil level alarm evndo the oil level when check is ok.
TO-20-MP GIS-T2102-01 ISO week: 10mo - 10fr Date: 02 Mar - 06 Mar Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MP | - | 900970626 | CLO | 4 | 1 | The minitrans unit on T2102 in Moneypoin
OPT | MP | TRAFO | 900944114 | CLO | 2 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | MP | 220 | 900944165 | CLO | 2 | 3 | 220kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - MONEYPOINT GIS T4003 [ESB GWM MP3]
TO-20-MP GIS-T4003-01 ISO week: 24we - 25we Date: 10 Jun - 17 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 | 2 | Total Maintenance Outage Duration Requested
CM | MP | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TRANSFORMER - MONEYPOINT GIS T4201
TO-20-MP GIS-T4201-01 ISO [year]week: 1we - N/A Date: 01 Jan - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Forced outage
TO-20-MP GIS-T4201-02 Status: Unscheduled
FOFAULT | MP | TRAFO | 901028372 | CANC | 2 | 1 | Ref- T4201 Bucholz alarm
CORRECT | MP |  | 901037956 | CANC |  | 1 | As part of the Fault Investigation into
TRANSFORMER - MONEYPOINT GIS T4202
TO-20-MP GIS-T4202-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MP |  | 901067748 | CANC |  | 1 | Atlantic Projects Company were required
CORRECT | MP | 220 | 901073579 | CANC |  | 1 | Camlin Power are to install an Intego bu
TO-20-MP GIS-T4202-01 Status: Unscheduled
| MP | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | MP | 220 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | MP | 400 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | MP | 400 |  | DO | 1 | 4 | 400kV GIS Cubicle Operational Test
OPT | MP | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - MONEYPOINT PROSPECT
TO-20-MP-PRO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | PRO | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-MP-PRO-1-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
TO-20-MP-PRO-1-03 Status: Unscheduled
AMCAB | MP | 220 | 901129060 | DO | 2 | 4 | Insp. 400 & 220 Station XLPE Cable
GENERATOR TRANSFORMER - MONEYPOINT T4001 [ESB GWM MP1]
TO-20-MP-T4001-01 ISO week: 48tu - 48th Date: 24 Nov - 26 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| MON | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | MP |  |  | DO | 2 | 1 | 400kV GIS Cubicle Operational Test
AMCAB | MP | - | 901005716 | DO | 2 | 4 | Insp. 400 & 220 Station XLPE Cable
FM | MP | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TSO CUSTOMER TRANSFORMER - MUNGRET T101 [Irish Cement]
TO-20-MUN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer outage requestfor tap changer maintenance on incoming transformer T101
TSO CUSTOMER TRANSFORMER - MUNGRET T102 [Irish Cement]
TO-20-MUN-T102-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of MTN-MUN-2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
TRANSFORMER - OLDSTREET T4202
TO-20-OST-T4202-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of OST-TY-1: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-OST-T4202-03 Status: Unscheduled
CORRECT | OST |  | 901090507 | CANC |  | 1 | Following the increase of H2 gas within
TO-20-OST-T4202-04 Status: Unscheduled
CORRECT | OST | TRAFO | 901039294 | CANC | 3 | 2 | Oldstreet T4202 Transformer: Transfix G9 Installation
TO-20-OST-T4202-02 Status: Unscheduled
|  | - |  |  | 20 |  | Total Maintenance Outage Duration Requested
[5 empty] | 2 |  | Operator approval evaluations
TRAFO | OST | TRAFO |  | DO | 5 | 1 | 400/220kV Trafo Tap Changer Inspection
OS | OST | 400 |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
TRAFO | OST | TRAFO |  | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT
OS | OST | Trafo | 901041548 | DO | 5 | 4 | 400/220kV Transformer Ordinary Service
CA | OST | 400 |  | DO | 4 | 1 | 400KV CUBICLE CONDITION ASSESSMENT
OS | OST | 220 |  | DO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | OST | 220 | 901038565 | DO | 4 | 1 | 220kV Cubicle Condition Assessment
CORRECT | OST | TRAFO | 901039331 | DO | 1 | 2 | Oldstreet T4202 Transformer: Drycol Replacement
220kV FEEDER - OLDSTREET TYNAGH
TO-20-OST-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-OST-TY-1-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
MO |  |  | 901039105 |  | 1 |  | 220kV SF6 Cubicle Operational Test
FO_MISC |  |  | 901084335 | DO | 1 | 4 | 2019HP-1[17]Bird Nests
CM | TYN | - | 901133678 | DO | 2 | 1 | 220kV SF6 Cubicle Ordinary Service DUE : 17-Jul-20
OPT | TYN | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
400kV FEEDER - OLDSTREET WOODLAND
TO-20-OST-WOO-1-01 ISO week: 42sa - 44fr Date: 17 Oct - 30 Oct Duration: 14 Days (9 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084928 | DO | 2 | 4 | 2019HP-1[103]Insulator Broken
FO_MISC |  |  | 901084929 | DO | 2 | 4 | 2019HP-1[115]Insulator Broken
FO_MISC |  |  | 901084930 | DO | 2 | 4 | 2019HP-1[272]Insulator Remove old insul
FO_STDMG |  |  | 901086387 | DO | 2 | 4 | 2019HP-1[90 ]Replace Member
FO_STDMG |  |  | 901086388 | DO | 2 | 4 | 2019HP-1[100]Replace Member
FO_STDMG |  |  | 901086389 | DO | 2 | 4 | 2019HP-1[120]Replace Member
TRAN |  | - | 900989127 | DO | 1 | 4 | 2018HP-1[99]Replace Memberrakers
TRAN |  | - | 900989128 | DO | 1 | 4 | 2018HP-1[100]Replace Memberrakers
TRAN |  | - | 900989185 | DO | 1 | 4 | 2018HP-1[115]Insulator-broken c/ph
TRAN |  | - | 900989188 | DO | 1 | 4 | 2018HP-1[162]Check(General)Remove object
FO_MISC |  |  | 901084336 | DO | 1 | 4 | 2019HP-1[76]Bird Nests
FO_MISC |  |  | 901084337 | DO | 1 | 4 | 2019HP-1[79]Bird Nests
FO_MISC |  |  | 901084338 | DO | 1 | 4 | 2019HP-1[93]Bird Nests
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SL32, FYS3L, FYG2L
OPT | OST | - | 901039088 | DO | 2 | 4 | 400kV SF6 Cubicle Operational Test
CORRECT | WOO | R4001 | 900821342 | DO | 10 | 1 | Some work done in 2014 Beltec 2 leaks HV
CORRECT | WOO |  | 900724385 | DO | 5 | 1 | O/1 Repair to leak in concrete of Bund
CORRECT | WOO |  | 901046071 | DO | 3 | 1 | SF6 leak repair
FM | WOO | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | WOO |  | 900788839 | DO |  | 2 | Misc- work not on other CORRECT counters
220kV FEEDER - PROSPECT TARBERT
TO-20-PRO-TB-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Prox outage required for pipeline survey
TO-20-PRO-TB-1-04 ISO week: 31mo - 31tu Date: 27 Jul - 28 Jul Duration: 2 Days (2 WD) Status: Scheduled
Prox outage required for pipeline survey
TO-20-PRO-TB-1-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_CABLE |  | - | 900952297 | CLO | 2 | 1 | Replacement of Cathodic Protection Battery
AMCAB | TB | - | 901113198 | CLO | 2 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | TB |  | 901129537 | CLO | 1 | 4 | 220kV MO Cubicle Operational Test
GENERATOR TRANSFORMER - SEALROCK T103 [Aughinish Alumina SK3]
TO-20-SK-T103-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-3: 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
TO-20-SK-T103-03 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequence of AUG-SK-3: 110 kV A1 @ AUG
TO-20-SK-T103-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CM |  |  | 901137683 | DO | 5 | 1 | Gas Leak Repar S Phase
AMCAB | SK | 110 | 901129121 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
GENERATOR TRANSFORMER - SEALROCK T104 [Aughinish Alumina SK4]
TO-20-SK-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | 4 day customer outage
PROX |  |  | PR0001 | DO | 2 |  | As a consequence of AUG-SK-4: 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
AMCAB | SK | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SK |  |  | DO | 2 | 4 | 110KV SF6 Cubicle Operational Test
TO-20-SK-T104-02 ISO week: 37tu - 37th Date: 08 Sep - 10 Sep Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of AUG-SK-4: 110 kV
Outage start @ 14:00 07 Sept 2020, Outage end @ 15:00 10 Sept 2020
Customer outage request
COUPLER/SECTIONALISING CB - SINGLAND 110SA1-2CB
TO-20-SNG-110SA1-2CB-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
DSO proximity request for works on SNG T102
OPT | SNG | - |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | SNG | 110-SA2/DEM2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-SNG-110SA1-2CB-03 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
proximity for CA on Singland T101
TO-20-SNG-110SA1-2CB-02 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Proposed
OPT | SNG | 110-SA1/DEM1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
DISTRIBUTION TRANSFORMER - SINGLAND T101 [SDCC]
TO-20-SNG-T101-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CA on Singland T101
DISTRIBUTION TRANSFORMER - SINGLAND T102 [SDCC]
TO-20-SNG-T102-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO request for CA on SNG T102
COUPLER/SECTIONALISING CB - THURLES 110SA1-2CB
TO-20-THU-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
CAPACITOR/SVC/REACTOR - THURLES CAP1
TO-20-THU-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
CAPACITOR/SVC/REACTOR - THURLES CAP2
TO-20-THU-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - THURLES T142 [SDCC]
TO-20-THU-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 4 |  | 110 kV A2 @ THU: Proximity outage for work on Thurles 110kV K1-2
DISTRIBUTION TRANSFORMER - TULLABRACK T141 [SDCC]
TO-20-TBK-T141-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | As a consequence of TBK,T-TBK-1: BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7VK611
110kV FEEDER - TULLABRACK tee BOOLTIAGH
TO-20-TBK,T-BOL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BOL | - | 901129965 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - TULLABRACK tee MONEYPOINT GIS
TO-20-TBK,T-MP GIS-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988895 | DO | 2 | 4 | 2018HP-1[98]Off PlumbPlumb poleset
FO_MISC |  |  | 901082688 | DO | 2 | 4 | 2019HP-1[99]Off Plumb -plumb poles
110kV FEEDER - TULLABRACK tee TULLABRACK
TO-20-TBK,T-TBK-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | BOL-MP GIS-TLK-1: Proximity outage for refurb works on Moneypoint Oldstreet (structure 55-55A)

## LETTERKENNY (Rgn)
110kV FEEDER - ARDNAGAPPARY TIEVEBRACK
TO-20-AGP-TIV-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TIV | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - BINBANE 110SA1
TO-20-BIN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA2: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | As a consequence of BIN-110SA2: Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA2: 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
SECTIONALISING DISCONNECT - BINBANE 110SA2
TO-20-BIN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 101 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-110SA2: Station is split for the entire outage
CAPX |  |  | CP0878 | DO | 61 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
CAPX |  |  | CP0878 | DO | 40 |  | As a consequence of BIN-110SA1: Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | As a consequence of BIN-110SA1: 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
110kV FEEDER - BINBANE CATHALEENS FALL
TO-20-BIN-CF-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-CF-1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
TO-20-BIN-CF-1-03 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
TO-20-BIN-CF-1-04 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
TO-20-BIN-CF-1-06 Status: Unscheduled
FO_COND | - | - | 901153752 | CLO | 2 | 1 | Hotspot 1 (AM No.110, Span 109-110) Centre Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153753 | CLO | 2 | 1 | Hotspot 2 (AM No.110, Span 109-110) Right Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153754 | CLO | 2 | 1 | Hotspot 3 (AM No.110, Span 110-111) Centre Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153755 | CLO | 2 | 1 | Hotspot 4 (AM No.110, Span 110-111) Right Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153756 | CLO | 2 | 1 | Hotspot 5 (AM No.116, Span 116-117) Left Deadend Termination (Repair by 5th Jul 2020)
FO_COND | - | - | 901153757 | CLO | 2 | 1 | Hotspot 6 (AM No.116, Span 116-117) Centre Deadend Termination (Repair by 5th Sep 2020)
FO_COND | - | - | 901153758 | CLO | 2 | 1 | Hotspot 7 (AM No.116, Span 116-117) Right Deadend Termination (Repair immediately)
FO_COND | - | - | 901153759 | CLO | 2 | 1 | Hotspot 8 (AM No.116, Span 115-116) Centre Deadend Termination (Repair by 5th Dec 2020)
FO_COND | - | - | 901153940 | CLO | 2 | 1 | Hotspot 9 (AM No.116, Span 115-116) Right Deadend Termination (Repair by 5th Dec 2020)
TO-20-BIN-CF-1-05 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, GRZ100
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - BINBANE T141 [NDCC]
TO-20-BIN-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T142 [NDCC]
TO-20-BIN-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remove droppers to existing sectionalising disconnect SA2 plus adding in additional insulators on A2 Busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T142-01 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 61 |  | Simultaneous BIN-110SA1 + BIN-T142: T142 out as part of SA2 outage, T142 to remain on hot stand-by during the first 61 days of SA2 outage, no return to service once outage #5 commences
TO-20-BIN-T142-05 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 40 |  | Simultaneous BIN-110SA1 + BIN-T142: Complete protection upgrade including installtion of new 110 kV CTs
TO-20-BIN-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 6 |  | Simultaneous 110 kV A2 @ BIN + BIN-T142: Implementation of SPS anti-islanding on T142
TO-20-BIN-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 5 |  | 110 kV A2 @ BIN: EI: Carry out works to busbar disconnects for 110 kV busbar protection integration and EI of T142 on final day of outage
TO-20-BIN-T142-04 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A2 @ BIN: EI: Remake droppers to sectionalising disconnect SA2 ,either leave in inline insulators or remove
DISTRIBUTION TRANSFORMER - BINBANE T143 [NDCC]
TO-20-BIN-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-T143-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
110kV FEEDER - BINBANE TIEVEBRACK
TO-20-BIN-TIV-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remove jumpers across sectionlising disconnects SA1 plus adding in additional inline insulators on A1 busbar for DWA purposes for building new sect cubicle
TO-20-BIN-TIV-1-02 Status: Unscheduled
CAPX |  |  | CP0878 | DO | 3 |  | Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: Simultaneous 110 kV A1 @ BIN + 110 kV A1 @ BIN: Implement additional signals on T141
CAPX |  |  | CP0878 | DO | 3 |  | 110 kV A1 @ BIN: EI: Remake droppers to sectionalising disconnect SA1 either leave in inline insulators or remove
BUSBAR SECTION - CATHALEENS FALL 110 kV A1
TO-20-110 kV A1 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV A2
TO-20-110 kV A2 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV B1
TO-20-110 kV B1 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CF: Busbar Changeover
BUSBAR SECTION - CATHALEENS FALL 110 kV B2
TO-20-110 kV B2 @ CF-01 ISO week: 29th Date: 16 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CF: Busbar Changeover
CAPACITOR/SVC/REACTOR - CATHALEENS FALL CAP2
TO-20-CF-CAP2-01 ISO week: 36fr - 37fr Date: 04 Sep - 11 Sep Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | CF | CAP | 900616524 | DO | 5 | 2 | FI-011-11 Oil Sampling of Instrument tra
CA | CF | CAP | 901050223 | DO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
110kV FEEDER - CATHALEENS FALL CLIFF
TO-20-CF-CL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
110kV FEEDER - CATHALEENS FALL CLOGHER 1
TO-20-CF-CLO-1-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1011 | DO | 2 |  | Slit trenching and ducting in close proximity to C-Fall 1 circuit in Clogher station compound for new windfarm connection
[5 empty] | 5 |  | Telecoms- fibre works
110kV FEEDER - CATHALEENS FALL CLOGHER 2
TO-20-CF-CLO-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOINSHW |  | - | 900649885 | DO | 3 | 1 | 2014HP-2[20,21]Insulator Fit Dups. Proximity Outag of Cath Falls-Clogher 110kV. Wayleave Issue
FO_MISC |  | - | 900819397 | DO | 1 | 2 | 2016HP-1[20]Insulator Fit Dups
FO_MISC |  | - | 900819398 | DO | 1 | 2 | 2016HP-1[21]Insulator Fit Dups
TO-20-CF-CLO-2-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1011 | DO | 2 |  | Slit trenching and ducting in close proximity to C-Fall 2 circuit in Clogher station compound for new windfarm connection
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | CLO | - | 901043763 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
110kV FEEDER - CATHALEENS FALL CORRACLASSY
TO-20-CF-COR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900819396 | DO | 8 | 2 | 2016HP-1[14]Off Plumb
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900649865 | DO | 2 | 1 | 2014HP-1[299]Off Plumb
FO_MISC |  | - | 900649866 | DO | 2 | 1 | 2014HP-1[298]Off Plumb
FO_MISC |  | - | 900649867 | DO | 2 | 1 | 2014HP-1[296]Off Plumb
FO_MISC |  | - | 900649868 | DO | 2 | 1 | 2014HP-1[295]Off Plumb
FO_MISC |  |  | 901084870 | DO | 2 | 4 | 2019HP-1[13]Earths-Replace Left pole e/w
FO_MISC |  |  | 901084950 | DO | 2 | 4 | 2019HP-1[277]Off Plumb -plumb poles
FO_MISC |  | - | 900898249 | DO | 1 | 3 | 2017HP-1[4]Vib Damps Dampers fatigue (Landowner access available May-July)
TRAN |  | - | 900985204 | DO | 1 | 4 | 2018HP-1[287]Check(General)-rusty Xarm
TRAN |  | - | 900985205 | DO | 1 | 4 | 2018HP-1[282]Check(General)-rusty Xarm
TRAN |  | - | 900985206 | DO | 1 | 4 | 2018HP-1[281]Check(General)-rusty Xarm
TRAN |  | - | 900985207 | DO | 1 | 4 | 2018HP-1[278]Check(General)-rusty Xarm
TRAN |  | - | 900985208 | DO | 1 | 4 | 2018HP-1[228]Check(General)-rusty Xarm
TRAN |  | - | 900985209 | DO | 1 | 4 | 2018HP-1[169]Check(General)-rusty Xarm
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CATHALEENS FALL SRANANAGH 1
TO-20-CF-SRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
FO_MISC |  | - | 900819401 | CLO | 2 | 2 | 2016HP-1[194]Check-General Ground works
FO_MISC |  | - | 900898210 | DO | 1 | 3 | 2017HP-1[30]Anti-Cl. Guard -Fit
AMCAB | CF | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CF | - | 901068533 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CATHALEENS FALL SRANANAGH 2
TO-20-CF-SRA-2-01 ISO week: 36we - 37fr Date: 02 Sep - 11 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900898213 | CLO | 7 | 3 | 2017HP-3[74,75,76]Off Plumb Poles
FO_MISC |  |  | 901084951 | CLO | 2 | 4 | 2019HP-1[77]Off Plumb -plumb poles
FO_MISC |  |  | 901084952 | CLO | 2 | 4 | 2019HP-1[185]Off Plumb -plumb poles
FO_MISC |  |  | 901084953 | CLO | 2 | 4 | 2019HP-1[186]Off Plumb -plumb poles
TRAN |  | - | 900985321 | CLO | 1 | 4 | 2018HP-1[44]Check(General)-old Xarm
TRAN |  | - | 900985335 | CLO | 1 | 4 | 2018HP-1[93]Check(General)rusty crossarm
FO_MISC |  |  | 901084269 | DO | 1 | 4 | 2019HP-1[247]Bird Nests
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511, REL521
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SRA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CATHALEENS FALL T103 [ESB GWM ER3]
TO-20-CF-T103-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Extra work day for IPP works on
OS | CF | - | 901129790 | CLO | 4 | 4 | 110KV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - CLIFF T101 [ESB GWM ER1]
TO-20-CL-T101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CL |  | 901129648 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - CLIFF T102 [ESB GWM ER2]
TO-20-CL-T102-01 ISO week: 35tu Date: 25 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
OPT | CL |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
BUSBAR SECTION - CLOGHER 110 kV A1
TO-20-110 kV A1 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV A2
TO-20-110 kV A2 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV B1
TO-20-110 kV B1 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHER 110 kV B2
TO-20-110 kV B2 @ CLO-01 ISO week: 38th Date: 17 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHER 110K1-2
TO-20-CLO-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CLO | - | 901043754 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
OPT | CLO | SA | 901050343 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - CLOGHER DRUMKEEN
TO-20-CLO-DRM-1-01 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084871 | DO | 1 | 4 | 2019HP-1[47]Earths-Replace
AMCAB | CLO | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | DRM | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CLOGHER MULREAVY
TO-20-CLO-MRY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - DRUMKEEN LETTERKENNY
TO-20-DRM-LET-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-DRM-LET-1-03 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL551
TO-20-DRM-LET-1-02 ISO week: 40tu Date: 29 Sep Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DRM | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - DRUMKEEN MEENTYCAT
TO-20-DRM-MEE-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
OS | DRM | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - GOLAGH T101 [Golagh GOL1]
TO-20-GOL-T101-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Full tee outage for work on Golagh tee Letterkenny
110kV FEEDER - GOLAGH tee CLOGHER
TO-20-GOL,T-CLO-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CLO | - |  | DO | 1 | 4 | Cable Insp. 110kV XLPE
OPT | CLO | - | 901045434 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
110kV FEEDER - GOLAGH tee GOLAGH
TO-20-GOL,T-GOL-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GOL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
FOFAULT | GOL | - | 900955641 | DO | 1 | 1 | flicker light on SMD o/o/o
110kV FEEDER - GOLAGH tee LETTERKENNY
TO-20-GOL,T-LET-1-01 ISO week: 34mo - 35su Date: 17 Aug - 30 Aug Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
CM | LET | - | 900720114 | DO | 10 | 2 | 1[142] Carry out ancillary works at Mast
OS | LET | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | LET | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | LET |  | 900952946 | DO | 3 | 1 | moisture in H8 surge arrestors
COUPLER/SECTIONALISING CB - LETTERKENNY 110SA1-3CB
TO-20-LET-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-110SA1-3CB-02 Status: Unscheduled
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | LET | - | 901080653 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CAPACITOR/SVC/REACTOR - LETTERKENNY CAP2
TO-20-LET-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | LET |  | 900332304 | DO | 1 | 2 | N O 1 Misc- work not on other C
CAPACITOR/SVC/REACTOR - LETTERKENNY M/CAP1
TO-20-LET-M/CAP1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
TO-20-LET-M/CAP1-01 Status: Unscheduled
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TRANSFORMER - LETTERKENNY STRABANE PST
TO-20-LET-PST-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-PST-03 Status: Unscheduled
PROT |  |  |  | DO | 2 |  | P1 Protection maintenance of 7SA511, MX3P3A
TO-20-LET-PST-02 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OS | LET | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | LET |  | 900952919 | DO | 1 | 1 | maintenane req on "S" phase arm of mecha
CAPACITOR/SVC/REACTOR - LETTERKENNY SVC
TO-20-LET-SVC-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
TO-20-LET-SVC-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | LET | - | 900863569 | DO | 5 | 1 | Replace 10kV LV Bushing at SVC
OS | LET | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
SVCAI | LET | SVC | 901006304 | DO | 2 | 4 | Annual Inspection of SVC
TO-20-LET-SVC-02 ISO week: 29mo - 34th Date: 13 Jul - 20 Aug Duration: 39 Days (28 WD) Status: Scheduled
CAPX |  |  | MC0330 | DO | 28 |  | SVC Refurbishment
DISTRIBUTION TRANSFORMER - LETTERKENNY T141 [NDCC]
TO-20-LET-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 40 |  | Facilitate the demolition of existing CT/VT supports and installation of new CT/VT and associated steelwork on T141 Bay
TO-20-LET-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0740 | DO | 1 |  | 110 kV A1 @ LET: EI: Energise T141
110kV FEEDER - LETTERKENNY TIEVEBRACK
TO-20-LET-TIV-1-01 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | LET | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | TIV | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LETTERKENNY TRILLICK [NDCC]
TO-20-LET-TLK-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | Proximity outage to install new lightning monopole
GENERATOR TRANSFORMER - MEENTYCAT T121 [Meentycat MCT]
TO-20-MEE-T121-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | As a consequence of work on Drumkeen-Meentycat 110 kV
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MEE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
GENERATOR TRANSFORMER - MULREAVY T131 [Mulreavy MB1/MB2]
TO-20-MRY-T131-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | MRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - SORNE HILL T122 [NDCC]
TO-20-SOR-T122-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - SORNE HILL T124 [NDCC]
TO-20-SOR-T124-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
110kV FEEDER - SORNE HILL TRILLICK [NDCC]
TO-20-SOR-TLK-1-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - TRILLICK T141 [NDCC]
TO-20-TLK-T141-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole
DISTRIBUTION TRANSFORMER - TRILLICK T142 [NDCC]
TO-20-TLK-T142-01 ISO week: 32tu Date: 04 Aug Duration: 1 Day (1 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0740 | DO | 1 |  | As a consequence of LET-TLK-1: Proximity outage to install new lightning monopole

## GALWAY (Rgn)
110kV FEEDER - BELLACORICK CASTLEBAR
TO-20-BK-CBR-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ BK: Proximity outage for work on Bellacorick 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BK-CBR-1-02 ISO week: 46th - 47th Date: 12 Nov - 19 Nov Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
YM03 | - | Line | 900979811 | DO | 3 | 1 | 2018HP-40m[59-60]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901088171 | DO | 3 | 1 | 2019HP-30m[168-169]TimCut 110kV(Rural)
FO_TIMB | - | Line | 901060073 | DO | 2 | 1 | HAZ CNF 80m[101-102] 8-9m High Timber U
OPT | BK | - | 901050277 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | CBR | - | 901050314 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
AMCAB | CBR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - CARROWBEG CASTLEBAR [SDCC]
TO-20-CBG-CBR-1-01 ISO week: 41fr Date: 09 Oct Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA513
XLPE inspection
DISTRIBUTION TRANSFORMER - CARROWBEG T142 [SDCC]
TO-20-CBG-T142-01 ISO week: 41mo - 42fr Date: 05 Oct - 16 Oct Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
DSO maintenance
As a consequence of work on Carrowbeg-Castlebar 110 kV
BUSBAR SECTION - CASHLA 110 kV A1
TO-20-110 kV A1 @ CSH-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-110 kV A1 @ CSH-06 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
TO-20-110 kV A1 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-110 kV A1 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
TO-20-110 kV A1 @ CSH-07 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV A1 @ CSH-08 Status: Unscheduled
CAPX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB
TO-20-110 kV A1 @ CSH-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-110 kV A1 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
BUSBAR SECTION - CASHLA 110 kV A2
TO-20-110 kV A2 @ CSH-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
TO-20-110 kV A2 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
TO-20-110 kV A2 @ CSH-05 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV A2 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
TO-20-110 kV A2 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-110 kV A2 @ CSH-06 Status: Unscheduled
CAPX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB
BUSBAR SECTION - CASHLA 110 kV B1
TO-20-110 kV B1 @ CSH-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
TO-20-110 kV B1 @ CSH-05 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-110 kV B1 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-110 kV B1 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
TO-20-110 kV B1 @ CSH-07 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV B1 @ CSH-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-110 kV B1 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
BUSBAR SECTION - CASHLA 110 kV B1/B2
TO-20-110 kV B1/B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
BUSBAR SECTION - CASHLA 110 kV B2
TO-20-110 kV B2 @ CSH-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
TO-20-110 kV B2 @ CSH-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
TO-20-110 kV B2 @ CSH-05 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CSH: Busbar Changeover
TO-20-110 kV B2 @ CSH-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-110 kV B2 @ CSH-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
COUPLER/SECTIONALISING CB - CASHLA 110K1-2
TO-20-CSH-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 110 kV B1/B2 @ CSH + CSH-110K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 110kV)
CAPX |  |  | CP1032 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla 110 kV Coupler bay at Cashla station
TO-20-CSH-110K1-2-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder
TO-20-CSH-110K1-2-04 Status: Unscheduled
CM | CSH |  | 901133361 | DO | 2 | 1 | DB 110kV Coupler R Phse Disconnect DUE : next available opportunity.
TO-20-CSH-110K1-2-03 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH |  | 901058830 | DO | 2 | 1 | O1 SA failed to open intermittently
CORRECT | CSH |  | 901058832 | DO | 2 | 1 | O1 DA2 seems to be operating slower than
BUSBAR SECTION - CASHLA 220 kV A1
TO-20-220 kV A1 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB
TO-20-220 kV A1 @ CSH-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV A2
TO-20-220 kV A2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV A4
TO-20-220 kV A4 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B1
TO-20-220 kV B1 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-220 kV B1 @ CSH-02 Status: Unscheduled
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B1/B2
TO-20-220 kV B1/B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
BUSBAR SECTION - CASHLA 220 kV B2
TO-20-220 kV B2 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CSH: Busbar Changeover
BUSBAR SECTION - CASHLA 220 kV B4
TO-20-220 kV B4 @ CSH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CSH: Busbar Changeover
COUPLER/SECTIONALISING CB - CASHLA 220K1-2
TO-20-CSH-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
TO-20-CSH-220K1-2-01 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-220K1-2-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 34 |  | Simultaneous 220 kV B1/B2 @ CSH + CSH-220K1-2: Lower DA & DB pantographs and earth, remove conductor from CB to post insulators (station split at 220kV)
CAPX |  |  | CP1032 | DO | 34 |  | Install Sprecher & Schuh type HPF-511 220 kV Circuit breaker replacement in the Cashla 220 kV Coupler bay at Cashla station
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CSH | - | 901041551 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
TO-20-CSH-220K1-2-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-220K1-2-05 ISO week: 41we - 43fr Date: 07 Oct - 23 Oct Duration: 17 Days (13 WD) Status: Scheduled
CM | CSH | - | 901133364 | DO | 2 | 1 | 220 kV Coupler k1-2 R Phase DB2 Pantograph. DUE : next available opportunity.
CM | CSH |  | 901133643 | DO | 2 | 1 | 220 kV Coupler k1-2 R Phas DA Pantograph DUE : next available opportunity.
CM | CSH | 220-SB2-4 | 901133644 | DO | 2 | 1 | 220 kV Coupler SB 2-4 S and T Phse Disconnect DUE : next available opportunity.
COUPLER/SECTIONALISING CB - CASHLA 220K2-4
TO-20-CSH-220K2-4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CSH | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TO-20-CSH-220K2-4-03 Status: Unscheduled
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
TO-20-CSH-220K2-4-01 ISO week: 12mo - 12we Date: 16 Mar - 18 Mar Duration: 3 Days (2 WD) Status: Scheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
CAPACITOR/SVC/REACTOR - CASHLA CAP1
TO-20-CSH-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
CAPACITOR/SVC/REACTOR - CASHLA CAP2
TO-20-CSH-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
110kV FEEDER - CASHLA CLOON
TO-20-CSH-CLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 1110 kV Circuit breaker replacement in the 110 kV Cloon bay at Cashla station
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-CLN-1: Remove droppers
TO-20-CSH-CLN-1-02 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900876649 | DO | 1 | 3 | 2017CP-1[2]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876650 | DO | 1 | 3 | 2017CP-4[5]Vib Damp Replace
FO_MISC |  | - | 900876651 | DO | 1 | 3 | 2017CP-1[8]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876652 | DO | 1 | 3 | 2017CP-1[12]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876653 | DO | 1 | 3 | 2017CP-1[16]Off Plumb Poles
FO_MISC |  | - | 900876654 | DO | 1 | 3 | 2017CP-1[18]Off Plumb Poles
FO_MISC |  | - | 900876655 | DO | 1 | 3 | 2017CP-1[22]Off Plumb Poles
FO_MISC |  | - | 900876656 | DO | 1 | 3 | 2017CP-2[22]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876657 | DO | 1 | 3 | 2017CP-6[23]Vib Damp Replace-All Phases
FO_MISC |  | - | 900876658 | DO | 1 | 3 | 2017CP-1[31]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876659 | DO | 1 | 3 | 2017CP-1[53]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876660 | DO | 1 | 3 | 2017CP-1[55]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876661 | DO | 1 | 3 | 2017CP-2[61]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876662 | DO | 1 | 3 | 2017CP-1[63]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876663 | DO | 1 | 3 | 2017CP-1[64]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876664 | DO | 1 | 3 | 2017CP-2[65]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876665 | DO | 1 | 3 | 2017CP-1[66]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876666 | DO | 1 | 3 | 2017CP-1[67]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876667 | DO | 1 | 3 | 2017CP-2[68]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876668 | DO | 1 | 3 | 2017CP-3[71]Vib Damp Replace-All Phases
FO_MISC |  | - | 900876669 | DO | 1 | 3 | 2017CP-2[72]Vib Damp Replace-Left & Mid
FO_MISC |  | - | 900876670 | DO | 1 | 3 | 2017CP-1[75]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876671 | DO | 1 | 3 | 2017CP-1[76]Vib Damp Replace-Left Phase
FO_MISC |  | - | 900876672 | DO | 1 | 3 | 2017CP-1[79]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876673 | DO | 1 | 3 | 2017CP-2[81]Vib Damp Replace-Mid & Right
FO_MISC |  | - | 900876674 | DO | 1 | 3 | 2017CP-2[83]Vib Damp Replace-Right Phase
FO_MISC |  | - | 900876675 | DO | 1 | 3 | 2017CP-1[84]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876676 | DO | 1 | 3 | 2017CP-1[86]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876677 | DO | 1 | 3 | 2017CP-1[87]Vib Damp Replace-Mid Phase
FO_MISC |  | - | 900876678 | DO | 1 | 3 | 2017CP-1[89]Vib Damp Replace
FO_MISC |  | - | 900876679 | DO | 1 | 3 | 2017CP-1[90]Vib Damp Replace
FO_MISC |  | - | 900876680 | DO | 1 | 3 | 2017CP-1[91]Vib Damp Replace
FO_MISC |  | - | 900876681 | DO | 1 | 3 | 2017CP-1[93]Vib Damp Replace
FO_MISC |  | - | 900876682 | DO | 1 | 3 | 2017CP-1[94]Vib Damp Replace
FO_MISC |  | - | 900876683 | DO | 1 | 3 | 2017CP-1[95]Vib Damp Replace
FO_MISC |  | - | 900876684 | DO | 1 | 3 | 2017CP-1[100]Vib Damp Replace-Right Phas
FO_MISC |  | - | 900876685 | DO | 1 | 3 | 2017CP-6[105]Vib Damp Replace
FO_MISC |  | - | 900876686 | DO | 1 | 3 | 2017CP-1[106]Vib Damp Replace
FO_MISC |  | - | 900876687 | DO | 1 | 3 | 2017CP-3[108]Vib Damp Replace
FO_MISC |  | - | 900876688 | DO | 1 | 3 | 2017CP-1[110]Vib Damp Replace
FO_MISC |  | - | 900876689 | DO | 1 | 3 | 2017CP-2[111]Vib Damp Replace
FO_MISC |  | - | 900876690 | DO | 1 | 3 | 2017CP-1[116]Vib Damp Replace
FO_MISC |  | - | 900876691 | DO | 1 | 3 | 2017CP-1[121]Vib Damp Replace
FO_MISC |  | - | 900876692 | DO | 1 | 3 | 2017CP-1[122]Off Plumb Insulators
FO_MISC |  | - | 900876693 | DO | 1 | 3 | 2017CP-2[123]Vib Damp Replace
FO_MISC |  | - | 900876694 | DO | 1 | 3 | 2017CP-4[124]Stays New stays to be dug
FO_MISC |  | - | 900876695 | DO | 1 | 3 | 2017CP-1[124]Off Plumb Insulators
FO_MISC |  | - | 900876696 | DO | 1 | 3 | 2017CP-2[124]Vib Damp Replace
FO_MISC |  | - | 900876697 | DO | 1 | 3 | 2017CP-1[127]Earths - Replace Lead
FO_MISC |  | - | 900897288 | CLO | 1 | 4 | 2017HP-1[103]Off Plumb -Poles
FO_MISC |  |  | 901084835 | DO | 1 | 2 | 2019HP-1[Stn]Insulator Broken
FO_MISC |  |  | 901084869 | DO | 1 | 3 | 2019HP-1[128]Earths-Replace Broken R/ph
FOSTRHW |  |  | 901086427 | DO | 1 | 3 | 2019HP-1[106]Replace Pole only -Rot
OS | CLN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASHLA DALTON
TO-20-CSH-DLT-1-01 ISO week: 47fr - 48fr Date: 20 Nov - 27 Nov Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
FOINSHW |  | - | 900564546 | DO | 2 | 1 | 2[166,167 ]Ins / H/D repl chk-Fi
FOINSHW |  | - | 900563143 | DO | 1 | 1 | 1[221]Ins & H/D repl chk-Fit Dup
TRAN |  | - | 900984695 | DO | 1 | 4 | 2018HP-1[9]Vib Dampers-Fatigue replace
TRAN |  | - | 900984733 | DO | 1 | 4 | 2018HP-1[212]Insulator-Off Plumb
OS | CSH | - | 900943159 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASHLA ENNIS
TO-20-CSH-ENN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-ENN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-CSH-ENN-1-02 ISO week: 25th - 26fr Date: 18 Jun - 26 Jun Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | CSH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | ENN | - |  | DO | 5 | 4 | 110kV MO Cubicle Ordinary Service
CA | ENN | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
220kV FEEDER - CASHLA FLAGFORD
TO-20-CSH-FLA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at flagford station in the Cashla 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement at Cashla station in the Flagford 220 kV bay (CB also to be replaced at remote end)
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 220 kV A1 @ CSH + CSH-FLA-1: Restring bay conductor to new CB
TO-20-CSH-FLA-1-04 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-FLA-1-06 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A1 @ FLA + CSH-FLA-1: Restring bay conductor DA to new CB
TO-20-CSH-FLA-1-07 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-08 Status: Unscheduled
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ FLA: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-FLA-1-10 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984858 | DO | 1 | 4 | 2018HP-1[am 247]Insulatorfit duplicates
FO_MISC |  |  | 901084304 | DO | 1 | 4 | 2019HP-1[134]Bird Nests
FO_MISC |  |  | 901084305 | DO | 1 | 4 | 2019HP-1[203]Bird Nests
FO_MISC |  |  | 901084306 | DO | 1 | 4 | 2019HP-1[210]Bird Nests
FO_MISC |  |  | 901084307 | DO | 1 | 4 | 2019HP-1[211]Bird Nests
FO_MISC |  |  | 901084308 | DO | 1 | 4 | 2019HP-1[212]Bird Nests
FO_MISC |  |  | 901084309 | DO | 1 | 4 | 2019HP-1[215]Bird Nests
FO_MISC |  |  | 901084310 | DO | 1 | 4 | 2019HP-1[240]Bird Nests
FO_MISC |  |  | 901084311 | DO | 1 | 4 | 2019HP-1[73]Bird Nests
FO_MISC |  |  | 901084312 | DO | 1 | 4 | 2019HP-1[78]Bird Nests
FO_MISC |  |  | 901084313 | CLO | 1 | 4 | 2019HP-1[80]Bird Nests
FO_MISC |  |  | 901084836 | DO | 1 | 4 | 2019HP-1[247]Insulator Fit Duplicate
OS | CSH | - | 900943133 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
OS | FLA | - | 900943176 | DO | 10 | 3 | 220kV MO Cubicle Ordinary Service
TO-20-CSH-FLA-1-09 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513., REL521
TO-20-CSH-FLA-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
110kV FEEDER - CASHLA GALWAY 1
TO-20-CSH-GAL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
TO-20-CSH-GAL-1-01 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 1 bay at Cashla station
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084837 | DO | 1 | 4 | 2019HP-1[12]Insulator Broken Insul
OS | CSH | - | 901042382 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | GAL | - | 901042209 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CSH-GAL-1-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remove droppers
TO-20-CSH-GAL-1-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-GAL-1: Remake droppers
110kV FEEDER - CASHLA GALWAY 2
TO-20-CSH-GAL-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-110K1-2 + CSH-GAL-2: Energise new Circuit Breaker replacement via the 110 kV Cashla Galway2 110 kV remote end feeder
TO-20-CSH-GAL-2-05 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
TO-20-CSH-GAL-2-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 110kV Circuit breaker replacement in the Galway 2 bay at Cashla station
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GAL | - | 901042210 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-CSH-GAL-2-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remove droppers
TO-20-CSH-GAL-2-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + CSH-GAL-2: Remake droppers
TO-20-CSH-GAL-2-06 ISO week: 24tu - 24th Date: 09 Jun - 11 Jun Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | LOU |  | 901139264 | CLO | 3 | 1 | Hotspot 1 (L1 Span 9/10) Left Midspan Joint (Repair by 27th Jul)
110kV FEEDER - CASHLA GALWAY 3
TO-20-CSH-GAL-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
TO-20-CSH-GAL-3-01 ISO week: 45we Date: 04 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GAL |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
220kV FEEDER - CASHLA PROSPECT
TO-20-CSH-PRO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
110kV FEEDER - CASHLA SALTHILL
TO-20-CSH-SAL-1-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084949 | DO | 2 | 4 | 2019HP-1[85]Off Plumb -plumb poles
PROX | SAL |  |  |  | 2 |  | Proximity for Salthil SA2 maintenance
AMCAB | SAL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SAL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - CASHLA T2101
TO-20-CSH-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-T2101-02 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
TO-20-CSH-T2101-03 ISO week: 26fr - 28fr Date: 26 Jun - 10 Jul Duration: 15 Days (11 WD) Status: Scheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH | TRAFO | 901038716 | DO | 8 | 2 | Cashla T2101: Corrosion on Fan Box. Replace
OS | CSH | 220 | 901129992 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CSH | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | CSH | TRAFO | 900944214 | CLO | 3 | 1 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
TRAFO | CSH | TRAFO | 900944679 | CLO | 3 | 1 | 220/110kV Trafo Tap Changer Inspection
TRANSFORMER - CASHLA T2102
TO-20-CSH-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required
TO-20-CSH-T2102-03 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 60 |  | Install Sprecher & Schuh type HPF-514 220 kV Circuit breaker replacement in the T2102 220 kV Bay at Cashla station
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ CSH + CSH-T2102: Remove droppers
TO-20-CSH-T2102-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous 220 kV B1 @ CSH + CSH-T2102: Lower the DA & DB pantographs Transfer all load to the A bar and switch out the B bar
TO-20-CSH-T2102-02 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | CSH | TRAFO | 901038717 | DO | 8 | 2 | Cashla T2102: Corrosion on Fan Box. Replace
OPT | CSH | 220 | 901038879 | DO | 1 | 4 | 220kV MO Cubicle Operational Test
OPT | CSH | 110 | 901038883 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
CORRECT | CSH | TRAFO | 901039321 | DO | 1 | 2 | Cashla T2102 Transformer: Drycol Replacement
OPT | CSH | TRAFO | 901045361 | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - CASHLA T2104
TO-20-CSH-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CSH | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CSH | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CSH | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
220kV FEEDER - CASHLA TYNAGH
TO-20-CSH-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-CSH-TY-1-05 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-TY-1-06 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required
TO-20-CSH-TY-1-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-09 Status: Unscheduled
CM | CSH | 220-DL | 901148822 | CLO | 2 | 1 | 01 Tynagh DL Fault
TO-20-CSH-TY-1-07 Status: Unscheduled
CAPX |  |  | CP1019 | DO | 7 |  | Fibre wrapping of the line - to be installed on OPGW earthwire
TO-20-CSH-TY-1-03 ISO week: 16th - 21th Date: 16 Apr - 21 May Duration: 36 Days (25 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985040 | DO | 1 | 4 | 2018HP-1[104]Vib DampersR/Ph
FO_MISC |  |  | 901084267 | DO | 1 | 4 | 2019HP-1[57]Bird Nests
FO_MISC |  |  | 901084268 | DO | 1 | 4 | 2019HP-1[107]Bird Nests
OPT | CSH | - | 901038878 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
YM03 | TYN | - | 900979523 | DO | 3 | 4 | DISC CONTACTS DAMAGED
OPT | TYN | - | 901039106 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CASTLEBAR 110SA1-2CB
TO-20-CBR-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | CBR | - | 901039130 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CASTLEBAR CLOON
TO-20-CBR-CLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085138 | DO | 3 | 4 | 2019HP-3[279,280,282]Vib Dampers -EW V/D
FO_STDMG |  | - | 901038334 | DO | 2 | 4 | 2018CP-1[72]Crossarm -Replace
FO_MISC |  |  | 901085137 | DO | 2 | 4 | 2019HP-2[59, 60]Vib Dampers -Replace
TRAN |  | - | 900985121 | DO | 1 | 4 | 2018HP-1[164]Vib Dampers-Fatigue replace
TRAN |  | - | 900985122 | DO | 1 | 4 | 2018HP-1[165]Vib Dampers-Fatigue replace
FO_MISC |  | - | 901038297 | DO | 1 | 4 | 2018CP-1[3]Off Plumb -Poles
FO_MISC |  | - | 901038298 | DO | 1 | 4 | 2018CP-1[12]Off Plumb -Poles
FO_MISC |  | - | 901038299 | DO | 1 | 4 | 2018CP-1[15]Off Plumb -Poles
FO_MISC |  | - | 901038300 | DO | 1 | 4 | 2018CP-1[15]Insulator -Off Plumb
FO_MISC |  | - | 901038301 | DO | 1 | 4 | 2018CP-1[17]Off Plumb -Poles
FO_MISC |  | - | 901038302 | DO | 1 | 4 | 2018CP-1[18]Off Plumb -Poles
FO_MISC |  | - | 901038303 | DO | 1 | 4 | 2018CP-1[19]Off Plumb -Poles
FO_MISC |  | - | 901038304 | DO | 1 | 4 | 2018CP-1[20]Off Plumb -Poles
FO_MISC |  | - | 901038305 | DO | 1 | 4 | 2018CP-1[21]Off Plumb -Poles
FO_MISC |  | - | 901038306 | DO | 1 | 4 | 2018CP-1[21]Insulator -Off Plumb
FO_MISC |  | - | 901038310 | DO | 1 | 4 | 2018CP-1[28]Vibration Dampers
FO_MISC |  | - | 901038311 | DO | 1 | 4 | 2018CP-1[30]Vibration Dampers
FO_STDMG |  | - | 901038312 | DO | 1 | 4 | 2018CP-1[30]Found/Site repair
FO_MISC |  | - | 901038313 | DO | 1 | 4 | 2018CP-1[31]Vibration Dampers
FO_MISC |  | - | 901038317 | DO | 1 | 4 | 2018CP-1[36]Anti Split Bolts
FO_STDMG |  | - | 901038319 | DO | 1 | 4 | 2018CP-1[43]Pole Bolt -Tighten
FO_MISC |  | - | 901038320 | DO | 1 | 4 | 2018CP-1[49]Off Plumb -Poles
FO_STDMG |  | - | 901038322 | DO | 1 | 4 | 2018CP-1[63]Pole Bolt -Tighten
FO_STDMG |  | - | 901038323 | DO | 1 | 4 | 2018CP-1[65]Pole Bolt -Tighten
FO_STDMG |  | - | 901038324 | DO | 1 | 4 | 2018CP-1[66]Pole Bolt -Tighten
FO_MISC |  | - | 901038327 | DO | 1 | 4 | 2018CP-1[82]Insulator -Off Plumb
FO_MISC |  | - | 901038328 | DO | 1 | 4 | 2018CP-1[77]Ubolts -Level
FO_MISC |  | - | 901038329 | DO | 1 | 4 | 2018CP-1[75]Insulator -Broken Disk
FO_MISC |  | - | 901038330 | DO | 1 | 4 | 2018CP-1[75]Anti Split Bolts
FO_MISC |  | - | 901038333 | DO | 1 | 4 | 2018CP-1[73]Anti Split Bolts
FO_MISC |  | - | 901038335 | DO | 1 | 4 | 2018CP-1[100]Off Plumb -Poles
FO_MISC |  | - | 901038336 | DO | 1 | 4 | 2018CP-1[101]Off Plumb -Poles
FO_MISC |  | - | 901038337 | DO | 1 | 4 | 2018CP-1[103]Off Plumb -Poles
FO_MISC |  | - | 901038338 | DO | 1 | 4 | 2018CP-1[105]Off Plumb -Poles
FO_MISC |  | - | 901038339 | DO | 1 | 4 | 2018CP-1[106]Off Plumb -Poles
FO_STDMG |  | - | 901038340 | DO | 1 | 4 | 2018CP-1[106]Found/Site repair
FO_MISC |  | - | 901038341 | DO | 1 | 4 | 2018CP-1[106]Insulator -Off Plumb
FO_STDMG |  | - | 901038342 | DO | 1 | 4 | 2018CP-1[108]Crossarm
FO_MISC |  | - | 901038343 | DO | 1 | 4 | 2018CP-1[109]Off Plumb -Poles
FO_MISC |  | - | 901038344 | DO | 1 | 4 | 2018CP-1[111]Off Plumb -Poles
FO_MISC |  | - | 901038345 | DO | 1 | 4 | 2018CP-1[111]Anti Split Bolts
FO_MISC |  | - | 901038346 | DO | 1 | 4 | 2018CP-1[114]Off Plumb -Poles
FO_MISC |  | - | 901038347 | DO | 1 | 4 | 2018CP-1[114]Insulator -Off Plumb
FO_MISC |  | - | 901038350 | DO | 1 | 4 | 2018CP-1[118]Off Plumb -Poles
FO_MISC |  | - | 901038351 | DO | 1 | 4 | 2018CP-1[119]Off Plumb -Poles
FO_STDMG |  | - | 901038353 | DO | 1 | 4 | 2018CP-1[121]Crossarm -Replace Bolt
FO_STDMG |  | - | 901038354 | DO | 1 | 4 | 2018CP-1[122]Crossarm -Tighten Bolt
FO_MISC |  | - | 901038355 | DO | 1 | 4 | 2018CP-1[123]Off Plumb -Poles
FO_MISC |  | - | 901038357 | DO | 1 | 4 | 2018CP-1[127]Off Plumb -Poles
FO_STDMG |  | - | 901038358 | DO | 1 | 4 | 2018CP-1[127]Found/Site repair -Sleepers
FO_MISC |  | - | 901038359 | DO | 1 | 4 | 2018CP-1[128]Off Plumb -Poles
FO_STDMG |  | - | 901038360 | DO | 1 | 4 | 2018CP-1[137]Pole Bolt -Replace
FO_MISC |  | - | 901038361 | DO | 1 | 4 | 2018CP-1[139]Off Plumb -Poles
FO_STDMG |  | - | 901038362 | DO | 1 | 4 | 2018CP-1[139]Crossarm
FO_MISC |  | - | 901038363 | DO | 1 | 4 | 2018CP-1[140]Off Plumb -Poles
FO_STDMG |  | - | 901038364 | DO | 1 | 4 | 2018CP-1[140]Crossarm
FO_STDMG |  | - | 901038366 | DO | 1 | 4 | 2018CP-1[147]Pole Bolt -Tighten
FO_MISC |  | - | 901038367 | DO | 1 | 4 | 2018CP-1[150]Vibration Dampers -Required
FO_MISC |  | - | 901038368 | DO | 1 | 4 | 2018CP-1[156]Stepbolts -Remove
FO_STDMG |  | - | 901038369 | DO | 1 | 4 | 2018CP-1[157]Pole Bolt -Tighten
FO_MISC |  | - | 901038370 | DO | 1 | 4 | 2018CP-1[157]Insulator -Off Plumb
FO_STDMG |  | - | 901038376 | DO | 1 | 4 | 2018CP-1[4]Pole Bolt -Bent
FO_MISC |  | - | 901038377 | DO | 1 | 4 | 2018CP-1[11]Earths - Replace -Bolt bent
FO_STDMG |  | - | 901038378 | DO | 1 | 4 | 2018CP-1[43]Pole Bolt -Bent
FO_STDMG |  | - | 901038383 | DO | 1 | 4 | 2018CP-1[165]Found/Site repair
FO_MISC |  | - | 901038385 | DO | 1 | 4 | 2018CP-1[178]Insulator -Off Plumb
FO_MISC |  | - | 901038388 | DO | 1 | 4 | 2018CP-1[187]Anti-Cl. Guard
FO_MISC |  | - | 901038393 | DO | 1 | 4 | 2018CP-1[214]Off Plumb -Poles
FO_MISC |  | - | 901038394 | DO | 1 | 4 | 2018CP-1[214]Insulator -Off Plumb
FO_MISC |  | - | 901038395 | DO | 1 | 4 | 2018CP-1[218]Off Plumb -Poles
FO_MISC |  | - | 901038396 | DO | 1 | 4 | 2018CP-1[218]Insulator -Off Plumb
FO_MISC |  | - | 901038400 | DO | 1 | 4 | 2018CP-1[233]Insulator -Off Plumb
FO_MISC |  | - | 901038403 | DO | 1 | 4 | 2018CP-1[246]Anti-Cl. Guard
FO_COND |  | - | 901038405 | DO | 1 | 4 | 2018CP-1[246]Conductor Check
FO_MISC |  | - | 901038418 | DO | 1 | 4 | 2018CP-1[260]Vibration Dampers -Replace
FO_MISC |  | - | 901038436 | DO | 1 | 4 | 2018CP-1[287]Off Plumb -Poles
FO_MISC |  | - | 901038437 | DO | 1 | 4 | 2018CP-1[288]Off Plumb -Poles
FO_STDMG |  | - | 901038443 | DO | 1 | 4 | 2018CP-1[277]Pole Bolt -Bent
FO_STDMG |  | - | 901038444 | DO | 1 | 4 | 2018CP-1[279]Pole Bolt -Bent
FO_MISC |  |  | 901084839 | DO | 1 | 4 | 2019HP-1[53]Insulator Broken Aux Insul
OS | CBR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CBR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | CLN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CASTLEBAR DALTON
TO-20-CBR-DLT-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CBR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | DLT | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CAPACITOR/SVC/REACTOR - CASTLEBAR SVC
TO-20-CBR-SVC-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0331 | DO | 28 |  | SVC Refurbishment
TO-20-CBR-SVC-02 ISO week: 45mo - 46tu Date: 02 Nov - 10 Nov Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SJ511, CPR097
OS | CBR | - | 901042289 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CBR | - | 901042362 | DO | 3 | 4 | Capacitor/SVC Ordinary Service
CA | CBR | SVC | 901050222 | CLO | 2 | 4 | Capacitor: measurement of can values, detailed checks & HV bay condition assessment
BUSBAR SECTION - CLOON 110 kV A2
TO-20-110 kV A2 @ CLN-01 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PR0001 |  | 2 |  | Proximity for EI of CLN T142
SECTIONALISING DISCONNECT - CLOON 110SA1
TO-20-CLN-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of CLN-110SA2: 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - CLOON 110SA2
TO-20-CLN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
OS | CLN | SA2 | 901039700 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CLOON LANESBORO
TO-20-CLN-LA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-LA-1-03 Status: Unscheduled
[5 empty] | 2 |  | Proximity for EI of CLN T142
TO-20-CLN-LA-1-04 Status: Unscheduled
CORRECT | LA | - | 900957961 | CANC | 3 | 1 | Repair fault busbar disconnect
TO-20-CLN-LA-1-05 Status: Unscheduled
FO_MISC |  | - | 900819454 | CANC | 1 | 2 | 2016HP-1[97]Stays - Check Check stays
TO-20-CLN-LA-1-01 ISO week: 42mo - 42fr Date: 12 Oct - 16 Oct Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085132 | DO | 1 | 4 | 2019HP-1[97]Stays-Replace Broken
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
OS | CLN | - | 901042219 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | LA | - | 901042220 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - CLOON T142 [SDCC]
TO-20-CLN-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-T142-02 ISO week: 26th - 26fr Date: 25 Jun - 26 Jun Duration: 2 Days (2 WD) Status: Reference (Tentative)
|  |  | PR0001 |  | 2 |  | EI of CLN T142 request from RC
CAPACITOR/SVC/REACTOR - DALTON CAP1
TO-20-DLT-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
TO-20-DLT-CAP1-02 Status: Unscheduled
CORRECT | DLT |  | 900945902 | CANC |  | 1 | Hot Spots Hot spot detected please refer
GENERATOR TRANSFORMER - DERRYBRIEN T121 [Derrybrien DY1]
TO-20-DYN-T121-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-DYN-1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-DYN-T121-01 Status: Reference (Unscheduled)
CAPX |  |  | CP0824 | DO | 5 |  | As a consequence of AGL-DYN-1: Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-DYN-T121-03 ISO week: 37mo - 37sa Date: 07 Sep - 12 Sep Duration: 6 Days (5 WD) Status: Reference
As a consequence of AGL-DYN-110kV
COUPLER/SECTIONALISING CB - GALWAY 110K1-2
TO-20-GAL-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-2-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K1-3
TO-20-GAL-110K1-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K1-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - GALWAY 110K2-3
TO-20-GAL-110K2-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | GAL | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GAL | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GAL | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-GAL-110K2-3-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
110kV FEEDER - GALWAY KNOCKRANNY
TO-20-GAL-KNY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
TO-20-GAL-KNY-1-01 ISO week: 11th Date: 12 Mar Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GAL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
CORRECT | GAL |  | 901080915 | CLO | 1 | 1 | O1 Knockranny CB low gas
110kV FEEDER - GALWAY SALTHILL
TO-20-GAL-SAL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
TO-20-GAL-SAL-1-01 ISO week: 45mo - 45tu Date: 02 Nov - 03 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612, GRL100
OPT | GAL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | SAL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GALWAY T101 [SDCC]
TO-20-GAL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
DISTRIBUTION TRANSFORMER - GALWAY T102 [SDCC]
TO-20-GAL-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T141 [SDCC]
TO-20-GAL-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - GALWAY T142 [SDCC]
TO-20-GAL-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ GAL: Proximity outage for work on Galway 110kV K1-2 Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - GALWAY T143 [SDCC]
TO-20-GAL-T143-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K2-3 Sect / Dist Ordinary Service (SA3)
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A3 @ GAL: Proximity outage for work on Galway 110kV K1-3 Sect / Dist Ordinary Service (SA3)
BUSBAR SECTION - KNOCKRANNY 110 kV A1
TO-20-110 kV A1 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV A2
TO-20-110 kV A2 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV B1
TO-20-110 kV B1 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KNOCKRANNY 110 kV B2
TO-20-110 kV B2 @ KNY-01 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
CAPACITOR/SVC/REACTOR - KNOCKRANNY FILTER1
TO-20-KNY-FILTER1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KNY | - | 901146372 | DO | 5 | 4 | HV Filter Ordinary Service
110kV FEEDER - KNOCKRANNY SALTHILL
TO-20-KNY-SAL-1-01 ISO week: 15tu - 15we Date: 07 Apr - 08 Apr Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CM | SAL | 110 | 901129456 | CANC | 2 | 1 | Visual inspection of HIS HV cable sealing end
TO-20-KNY-SAL-1-02 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
OPT | KNY | - | 900858560 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
AMCAB | SAL | - |  | DO | 2 | 1 | CSE Inspection, ref. Galway cubicle CSE Failure in Salthill (FO 19-26)
110kV FEEDER - KNOCKRANNY SCREEBE [SDCC]
TO-20-KNY-SCR-1-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | KNY | - | 901006383 | DO | 2 | 2 | Annual Insp. 110kV Feeder XLPE Cable
TO-20-KNY-SCR-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Reference
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KNY | - | 900942465 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
110kV FEEDER - KNOCKRANNY UGGOOL
TO-20-KNY-UGL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - SALTHILL 110SA1-2CB
TO-20-SAL-110SA1-2CB-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ611
OS | SAL | 110-SA2 | 900944542 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service
DISTRIBUTION TRANSFORMER - SALTHILL T102 [SDCC]
TO-20-SAL-T102-01 ISO week: 36tu - 36fr Date: 01 Sep - 04 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | SAL |  |  |  | 2 |  | Proximity for SA2 Maintenance
110kV FEEDER - SOMERSET tee CASHLA
TO-20-SOM,T-CSH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla Shannonbridge 110 kV bay at cashla station.
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-CSH-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-CSH-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084838 | DO | 2 | 4 | 2019HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900727084 | DO | 1 | 1 | 2015HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900902253 | DO | 1 | 3 | 2017CP-1[87]Off Plumb Poles
FO_STDMG |  | - | 900902255 | DO | 1 | 3 | 2017CP-1[95]Found/Site repair -Sleeper
FO_MISC |  | - | 900902263 | CLO | 1 | 3 | 2017CP-1[173]Off Plumb Poles
FO_MISC |  | - | 900902264 | CLO | 1 | 3 | 2017CP-1[175]Off Plumb Poles
FO_MISC |  | - | 900902266 | DO | 1 | 3 | 2017CP-1[184]Off Plumb Insuls
FO_MISC |  | - | 900902268 | CLO | 1 | 3 | 2017CP-1[220]Off Plumb Insuls
TRAN |  | - | 900984945 | DO | 1 | 4 | 2018HP-1[152]Foundation/Site repair-stay
FO_MISC |  |  | 901084265 | CLO | 1 | 4 | 2019HP-1[181]Bird Nests
FO_MISC |  |  | 901084266 | CLO | 1 | 4 | 2019HP-1[260]Bird Nests
CORRECT | CSH |  | 900907890 | DO | 1 | 1 | Counter not working. To be replaced.
OPT | CSH | - | 901076462 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
COUPLER/SECTIONALISING CB - UGGOOL 110SA1-2CB
TO-20-UGL-110SA1-2CB-01 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110-SA1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - UGGOOL T131 [Uggool]
TO-20-UGL-T131-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T131-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T132 [Seecon]
TO-20-UGL-T132-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-UGL-T132-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | As a consequnce of Knockranny - Uggool 110kV
GENERATOR TRANSFORMER - UGGOOL T134 [Seecon]
TO-20-UGL-T134-01 ISO week: 37mo Date: 07 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | UGL | - | 900942781 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-UGL-T134-02 ISO week: 37tu Date: 08 Sep Duration: 1 Day (1 WD) Status: Scheduled
As a consequnce of Knockranny - Uggool 110kV

## ENNISCORTHY (Rgn)
BUSBAR SECTION - ARKLOW 110 kV A1
TO-20-110 kV A1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV A2
TO-20-110 kV A2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV B1
TO-20-110 kV B1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 110 kV B2
TO-20-110 kV B2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV A1
TO-20-220 kV A1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV A2
TO-20-220 kV A2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV B1
TO-20-220 kV B1 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ ARK: Busbar Changeover
BUSBAR SECTION - ARKLOW 220 kV B2
TO-20-220 kV B2 @ ARK-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ ARK: Busbar Changeover
COUPLER/SECTIONALISING CB - ARKLOW 220K1-2
TO-20-ARK-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | ARK | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
110kV FEEDER - ARKLOW BALLYBEG
TO-20-ARK-BEG-1-01 ISO week: 9tu - 9we Date: 25 Feb - 26 Feb Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084881 | CLO | 2 | 2 | 2019HP-1[51]Insulator Broken Lower/ph
OPT | BEG | - | 901129646 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARKLOW BANOGE
TO-20-ARK-BOG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085135 | DO | 1 | 2 | 2019HP-1[129]Vib Dampers EW Damper
CM | ARK | 110-DL | 901134734 | DO | 2 | 1 | R phase Banoge 110kV CubicleDL., R phase connectio hotpot repair due by 17thAugust 2020
OPT | BOG | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - ARKLOW CARRICKMINES GIS
TO-20-ARK-CKM GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CKM |  | 900532102 | CANC |  | 2 | ESBi Repeat Insulation Tests on VT all p
TO-20-ARK-CKM GIS-1-01 ISO week: 22mo - 42fr Date: 25 May - 16 Oct Duration: 145 Days (103 WD) Status: Forced Out
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
YM03 |  | - | 900979480 | CLO | 1 | 2 | Timber HAZCNF_20M (122-123)
CM | ARK | - | 901134735 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GISbushing connection DUE : 17-Nov-20
CM | ARK | - | 901134736 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GIS Copper earth strap DUE : 17-Jul-20
CM | ARK | 110-DL | 901134737 | DO | 2 | 1 | T phase Carrickmines 220kVCubicle. T phase GIS Copper earth strp hotspot DUE : IMMEDIATELY
YM03 | ARK | - | 900978744 | CANC | 1 | 2 | Replace SF6 density gauge on GIS to AIS
OPT | ARK | - | 901039045 | DO | 1 | 3 | 220kV GIS Cubicle Operational Test
OS | CKM | - | 901042325 | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | CKM |  | 900596268 | DO | 2 | 2 | 01 outage required. Hot Spots
220kV FEEDER - ARKLOW LODGEWOOD
TO-20-ARK-LWD-1-03 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
MC0335 | [6 empty] | Proximity outage of the Arklow Lodgewood
TO-20-ARK-LWD-1-01 ISO week: 40we - 42fr Date: 30 Sep - 16 Oct Duration: 17 Days (13 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084299 | DO | 1 | 2 | 2019HP-1[21]Bird Nests remove birds nest
CORRECT | ARK |  | 900908600 | DO |  | 2 | Wire in low air alarm as per original de
OPT | LWD | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CM | LWD | - | 901134792 | DO | 1 | 1 | T Phase Arklow 220kV Cubicle. T Phase VT connection DUE : 17-Jul-20
110kV FEEDER - ARKLOW SHELTON ABBEY 2
TO-20-ARK-SHE-2-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
Proximity to allow ESBN to replace corroded gantry in Shelton Abbey Compound
OS | ARK | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | SHE | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TRANSFORMER - ARKLOW T2101
TO-20-ARK-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | ARK | 110 |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
SECTIONALISING DISCONNECT - BALLYBEG 110SA2
TO-20-BEG-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | BEG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - BALLYBEG CARRICKMINES GIS
TO-20-BEG-CKM GIS-1-01 ISO week: 46tu - 46fr Date: 10 Nov - 13 Nov Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
YM03 |  | - | 900979776 | DO | 1 | 4 | 2018HP-1[104]Foundation/Site repair
OS | BEG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CKM | - | 900944045 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
110kV FEEDER - BALLYWATER CRANE [Ballywater BW1]
TO-20-BWR-CRA-1-01 ISO week: 23tu Date: 02 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA513
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CRA |  | 901129684 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BANOGE CRANE
TO-20-BOG-CRA-1-01 ISO week: 48fr Date: 27 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BOG | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CRA | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CASTLEDOCKRELL LODGEWOOD [Castledockrell CK1]
TO-20-CDK-LWD-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-CDK-LWD-1-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SA612
OS | LWD | - | 901129863 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | LWD | - | 901129181 | CLO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - CASTLEDOCKRELL T121 [Castledockrell CK1]
TO-20-CDK-T121-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CDK-LWD-1: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
110kV FEEDER - CRANE LODGEWOOD
TO-20-CRA-LWD-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-CRA-LWD-1-01 ISO week: 31mo - 31we Date: 27 Jul - 29 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900563038 | DO | 1 | 3 | 1[14]Off Plumb
FO_MISC |  | - | 900819497 | DO | 1 | 3 | 2016HP-1[14]Off Plumb Straighten P-set
FO_MISC |  | - | 900898042 | DO | 1 | 3 | 2017HP-1[14]Off Plumb -Poles
TRAN |  | - | 900985977 | DO | 1 | 4 | 2018HP-1[14]Off Plumb
TRAN |  | - | 900985979 | DO | 1 | 4 | 2018HP-1[25]Off Plumb
TRAN |  | - | 900985980 | DO | 1 | 4 | 2018HP-1[26]Off Plumb
FO_MISC |  |  | 901090924 | DO | 1 | 2 | 2019HP-1[14]Off Plumb -plumb poles
NOTE | [6 empty] | Final confirmaton on 25th of July regarding land access
AMCAB | CRA | - | 901113582 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CRA |  | 901129686 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CM | CRA | - | 901132793 | CLO | 1 | 2 | Inspect Pfisterer CSE and record serial number
OPT | LWD |  | 901129595 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CRANE WEXFORD
TO-20-CRA-WEX-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
TO-20-CRA-WEX-1-02 ISO week: 25we - 26we Date: 17 Jun - 24 Jun Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900902495 | DO | 3 | 2 | 2017CP-3[13, 24, 25]Off Plumb -Poles
FO_MISC |  | - | 900902451 | CLO | 1 | 2 | 2017CP-1[106]Off Plumb Insulator
FO_MISC |  | - | 900902473 | CLO | 1 | 2 | 2017CP-1[38]Shear Block - Repair
FO_STDMG |  | - | 900902474 | CLO | 1 | 2 | 2017CP-1[38]Replace Member -Bar 225
FO_MISC |  | - | 900902506 | CLO | 1 | 2 | 2017CP-1[106]Off Plumb -Poles
OPT | CRA |  | 901129685 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | WEX | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | WEX | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
110kV FEEDER - CRORY LODGEWOOD [SDCC]
TO-20-CRY-LWD-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA611, 7SJ804
OS | LWD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - CRORY T121 [SDCC]
TO-20-CRY-T121-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of CRY-LWD-1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
220kV FEEDER - CULLENAGH GREAT ISLAND GIS
TO-20-CUL-GI GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
TO-20-CUL-GI GIS-1-02 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
TO-20-CUL-GI GIS-1-06 Status: Unscheduled
FO_MISC |  | - | 900855588 | CANC | 3 | 2 | Line Towers 35 - Replace angle insulator
OS | CUL | - | 900943447 | CANC | 6 | 3 | 220kV SF6 Cubicle Ordinary Service
CA | CUL | - | 900943872 | CANC | 3 | 3 | 220kV Cubicle Condition Assessment
AMCAB | GI | - | 901006385 | CANC | 2 | 2 | Cable Insp. 110kV XLPE
OPT | GI | - | 900840902 | CANC | 1 | 3 | 220kV MO Cubicle Operational Test
TO-20-CUL-GI GIS-1-04 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Proposed
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
FO_MISC |  | - | 900855589 | DO | 2 | 2 | Line Towers 35 & 36 (Angle & Intermediate) - Replace intermediate insulators and measurement of existing strain insulator chain length
FOINSHW |  |  | 901086391 | DO | 2 | 2 | 2019HP-3[27,28,29]Clean Insulators
BUSBAR SECTION - GREAT ISLAND 110 kV A1
TO-20-110 kV A1 @ GI-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND 110 kV A2
TO-20-110 kV A2 @ GI-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV A2 @ GI-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects.
BUSBAR SECTION - GREAT ISLAND 110 kV B1
TO-20-110 kV B1 @ GI-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND 110 kV B2
TO-20-110 kV B2 @ GI-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0002 | DO | 1 |  | Busbar Changeover
TO-20-110 kV B2 @ GI-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 IN TURN @ GI: Install busbar fixed contacts for the new pantograph disconnects.
COUPLER/SECTIONALISING CB - GREAT ISLAND 110K1-2
TO-20-GI-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-110K1-2-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GI | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
BUSBAR SECTION - GREAT ISLAND GIS 220 kV A1
TO-20-220 kV A1 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV A2
TO-20-220 kV A2 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV B1
TO-20-220 kV B1 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GREAT ISLAND GIS 220 kV B2
TO-20-220 kV B2 @ GI GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220K1
TO-20-GI GIS-220K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220K2
TO-20-GI GIS-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SA1-2CB
TO-20-GI GIS-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV A1 @ GI GIS: Busbar Changeover
TO-20-GI GIS-220SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SB1-2CB
TO-20-GI GIS-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B2 @ GI GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 220 kV B1 @ GI GIS: Busbar Changeover
220kV FEEDER - GREAT ISLAND GIS KELLIS
TO-20-GI GIS-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 901050728 | DO | 12 | 4 | Repair earth on 24 DC towers
FO_MISC |  | - | 900898107 | DO | 1 | 3 | 2017HP-1[196]Earths-Check earth bond top
FO_MISC |  | - | 900898108 | DO | 1 | 3 | 2017HP-1[207]Earths-Check earth bond top
FO_MISC |  | - | 900898109 | DO | 1 | 3 | 2017HP-1[214]Vib Damps EW damper fatigue
TRAN |  | - | 900987495 | DO | 1 | 4 | 2018HP-1[117]Insulatorbroken insulator
TRAN |  | - | 900987496 | DO | 1 | 4 | 2018HP-1[216]Insulatorbroken insulator
FO_MISC |  |  | 901085220 | DO |  | 2 | 2019HP-1[211]Vib Dampers EW VD fatigued
FO_MISC |  |  | 901085221 | DO |  | 4 | 2019HP-1[212]Vib Dampers EW VD fatigued
OS | GI | - | 901042324 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
AMCAB | GI | 220 | 901006258 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
OS | KLS | - | 901042334 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
220kV FEEDER - GREAT ISLAND GIS LODGEWOOD
TO-20-GI GIS-LWD-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FOINSHW |  | - | 900898158 | CLO | 2 | 2 | 2017HP-3[73/76]Insul & HW replace check
FO_MISC |  |  | 901084416 | CLO | 1 | 2 | 2019HP-1[39]Bird Nests remove birds nest
FO_MISC |  |  | 901084417 | CLO | 1 | 2 | 2019HP-1[67]Bird Nests remove birds nest
FO_MISC |  |  | 901084418 | CLO | 1 | 2 | 2019HP-1[68]Bird Nests remove birds nest
FOSTRHW |  |  | 901086406 | DO |  | 2 | 2019HP-1[1]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086407 | DO |  | 2 | 2019HP-1[2]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086408 | DO |  | 2 | 2019HP-1[3]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086409 | DO |  | 2 | 2019HP-1[4]Check Structure -Contact E&MP
FOSTRHW |  |  | 901086410 | DO |  | 2 | 2019HP-1[5]Check Structure -Contact E&MP
GENERATOR TRANSFORMER - GREAT ISLAND GIS T2004 [SSE Generation Ireland GI4]
TO-20-GI GIS-T2004-01 ISO week: 40th - 41fr Date: 01 Oct - 09 Oct Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage request for Telemess 01/10-09/10
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
110kV FEEDER - GREAT ISLAND KILKENNY
TO-20-GI-KKY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 100 |  | Circuit and Bay works at Kilkenny & Great Island
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous CUL-GI GIS-1 + GI-KKY-1: Proximity outage 2 Stringing works at crossing point
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-KKY-1-04 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 1 |  | EI: Simultaneous GI-KKY-1 + GI-KKY-1: Energisation of circuit
TO-20-GI-KKY-1-05 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ KKY: Proximity outage for work on Kilkenny 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084415 | CLO | 1 | 2 | 2019HP-1[89]Bird Nests remove birds nest
FO_MISC |  |  | 901084980 | CLO |  | 2 | 2019HP-1[112]Off Plumb -plumb poles
FO_MISC |  |  | 901084981 | CLO |  | 2 | 2019HP-1[116]Off Plumb -plumb poles
FOSTRHW |  |  | 901086403 | CLO |  | 2 | 2019HP-1[15]Check Structure struct & HW
FOSTRHW |  |  | 901086404 | CLO |  | 2 | 2019HP-1[16]Check Structure struct & HW
FOSTRHW |  |  | 901086405 | CLO |  | 2 | 2019HP-1[129]Check Structure -Check Rot
CORRECT | GI |  | 901068754 | CLO |  | 2 | 110kV CTVTs Restest: Sphase .96% PF, TPh
CORRECT | KKY |  | 901072125 | CLO | 5 | 1 | surge counter unreadable , gas gauge rot
CORRECT | KKY |  | 901090669 | CLO | 5 | 1 | manometer needs replacing
CM | KKY |  | 901133697 | CLO | 3 | 1 | Replacement of Stolen Earths
TO-20-GI-KKY-1-07 ISO week: 41we - 42th Date: 07 Oct - 15 Oct Duration: 9 Days (7 WD) Status: Scheduled
TRAN |  | - | 900987497 | DO | 2 | 4 | 2018HP-1[10]Off Plumb
TRAN |  | - | 900987502 | DO | 2 | 4 | 2018HP-1[112]Off Plumb
TRAN |  | - | 900987503 | DO | 2 | 4 | 2018HP-1[113]Off Plumb
| GRI | - | 901160926 | DO | 3 | 1 | Follow on work to replace stolen earths after copper theft
OS | KKY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-20-GI-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to remove EM1
TO-20-GI-T141-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 4 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to erect EM1
TO-20-GI-T141-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0945 | DO | 6 |  | Simultaneous GI-KKY-1 + GI-T141: Works on EM1 to pull conductor
DISTRIBUTION TRANSFORMER - GREAT ISLAND T142 [SDCC]
TO-20-GI-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-T142-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Reference
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
TRANSFORMER - GREAT ISLAND T2101
TO-20-GI-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | GI | TRAFO | 901038643 | CANC | 2 | 2 | Camlin is to replace faulty transformer online oil DGA monitor on T2101 in Gt Island station.
CORRECT | GI | TRAFO | 901028698 | CANC | 1 | 2 | CREST Analysis of Paint Samples on T2101 220kV Station.
TO-20-GI-T2101-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | GI | 220 |  | DO | 2 | 4 | Cable Insp. 220kV Feeder XLPE
OPT | GI | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | GI | TRAFO |  | DO | 1 | 3 | 220/110 & 275/220 Trafo Operational Test
CORRECT | GI |  | 900943754 | DO |  | 2 | LOWER FAN BOX FIXING BROKEN....FIX
TRANSFORMER - GREAT ISLAND T2102
TO-20-GI-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-T2102-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GI | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | GI | TRAFO | 901039261 | CLO | 1 | 2 | Great Island T2102:Replace faulty oil level gauge Replace all fans Retest overall tan deltas Treat corrosion
110kV FEEDER - GREAT ISLAND WATERFORD 1
TO-20-GI-WAT-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727280 | CANC | 1 | 1 | 2015HP-1[37]Off Plumb Pole
TO-20-GI-WAT-1-05 Status: Unscheduled
FO_MISC |  | - | 900853147 | CANC | 3 | 2 | Check (General)-Painting Req. Tower 50 & 51
110kV FEEDER - GREAT ISLAND WATERFORD 2
TO-20-GI-WAT-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage Stringing works at crossing point
TO-20-GI-WAT-2-03 Status: Unscheduled
CAPX |  |  | CP0945 | DO | 5 |  | Simultaneous GI-KKY-1 + GI-WAT-2: Proximity outage 2 Stringing works at crossing point
TO-20-GI-WAT-2-05 Status: Unscheduled
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A1 @ WAT: Proximity outage for work on Waterford 110kV Sect / Dist Ordinary Service (SA1)
TO-20-GI-WAT-2-01 Status: Unscheduled
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-WAT-2-04 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900650529 | CLO | 1 | 2 | 2014HP-1[8]Off Plumb
FO_MISC |  | - | 900650531 | CLO | 1 | 2 | 2014HP-1[11]Off Plumb
FO_MISC |  | - | 900650532 | CLO | 1 | 2 | 2014HP-1[14]Off Plumb
FO_MISC |  | - | 900650533 | CLO | 1 | 2 | 2014HP-1[15]Off Plumb
FO_MISC |  | - | 900650534 | CLO | 1 | 2 | 2014HP-1[16]Off Plumb
FOSTRHW |  | - | 900650536 | CLO | 1 | 2 | 2014HP-1[26]Check Structure split in RHP
FOSTRHW |  | - | 900650537 | CLO | 1 | 2 | 2014HP-1[27]Check Structure split in RHP
FO_MISC |  | - | 900683451 | CLO | 1 | 2 | 1[50] Insulators Off Plumb
FO_MISC |  |  | 901084982 | CLO |  | 2 | 2019HP-1[11]Off Plumb -plumb poles
FOINSHW |  |  | 901085556 | CLO |  | 2 | 2019HP-1[18]Insul&HW Replac check
FOINSHW |  |  | 901085557 | CLO |  | 2 | 2019HP-1[19]Insul&HW Replac check
OPT | GI | - | 901038787 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WAT | - | 901038982 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GREAT ISLAND WEXFORD
TO-20-GI-WEX-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0894 | DO | 5 |  | 110 kV A2/B2 @ GI: EI: Commissioning pantograph disconnects and complete energisation of the new T142 transformer and associated 110kV cable section.
TO-20-GI-WEX-1-02 ISO week: 9fr - 13fr Date: 28 Feb - 27 Mar Duration: 29 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0894 | DO | 20 |  | 110 kV A2/B2 @ GI: Installation of HV equipment for new DSO trafo. Primary conductoring of electrical equipment for new DSO trafo
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | GI |  | 901129619 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WEX |  | 901129640 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - LODGEWOOD 110SA1
TO-20-LWD-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LWD | - | 901042978 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-LWD-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of LWD-110SA2: 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
SECTIONALISING DISCONNECT - LODGEWOOD 110SA2
TO-20-LWD-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | LWD |  |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-LWD-110SA2-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of LWD-110SA1: 110 kV A1 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
COUPLER/SECTIONALISING CB - LODGEWOOD 220K1-2
TO-20-LWD-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | LWD | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | LWD | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | LWD | 220-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | LWD | 220-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TRANSFORMER - LODGEWOOD T2102
TO-20-LWD-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LWD: Proximity outage for work on Lodgewood 220kV K1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-LWD-T2102-01 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | LWD | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CA | LWD | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OPT | LWD | TRAFO |  | DO |  | 4 | 220/110 & 275/220 Trafo Operational Test
TSO CUSTOMER TRANSFORMER - SHELTON ABBEY T102 [Holfeld Plastics]
TO-20-SHE-T102-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
proximity outage to allow ESBN carry out the replacement of the corroded gantry in Shelton Abbey compound
SECTIONALISING DISCONNECT - WEXFORD 110SA1
TO-20-WEX-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | As a consequence of WEX-110SA2: 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
SECTIONALISING DISCONNECT - WEXFORD 110SA2
TO-20-WEX-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
CAPACITOR/SVC/REACTOR - WEXFORD CAP2
TO-20-WEX-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
CAPACITOR/SVC/REACTOR - WEXFORD CAP4
TO-20-WEX-CAP4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T122 [SDCC]
TO-20-WEX-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment
DISTRIBUTION TRANSFORMER - WEXFORD T142 [SDCC]
TO-20-WEX-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0486 | DO | 75 |  | 110 kV A2 @ WEX: EI: Install new CT/VT & BZP on T142 Install new CT/VT & BZP on Crane 110kV Bay
CAPX |  |  | CP0972 | DO | 75 |  | 110 kV A2 @ WEX: EI: Installation of new busbar support structures, new equipment on Crane, T142 and T122 bays, commission all new equipment

## DUNDALK (Rgn)
110kV FEEDER - ARVA NAVAN
TO-20-ARV-NAV-1-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086419 | DO | 2 | 1 | 2019HP-1[132]Replace Pole only -Rot
FOSTRHW |  |  | 901086420 | DO | 2 | 1 | 2019HP-1[191]Replace Pole only -Rot
TO-20-ARV-NAV-1-01 ISO week: 9mo - 10fr Date: 24 Feb - 06 Mar Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084868 | DO | 2 | 4 | 2019HP-1[6]Earths-Replace earth lead
FOSTRHW |  |  | 901086415 | DO | 2 | 1 | 2019HP-1[4]Replace Pole only -Rot
FOSTRHW |  |  | 901086416 | DO | 2 | 1 | 2019HP-1[58]Replace Pole only -Rot
FOSTRHW |  |  | 901086417 | DO | 2 | 1 | 2019HP-1[63]Replace Pole only -Rot
FOSTRHW |  |  | 901086418 | CLO | 2 | 1 | 2019HP-1[128]Replace Pole only -Rot
FOSTRHW |  |  | 901086421 | CLO | 2 | 1 | 2019HP-1[199]Replace Pole only -Rot
FOSTRHW |  |  | 901086422 | CLO | 2 | 1 | 2019HP-1[229]Replace Pole only -Rot
FOSTRHW |  |  | 901086423 | CLO | 2 | 1 | 2019HP-1[230]Replace Pole only -Rot
FOSTRHW |  |  | 901086424 | CLO | 2 | 1 | 2019HP-1[319]Replace Pole only -Rot
CA | NAV | - | 901129179 | CLO | 5 | 4 | 110kV CUBICLE CONDITION ASSESSMENT
OS | NAV | - | 901129885 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - BALTRASNA DRYBRIDGE
TO-20-BAL-DRY-1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086425 | CLO | 3 | 1 | 2019HP-1[56]Replace Pole only -Rot
TRAN |  | - | 900983998 | CLO | 2 | 4 | 2018HP-1[98]Insul&HW Replace check
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | BAL |  | 901129588 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DRY |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDUFF PLATIN
TO-20-CDU-PLA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU |  | 900891899 | DO | 2 | 2 | O/1 Change R Phase surge counter
TO-20-CDU-PLA-1-03 ISO week: 39fr - 40mo Date: 25 Sep - 28 Sep Duration: 4 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985861 | DO | 1 | 4 | 2018HP-1[39]Check Struct/Found/etc-Base
TRAN |  | - | 900985862 | DO | 1 | 4 | 2018HP-1[41]Check Struct/Found/etc-Base
TRAN |  | - | 900985863 | DO | 1 | 4 | 2018HP-1[46]Check Struct/Found/etc-Base
TRAN |  | - | 900985864 | DO | 1 | 4 | 2018HP-1[50]Check Struct/Found/etc-Base
OPT | PLA |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA1
TO-20-DRY-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
OS | DRY | SA1 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-DRY-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - DRYBRIDGE 110SA2
TO-20-DRY-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of DRY-110SA1: 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DRYBRIDGE GORMAN
TO-20-DRY-GOR-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085139 | DO | 2 | 4 | 2019HP-2[105]Vib Dampers -Replace
OS | DRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | GOR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - DRYBRIDGE LOUTH
TO-20-DRY-LOU-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
TO-20-DRY-LOU-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | DRY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - DRYBRIDGE PLATIN
TO-20-DRY-PLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | PLA |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-DRY-PLA-1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DRYBRIDGE T141 [NDCC]
TO-20-DRY-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A1 @ DRY: Proximity outage for work on Drybridge 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DUNDALK LOUTH
TO-20-DDK-LOU-1-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | DDK |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-DDK-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 901087469 | DO | 1 | 1 | EMP AMS Replace CB Counter
TO-20-DDK-LOU-1-03 Status: Unscheduled
CORRECT | DDK |  | 901082258 | CANC |  | 1 | N O 1 Louth H4 (Mal)Louth DL Fault
110kV FEEDER - DUNDALK MULLAGHARLIN
TO-20-DDK-MLN-1-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
220kV FEEDER - FLAGFORD LOUTH
TO-20-FLA-LOU-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-514 220kV Circuit breaker replacement in the Louth 220 kV bay at flagford station
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 220 kV A2 @ FLA + FLA-LOU-1: Restring bay conductor DA to new CB
TO-20-FLA-LOU-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-LOU-1 + FLA-T2101: Energise new Circuit Breaker replacement via the 220 kV Flagford Louth feeder
TO-20-FLA-LOU-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous FLA-220K1-2 + FLA-LOU-1: Energise new Circuit Breaker replacement via the 220 kV flagford louth feeder
TO-20-FLA-LOU-1-01 ISO week: 38mo - 41fr Date: 14 Sep - 09 Oct Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP0867 | DO | 40 |  | Outage to enable refurbishment of OHL, Remove ground proximity clearances and tower reinforcements
|  | - |  |  | 13 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Outage for timber cutting. RC 3 days request
FO_MISC |  |  | 901084409 | DO | 1 | 4 | 2019HP-1[4]Bird Nests
FO_MISC |  |  | 901084410 | DO | 1 | 4 | 2019HP-1[25]Bird Nests
FO_MISC |  |  | 901084411 | DO | 1 | 4 | 2019HP-1[38]Bird Nests
FO_MISC |  |  | 901084412 | CLO | 1 | 4 | 2019HP-1[192]Bird Nests
FO_MISC |  |  | 901084915 | DO | 1 | 4 | 2019HP-1[65]Insulator Broken R/ph
FO_MISC |  |  | 901084916 | DO | 1 | 4 | 2019HP-1[156]Insulator Broken C/ph
FOMISC | FLA | - | 900566631 | DO | 4 | 1 | Install Game Guards
OS | LOU | - | 901042380 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038537 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
COUPLER/SECTIONALISING CB - GORMAN 110K1-2
TO-20-GOR-110K1-2-01 ISO week: 27mo - 27fr Date: 29 Jun - 03 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CM | GOR | - | 900776802 | CLO | 3 | 2 | Complete Siemens CB mod
CORRECT | GOR | - | 900693010 | DO | 1 | 2 | Install interlocking coils.
220kV FEEDER - GORMAN LOUTH
TO-20-GOR-LOU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084278 | DO | 1 | 4 | 2019HP-1[75]Bird Nests
OPT | GOR | - | 901068548 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OS | LOU | - | 901050444 | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
220kV FEEDER - GORMAN MAYNOOTH
TO-20-GOR-MAY-1-01 ISO week: 17mo - 19fr Date: 20 Apr - 08 May Duration: 19 Days (14 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819639 | DO | 2 | 3 | 2016HP-1[141]Insulator Check on gantry
TRAN |  | - | 900987259 | DO | 1 | 4 | 2018HP-1[136]Check Struct/Found/etc-Base
OS | GOR | - | 900943466 | DO | 5 | 3 | 220kV SF6 Cubicle Ordinary Service
OS | MAY | - | 900943354 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CM | MAY | - | 901076414 | CLO | 4 | 1 | Copper earths stolen from 220kV CT, VT and chokes to be reinstalled
CORRECT | MAY |  | 901080652 | CANC | 1 | 1 | Low Oil / Leak- T Phase Oil Looks Low
110kV FEEDER - GORMAN MEATH HILL
TO-20-GOR-MTH-1-01 ISO week: 12th Date: 19 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MTH |  | 901117748 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 1
TO-20-GOR-NAV-1-01 ISO week: 12we Date: 18 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | NAV |  | 901129624 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 2
TO-20-GOR-NAV-2-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GOR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | NAV |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - GORMAN NAVAN 3
TO-20-GOR-NAV-3-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
AMCAB | GOR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | NAV | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - GORMAN PLATIN
TO-20-GOR-PLA-1-01 ISO week: 12fr Date: 20 Mar Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | PLA |  | 901129660 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - GORMAN T2101
TO-20-GOR-T2101-01 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | GOR |  | 900867380 | CLO | 2 | 1 | ESBIN01 GE are to supply replacement hyd
CORRECT | GOR |  | 900934390 | CLO | 2 | 1 | Following up the faulty sensor alarm on
CORRECT | GOR |  | 901059815 | DO | 2 | 1 | Replace hydran Sensor
110kV FEEDER - LISDRUM LOUTH
TO-20-LIS-LOU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
CORRECT | LOU |  |  | DO | 3 | 1 | Hotspot 1 (SC AM No.52 Span 51/52) Jumper terminal (Repair ASAP)
TO-20-LIS-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 900982920 | DO | 3 | 1 | Surge counters need replacement on R/S/T
TO-20-LIS-LOU-1-01 ISO week: 29th - 29fr Date: 16 Jul - 17 Jul Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | LIS |  | 901129596 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - LOUTH 110 kV A1
TO-20-110 kV A1 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV A2
TO-20-110 kV A2 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV B1
TO-20-110 kV B1 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 110 kV B2
TO-20-110 kV B2 @ LOU-01 ISO week: 35th Date: 27 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV A1
TO-20-220 kV A1 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV A2
TO-20-220 kV A2 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV B1
TO-20-220 kV B1 @ LOU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 90 |  | Replace DB1 and coupler CB
TO-20-220 kV B1 @ LOU-02 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 2 |  | connection between new DB1 and DA1
TO-20-220 kV B1 @ LOU-03 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 1 |  | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB
CAPX |  |  | CP0799 | DO | 1 |  | Energise new coupler DB1 and coupler CB
TO-20-220 kV B1 @ LOU-04 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | BB changeover
BUSBAR SECTION - LOUTH 220 kV B2
TO-20-220 kV B2 @ LOU-01 ISO week: 36th Date: 03 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | BB changeover
COUPLER/SECTIONALISING CB - LOUTH 220K1-2
TO-20-LOU-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 90 |  | Replacement of coupler
TO-20-LOU-220K1-2-02 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | LOU |  | 901074162 | CANC | 3 | 1 | N O 1 F00 220 Coupler Switching and Ex
OPT | LOU | - | 901038920 | DO | 1 | 3 | 220kV MO Cubicle Operational Test
TRANSFORMER - LOUTH AT1
TO-20-LOU-AT1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900821328 | CANC |  | 1 | Replace Drycol Breather
TO-20-LOU-AT1-01 ISO week: 27mo - 30we Date: 29 Jun - 22 Jul Duration: 24 Days (18 WD) Status: Scheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
OS | LOU | 220 | 901041554 | CLO | 10 | 4 | 220kV MO Cubicle Ordinary Service
OS | LOU | 275 | 901041555 | CLO | 7 | 4 | 275kV MO Cubicle Ordinary Service
OS | LOU | Trafo | 901042117 | CLO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CA | LOU | 275 | 901129257 | CLO | 3 | 4 | 275KV CUBICLE CONDITION ASSESSMENT
TRAFO | LOU | TRAFO | 901129265 | CLO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
TRAFO | LOU | TRAFO | 901130086 | CLO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
CORRECT | LOU | TRAFO | 901039328 | DO | 1 | 2 | Louth AT1 Transformer: Drycol Replacement
TRANSFORMER - LOUTH AT2
TO-20-LOU-AT2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOFAULT | LOU | TRAFO | 900962773 | CANC | 1 | 1 | O 1 AT2 Trafo mech box Excessive conde
TO-20-LOU-AT2-01 ISO week: 31th - 34th Date: 30 Jul - 20 Aug Duration: 22 Days (15 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | LOU | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | LOU | Trafo |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | LOU | 275 |  | DO | 4 | 4 | 275kV SF6 Cubicle Ordinary Service
AMCAB | LOU | 275 |  | DO | 3 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | LOU |  | 901059811 | DO | 3 | 1 | Invesigate system fault
TRANSFORMER - LOUTH AT3
TO-20-LOU-AT3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900821331 | CANC |  | 1 | Replace Drycol Breather
CORRECT | LOU |  | 900908057 | NS |  | 1 | Replace Conservator tank supports AT3
TO-20-LOU-AT3-01 ISO week: 30th - 31we Date: 23 Jul - 29 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | LOU | 220 | 901129023 | CLO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | LOU | TRAFO | 901039329 | DO | 1 | 2 | Louth AT3 Transformer: Drycol Replacement
CORRECT | LOU |  | 901059908 | DO | 1 | 1 | Replace Sensor
CAPACITOR/SVC/REACTOR - LOUTH CAP1
TO-20-LOU-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900982921 | DO | 1 | 1 | Surge counters/Ammeters on R/S/T phases
110kV FEEDER - LOUTH MEATH HILL
TO-20-LOU-MTH-1-01 ISO week: 19tu - 19fr Date: 05 May - 08 May Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085133 | DO | 1 | 4 | 2019HP-1[72]Stays-Replace broken
CORRECT | LOU |  | 901087475 | CLO | 4 | 1 | EMP AMS: Check VT bellows on R,S and T p
110kV FEEDER - LOUTH MULLAGHARLIN
TO-20-LOU-MLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-LOU-MLN-1-03 Status: Unscheduled
CORRECT | LOU |  | 901059534 | CANC |  | 1 | N O 1 H01 Mullagharlin Switching and
TO-20-LOU-MLN-1-02 ISO week: 45fr Date: 06 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LOUTH RATRUSSAN
TO-20-LOU-RRU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084279 | CLO | 1 | 4 | 2019HP-1[123]Bird Nests
FO_MISC |  |  | 901084320 | CLO | 1 | 4 | 2019HP-1[126]Bird Nests
FO_MISC |  |  | 901084321 | CLO | 1 | 4 | 2019HP-1[128]Bird Nests
FO_MISC |  |  | 901084322 | CLO | 1 | 4 | 2019HP-1[130]Bird Nests
FO_MISC |  |  | 901084924 | CLO | 1 | 4 | 2019HP-1[197]Insulator broken aux string
OS | LOU | - | 901050323 | CLO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OPT | RRU | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-LOU-RRU-1-03 Status: Unscheduled
YM03 | - | Line | 901110486 | CLO | 5 | 1 | Am No.165 165 - 166 Right Dead end termination Replace joint within 3 months pending TSO review.
YM03 | - | Line | 901110487 | CLO | 5 | 1 | R1 107 - 108 Right Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110488 | CLO | 5 | 1 | Am No.51 51 - 52 Right Dead end termination Replace joint immediately pending TSO review.
TRANSFORMER - LOUTH T2101
TO-20-LOU-T2101-01 ISO week: 45tu - 45th Date: 03 Nov - 05 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | LOU | TRAFO | 901039288 | NS | 3 | 2 | Louth T2101 Transformer: Camlin Totus G9 Gas in Oil Monitor
OPT | LOU | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - LOUTH T2102
TO-20-LOU-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900908023 | CANC |  | 1 | Repair leak on LV bushing, bushing needs
CORRECT | LOU |  | 900908033 | CANC |  | 1 | Shot blast and treat main cover corrosio
CORRECT | LOU |  | 900950041 | NS |  | 1 | ABB to repair an oil leak on Louth T2102
TO-20-LOU-T2102-01 ISO week: 11mo - 12fr Date: 09 Mar - 20 Mar Duration: 12 Days (9 WD) Status: Scheduled
|  | - |  |  | 13 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of R1Z23b, ISM21
CORRECT | LOU | TRAFO | 901039286 | CLO | 5 | 2 | Louth T2102 Transformer: Repair leak on LV bushing, bushing needs to be removed and seals replaced by ABB Repeat tan delta and FDS tests on transformer
CORRECT | LOU |  | 900789878 | CLO | 2 | 1 | repair leak on LV bushings
CORRECT | LOU |  | 901087467 | DO | 1 | 1 | EMP AMS Replace CB Counter
OPT | LOU | 110 | 901129471 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | LOU | 220 | 901129539 | CLO | 1 | 4 | 220kV MO Cubicle Operational Test
TRANSFORMER - LOUTH T2103
TO-20-LOU-T2103-01 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | LOU | Trafo | 901042116 | DO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | LOU | 220 | 901042343 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | LOU | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
FM | LOU | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TRANSFORMER - LOUTH T2104
TO-20-LOU-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | LOU |  | 900873633 | CANC |  | 1 | ESBIN01 GE are to supply a new Hydran 20
TO-20-LOU-T2104-01 ISO week: 10we - 10fr Date: 04 Mar - 06 Mar Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA511, 7UT92
OPT | LOU | 220 | 901038922 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | LOU | 110 | 901038927 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | LOU | TRAFO | 901045371 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
275kV FEEDER - LOUTH TANDRAGEE 2
TO-20-LOU-TAN-2-01 ISO week: 31th - 34th Date: 30 Jul - 20 Aug Duration: 22 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513, LFZP111
220kV FEEDER - LOUTH WOODLAND
TO-20-LOU-WOO-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| LOU |  |  |  | 3 |  | 220kV Cubicle Condition Assessment
TO-20-LOU-WOO-1-01 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 1 |  | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB
TO-20-LOU-WOO-1-04 Status: Unscheduled
CORRECT | WOO |  | 900444614 | NS |  | 2 | O. ESBI Inspect and test all the cylind
TO-20-LOU-WOO-1-02 ISO week: 22mo - 25fr Date: 25 May - 19 Jun Duration: 26 Days (19 WD) Status: Scheduled
CAPX |  |  | MC0334 | DO | 15 |  | Uprate bay conductor on Louth - Woodland circuit
|  | - |  |  | 11 |  | Total Maintenance Outage Duration Requested
|  |  | 900944377 |  | 4 |  | 1[67] Replace all composite strain insulators with glass
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL521
|  |  | 900988605 |  | 1 |  | 2018HP-1[Am 128]Bird Nests
|  |  | 900988614 |  | 1 |  | 2018HP-1[189]Check Struct/Found/etc-base
| LOU |  |  |  | 10 |  | 220kV MO Cubicle Ordinary Service
OS | LOU | - | 901050446 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038535 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
PROT | LOU |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA612, REL521
CORRECT | LOU |  | 901081602 | DO |  | 1 | N O 1 Woodland F03 Switching and Extra
| WOO |  |  |  | 5 |  | 220kV SF6 Cubicle Ordinary Service
OS | WOO | - | 901042336 | CLO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
PROT | WOO |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA513, REL521
SECTIONALISING DISCONNECT - MULLAGHARLIN 110SA1
TO-20-MLN-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MLN |  | 901059536 | CANC |  | 1 | N O 1 H00 SA2 Switching and Extra hou
TO-20-MLN-110SA1-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of MLN-110SA2: 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MULLAGHARLIN 110SA2
TO-20-MLN-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1101 | DO | 27 |  | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: Civil works on bay H1 and H0
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
OS | MLN | SA2 | 901039708 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MLN-110SA2-02 ISO week: 44tu - 44th Date: 27 Oct - 29 Oct Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 3 |  | As a consequence of MLN-110SA1: 110 kV A1 @ MLN: 1 - H3-T121 Transfomer relabelling to H3-T123
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T121 [Xerox]
TO-20-MLN-T121-02 ISO week: 32th - 32fr Date: 06 Aug - 07 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Customer outage request
TO-20-MLN-T121-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
CAPX |  |  | CP1101 | DO | 2 |  | T121 Trafo Relabelling to T123
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T122 [Xerox]
TO-20-MLN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-MLN-T122-03 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request
COUPLER/SECTIONALISING CB - NAVAN 110SA1-2CB
TO-20-NAV-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | NAV | 110-SA2 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV | 110-SA1 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | NAV |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-NAV-110SA1-2CB-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
CAPACITOR/SVC/REACTOR - NAVAN M/CAP1
TO-20-NAV-M/CAP1-01 ISO [year]week: 1we - N/A Date: 01 Jan - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
forced out
TO-20-NAV-M/CAP1-02 Status: Unscheduled
OS | NAV | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - PLATIN T105 [Irish Cement]
TO-20-PLA-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
Customer works
CORRECT | PLA |  | 901087478 | DO | 5 | 2 | Replace CB Counter

## DUBLIN (Rgn)
220kV FEEDER - ARKLOW CARRICKMINES GIS
TO-20-ARK-CKM GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CKM |  | 900532102 | CANC |  | 2 | ESBi Repeat Insulation Tests on VT all p
TO-20-ARK-CKM GIS-1-01 ISO week: 22mo - 42fr Date: 25 May - 16 Oct Duration: 145 Days (103 WD) Status: Forced Out
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
YM03 |  | - | 900979480 | CLO | 1 | 2 | Timber HAZCNF_20M (122-123)
CM | ARK | - | 901134735 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GISbushing connection DUE : 17-Nov-20
CM | ARK | - | 901134736 | DO | 2 | 1 | R phase connection Carrickmines 220kVCubicle. R phase GIS Copper earth strap DUE : 17-Jul-20
CM | ARK | 110-DL | 901134737 | DO | 2 | 1 | T phase Carrickmines 220kVCubicle. T phase GIS Copper earth strp hotspot DUE : IMMEDIATELY
YM03 | ARK | - | 900978744 | CANC | 1 | 2 | Replace SF6 density gauge on GIS to AIS
OPT | ARK | - | 901039045 | DO | 1 | 3 | 220kV GIS Cubicle Operational Test
OS | CKM | - | 901042325 | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CORRECT | CKM |  | 900596268 | DO | 2 | 2 | 01 outage required. Hot Spots
110kV FEEDER - BALLYBEG CARRICKMINES GIS
TO-20-BEG-CKM GIS-1-01 ISO week: 46tu - 46fr Date: 10 Nov - 13 Nov Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
YM03 |  | - | 900979776 | DO | 1 | 4 | 2018HP-1[104]Foundation/Site repair
OS | BEG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CKM | - | 900944045 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
110kV FEEDER - BALTRASNA CORDUFF
TO-20-BAL-CDU-1-01 ISO week: 32we Date: 05 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BAL |  | 901129589 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALTRASNA DRYBRIDGE
TO-20-BAL-DRY-1-01 ISO week: 33mo - 33th Date: 10 Aug - 13 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086425 | CLO | 3 | 1 | 2019HP-1[56]Replace Pole only -Rot
TRAN |  | - | 900983998 | CLO | 2 | 4 | 2018HP-1[98]Insul&HW Replace check
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | BAL |  | 901129588 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DRY |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BARODA NEWBRIDGE
TO-20-BDA-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BDA-NEW-1-01 Status: Unscheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | BDA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | BDA | - |  | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CA | NEW | - |  | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | NEW | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | DO | 3 | 1 | surge counter illigable
BUSBAR SECTION - BELCAMP 110 kV A1
TO-20-110 kV A1 @ BLC-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
BUSBAR SECTION - BELCAMP 110 kV A3
TO-20-110 kV A3 @ BLC-01 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
BUSBAR SECTION - BELCAMP 110 kV B1
TO-20-110 kV B1 @ BLC-01 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
BUSBAR SECTION - BELCAMP 110 kV B3
TO-20-110 kV B3 @ BLC-01 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
COUPLER/SECTIONALISING CB - BELCAMP 110K1
TO-20-BLC-110K1-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
CAPX |  |  | CP1013 | DO | 2 |  | EI: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110K1-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110K3
TO-20-BLC-110K3-02 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
CAPX |  |  | CP1013 | DO | 2 |  | EI: Energise Belcamp-Darndale-3
TO-20-BLC-110K3-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110SA1-3CB
TO-20-BLC-110SA1-3CB-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110SA1-3CB-03 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
TO-20-BLC-110SA1-3CB-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
COUPLER/SECTIONALISING CB - BELCAMP 110SB1-3CB
TO-20-BLC-110SB1-3CB-02 ISO week: 46mo - 46tu Date: 09 Nov - 10 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ BLC: EI: Simultaneous 110 kV A1/B1 IN TURN @ BLC + BLC-110K1: Energise Belcamp-Darndale-1 and Darndale 110 kV station
TO-20-BLC-110SB1-3CB-03 ISO week: 46we - 46th Date: 11 Nov - 12 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B3 @ BLC: EI: Simultaneous 110 kV A3/B3 IN TURN @ BLC + BLC-110K3: Energise Belcamp-Darndale-3
TO-20-BLC-110SB1-3CB-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
110kV FEEDER - BELCAMP DARNDALE 1
TO-20-BLC-DND-1-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
110kV FEEDER - BELCAMP DARNDALE 3
TO-20-BLC-DND-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013_OS | DO | 2 |  | EI: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-BLC-DND-3-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
220kV FEEDER - BELCAMP FINGLAS
TO-20-BLC-FIN-1-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
TRANSFORMER - BELCAMP T2103
TO-20-BLC-T2103-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
110kV FEEDER - BLAKE tee MAYNOOTH
TO-20-BLK,T-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900400277 | DO | 7 | 1 | 7[3,8,11,14,23,24,28]Replace damaged mem
TRAN |  | - | 900988632 | DO | 1 | 4 | 2018HP-1[31]Check Struct/Found/etc-Base
OS | MAY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | MAY | - | 900691700 | DO | 4 | 3 | Step bolts required [2,3,4,5,6,8,10,13,14,17,19,20,21,23,24,25,26,27,28,29,31,33,34,35,37]
CM | MAY | - | 901076412 | DO | 3 | 1 | Copper earths stolen from 110kV CTs to be reinstalled
BUSBAR SECTION - CARRICKMINES 220 kV A1
TO-20-220 kV A1 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV A2
TO-20-220 kV A2 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV B1
TO-20-220 kV B1 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM: Busbar Changeover
BUSBAR SECTION - CARRICKMINES 220 kV B2
TO-20-220 kV B2 @ CKM-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES 220K1-2
TO-20-CKM-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | CKM |  | 900959119 | DO | 2 | 2 | O/1 Missing 220kV coupler on Indicator R
BUSBAR SECTION - CARRICKMINES GIS 220 kV A1
TO-20-220 kV A1 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A2
TO-20-220 kV A2 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A3
TO-20-220 kV A3 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV A4
TO-20-220 kV A4 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B1
TO-20-220 kV B1 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B2
TO-20-220 kV B2 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B3
TO-20-220 kV B3 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
BUSBAR SECTION - CARRICKMINES GIS 220 kV B4
TO-20-220 kV B4 @ CKM GIS-01 ISO week: 10th Date: 05 Mar Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220K3
TO-20-CKM GIS-220K3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220K4
TO-20-CKM GIS-220K4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
TO-20-CKM GIS-220K4-02 ISO week: 27mo - 27tu Date: 29 Jun - 30 Jun Duration: 2 Days (2 WD) Status: Scheduled
Outage for EI of T2101
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA1-2CB
TO-20-CKM GIS-220SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA1-3CB
TO-20-CKM GIS-220SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SA2-4CB
TO-20-CKM GIS-220SA2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB1-2CB
TO-20-CKM GIS-220SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB1-3CB
TO-20-CKM GIS-220SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B3 @ CKM GIS: 220 kV A3/B3 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CKM GIS: 220 kV A1/B1 IN TURN @ CKM GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220SB2-4CB
TO-20-CKM GIS-220SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B4 @ CKM GIS: 220 kV A4/B4 IN TURN @ CKM GIS: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CKM GIS: 220 kV A2/B2 IN TURN @ CKM GIS: Busbar Changeover
220kV FEEDER - CARRICKMINES GIS DUNSTOWN
TO-20-CKM GIS-DSN-1-01 ISO week: 17mo - 17fr Date: 20 Apr - 24 Apr Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900984573 | DO | 1 | 4 | 2018HP-1[8]Check Struct/Found/etc-Base
TRAN |  | - | 900984585 | DO | 1 | 4 | 2018HP-1[34]Check Struct/Found/etc-Base
TRAN |  | - | 900984592 | DO | 1 | 4 | 2018HP-1[48]Check Struct/Found/etc-Base
TRAN |  | - | 900984613 | DO | 1 | 4 | 2018HP-1[123]Check Struct/Found/etc-Base
TRAN |  | - | 900984617 | DO | 1 | 4 | 2018HP-1[131]Check Struct/Found/etc-Base
OPT | CKM | - | 901038749 | CLO | 1 | 1 | 220kV MO Cubicle Operational Test
CORRECT | DSN |  | 900444584 | DO | 5 | 2 | O. ESBI Inspect and test all the cylinde
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
220kV FEEDER - CARRICKMINES GIS IRISHTOWN
TO-20-CKM GIS-ISH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | placeholder for maintenance
CAPACITOR/SVC/REACTOR - CARRICKMINES GIS R2001
TO-20-CKM GIS-R2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SJ611, RET670, POW-RPH3
220kV FEEDER - CARRICKMINES POOLBEG
TO-20-CKM-PB-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
TO-20-CKM-PB-1-01 ISO week: 47mo - 48fr Date: 16 Nov - 27 Nov Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
| Cable | - |  | DO | 10 | 1 | Detection and repair of fluid leak
AMCAB | Cable | - | 900925587 | DO | 10 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OS | CKM | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
CA | CKM | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TRANSFORMER - CARRICKMINES PST2201
TO-20-CKM-PST2201-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | As a consequence of CKM-PB-1: Proximity outage for work on Poolbeg 220kV K1-3
CAPACITOR/SVC/REACTOR - CARRICKMINES R2001
TO-20-CKM-R2001-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CKM | R2001 | 901038711 | CANC |  | 2 | Carrickmines R2001 Shunt Reactor: Fit bushing monitor (HV and LV)
TO-20-CKM-R2001-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
OPT | CKM | 220-R2001 |  | DO | 1 | 4 | HV Reactor Operational Test
CORRECT | CKM |  | 900525391 | DO |  | 2 | N 0 1 non outage(important)
TRANSFORMER - CARRICKMINES T2102 [NDCC]
TO-20-CKM-T2102-01 ISO week: 31we Date: 29 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
220kV FEEDER - CASTLEBAGGOT INCHICORE 1
TO-20-CBT-INC-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 10 |  | Proximity outage to allow for erection of HV equipment in interface compound.
220kV FEEDER - CASTLEBAGGOT INCHICORE 2
TO-20-CBT-INC-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 2 |  | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required
220kV FEEDER - CASTLEBAGOT MAYNOOTH 1
TO-20-CBT-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 10 |  | Proximity outage to allow for erection of HV equipment in interface compound.
BUSBAR SECTION - CLOGHRAN 110 kV A1
TO-20-110 kV A1 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV A2
TO-20-110 kV A2 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV B1
TO-20-110 kV B1 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
BUSBAR SECTION - CLOGHRAN 110 kV B2
TO-20-110 kV B2 @ CLG-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110K1
TO-20-CLG-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110K2
TO-20-CLG-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110SA1-2CB
TO-20-CLG-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV A1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
COUPLER/SECTIONALISING CB - CLOGHRAN 110SB1-2CB
TO-20-CLG-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B2 @ CLG: 110 kV A2/B2 IN TURN @ CLG: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 110 kV B1 @ CLG: 110 kV A1/B1 IN TURN @ CLG: Busbar Changeover
110kV FEEDER - CLOGHRAN CORDUFF
TO-20-CLG-CDU-1-02 ISO week: 27tu - 27th Date: 30 Jun - 02 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 900637313 | CLO | 2 | 2 | O/1 SURGE ARRESTOR BROKEN
OPT | CDU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CLG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHRAN FINGLAS GIS
TO-20-CLG-FIN GIS-1-01 ISO week: 48we - 48fr Date: 25 Nov - 27 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | CLO | - | 900840443 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
AMCAB | FIN | - | 901115062 | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - CLOGHRAN T121 [Amazon]
TO-20-CLG-T121-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
| CLG |  |  |  | 5 |  | 5 Day Customer Outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T122 [Amazon]
TO-20-CLG-T122-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T123 [Amazon]
TO-20-CLG-T123-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 5 |  | 5 Day Customer outage
OPT | CLG | 110 | 901030848 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLOGHRAN T124 [Amazon]
TO-20-CLG-T124-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 4 |  | 4 day customer outage
AMCAB | CLG | 110 | 901006517 | DO | 3 | 3 | Annual Insp. 110kV Feeder XLPE Cable
TSO CUSTOMER TRANSFORMER - CLOGHRAN T126 [Amazon]
TO-20-CLG-T126-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
BUSBAR SECTION - CLONEE 220 kV A1
TO-20-220 kV A1 @ CLE-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-220 kV A1 @ CLE-03 ISO week: 44we - 47we Date: 28 Oct - 18 Nov Duration: 22 Days (16 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 17 |  | Civil and Electrical Installation Works associated with new F1 bay
BUSBAR SECTION - CLONEE 220 kV A2
TO-20-220 kV A2 @ CLE-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
BUSBAR SECTION - CLONEE 220 kV B1
TO-20-220 kV B1 @ CLE-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-220 kV B1 @ CLE-03 ISO week: 47th - 48fr Date: 19 Nov - 27 Nov Duration: 9 Days (7 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 7 |  | Civil and Electrical Installation Works associated with new F1 bay
BUSBAR SECTION - CLONEE 220 kV B2
TO-20-220 kV B2 @ CLE-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
COUPLER/SECTIONALISING CB - CLONEE 220K1
TO-20-CLE-220K1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A1 @ CLE: 220 kV A1/B1 IN TURN @ CLE: Busbar Changeover
TO-20-CLE-220K1-06 ISO week: 47th - 48fr Date: 19 Nov - 27 Nov Duration: 9 Days (7 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 7 |  | As a consequence of 220 kV B1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay
TO-20-CLE-220K1-05 ISO week: 44we - 47we Date: 28 Oct - 18 Nov Duration: 22 Days (16 WD) Status: Scheduled
CAPX |  |  | CP1049 | DO | 17 |  | As a consequence of 220 kV A1 @ CLE: Civil and Electrical Installation Works associated with new F1 bay
COUPLER/SECTIONALISING CB - CLONEE 220K2
TO-20-CLE-220K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV B2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
CAPX |  |  | BB0001 | DO | 1 |  | As a consequence of 220 kV A2 @ CLE: 220 kV A2/B2 IN TURN @ CLE: Busbar Changeover
220kV FEEDER - CLONEE CORDUFF
TO-20-CLE-CDU-1-01 ISO week: 47th - 49we Date: 19 Nov - 02 Dec Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | CLE | - | 901045472 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLONEE T221 [Facebook]
TO-20-CLE-T221-02 ISO week: 39mo - 41mo Date: 21 Sep - 05 Oct Duration: 15 Days (11 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 10 |  | Customer outage request
TSO CUSTOMER TRANSFORMER - CLONEE T224 [Facebook]
TO-20-CLE-T224-01 ISO week: 37we - 38th Date: 09 Sep - 17 Sep Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CLE |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CLONEE WOODLAND
TO-20-CLE-WOO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985608 | DO | 1 | 4 | 2018HP-1[3]Check Struct/Found/etc-base
OS | WOO | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | WOO | - | 901046058 | DO | 1 | 4 | HV Pressure Vessel Inspection
COUPLER/SECTIONALISING CB - COLLEGE PARK 110SA1-2CB
TO-20-COL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS_LO | COL | 110-DEA1(Q13) | 900744240 | DO | 3 | 3 | 110kV Sect / Dist Ordinary Service
OPT | COL | - | 900839239 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
OPT_LO | COL | 110-SA1/DEM1 | 900859195 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT_LO | COL | 110-SA2/DEM2 | 900859196 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | COL | 110-DEA2(Q14) | 900859226 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
TO-20-COL-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
COUPLER/SECTIONALISING CB - COLLEGE PARK 110SA1-3CB
TO-20-COL-110SA1-3CB-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-COL-110SA1-3CB-01 Status: Unscheduled
|  |  | PROT |  |  |  | P1 Protection maintenance of 7SJ511
TO-20-COL-110SA1-3CB-02 Status: Unscheduled
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS_LO | COL | 110-SA1 | 900744242 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service
OS | COL | - | 900777933 | DO | 3 | 1 | 110kV GIS Cubicle Ordinary Service
OS_LO | COL | 110-DEA1(Q12) | 900778172 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service
OS_LO | COL | 110-DEA3(Q11) | 900745182 | DO | 2 | 1 | 110kV Sect / Dist Ordinary Service
OS_LO | COL | 110-SA3 | 900778168 | DO | 2 | 1 | 110kV Sect / Dist Ordinary Service
OPT | COL | 110-SA1 | 901076464 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
TO-20-COL-110SA1-3CB-03 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
110kV FEEDER - COLLEGE PARK CORDUFF
TO-20-COL-CDU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-COL-CDU-1-01 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
TO-20-COL-CDU-1-02 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | COL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | COL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-COL-CDU-1-04 Status: Unscheduled
CM | COR | - | 900981227 | CLO | 2 | 1 | R Phase Hotspot found on R Phase CT HV Connection DUE IMMEDIATELY0
110kV FEEDER - COLLEGE PARK FINGLAS GIS
TO-20-COL-FIN GIS-1-01 ISO week: 9th - 10tu Date: 27 Feb - 03 Mar Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086432 | CLO | 2 | 2 | 2019HP-1[14]Replace Pole only -Rot
OS | COL | - | 901128698 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - COLLEGE PARK T101 [NDCC]
TO-20-COL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - COLLEGE PARK T103 [NDCC]
TO-20-COL-T103-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
PROX |  |  | PR0004 | DO | 3 |  | As a consequence of COL-110SA1-3CB: 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
BUSBAR SECTION - CORDUFF 110 kV A1
TO-20-110 kV A1 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV A2
TO-20-110 kV A2 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV A2 @ CDU-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2
TO-20-110 kV A2 @ CDU-01 ISO week: 23tu - 25we Date: 02 Jun - 17 Jun Duration: 16 Days (12 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 12 |  | Install DA bases on H2
BUSBAR SECTION - CORDUFF 110 kV A3
TO-20-110 kV A3 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV A3 @ CDU-06 Status: Unscheduled
CAPX |  |  | CP1009_OS | DO | 15 |  | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay
TO-20-110 kV A3 @ CDU-05 ISO week: 38tu - 38th Date: 15 Sep - 17 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | To facilitate CB connection works associated with DN0241/CP1025 Corduff
TO-20-110 kV A3 @ CDU-03 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | 110 kV A3/B3 IN TURN @ CDU: Test interlocking
TO-20-110 kV A3 @ CDU-02 ISO week: 23tu - 24fr Date: 02 Jun - 12 Jun Duration: 11 Days (9 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11
BUSBAR SECTION - CORDUFF 110 kV A4
TO-20-110 kV A4 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B1
TO-20-110 kV B1 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B2
TO-20-110 kV B2 @ CDU-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A2/B2 IN TURN @ CDU: Install electrical equipment on H2
TO-20-110 kV B2 @ CDU-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 12 |  | Install DB bases on H2
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CDU: Busbar Changeover
BUSBAR SECTION - CORDUFF 110 kV B3
TO-20-110 kV B3 @ CDU-04 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A3/B3 IN TURN @ CDU: Busbar Changeover
TO-20-110 kV B3 @ CDU-05 Status: Unscheduled
CAPX |  |  | CP1009_OS | DO | 15 |  | 110 kV A3/B3 IN TURN @ CDU: Install civil bases in Cruiserath 1 (F11) Bay
TO-20-110 kV B3 @ CDU-03 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 3 |  | 110 kV A3/B3 IN TURN @ CDU: Test interlocking
TO-20-110 kV B3 @ CDU-02 ISO week: 23tu - 24fr Date: 02 Jun - 12 Jun Duration: 11 Days (9 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 10 |  | 110 kV A3/B3 IN TURN @ CDU: Install electrical equipment on H11
BUSBAR SECTION - CORDUFF 110 kV B4
TO-20-110 kV B4 @ CDU-01 ISO week: 9th Date: 27 Feb Duration: 1 Day (1 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 110 kV A4/B4 IN TURN @ CDU: Busbar Changeover
COUPLER/SECTIONALISING CB - CORDUFF 110K1-2
TO-20-CDU-110K1-2-01 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 3 |  | Test interlocking
COUPLER/SECTIONALISING CB - CORDUFF 110K1-3
TO-20-CDU-110K1-3-01 ISO week: 47we - 47fr Date: 18 Nov - 20 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1025 | DO | 3 |  | Test interlocking
SECTIONALISING DISCONNECT - CORDUFF 110SA2-4
TO-20-CDU-110SA2-4-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 901087518 | DO | 4 | 2 | Misc- earthing required
OPT | CDU | 110-SA |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | 110-SA2-4 |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
BUSBAR SECTION - CORDUFF 220 kV A1
TO-20-220 kV A1 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 5 |  | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV A2
TO-20-220 kV A2 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV A3
TO-20-220 kV A3 @ CDU-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0005 | DO | 5 |  | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3
BUSBAR SECTION - CORDUFF 220 kV B1
TO-20-220 kV B1 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0004 | DO | 5 |  | 220 kV A1/B1 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV B2
TO-20-220 kV B2 @ CDU-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A2/B2 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-2
BUSBAR SECTION - CORDUFF 220 kV B3
TO-20-220 kV B3 @ CDU-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0005 | DO | 5 |  | 220 kV A3/B3 IN TURN @ CDU: Proximity outage for work on Corduff 220kV K1-3
COUPLER/SECTIONALISING CB - CORDUFF 220K1-2
TO-20-CDU-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
Proximity outage of Corduff 220 kV A1/B1 IN TURN required for this outage
CORRECT | CDU |  | 900909533 | DO | 5 | 2 | O/1 FIT EARTHING STIRRUPS TO CUBICLE
COUPLER/SECTIONALISING CB - CORDUFF 220K1-3
TO-20-CDU-220K1-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU |  | 900909532 | DO | 5 | 2 | o/1 FIT EARTHING STIRRUPS TO CUBICLE
CORRECT | CDU | - | 900889827 | CANC | 2 | 1 | Repair PI fault on DA3
TO-20-CDU-220K1-3-01 ISO week: 42tu Date: 13 Oct Duration: 1 Day (1 WD) Status: Scheduled
OPT | CDU | 220-SB3 | 901076475 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | 220-SA3 | 901076476 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | CDU | - | 901076486 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CORDUFF FINGLAS 1
TO-20-CDU-FIN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CDU | - | 901039067 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | FIN | - | 901038698 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-CDU-FIN-1-03 Status: Unscheduled
PROX |  |  | PR0004 | DO | 5 |  | 220 kV A3/B3 @ CDU: Proximity outage for work on Corduff 220kV K1-3
TO-20-CDU-FIN-1-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
220kV FEEDER - CORDUFF FINGLAS 2
TO-20-CDU-FIN-2-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 2 |  | EI: Energise Belcamp-Finglas cable, Belcamp-T2103 and Belcamp 110 kV station
TO-20-CDU-FIN-2-08 ISO week: 39mo - 39tu Date: 21 Sep - 22 Sep Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 2 |  | Proximity outage required to remove scaffolding at the new Belcamp bay.
TO-20-CDU-FIN-2-07 ISO week: 37fr - 37su Date: 11 Sep - 13 Sep Duration: 3 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay
Switching to start from 18:00 11 Sept
TO-20-CDU-FIN-2-01 ISO week: 24we - 33mo Date: 10 Jun - 10 Aug Duration: 62 Days (43 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - | 901042328 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | FIN | - | 901031837 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CORDUFF HUNTSTOWN
TO-20-CDU-HN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 5 | 4 | Cable Insp. 220kV Feeder XLPE
110kV FEEDER - CORDUFF MACETOWN
TO-20-CDU-MCE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
CORRECT | MCE |  | 901072034 | CLO | 2 | 2 | CORDUFF SCADA SWITCH FAULTY
OPT | MCE |  | 901129598 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDUFF MULLINGAR
TO-20-CDU-MUL-1-02 ISO week: 28mo - 28we Date: 06 Jul - 08 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084099 | CLO | 2 | 2 | 2019HP-1[48]Arching Horns check
FO_MISC |  | - | 900902317 | DO | 1 | 3 | 2017CP-1[285]Off Plumb pole
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
TO-20-CDU-MUL-1-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
110kV FEEDER - CORDUFF PLATIN
TO-20-CDU-PLA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU |  | 900891899 | DO | 2 | 2 | O/1 Change R Phase surge counter
TO-20-CDU-PLA-1-03 ISO week: 39fr - 40mo Date: 25 Sep - 28 Sep Duration: 4 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985861 | DO | 1 | 4 | 2018HP-1[39]Check Struct/Found/etc-Base
TRAN |  | - | 900985862 | DO | 1 | 4 | 2018HP-1[41]Check Struct/Found/etc-Base
TRAN |  | - | 900985863 | DO | 1 | 4 | 2018HP-1[46]Check Struct/Found/etc-Base
TRAN |  | - | 900985864 | DO | 1 | 4 | 2018HP-1[50]Check Struct/Found/etc-Base
OPT | PLA |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - CORDUFF RYEBROOK GIS
TO-20-CDU-RYB GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0668 | DO | 30 |  | EI: Replacement of tower 29 on Corduff Ryebrook OHL.
TO-20-CDU-RYB GIS-1-01 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T133
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
110kV FEEDER - CORDUFF SNUGBOROUGH
TO-20-CDU-SNU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T101 and Coupler K1
TO-20-CDU-SNU-1-02 Status: Unscheduled
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T103
TO-20-CDU-SNU-1-03 Status: Unscheduled
De-gas 110kV Cubicles for repair
TRANSFORMER - CORDUFF T2101
TO-20-CDU-T2101-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | CDU | TRAFO | 901039324 | NS | 1 | 2 | Corduff T2101 Transformer: Drycol Replacment
TO-20-CDU-T2101-01 Status: Unscheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 900776813 | DO | 5 | 2 | Repair faulty gas connections
OS | CDU | 220 | 901042339 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CDU | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CDU | TRAFO | 901042113 | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | CDU |  | 901090021 | DO | 1 | 2 | Misc- Silica gel needs replacing
TO-20-CDU-T2101-02 ISO week: 31we - 32we Date: 29 Jul - 05 Aug Duration: 8 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1025 | DO | 5 |  | Outage on T2101 F3/H5 to facilitate excavation works for project CP1025 required under transformer flyover
TRANSFORMER - CORDUFF T2102
TO-20-CDU-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CDU | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CDU | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CDU | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | CDU | TRAFO | 901039325 | DO | 2 | 2 | Corduff T2102 Transformer: Drycol Replacment
220kV FEEDER - CORDUFF WOODLAND
TO-20-CDU-WOO-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| WOO | - | 901125085 | CLO | 5 | 1 | 0/1 Invetigate and Repair SF6 leak
TO-20-CDU-WOO-1-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900816866 | DO | 1 | 2 | 2016CP-1[18]Replace Member Raker
FO_STDMG |  | - | 900816871 | DO | 1 | 2 | 2016CP-1[33]Replace Member Stub-bars
FOSTRHW |  | - | 900819486 | DO | 1 | 2 | 2016HP-1[1-11]Check Structure -Painting
CORRECT | WOO |  | 900444597 | DO | 5 | 2 | O. ESBI Inspect and test all the cylind
CORRECT | WOO |  | 901038603 | DO | 5 | 2 | SF6 Cublicle Ordinary Serice DA, DB and
OS | WOO | - | 901042329 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | WOO | - | 901129132 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | WOO |  | 900532138 | NS |  | 2 | Inspect and test all the cylinders, pist
TO-20-CDU-WOO-1-01 ISO week: 34we - 35tu Date: 19 Aug - 25 Aug Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | MC0333 | DO | 5 |  | Uprate bay conductor on Corduff - Woodland circuit
[5 empty] | 2 |  | P2 Prot Maintenance
SF6 leak repairs
OPT | CDU | - | 901039068 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
BUSBAR SECTION - DARNDALE 110 kV A1
TO-20-110 kV A1 @ DND-02 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
BUSBAR SECTION - DARNDALE 110 kV A2
TO-20-110 kV A2 @ DND-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
BUSBAR SECTION - DARNDALE 110 kV B1
TO-20-110 kV B1 @ DND-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
BUSBAR SECTION - DARNDALE 110 kV B2
TO-20-110 kV B2 @ DND-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-110 kV B2 @ DND-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110K1
TO-20-DND-110K1-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
COUPLER/SECTIONALISING CB - DARNDALE 110K2
TO-20-DND-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110K2-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110SA1-2CB
TO-20-DND-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ AMC: 110 kV A2/B3 IN TURN @ AMC: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110SA1-2CB-02 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
TO-20-DND-110SA1-2CB-03 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV A2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
COUPLER/SECTIONALISING CB - DARNDALE 110SB1-2CB
TO-20-DND-110SB1-2CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013_OS | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-DND-110SB1-2CB-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B1 @ DND: 110 kV A1/B1 IN TURN @ DND: EI: Energise Darndale T123
TO-20-DND-110SB1-2CB-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Tentative
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
CAPX |  |  | CP1013 | DO | 2 |  | As a consequence of 110 kV B2 @ DND: 110 kV A2/B2 IN TURN @ DND: EI: Energise Darndale T122
110kV FEEDER - DERRYIRON MAYNOOTH
TO-20-DER-MAY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | - | 901045929 | CANC | 3 | 1 | Investigate CB gas leak & repair if possible
TO-20-DER-MAY-1-01 ISO week: 39mo - 42fr Date: 21 Sep - 16 Oct Duration: 26 Days (20 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  |  |  | 2 |  | proximity needed of Derryiron - Maynooth for maintenance on Dunstown - Maynooth 2
FO_MISC |  |  | 901084970 | DO | 2 | 4 | 2019HP-1[4]Off Plumb -plumb poles
FO_MISC |  |  | 901084971 | DO | 2 | 4 | 2019HP-1[28]Off Plumb -plumb poles
FO_MISC |  |  | 901084972 | DO | 2 | 4 | 2019HP-1[29]Off Plumb -plumb poles
FO_MISC |  |  | 901084973 | DO | 2 | 4 | 2019HP-1[160]Off Plumb -plumb poles
FO_MISC |  |  | 901084974 | DO | 2 | 4 | 2019HP-1[161]Off Plumb -plumb poles
FO_MISC |  |  | 901084975 | DO | 2 | 4 | 2019HP-1[164]Off Plumb -plumb poles
FO_MISC |  |  | 901084976 | DO | 2 | 4 | 2019HP-1[181]Off Plumb -plumb poles
FO_MISC |  |  | 901084977 | DO | 2 | 4 | 2019HP-1[182]Off Plumb -plumb poles
FO_MISC |  |  | 901084978 | DO | 2 | 4 | 2019HP-1[183]Off Plumb -plumb poles
FOSTRHW |  |  | 901086429 | DO | 2 | 1 | 2019HP-1[75]Replace Pole only -Rot
FOSTRHW |  |  | 901086430 | DO | 2 | 1 | 2019HP-1[106]Replace Pole only -Rot
FOSTRHW |  |  | 901086431 | DO | 2 | 1 | 2019HP-1[124]Replace Pole only -Rot
PROX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Dunstown-Maynooth-2 220 kV
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
| - | Line | 901150823 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 116 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150824 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 117 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150825 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 118 need to be replaced by the autumn 2020 before winter storms commence.
OPT | DER |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY |  | 901080694 | DO | 3 | 2 | Missing Earths on Earths on CB
AMCAB | MAY | - | 900944029 | DO | 2 | 3 | Annual Insp. 110 Feeder OF Cable
110kV FEEDER - DUNFIRTH tee RINAWADE
TO-20-DFR,T-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DFR,T-RNW-1-01 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | RNW | - |  | DO | 10 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - DUNSTOWN 220 kV A1
TO-20-220 kV A1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV A2
TO-20-220 kV A2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV B1
TO-20-220 kV B1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 220 kV B2
TO-20-220 kV B2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ DSN: Busbar Changeover
COUPLER/SECTIONALISING CB - DUNSTOWN 220K1-2
TO-20-DSN-220K1-2-01 ISO week: 46tu - 47th Date: 10 Nov - 19 Nov Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CORRECT | DSN | 220-SA | 901080785 | DO | 5 | 1 | Replace stolen earths
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OPT | DSN | - | 901038890 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | DSN | 220-SA | 901039168 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | DSN | 220-SB | 901039169 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
BUSBAR SECTION - DUNSTOWN 400 kV A1
TO-20-400 kV A1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 400 kV A2
TO-20-400 kV A2 @ DSN-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover
TO-20-400 kV A2 @ DSN-02 ISO week: 38we - 38fr Date: 16 Sep - 18 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 3 |  | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI).
TO-20-400 kV A2 @ DSN-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
BUSBAR SECTION - DUNSTOWN 400 kV B1
TO-20-400 kV B1 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A1/B1 IN TURN @ DSN: Busbar Changeover
BUSBAR SECTION - DUNSTOWN 400 kV B2
TO-20-400 kV B2 @ DSN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 | DO | 1 |  | 400 kV A2/B2 IN TURN @ DSN: Busbar Changeover
COUPLER/SECTIONALISING CB - DUNSTOWN 400K1-2
TO-20-DSN-400K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | DSN |  | 900444678 | NS |  | 2 | O. ESBI Inspect and test all the cylind
TO-20-DSN-400K1-2-01 ISO week: 33mo - 35fr Date: 10 Aug - 28 Aug Duration: 19 Days (15 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | DSN | - |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CORRECT | DSN |  | 900531917 | DO | 5 | 2 | Inspect and test all the cylinders, pist
FM | DSN | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OS | DSN | 400-SB |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-SA |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEB2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEB1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEA2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | DSN | 400-DEA1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
220kV FEEDER - DUNSTOWN KELLIS
TO-20-DSN-KLS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1017 | DO | 7 |  | Proximity outage for stringing of Donard Test Line
TO-20-DSN-KLS-1-03 Status: Unscheduled
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Great Island-Kellis 220 kV
TO-20-DSN-KLS-1-02 Status: Unscheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 3 |  | Replace stolen earths
FO_MISC |  |  | 901084901 | DO | 2 | 4 | 2019HP-1[39]Insulator Strain insul
FOINSHW |  |  |  |  | 1 |  | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  |  |  |  | 1 |  | 2017HP-1[103]Anti-Cl. Guard fit
FOINSHW |  | - | 900819574 | DO | 1 | 2 | 2016HP-3[157]Strain/Dup 220kV replace
FO_MISC |  | - | 900898068 | DO | 1 | 3 | 2017HP-1[103]Anti-Cl. Guard fit
TRAN |  | - | 900986534 | DO | 1 | 4 | 2018HP-1[39]Insulatorbroken insulator
TRAN |  | - | 900986536 | DO | 1 | 4 | 2018HP-1[173]Earths-Replace-Earth Strap
TRAN |  | - | 900986537 | DO | 1 | 4 | 2018HP-1[174]Earths-Replace-Earth Strap
TRAN |  | - | 900986538 | DO | 1 | 4 | 2018HP-1[176-177]Vib Dampers-EW damper
TRAN |  | - | 900986539 | DO | 1 | 4 | 2018HP-1[178-179]Vib Dampers-EW damper
CORRECT | DSN |  | 900444600 | DO | 5 | 2 | O. ESBI Inspect and test all the cylind
CORRECT | DSN |  | 900566652 | DO | 2 | 2 | ESBI 01. VT Insulation retest Important
CM | DSN | - | 900719181 | DO | 2 | 2 | 2[140,143] Replace bent/damaged steel member
FM | DSN | - | 901045782 | DO | 2 | 4 | HV Pressure Vessel Inspection
OPT | DSN | - | 900955895 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
CM | KLS |  |  | DO | 3 | 1 | Replacement of Stolen Earths
OPT | KLS | - | 900955894 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - DUNSTOWN MAYNOOTH 1
TO-20-DSN-MAY-1-01 ISO week: 30mo - 30fr Date: 20 Jul - 24 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900986540 | DO | 4 | 4 | 2018HP-1[1]Insulatorfit dups on lead ins
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA513, 7SL32
CORRECT | DSN | - | 901080780 | CLO | 5 | 1 | Replace stolen earths
FM | DSN | - | 901043824 | DO | 1 | 4 | HV Pressure Vessel Inspection
CM | MAY | - | 901076413 | CLO | 3 | 1 | Copper earths stolen from 220kV DE and CTs to be reinstalled
FO_MISC | MAY |  | 901084902 | DO | 2 | 2 | 2019HP-1[Stn]Insulator BB in Maynooth
CORRECT | MAY |  | 901080649 | CLO |  | 2 | Oil Gauges To Be Cleaned
220kV FEEDER - DUNSTOWN MAYNOOTH 2
TO-20-DSN-MAY-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOINSHW |  | - | 900483534 | CANC | 2 | 1 | 2[77&am 78]Insulator fit duplicate. Proximity outage of Derryiron-Maynooth 110kV required
CM | DSN | - | 900943761 | NS | 5 |  | Replace Cylinders
CORRECT | DSN | - | 901080781 | CANC | 5 | 1 | Replace stolen earths
TO-20-DSN-MAY-2-01 ISO week: 41mo - 43fr Date: 05 Oct - 23 Oct Duration: 19 Days (15 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900986545 | DO | 1 | 4 | 2018HP-1[14]Insulatorbroken
TRAN |  | - | 900986550 | DO | 1 | 4 | 2018HP-1[39]Insulatorfit duplicates
TRAN |  | - | 900986551 | DO | 1 | 4 | 2018HP-1[40]Insulatorfit duplicates
TRAN |  | - | 900986552 | DO | 1 | 4 | 2018HP-1[57-57A]Conflicts-fit guard wire
TRAN |  | - | 900986554 | DO | 1 | 4 | 2018HP-1[77]Insulatorfit duplicates
TRAN |  | - | 900986555 | DO | 1 | 4 | 2018HP-1[78]Insulatorfit duplicates
FO_MISC |  |  | 901084903 | DO | 1 | 2 | 2019HP-1[14]Insulator Broken C/ph
OS | DSN | - | 901042331 | DO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
CA | DSN | - | 901038532 | DO | 3 | 1 | 220kV Cubicle Condition Assessment
OS | MAY | - | 901042332 | DO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
400kV FEEDER - DUNSTOWN MONEYPOINT GIS
TO-20-DSN-MP GIS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0873 | DO | 50 |  | EI: Line refurb works
CORRECT | DSN |  | 900531814 | DO | 5 | 2 | Inspect and test all the cylinders, pist
TO-20-DSN-MP GIS-1-03 Status: Unscheduled
FO_MISC |  |  | 901084904 | DO | 2 | 4 | 2019HP-1[361]Insulator Broken
FO_MISC |  |  | 901084905 | DO | 2 | 4 | 2019HP-1[371]Insulator Broken
FO_MISC |  |  | 901084906 | DO | 2 | 4 | 2019HP-1[396]Insulator Broken
FO_MISC |  |  | 901084907 | DO | 2 | 4 | 2019HP-1[402]Insulator Broken
FO_MISC |  |  | 901084908 | DO | 2 | 4 | 2019HP-1[410]Insulator Broken
FO_MISC |  |  | 901084909 | DO | 2 | 4 | 2019HP-1[486]Insulator Broken
FO_MISC |  |  | 901084910 | DO | 2 | 4 | 2019HP-1[563]Insulator Broken
FO_MISC |  |  | 901084911 | DO | 2 | 4 | 2019HP-1[564]Insulator Broken
TRAN |  | - | 900986826 | DO | 1 | 4 | 2018HP-1[214]ACGFit ACG
FO_MISC |  |  | 901084407 | DO | 1 | 4 | 2019HP-1[331]Bird Nests
FO_MISC |  |  | 901084408 | DO | 1 | 4 | 2019HP-1[567]Bird Nests
TRAN |  | - | 900986733 | NS |  | 1 | 2018HP-1[371]Bird Nestsremove asap
TRAN |  | - | 900986835 | NS |  | 1 | 2018HP-1[238]Bird Nestsremove asap
CORRECT | DSN | - | 901038719 | DO | 21 | 2 | Dunstown R4001 Reactor: Refurbush Reactor, regasket & paint
CORRECT | DSN |  | 900444627 | NS |  | 2 | O. ESBI Inspect and test all the cylinde
CORRECT | DSN |  | 900489556 | NS |  | 2 | O. ESBI Inspect and test all the cylind
CM | DSN | 400-R4001 | 900690047 | NS |  | 1 | O/1 R4001 DRYCOL INTERNAL FAULT
FM | MP | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TO-20-DSN-MP GIS-1-02 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Tentative
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
FM | DSN | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
TRANSFORMER - DUNSTOWN T4201
TO-20-DSN-T4201-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | DSN | TRAFO | 901038718 | CLO | 7 | 2 | Dunstown T4201: Refurb work on OLTC diverters and remove elemental sulphur Look at long term plan for this trafo with Eirgrid Install on line IDD/Camlin bushing monitor Long outage required in refurb is being done. Fit bushing monitor (HV and LV)
TO-20-DSN-T4201-03 Status: Unscheduled
CM | DSN | TRAFO | 901133926 | DO | 14 | 1 | Partial Discharge Test on T4201. Use OD1385.
CA | DSN | 220 | 901038531 | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT - Use OD1385
TRAFO | DSN | TRAFO | 901146361 | DO | 3 | 1 | 400/220kV Trafo Tap Changer Inspection. Use OD1385.
TO-20-DSN-T4201-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SL24, 7SL24, 7UT22
CA | DSN | 400 | 901129262 | DO | 3 | 4 | 400KV CUBICLE CONDITION ASSESSMENT Use OD1385
CORRECT | DSN | - | 900533460 | CLO | 1 | 1 | ESBI 0 1 - A Siemens transformer test sp
CORRECT | DSN | - | 900534083 | CLO | 1 | 1 | ESBI 01 outage required. A Siemens senio
CORRECT | DSN | TRAFO | 900546841 | CLO | 1 | 1 | Replace contacts in the trafo
CORRECT | DSN | - | 900606811 | NS | 1 | 2 | ESBI 01 outage required (important)Misc-
CORRECT | DSN | - | 900781800 | CLO | 1 | 1 | ESBI01 GE are to repair and recommission
CORRECT | DSN |  | 900543177 | NS |  | 2 | Earth Winding externally to facilitate t
CORRECT | DSN |  | 900543178 | NS |  | 2 | Online Oil Regen required due to high le
TO-20-DSN-T4201-01 ISO week: 12we - 16th Date: 18 Mar - 16 Apr Duration: 30 Days (20 WD) Status: Scheduled
|  | - |  |  | 25 |  | Total Maintenance Outage Duration Requested
OS | DSN | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | DSN | 220 | 901042340 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | DSN | 400 | 901130035 | CLO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
TRAFO | DSN | TRAFO | 901146154 | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1385.
CORRECT | DSN | - | 901045931 | CLO | 3 | 1 | Investigate CB gas leak & repair if possible
FM | DSN | - |  | NS | 1 | 4 | HV Pressure Vessel Inspection
FM | DSN | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | DSN | 220 | 901045943 | NS | 1 | 4 | Oil Sampling - VT's UTF245 ESBI
OS | DSN | TRAFO | 901130061 | CLO |  | 4 | 400/220kV Transformer Ordinary Service
TRANSFORMER - DUNSTOWN T4202
TO-20-DSN-T4202-01 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | MC0316 | DO | 15 |  | Stand new equipment, install new post insulators and string new T4202 bay conductor as far as the 400 kV CB.
CAPX |  |  | MC0316 | DO | 3 |  | EI: Simultaneous 400 kV A2 @ DSN + DSN-T4202: String new T4202 400 kV bay conductor between the 400 kV CB and busbar disconnect (DA2 only) and energise (EI).
TO-20-DSN-T4202-02 ISO week: 36mo - 36fr Date: 31 Aug - 04 Sep Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | DSN | - | 901080786 | DO | 4 | 1 | Replace stolen earths
OPT | DSN | 220 | 901038892 | DO | 3 | 3 | 220kV SF6 Cubicle Operational Test
OPT | DSN | TRAFO | 901045409 | DO | 3 | 3 | 400/220kV Transformer Operational Test
OPT | DSN | 400 | 901045732 | DO | 3 | 3 | 400kV SF6 Cubicle Operational Test
TO-20-DSN-T4202-03 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | MC0316 | DO | 10 |  | 400 kV A2/B2 @ DSN: Civil works to dig and pour bases for post insulators on 400 kV side of T4202.
220kV FEEDER - DUNSTOWN TURLOUGH HILL
TO-20-DSN-TH-1-02 ISO week: 46th Date: 12 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| TH |  |  |  | 1 |  | Relay Replacement at TH
TO-20-DSN-TH-1-01 ISO week: 9we - 10fr Date: 26 Feb - 06 Mar Duration: 10 Days (8 WD) Status: Scheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
TRAN |  | - | 900986853 | CLO | 2 | 4 | 2018HP-1[39]Insulatorbroken
TRAN |  | - | 900986859 | CLO | 2 | 4 | 2018HP-1[82]Insulatorbroken
FO_MISC |  |  | 901084913 | CLO | 2 | 2 | 2019HP-1[45]Insulator Broken L/ph
CORRECT | DSN | - | 901080783 | CLO | 4 | 1 | Replace stolen earths
OPT | DSN | - | 901038891 | CLO | 1 | 3 | 220kV SF6 Cubicle Operational Test
AMCAB | TH | - | 900913182 | DO | 2 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | TH | - | 901038978 | CLO | 1 | 3 | 220kV MO Cubicle Operational Test
CORRECT | TH |  | 901083956 | DO | 1 | 2 | Misc- CT R-Phase cover to be refitted du
BUSBAR SECTION - FINGLAS 110 kV A1
TO-20-110 kV A1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A2
TO-20-110 kV A2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV A3
TO-20-110 kV A3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B1
TO-20-110 kV B1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B2
TO-20-110 kV B2 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 110 kV B3
TO-20-110 kV B3 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS 110K1-2
TO-20-FIN-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901038699 | DO | 1 | 3 | 110kV MO Cubicle Operational Test
OPT | FIN | 110-SB2 | 901039137 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SB1 | 901039138 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SA2 | 901039139 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
OPT | FIN | 110-SA1 | 901039140 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - FINGLAS 110K2-3
TO-20-FIN-110K2-3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | FIN | - |  | DO | 6 | 4 | 110kV GIS Cubicle Ordinary Service
OS | FIN | 110-SB4 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SB3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SA4 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | FIN | 110-SA3 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - FINGLAS 220 kV A1
TO-20-220 kV A1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV A2
TO-20-220 kV A2 @ FIN-11 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV B1
TO-20-220 kV B1 @ FIN-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A1/B1 IN TURN @ FIN: Busbar Changeover
BUSBAR SECTION - FINGLAS 220 kV B2
TO-20-220 kV B2 @ FIN-11 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 220 kV A2/B2 IN TURN @ FIN: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS 220K1-2
TO-20-FIN-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901038696 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | FIN | 220-SA | 901039135 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | FIN | 220-SB | 901039136 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
CORRECT | FIN | - | 901046377 | DO | 1 | 1 | Investigate sync close of 220 kV couple K1 CB. CB Direct Closed. Angle difference <1 deg and voltage difference <0.5 kV.
BUSBAR SECTION - FINGLAS GIS 110 kV A1
TO-20-110 kV A1 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A2
TO-20-110 kV A2 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A3
TO-20-110 kV A3 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A4
TO-20-110 kV A4 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A5
TO-20-110 kV A5 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV A6
TO-20-110 kV A6 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B1
TO-20-110 kV B1 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B2
TO-20-110 kV B2 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B3
TO-20-110 kV B3 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B4
TO-20-110 kV B4 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B5
TO-20-110 kV B5 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
BUSBAR SECTION - FINGLAS GIS 110 kV B6
TO-20-110 kV B6 @ FIN GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K1
TO-20-FIN GIS-110K1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | FIN | - | 901043767 | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-FIN GIS-110K1-02 Status: Unscheduled
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K2
TO-20-FIN GIS-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K5
TO-20-FIN GIS-110K5-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110K6
TO-20-FIN GIS-110K6-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA1-2CB
TO-20-FIN GIS-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA1-3CB
TO-20-FIN GIS-110SA1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA2-4CB
TO-20-FIN GIS-110SA2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA3-5CB
TO-20-FIN GIS-110SA3-5CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SA4-6CB
TO-20-FIN GIS-110SA4-6CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV A4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB1-2CB
TO-20-FIN GIS-110SB1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB1-3CB
TO-20-FIN GIS-110SB1-3CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B1 @ FIN GIS: 110 kV A1/B1 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB2-4CB
TO-20-FIN GIS-110SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B2 @ FIN GIS: 110 kV A2/B2 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB3-5CB
TO-20-FIN GIS-110SB3-5CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B5 @ FIN GIS: 110 kV A5/B5 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B3 @ FIN GIS: 110 kV A3/B3 IN TURN @ FIN GIS: Busbar Changeover
COUPLER/SECTIONALISING CB - FINGLAS GIS 110SB4-6CB
TO-20-FIN GIS-110SB4-6CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B6 @ FIN GIS: 110 kV A6/B6 IN TURN @ FIN GIS: Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | As a consequence of 110 kV B4 @ FIN GIS: 110 kV A4/B4 IN TURN @ FIN GIS: Busbar Changeover
110kV FEEDER - FINGLAS GIS GLASMORE [NDCC]
TO-20-FIN GIS-GLA-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | FIN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TRANSFORMER - FINGLAS GIS T2101
TO-20-FIN GIS-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | FIN | 220 | 901038497 | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | FIN | TRAFO | 901042114 | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | FIN |  | 901080725 | DO | 2 | 2 | T2101 220KV CB Over Pressure
TRANSFORMER - FINGLAS GIS T2104
TO-20-FIN GIS-T2104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN |  | 900852318 | NS |  | 2 | Hotspot repair S phase 220KV VT connecti
TRANSFORMER - FINGLAS GIS T2106
TO-20-FIN GIS-T2106-01 ISO week: 20mo - 31mo Date: 11 May - 27 Jul Duration: 78 Days (55 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | FIN | 110 | 901129786 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CORRECT | FIN | - | 900973442 | DO | 3 | 2 | ESBI Replace faulty isolation valve on S
OPT | FIN | TRAFO | 901045418 | CLO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | FIN | 220 | 901129542 | CLO | 3 | 3 | 220kV SF6 Cubicle Operational Test
CORRECT | FIN |  | 901059907 | CLO |  | 2 | Investigate Hydran alarms not working
220kV FEEDER - FINGLAS HUNTSTOWN
TO-20-FIN-HN-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN | - | 900479248 | CANC | 3 | 2 | HUNTSTOWN 220KV DL PI IN EIRGRID WHEN DL
TO-20-FIN-HN-1-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | FIN |  | 901076401 | DO | 3 | 1 | Replace CB counter/ complete CA on VT's & SA's
CM | HUN | 220-DL | 901128554 | DO | 2 | 1 | T Phase Hotspot on T phase DL/DE disconnect DUE : 17-Jul-20
220kV FEEDER - FINGLAS NORTH WALL
TO-20-FIN-NW-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
TO-20-FIN-NW-1-02 Status: Unscheduled
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | FIN | - | 901042333 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | FIN | 220 | 901038498 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OPT | NW | - | 901039120 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
220kV FEEDER - FINGLAS SHELLYBANKS
TO-20-FIN-SHL-1-04 ISO week: 37fr - 37su Date: 11 Sep - 13 Sep Duration: 3 Days (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outages of Shellybanks & Corduff #2 bay to facilitate works on the new Belcamp bay
Switching to start at 18:00 11 Sept
TO-20-FIN-SHL-1-05 ISO week: 39we - 39fr Date: 23 Sep - 25 Sep Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0437 | DO | 3 |  | Proximity outage required to remove scaffolding at the new Belcamp bay.
TO-20-FIN-SHL-1-01 ISO week: 11fr - 22fr Date: 13 Mar - 29 May Duration: 78 Days (52 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 10 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TRANSFORMER - FINGLAS T2103
TO-20-FIN-T2103-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | FIN | TRAFO | 901039279 | CANC | 1 | 2 | Finglas T2103 Transformer: Drycol Replacement
TRANSFORMER - FINGLAS T2104
TO-20-FIN-T2104-01 ISO week: 38mo - 49fr Date: 14 Sep - 04 Dec Duration: 82 Days (59 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | FIN | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | FIN | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | FIN | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | FIN | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRAFO | FIN | TRAFO |  | DO |  | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | FIN | TRAFO |  | DO |  | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | FIN |  | 900474794 | DO |  | 2 | 0. 1. ESBI CB - Abnormal timing results
220kV FEEDER - GORMAN MAYNOOTH
TO-20-GOR-MAY-1-01 ISO week: 17mo - 19fr Date: 20 Apr - 08 May Duration: 19 Days (14 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819639 | DO | 2 | 3 | 2016HP-1[141]Insulator Check on gantry
TRAN |  | - | 900987259 | DO | 1 | 4 | 2018HP-1[136]Check Struct/Found/etc-Base
OS | GOR | - | 900943466 | DO | 5 | 3 | 220kV SF6 Cubicle Ordinary Service
OS | MAY | - | 900943354 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CM | MAY | - | 901076414 | CLO | 4 | 1 | Copper earths stolen from 220kV CT, VT and chokes to be reinstalled
CORRECT | MAY |  | 901080652 | CANC | 1 | 1 | Low Oil / Leak- T Phase Oil Looks Low
DISTRIBUTION TRANSFORMER - GRIFFINRATH T141 [NDCC]
TO-20-GRI-T141-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of GRI,T-GRI-1: GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI-T141-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Reference (Tentative)
Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
110kV FEEDER - GRIFFINRATH tee GRANGE CASTLE
TO-20-GRI,T-GCA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-GCA-1-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900331371 | DO | 3 | 1 | 4[6,23,27,34]Repair damaged member
TRAN |  | - | 900987373 | DO | 2 | 4 | 2018HP-1[1]Check Struct/Found/etc-Base
TRAN |  | - | 900987374 | DO | 2 | 4 | 2018HP-1[32]Check Struct/Found/etc-Base
TRAN |  | - | 900987375 | DO | 2 | 4 | 2018HP-1[41]Check Struct/Found/etc-Base
FO_MISC |  | - | 900819656 | DO | 1 | 2 | 2016HP-39[1-39]Check-General Tower paint
AMCAB | GCA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - GRIFFINRATH tee GRIFFINRATH
TO-20-GRI,T-GRI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-GRI-1-02 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
as a consequence of: Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
110kV FEEDER - GRIFFINRATH tee MAYNOOTH
TO-20-GRI,T-MAY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | GCA-GRI-MAY-1: Proximity outage for work on Maynooth 220 kV K1-2
TO-20-GRI,T-MAY-1-01 ISO week: 44tu - 44we Date: 27 Oct - 28 Oct Duration: 2 Days (2 WD) Status: Tentative
[5 empty] | 4 |  | Full tee out for GRIFFINRATH tee-GRANGE CASTLE out
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MAY | - | 901039026 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - HUNTSTOWN T2002 [Viridian Power HN2]
TO-20-HN-T2002-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | HUN | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
TO-20-HN-T2002-01 ISO week: 36th - 36fr Date: 03 Sep - 04 Sep Duration: 2 Days (2 WD) Status: Tentative
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
GENERATOR TRANSFORMER - HUNTSTOWN T2010/11 [Viridian Power HNC]
TO-20-HN-T2010/11-01 ISO week: 38th - 47tu Date: 17 Sep - 17 Nov Duration: 62 Days (43 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | HUN | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | HUN |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
BUSBAR SECTION - INCHICORE 220 kV A6
TO-20-220 kV A6 @ INC-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A6/B6 busbars in turn
BUSBAR SECTION - INCHICORE 220 kV B6
TO-20-220 kV B6 @ INC-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
A6/B6 busbars in turn
COUPLER/SECTIONALISING CB - INCHICORE 220K1-2
TO-20-INC-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of ISM21
COUPLER/SECTIONALISING CB - INCHICORE 220K2-4
TO-20-INC-220K2-4-01 ISO week: 43tu - 43th Date: 20 Oct - 22 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7SJ511
CORRECT | INC | - | 900977717 | DO | 2 | 2 | CB counter needs replacing
OPT | INC | 220-DEA4 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | - | 901076460 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | INC | 220-SA2-4 | 901076477 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | 220-DEB4 | 901076478 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | INC | 220-SB2-4 | 901076479 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - INCHICORE 220K4-6
TO-20-INC-220K4-6-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | INC | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | INC | 220-DEA4 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEB6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-SA4-6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEA6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-DEB4 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | INC | 220-SB4-6 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
220kV FEEDER - INCHICORE IRISHTOWN
TO-20-INC-ISH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 10 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | INC | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | ISH | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | ISH | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TO-20-INC-ISH-1-02 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Tentative
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL551
CORRECT | INC |  | 900390350 | DO |  | 2 | Inchicore Eirgrid RTU: MW, MVAr on the
| ISH | 110 |  | DO | 2 | 1 | Repair Sf6 leak
220kV FEEDER - INCHICORE MAYNOOTH 2
TO-20-INC-MAY-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0872 | DO | 20 |  | Erect cable sealing ends, complete remote end works, loop-in Castlebagot Station to Inchicore-Maynooth 2 (EI will be required) - This will re-energise as CBT - May 2 and CBT - Inch 2
CAPX |  |  | CP0872 | DO | 2 |  | EI: Simultaneous CBT-INC-2 + INC-MAY-2: EI loop-in Castlebagot Station to Inchicore-Maynooth 2 - Bars in turn also required
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | INC | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
220kV FEEDER - INCHICORE POOLBEG 1
TO-20-INC-PB-1-01 ISO week: 40mo - 41fr Date: 28 Sep - 09 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - | 901129050 | CLO | 10 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
220kV FEEDER - INCHICORE POOLBEG 2
TO-20-INC-PB-2-01 ISO week: 42mo - 43fr Date: 12 Oct - 23 Oct Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0692 | DO | 10 |  | Installation of ducting
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - |  | DO | 10 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
OPT | INC | - | 901039093 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | PB | - | 901068550 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TRANSFORMER - INCHICORE T2102 [NDCC]
TO-20-INC-T2102-01 ISO week: 31fr Date: 31 Jul Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA511, R1Z23b, ISM21
TRANSFORMER - INCHICORE T2104 [NDCC]
TO-20-INC-T2104-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, 7SA511, 7UT512
TRANSFORMER - INCHICORE T2106 [NDCC]
TO-20-INC-T2106-01 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| INC |  |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | INC | 220 |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | INC | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CORRECT | INC |  | 901084736 | DO | 3 | 1 | Low Gas / Leak- REPAIR SF6 LEAK
TO-20-INC-T2106-02 ISO week: 29mo - 30fr Date: 13 Jul - 24 Jul Duration: 12 Days (10 WD) Status: Reference
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
COUPLER/SECTIONALISING CB - IRISHTOWN 220K1-2
TO-20-ISH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | ISH | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | ISH | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
| ISH | - |  | DO | 3 | 4 | 220kV GIS Busbar Assessment
OS | ISH | 220-DEB2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | ISH | 220-SB1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | ISH | 220-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | ISH | 220-DEA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
220kV FEEDER - IRISHTOWN SHELLYBANKS
TO-20-ISH-SHL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB1
TO-20-ISH-SHL-1-03 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - |  | DO | 5 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 110-DL |  | DO | 3 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-ISH-SHL-1-01 Status: Unscheduled
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB2
CORRECT | ISH |  | 900977047 | DO | 2 | 2 | Circuit Breaker to be timed
110kV FEEDER - KILTEEL MAYNOOTH
TO-20-KTL-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900247574 | DO | 2 | 3 | Replace Member mast no 86 replace bent b
FO_MISC |  | - | 900897418 | DO | 1 | 2 | 2017HP-1[11]Off Plumb -Poles
OPT | KTL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILTEEL MONREAD
TO-20-KTL-MON-1-01 ISO week: 23tu - 24mo Date: 02 Jun - 08 Jun Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MON |  | 901076758 | CLO | 5 | 1 | Low Gas
OPT | MON | - | 901055117 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - LOUTH WOODLAND
TO-20-LOU-WOO-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| LOU |  |  |  | 3 |  | 220kV Cubicle Condition Assessment
TO-20-LOU-WOO-1-01 Status: Unscheduled
CAPX |  |  | CP0799 | DO | 1 |  | EI: Simultaneous 220 kV B1 @ LOU + LOU-WOO-1: Energise new coupler DB1 and coupler CB
TO-20-LOU-WOO-1-04 Status: Unscheduled
CORRECT | WOO |  | 900444614 | NS |  | 2 | O. ESBI Inspect and test all the cylind
TO-20-LOU-WOO-1-02 ISO week: 22mo - 25fr Date: 25 May - 19 Jun Duration: 26 Days (19 WD) Status: Scheduled
CAPX |  |  | MC0334 | DO | 15 |  | Uprate bay conductor on Louth - Woodland circuit
|  | - |  |  | 11 |  | Total Maintenance Outage Duration Requested
|  |  | 900944377 |  | 4 |  | 1[67] Replace all composite strain insulators with glass
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, REL521
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL521
|  |  | 900988605 |  | 1 |  | 2018HP-1[Am 128]Bird Nests
|  |  | 900988614 |  | 1 |  | 2018HP-1[189]Check Struct/Found/etc-base
| LOU |  |  |  | 10 |  | 220kV MO Cubicle Ordinary Service
OS | LOU | - | 901050446 | CLO | 10 | 1 | 220kV MO Cubicle Ordinary Service
CA | LOU | - | 901038535 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
PROT | LOU |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA612, REL521
CORRECT | LOU |  | 901081602 | DO |  | 1 | N O 1 Woodland F03 Switching and Extra
| WOO |  |  |  | 5 |  | 220kV SF6 Cubicle Ordinary Service
OS | WOO | - | 901042336 | CLO | 5 | 1 | 220kV SF6 Cubicle Ordinary Service
PROT | WOO |  |  | DO | 2 |  | P3 Protection Maintenance of 7SA513, REL521
SECTIONALISING DISCONNECT - MACETOWN 110SA2
TO-20-MCE-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OS | MCE | SA2 | 901039707 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - MACETOWN SNUGBOROUGH
TO-20-MCE-SNU-1-01 ISO week: 47mo - 47we Date: 16 Nov - 18 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901068538 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | SNU | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SNU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MACETOWN T121 [IBM]
TO-20-MCE-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ511
TSO CUSTOMER TRANSFORMER - MACETOWN T124 [IBM]
TO-20-MCE-T124-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901038753 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - MAYNOOTH 110 kV A1
TO-20-110 kV A1 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A2
TO-20-110 kV A2 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A3
TO-20-110 kV A3 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV A4
TO-20-110 kV A4 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B1
TO-20-110 kV B1 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B2
TO-20-110 kV B2 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B3
TO-20-110 kV B3 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 110 kV B4
TO-20-110 kV B4 @ MAY-01 ISO week: 47th Date: 19 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - MAYNOOTH 110K1-2
TO-20-MAY-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | MAY | 110-SB2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - MAYNOOTH 110K3-4
TO-20-MAY-110K3-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
OS | MAY | - | 901042253 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MAY | - | 900858412 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | MAY | 110-SA5 | 901038574 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SA6 | 901038575 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SB6 | 901038576 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
OS | MAY | 110-SB5 | 901038577 | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - MAYNOOTH 220 kV A1
TO-20-220 kV A1 @ MAY-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV
TO-20-220 kV A1 @ MAY-02 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV A2
TO-20-220 kV A2 @ MAY-01 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV B1
TO-20-220 kV B1 @ MAY-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 220 kV A1/B1 IN TURN @ MAY: Proximity outage for work on Dunstown-Maynooth-1 220 kV
TO-20-220 kV B1 @ MAY-02 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - MAYNOOTH 220 kV B2
TO-20-220 kV B2 @ MAY-01 ISO week: 48th Date: 26 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - MAYNOOTH 220K1-2
TO-20-MAY-220K1-2-01 ISO week: 38tu - 38th Date: 15 Sep - 17 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | MAY | 220-SA1 |  | DO | 2 | 1 | Maynooth 220kV Coupler Sectionaliser SA2 All, left to right R,S & T Hotspot found on all 3 phases ofSA2 sectionaliser disconnects DUE : next available opportunity.
CM | MAY | 220-SA1 |  | DO | 2 | 1 | Maynooth 220kV Coupler Sectionaliser SA1 T Phas e Hotspot found on T phase SA1 sectionaliser disconnect DUE: next available opportunity.
OPT | MAY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | MAY | 220-SB2 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SB1 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SA2 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | MAY | 220-SA1 |  | DO | 1 | 4 | 220kV Sect / Dist Operational Test
110kV FEEDER - MAYNOOTH RINAWADE
TO-20-MAY-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 220 kV K3-4
TO-20-MAY-RNW-1-03 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-MAY-RNW-1-01 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MAY | - | 901042239 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | RNW | - | 901038949 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MAYNOOTH RYEBROOK GIS
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: T132 EI - outage of feeder bay required for 2 days
TO-20-MAY-RYB GIS-1-04 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T131
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
220kV FEEDER - MAYNOOTH SHANNONBRIDGE
TO-20-MAY-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN | - | Line | 901110127 | CLO | 2 | 1 | Hotspot 1 (R1 Span 81/82) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110131 | DO | 2 | 1 | Hotspot 2 (R2 Span 255/256) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110136 | DO | 2 | 1 | Hotspot 3 (R1 Span 271/272) Right phase midspan (Repair by 17th July 2020)
TO-20-MAY-SH-1-01 ISO week: 26mo - 27th Date: 22 Jun - 02 Jul Duration: 11 Days (9 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819839 | DO | 4 | 2 | 2016HP-2[2 & 3]Insulator Fit Dups
FO_MISC |  |  | 901090694 | DO | 2 | 4 | 2019HP-1[47-48]Conflicts 10/20kV pole
FO_MISC |  |  | 901090695 | DO | 2 | 4 | 2019HP-1[51-52]Conflicts 10/20kV pole
CM | MAY | - | 901076415 | CLO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
CA | SH | - | 901038544 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TRANSFORMER - MAYNOOTH T2101
TO-20-MAY-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MAY | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | MAY | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | MAY | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | MAY | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | MAY | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 - Ordinary Service
TRANSFORMER - MAYNOOTH T2102
TO-20-MAY-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | TRAFO | 900373274 | NS | 1 | 2 | O 1. ESBI Inpsect transformer (Tamini) f
CM | MAY | TRAFO | 900693054 | NS | 1 | 2 | Replace/repair rust on main cover bolts and channel on top of the tank
TO-20-MAY-T2102-01 ISO week: 29tu - 29fr Date: 14 Jul - 17 Jul Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OPT | MAY | TRAFO | 901080655 | DO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
OPT | MAY | 220 |  | DO | 1 | 4 | 220kV MO Cubicle Operational Test
OPT | MAY | 110 | 901038584 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY | TRAFO | 901039322 | DO | 1 | 2 | Maynooth T2102 Transformer: Drycol Replacement
TRANSFORMER - MAYNOOTH T2103
TO-20-MAY-T2103-01 ISO week: 37mo - 37we Date: 07 Sep - 09 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CM | MAY | 110 | 901128564 | DO | 2 | 1 | Hotspot 1 (110kV T-phase DB) Repair by 19th Sep 2020
OPT | MAY | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | MAY | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | MAY | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY | TRAFO | 901039289 | DO | 1 | 2 | maynooth T2103 Transformer: E6 dial stat faulty, shot blast and treat major main cover corrosion, retest CT and LV S phase bushing, repair several fans
TRANSFORMER - MAYNOOTH T2104
TO-20-MAY-T2104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | TRAFO | 901039323 | DO | 1 | 2 | Maynooth T2104 Transformer: Drycol Replacement
TO-20-MAY-T2104-03 Status: Unscheduled
CORRECT | MAY | TRAFO | 901039290 | NS | 7 | 2 | Maynooth T2104 Transformer: Refurbish fans and treat corrosion on top cover. Can be done as part of next OS
TO-20-MAY-T2104-01 ISO week: 32tu - 32fr Date: 04 Aug - 07 Aug Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, 7SA612, RET521
OPT | MAY | 220 | 901039022 | CLO | 3 | 3 | 220kV SF6 Cubicle Operational Test
OPT | MAY | TRAFO | 901045376 | CLO | 3 | 3 | 220/110 & 275/220 Trafo Operational Test
CORRECT | MAY |  | 901080648 | CLO | 1 | 2 | Silica On T2104 To Be Replaced
220kV FEEDER - MAYNOOTH TURLOUGH HILL
TO-20-MAY-TH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900988793 | DO | 2 | 2 | 2018HP-1[5]Insulatorfit duplicate
TRAN |  | - | 900988794 | DO | 2 | 2 | 2018HP-1[6]Insulatorfit duplicate
CORRECT | TH |  | 901087476 | NS | 10 | 2 | Full overhaul of Circuit Breaker
CORRECT | TH |  | 901084687 | NS | 5 | 2 | 1.Replace R phase CB pole and drive insu
TO-20-MAY-TH-1-01 Status: Unscheduled
CAPX |  |  | CP1022 | DO | 25 |  | EI: Replacement and Commissioning of PLC Equipment
TRAN |  | - | 900988802 | DO | 2 | 2 | 2018HP-1[173]Insulatorbroken
FO_MISC |  |  | 901084925 | DO | 2 | 2 | 2019HP-1[99]Insulator Broken insulator
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
CORRECT | MAY |  | 901080651 | DO | 2 | 1 | Low Oil / Leak- CB Oil Low
AMCAB | TH | - | 901005625 | DO | 3 | 4 | Annual Insp. 400 & 220 Feeder OF Cable
TO-20-MAY-TH-1-04 Status: Unscheduled
CM | TH | - | 901128568 | CLO | 2 | 1 | S Phase Hotspot found on S Phas HV Connection by 6th July 2020
TO-20-MAY-TH-1-03 ISO week: 28mo - 28tu Date: 06 Jul - 07 Jul Duration: 2 Days (2 WD) Status: Scheduled
| TH |  | 20CM0450 |  | 2 |  | S Phase Hotspot found on S Phase HV connection by 6th July
220kV FEEDER - MAYNOOTH WOODLAND
TO-20-MAY-WOO-1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901076417 |  | 3 |  | Copper earths stolen from 220kV CT and VT to be reinstalled
TO-20-MAY-WOO-1-02 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  | - | 900819860 | DO | 1 | 2 | 2016HP-1[5-71]Check Structure -Painting
TRAN |  | - | 900988803 | DO | 1 | 4 | 2018HP-1[5]Check Struct/Found/etc-base
CM | MAY | - | 901076417 | DO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
FM | WOO | - | 900943534 | DO | 2 | 3 | HV Pressure Vessel Inspection
220kV FEEDER - NORTH WALL POOLBEG
TO-20-NW-PB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
AMCAB | Cable | - | 900913186 | DO | 5 | 3 | Annual Insp. 400 & 220 Feeder OF Cable
OS | NW | 220-DA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OPT | NW | - | 901039122 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OS | PB | - |  | DO | 5 | 4 | 220kV GIS Cubicle Ordinary Service
CA | PB | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
TO-20-NW-PB-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
GENERATOR TRANSFORMER - NORTH WALL T2004/5 [ESB GWM NW5]
TO-20-NW-T2004/5-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 12 |  | 220 kV A1 @ NW: Proximity outage for work on North Wall-Poolbeg 220 kV
400kV FEEDER - OLDSTREET WOODLAND
TO-20-OST-WOO-1-01 ISO week: 42sa - 44fr Date: 17 Oct - 30 Oct Duration: 14 Days (9 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084928 | DO | 2 | 4 | 2019HP-1[103]Insulator Broken
FO_MISC |  |  | 901084929 | DO | 2 | 4 | 2019HP-1[115]Insulator Broken
FO_MISC |  |  | 901084930 | DO | 2 | 4 | 2019HP-1[272]Insulator Remove old insul
FO_STDMG |  |  | 901086387 | DO | 2 | 4 | 2019HP-1[90 ]Replace Member
FO_STDMG |  |  | 901086388 | DO | 2 | 4 | 2019HP-1[100]Replace Member
FO_STDMG |  |  | 901086389 | DO | 2 | 4 | 2019HP-1[120]Replace Member
TRAN |  | - | 900989127 | DO | 1 | 4 | 2018HP-1[99]Replace Memberrakers
TRAN |  | - | 900989128 | DO | 1 | 4 | 2018HP-1[100]Replace Memberrakers
TRAN |  | - | 900989185 | DO | 1 | 4 | 2018HP-1[115]Insulator-broken c/ph
TRAN |  | - | 900989188 | DO | 1 | 4 | 2018HP-1[162]Check(General)Remove object
FO_MISC |  |  | 901084336 | DO | 1 | 4 | 2019HP-1[76]Bird Nests
FO_MISC |  |  | 901084337 | DO | 1 | 4 | 2019HP-1[79]Bird Nests
FO_MISC |  |  | 901084338 | DO | 1 | 4 | 2019HP-1[93]Bird Nests
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SL32, FYS3L, FYG2L
OPT | OST | - | 901039088 | DO | 2 | 4 | 400kV SF6 Cubicle Operational Test
CORRECT | WOO | R4001 | 900821342 | DO | 10 | 1 | Some work done in 2014 Beltec 2 leaks HV
CORRECT | WOO |  | 900724385 | DO | 5 | 1 | O/1 Repair to leak in concrete of Bund
CORRECT | WOO |  | 901046071 | DO | 3 | 1 | SF6 leak repair
FM | WOO | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | WOO |  | 900788839 | DO |  | 2 | Misc- work not on other CORRECT counters
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA1
TO-20-PA-110SA1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
SECTIONALISING DISCONNECT - POLLAPHUCA 110SA2
TO-20-PA-110SA2-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of works on Stratford tee Pollaphuca
GENERATOR TRANSFORMER - POLLAPHUCA T101 [ESB GWM LI1/LI2/LI4]
TO-20-PA-T101-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA511
As a consequence of works on Stratford tee Pollaphuca
CORRECT | PA |  | 901079398 | DO | 2 | 2 | Check the bellows of the current transfo
CORRECT | PA |  | 901079400 | DO | 2 | 2 | Change the oil in the circuit breaker
CORRECT | PA |  | 901087470 | DO | 1 | 2 | EMP AMS: Replace CB Counter
COUPLER/SECTIONALISING CB - POOLBEG 220K2-3
TO-20-PB-220K2-3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | PB | - |  | DO | 4 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | PB | 220-SB2-3 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | PB | 220-SA2-3 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - POOLBEG 220K3-4
TO-20-PB-220K3-4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | PB | - | 901042163 | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | PB | 220-SA3-4 | 901039697 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | PB | 220-SB3-4 | 901039698 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-PB-220K3-4-01 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
SECTIONALISING DISCONNECT - POOLBEG 220SA1-2
TO-20-PB-220SA1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OS | PB | 110-SA1-2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-PB-220SA1-2-02 Status: Unscheduled
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
SECTIONALISING DISCONNECT - POOLBEG 220SB1-2
TO-20-PB-220SB1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Poolbeg 220kV K1-3
CAPACITOR/SVC/REACTOR - POOLBEG R2001
TO-20-PB-R2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | PB | - | 900942637 | DO | 2 | 3 | 220kV SF6 Cubicle Operational Test
AMCAB | PB | R2001 | 900944063 | DO | 2 | 3 | Insp. 400 & 220 Feeder XLPE Cable
OPT | PB | R2001 | 900944210 | DO | 1 | 3 | HV Reactor Operational Test
CAPACITOR/SVC/REACTOR - POOLBEG R2002
TO-20-PB-R2002-01 ISO week: 24we - 24fr Date: 10 Jun - 12 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | PB | - | 901038594 | DO | 2 | 4 | Insp. 400 & 220 Feeder XLPE Cable
OPT | PB |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | PB | R2002 | 901038596 | DO | 1 | 4 | HV Reactor Operational Test
CAPACITOR/SVC/REACTOR - POOLBEG R223-4
TO-20-PB-R223-4-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
CA | PB | 220-R223-4 | 900858397 | DO | 3 | 3 | 220KV REACTOR CONDITION ASSESSMENT
CA | PB | 220-BAY4 | 900858465 | DO | 3 | 3 | 220KV CUBICLE CONDITION ASSESSMENT
CA | PB | 220-BAY3 | 900858466 | DO | 3 | 3 | 220KV CUBICLE CONDITION ASSESSMENT
AMCAB | PB | Bay4 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
AMCAB | PB | Bay3 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | PB | 220-R223-4 | 901045341 | DO | 2 | 4 | HV Reactor Operational Test
OPT | PB | 220-BAY3 | 901038941 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
OPT | PB | 220-BAY4 | 901038945 | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-PB-R223-4-02 ISO week: 48tu - 51th Date: 24 Nov - 17 Dec Duration: 24 Days (18 WD) Status: Scheduled
| PB |  |  |  | 18 |  | FS6 repair
220kV FEEDER - POOLBEG SHELLYBANKS
TO-20-PB-SHL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D1/CB3
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV D2/CB3
TO-20-PB-SHL-1-03 Status: Unscheduled
[5 empty] | 3 |  | Density Switch Replacement
TRANSFORMER - PORTAN T4301
TO-20-PRN-T4301-01 ISO week: 35th - 35fr Date: 27 Aug - 28 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | POR | 400 |  | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test
400kV FEEDER - PORTAN WOODLAND
TO-20-PRN-WOO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | 400 |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | WOO | 400-1 |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CA | WOO | 400-1 |  | DO | 3 | 4 | 400kV Cubicle Condition Assessment
SECTIONALISING DISCONNECT - RINAWADE 110SA1
TO-20-RNW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
OS | RNW | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-RNW-110SA1-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RNW-110SA2: 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - RINAWADE 110SA2
TO-20-RNW-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RNW-110SA1: 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RNW-110SA2-01 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
| RNW |  |  |  | 3 |  | Total Maintenance Outage Duration Requested
OS | RNW | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TSO CUSTOMER TRANSFORMER - RINAWADE T121 [Hewlett Packard]
TO-20-RNW-T121-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RNW-T121-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SJ511
OPT | RNW | - | 901038951 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - RINAWADE T122 [Hewlett Packard]
TO-20-RNW-T122-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RNW | - | 901038952 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - RYEBROOK GIS 110 kV A1
TO-20-110 kV A1 @ RYB GIS-02 ISO week: 45we - 45th Date: 04 Nov - 05 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-110 kV A1 @ RYB GIS-03 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T131
TO-20-110 kV A1 @ RYB GIS-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
BUSBAR SECTION - RYEBROOK GIS 110 kV A1/A2/A4
TO-20-110 kV A1/A2/A4 @ RYB GIS-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: T132 EI - outage of feeder bay required for 2 days
BUSBAR SECTION - RYEBROOK GIS 110 kV A3
TO-20-110 kV A3 @ RYB GIS-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-110 kV A3 @ RYB GIS-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
BUSBAR SECTION - RYEBROOK GIS 110 kV B1
TO-20-110 kV B1 @ RYB GIS-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
BUSBAR SECTION - RYEBROOK GIS 110 kV B3
TO-20-110 kV B3 @ RYB GIS-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
BUSBAR SECTION - RYEBROOK GIS 110 kV B4
TO-20-110 kV B4 @ RYB GIS-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110K3
TO-20-RYB GIS-110K3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB | - | 900942678 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110K3-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-RYB GIS-110K3-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110K4
TO-20-RYB GIS-110K4-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
TO-20-RYB GIS-110K4-01 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB | - | 900942679 | DO | 1 | 3 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110K4-03 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA1-2CB
TO-20-RYB GIS-110SA1-2CB-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131
TO-20-RYB GIS-110SA1-2CB-03 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
TO-20-RYB GIS-110SA1-2CB-02 ISO week: 45we - 45th Date: 04 Nov - 05 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-RYB GIS-110SA1-2CB-01 ISO week: 46mo - 46we Date: 09 Nov - 11 Nov Duration: 3 Days (3 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA1-3CB
TO-20-RYB GIS-110SA1-3CB-05 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
TO-20-RYB GIS-110SA1-3CB-04 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Energise T131
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1 @ RYB GIS: EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
TO-20-RYB GIS-110SA1-3CB-02 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A3 @ RYB GIS: EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
TO-20-RYB GIS-110SA1-3CB-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV A3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SA2-4CB
TO-20-RYB GIS-110SA2-4CB-02 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 2 |  | As a consequence of 110 kV A1/A2/A4 @ RYB GIS: EI: T132 EI - outage of feeder bay required for 2 days
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB1-2CB
TO-20-RYB GIS-110SB1-2CB-01 ISO week: 44th - 45mo Date: 29 Oct - 02 Nov Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB1-3CB
TO-20-RYB GIS-110SB1-3CB-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RYB |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-RYB GIS-110SB1-3CB-04 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B1 @ RYB GIS: 110 kV A1/B1 IN TURN @ RYB GIS: Intel request T131 - differential stability testing 3 day A1 or B1 section of busbar & sectionaliser (SA 1-3 or SB 1-3) & sectionaliser (SA 1-2 or SB 1-2)
TO-20-RYB GIS-110SB1-3CB-01 ISO week: 48mo - 48we Date: 23 Nov - 25 Nov Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B3 @ RYB GIS: 110 kV A3/B3 IN TURN @ RYB GIS: Differential stability testing associated with T133
COUPLER/SECTIONALISING CB - RYEBROOK GIS 110SB2-4CB
TO-20-RYB GIS-110SB2-4CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 3 |  | As a consequence of 110 kV B4 @ RYB GIS: Associated with T132. Intel request during differential stability testing 3 day. B4 section of busbar + sectionaliser (SB 2-4) + K4 coupler
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T105 [Intel]
TO-20-RYB GIS-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T106 [Intel]
TO-20-RYB GIS-T106-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TO-20-RYB GIS-T106-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T107 [Intel]
TO-20-RYB GIS-T107-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - | 900926063 | DO | 2 | 3 | INSP. 110 STATION XLPE CABLE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T108 [Intel]
TO-20-RYB GIS-T108-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | RYB | - |  | DO | 2 | 4 | INSP. 110 STATION XLPE CABLE
TO-20-RYB GIS-T108-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T109 [Intel]
TO-20-RYB GIS-T109-01 ISO week: 22tu - 23tu Date: 26 May - 02 Jun Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - | 901129747 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T131 [Intel]
TO-20-RYB GIS-T131-01 ISO week: 47mo Date: 16 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 1 |  | Intel request to test transformer oil from T131. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB1
TO-20-SHL-D1/CB1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SHL |  |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
TO-20-SHL-D1/CB1-02 ISO week: 23mo - 23we Date: 01 Jun - 03 Jun Duration: 3 Days (2 WD) Status: Tentative
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2016
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB2
TO-20-SHL-D1/CB2-01 ISO week: 34fr - 35tu Date: 21 Aug - 25 Aug Duration: 5 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2014
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | SHL |  |  | DO | 1 | 4 | 220kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - SHELLYBANKS D1/CB3
TO-20-SHL-D1/CB3-01 ISO week: 34mo - 35tu Date: 17 Aug - 25 Aug Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2014
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB1
TO-20-SHL-D2/CB1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TO-20-SHL-D2/CB1-02 ISO week: 23mo - 23we Date: 01 Jun - 03 Jun Duration: 3 Days (2 WD) Status: Tentative
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV T2016
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB2
TO-20-SHL-D2/CB2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
TO-20-SHL-D2/CB2-02 ISO week: 23fr - 23su Date: 05 Jun - 07 Jun Duration: 3 Days (1 WD) Status: Scheduled
CORRECT | SHL |  | 901079135 | DO | 3 | 2 | D5 disconnect failed to operate correctl
COUPLER/SECTIONALISING CB - SHELLYBANKS D2/CB3
TO-20-SHL-D2/CB3-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | SHL | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | SHL | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
GENERATOR TRANSFORMER - SHELLYBANKS T2014 [ESB GWM PB4]
TO-20-SHL-T2014-01 ISO week: 34mo - 34th Date: 17 Aug - 20 Aug Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D1/CB3
OS | SHL | 220-DT |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
AMCAB | SHL | cable | 900838786 | DO | 2 | 3 | Annual Insp. 400 & 220 Statn. XLPE Cable
GENERATOR TRANSFORMER - SHELLYBANKS T2015 [ESB GWM PB5]
TO-20-SHL-T2015-01 ISO week: 24mo - 24th Date: 08 Jun - 11 Jun Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0004 | DO | 4 |  | Proximity outage for work on Shellybanks 220kV D2/CB2
PROX |  |  | PR0004 | DO | 2 |  | Proximity outage for work on Shellybanks 220kV D2/CB3
AMCAB | SHL | - | 901129026 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130137 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
GENERATOR TRANSFORMER - SHELLYBANKS T2016 [ESB GWM PB6]
TO-20-SHL-T2016-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
AMCAB | SHL | 220 | 901129027 | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | SHL | 220-DT | 901130138 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-SHL-T2016-02 ISO week: 23mo - 23th Date: 01 Jun - 04 Jun Duration: 4 Days (3 WD) Status: Scheduled
PROX |  |  | PR0004 | DO | 4 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV D2/CB1
PROX |  |  | PR0004 | DO | 3 |  | 220 kV A1 @ SHL: Proximity outage for work on Shellybanks 220kV T2016
| SHL |  |  |  | 4 |  | Resolve DL S6 Leak
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110K2
TO-20-SNU-110K2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | - | 901068540 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SA1-2CB
TO-20-SNU-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | 110-SA1-2 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SB1-2CB
TO-20-SNU-110SB1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | SNU | 110-SB1-2 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - STRATFORD tee POLLAPHUCA
TO-20-STR,T-PA-1-01 ISO week: 35mo - 39mo Date: 24 Aug - 21 Sep Duration: 29 Days (21 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 21 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 900864747 | DO | 2 | 4 | 2019HP-1[13]Off Plumb -plumb poles
FO_STDMG |  | - | 900898188 | CLO | 2 | 3 | 2017HP-1[14]Crossarm Replacement Replace
FO_MISC |  | - | 900864747 | CLO | 1 | 2 | 2016CP-1[13]Off Plumb Poles
FOSTRHW |  | - | 900973774 | CANC | 1 | 1 | 1[33]Replace Rotten Pole
FO_MISC |  | - | 900975368 | CLO | 1 | 1 | 1[53]Install ACG on mast no. 53
TRAN |  | - | 900989394 | DO | 1 | 4 | 2018HP-1[15]Off Plumb-Poles
OS | PA | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | PA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
BUSBAR SECTION - TURLOUGH HILL 220 kV B2
TO-20-220 kV B2 @ TH-01 ISO week: 39fr Date: 25 Sep Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Black Start Test
COUPLER/SECTIONALISING CB - TURLOUGH HILL 220K1-2
TO-20-TH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | TH | - |  | DO | 10 | 4 | 220kV MO Cubicle Ordinary Service
GENERATOR TRANSFORMER - TURLOUGH HILL T2001/2 [ESB GWM TH1/TH2]
TO-20-TH-T2001/2-01 ISO week: 29mo - 29tu Date: 13 Jul - 14 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 | 2 | Total Maintenance Outage Duration Requested
AMCAB | TH | - | 901005766 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
GENERATOR TRANSFORMER - TURLOUGH HILL T2003/4 [ESB GWM TH3/TH4]
TO-20-TH-T2003/4-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | TH | 220 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TO-20-TH-T2003/4-03 ISO week: 39fr Date: 25 Sep Duration: 1 Day (1 WD) Status: Scheduled
[5 empty] | 1 |  | Black Start Test
TO-20-TH-T2003/4-01 ISO week: 27mo - 27tu Date: 29 Jun - 30 Jun Duration: 2 Days (2 WD) Status: Scheduled
AMCAB | TH | - | 901005768 | DO | 2 | 3 | Annual Insp. 400 & 220 Station OF Cable
COUPLER/SECTIONALISING CB - WOODLAND 220K1-2
TO-20-WOO-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | WOO | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | WOO | - |  | DO | 2 | 4 | HV Pressure Vessel Inspection
OS | WOO | 220-SB |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | WOO | 220-SA |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
COUPLER/SECTIONALISING CB - WOODLAND 400K1-2
TO-20-WOO-400K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of 7TG17
OS | WOO | - |  | DO | 5 | 4 | 400kV SF6 Cubicle Ordinary Service
CORRECT | WOO |  | 900531762 | DO | 5 | 2 | Inspect and test all the cylinders, pist
CA | WOO | - |  | DO | 3 | 4 | 400kV Cubicle Condition Assessment
OS | WOO | 400-SB |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-SA |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEB2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEB1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEA2 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
OS | WOO | 400-DEA1 |  | DO | 2 | 4 | 400kV Sect / Dist Ordinary Service
TO-20-WOO-400K1-2-02 Status: Unscheduled
CORRECT | WOO |  | 900444684 | NS | 5 | 2 | O. ESBI Inspect and test all the cylind
TRANSFORMER - WOODLAND T4201
TO-20-WOO-T4201-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 25 |  | Total Maintenance Outage Duration Requested
TO-20-WOO-T4201-03 Status: Unscheduled
| WOO | - |  | DO | 25 |  | Total Maintenance Outage Duration Requested
TO-20-WOO-T4201-01 Status: Unscheduled
CM | WOO | TRAFO |  | DO | 14 | 1 | Partial Discharge Test on T4201.Use OD1392
| WOO | TRAFO |  | DO | 5 | 1 | 400/220KV TRAFO CONDITION ASSESSMENT. Use OD1392.
TRAFO | WOO | TRAFO |  | DO | 3 | 1 | 400/220kV Trafo Tap Changer Inspection. Use OD1392.
OPT | WOO | 220 | 900942806 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test. Use OD1392.
FM | WOO | - | 901114185 | DO | 1 | 4 | HV Pressure Vessel Inspection. Use OD1392
OPT | WOO | TRAFO | 901129762 | DO | 1 | 4 | 400/220kV Transformer Operational Test. Use OD1392.
OPT | WOO | 400 | 901146366 | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test. Use OD1392.
CORRECT | WOO |  | 900801507 | DO |  | 2 | o/1 air pressure alarm req for CB. Use OD1392
TRANSFORMER - WOODLAND T4202
TO-20-WOO-T4202-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | WOO |  | 900532120 | NS | 5 | 2 | Inspect and test all the cylinders, pist
TO-20-WOO-T4202-01 ISO week: 26we - 27fr Date: 24 Jun - 03 Jul Duration: 10 Days (8 WD) Status: Scheduled
[5 empty] | 5 |  | SF6 leak on transformer bays
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | WOO |  | 901073407 | CANC | 2 | 2 | Corrective- T4202 220KV CB LOW
OPT | WOO | 400 |  | DO | 1 | 4 | 400kV SF6 Cubicle Operational Test
OPT | WOO | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CORRECT | WOO |  | 901073092 | DO | 1 | 2 | SF6 GAUGE TO BE REPLACED AS PER ESBI
CORRECT | WOO |  | 901081577 | DO | 1 | 2 | Corrective- T4202 Surge Counters Unreada
OPT | WOO | TRAFO |  | DO |  | 4 | 400/220kV Transformer Operational Test
TRANSFORMER - WOODLAND T4204
TO-20-WOO-T4204-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | WOO | TRAFO |  | DO | 1 | 4 | 400/220kV Transformer Operational Test
OPT | WOO | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-WOO-T4204-02 Status: Unscheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7SA612, RET670

## DEMAND (Rgn)
110kV FEEDER - AGHADA WHITEGATE [Irving Oil]
TO-20-AD-WHI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 | 2 | Total Maintenance Outage Duration Requested
OS | AD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - ANNER DOON
TO-20-ANR-DOO-1-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | DOO | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
| DOO |  |  | DO | 1 | 1 | Replacement of Stolen Earths
OPT | DOO | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - ANNER T101 [Medite]
TO-20-ANR-T101-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
TSO CUSTOMER TRANSFORMER - ANNER T103 [Medite]
TO-20-ANR-T103-01 ISO week: 39tu - 39we Date: 22 Sep - 23 Sep Duration: 2 Days (2 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Anner-Doon 110 kV
110kV FEEDER - ARKLOW SHELTON ABBEY 2
TO-20-ARK-SHE-2-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
Proximity to allow ESBN to replace corroded gantry in Shelton Abbey Compound
OS | ARK | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | SHE | 110-DL/DE |  | DO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - ARVA GORTAWEE
TO-20-ARV-GWE-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-ARV-GWE-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084866 | DO | 1 | 4 | 2019HP-1[157]Earths-Replace LPH e/w
FO_MISC |  |  | 901084867 | DO | 1 | 4 | 2019HP-1[158]Earths-Replace RPH e/w
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA612, REL521
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - AUGHINISH 110SA1-2CB
TO-20-AUG-110SA1-2CB-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
OS | AUG | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-AUG-110SA1-2CB-01 Status: Unscheduled
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
PROT |  |  |  | DO | 1 |  | P1 Protection maintenance of ISM21
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | AUG | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - AUGHINISH CASTLEFARM 1
TO-20-AUG-CFM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
OS | AUG | - | 901129898 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | AUG | - | 901129107 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-AUG-CFM-1-02 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Scheduled
1[EM 48] replacement of 110kV strain/duplicate insulator
Customer outage request
As a consequence of CFM T101
110kV FEEDER - AUGHINISH CASTLEFARM 2
TO-20-AUG-CFM-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A2 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA2)
TO-20-AUG-CFM-2-03 Status: Unscheduled
CORRECT | AUG |  | 901030139 | CANC | 1 | 2 | Assist with Relay Testing
TO-20-AUG-CFM-2-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SJ611, RADSB
901158967 | [6 empty] | Paint 110kV Tower
901158971 | [6 empty] | Replacement of Insulators
As a consequence of CFM-T102
Customer outage 14 @ CFM T102 14 Sept - 02 Oct
OS | AUG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AUGHINISH KILPADDOGE
TO-20-AUG-KPG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | KPG | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| KPG |  |  |  | 3 |  | Outstanding issues with the AR Supervisory scheme on the bay including testing and recommissioning of the BCU and testing of new commands and PI back to NCC
TO-20-AUG-KPG-1-02 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901110437 | CLO | 2 | 1 | Hotspot 8 (DC Cable Tower No.160 Span 159/160) Lower (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110438 | CLO | 2 | 1 | Hotspot 7 (DC Cable Tower No.160 Span 159/160) Top (DC) Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110439 | CLO | 2 | 1 | Hotspot 4 (Transposition Tower No. 58 Span 57/58) Left Jumper Terminal (Repair by 24th Jul)
TRAN | - | Line | 901110456 | CLO | 2 | 1 | Hotspot 2 (Transposition Tower No. 58 Span 58/59) Centre Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110457 | CLO | 2 | 1 | Hotspot 3 (Transposition Tower No. 58 Span 58/59) Left Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110460 | CLO | 2 | 1 | Hotspot 5 (Transposition Tower No. 58 Span 57/58) Centre Jumper Terminal (Repair by 24th May)
TRAN | - | Line | 901110461 | CLO | 2 | 1 | Hotspot 6 (Transposition Tower No. 58 Span 57/58) Right Jumper Terminal (Repair by 24th Oct)
TRAN | - | Line | 901110462 | CLO | 2 | 1 | Hotspot 1 (Transposition Tower No. 58 Span 58/59) Right Jumper Terminal (Repair by 24th Oct)
110kV FEEDER - AUGHINISH MONETEEN
TO-20-AUG-MTN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 2 |  | 110 kV A1 @ AUG: Proximity outage for work on Aughinish 110kV Coupler/Sectionalising CB Ordinary Service including busbar disconnects (SA1)
FO_MISC |  |  | 901084931 | DO | 1 | 4 | 2019HP-1[19]Off Plumb -plumb poles
OPT | AUG |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MTN |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - BALLYDINE CULLENAGH
TO-20-BDN-CUL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900727019 | CANC | 3 | 1 | 2015HP-3[26,35,40]Off Plumb Poles
TO-20-BDN-CUL-1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BDN-CUL-1-02 ISO week: 37we - 37fr Date: 09 Sep - 11 Sep Duration: 3 Days (3 WD) Status: Scheduled
FO_MISC |  | - | 900649538 | DO | 4 | 1 | 2014HP-[27,35,40,48,55,56]Off Plumb
FO_MISC |  | - | 900649539 | DO | 4 | 1 | 2014HP-[58,59,60,77,97,99,107]Off Plumb
110kV FEEDER - BALLYDINE DOON
TO-20-BDN-DOO-1-01 ISO week: 31th - 32th Date: 30 Jul - 06 Aug Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983907 | CLO | 2 | 1 | 2018HP-1[2]Replace Pole only-Rot
OS | BDN | - | 901151576 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | BDN |  | 901091975 | CLO | 3 | 1 | Replacement of Stolen Earths
OPT | DOO |  | 901129614 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK1 [Merck Sharp & Dohme]
TO-20-BDN-MRK1-01 ISO week: 30we - 30fr Date: 22 Jul - 24 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BDN: Proximity outage for work on Ballydine 110kV Sect / Dist Ordinary Service (SA1)
Replace Stolen Earths
OPT | BDN |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - BALLYDINE MRK3 [Merck Sharp & Dohme]
TO-20-BDN-MRK3-01 ISO week: 29mo - 30mo Date: 13 Jul - 20 Jul Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | BDN | - | 901042188 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
CM | BDN | - | 901091974 | CLO | 3 | 1 | Replace Stolen Earths
110kV FEEDER - BANDON BRINNY 1
TO-20-BAN-BRI-1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON BRINNY 2
TO-20-BAN-BRI-2-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| BAN | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON DUNMANWAY
TO-20-BAN-DMY-1-02 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BAN-DMY-1-04 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
As consequence of Bandon-Brinny 110kV outage
TO-20-BAN-DMY-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  | 901129476 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON RAFFEEN
TO-20-BAN-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900984137 | DO | 1 | 4 | 2018HP-1[MP141]Arcing horns-Replace
FO_MISC |  |  | 900995455 | DO | 1 | 2 | 2019HP-1[141]Arching Horns -Missing
TO-20-BAN-RAF-1-01 ISO week: 37we - 38tu Date: 09 Sep - 15 Sep Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084834 | DO | 2 | 2 | 2019HP-1[151]Insulator broken aux insul
TRAN |  | - | 900984142 | DO | 1 | 4 | 2018HP-1[77]Off PlumbPlumb poles
OPT | BAN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | RAF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | RAF | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | RAF | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | RAF |  | 901147760 | DO | 2 | 1 | Hotspot 1 (Strain Pole No.114, Span 114/115) Centre Jumper Terminal (Repair by 6th Nov)
CORRECT | RAF |  | 901028752 | DO | 1 | 1 | O1-Bandon 110kv Cubicle Moss Build Up
CORRECT | RAF |  | 901028753 | DO | 1 | 1 | O1-Bandon 110kv CB SF6 Indicator corrode
COUPLER/SECTIONALISING CB - BARODA 110SA1-2CB
TO-20-BDA-110SA1-2CB-01 ISO week: 30mo - 30we Date: 20 Jul - 22 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CORRECT | BDA |  | 901087481 | DO | 2 | 1 | Arrange outage to complete testing of Ci
110kV FEEDER - BARODA MONREAD
TO-20-BDA-MON-1-01 ISO week: 13mo - 13fr Date: 23 Mar - 27 Mar Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | BDA | - | 901129957 | CLO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | BDA | - | 900567665 | DO | 2 | 4 | Repair Mid-Point Link Box
CA | BDA | - | 901129183 | CLO | 2 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | BDA | - | 900567665 | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CORRECT | BDA |  | 901076771 | DO | 1 | 1 | Reclosing sw protection panel : while tu
OS | MON | - | 901129932 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | MON |  | 901076757 | DO | 1 | 1 | PI on DL/DE o/o/o
CORRECT | MON |  | 901076765 | DO | 1 | 1 | CT T-phase insulator damaged
110kV FEEDER - BARODA NEWBRIDGE
TO-20-BDA-NEW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ NEW: Proximity outage for work on Newbridge 110kV Sect / Dist Ordinary Service (SA2)
TO-20-BDA-NEW-1-01 Status: Unscheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | BDA | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | BDA | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
AMCAB | BDA | - |  | DO | 1 | 1 | Inspect Phisterer CSE's (check serial number)
CA | NEW | - |  | DO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | NEW | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | NEW |  | 901078182 | DO | 3 | 1 | surge counter illigable
TSO CUSTOMER TRANSFORMER - BARODA T101 [Pfizer]
TO-20-BDA-T101-01 ISO week: 35mo - 36we Date: 24 Aug - 02 Sep Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - |  | DO | 4 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | BDA |  | 900796245 | DO | 1 | 1 | Fire alarm to be certafied
TSO CUSTOMER TRANSFORMER - BARODA T102 [Pfizer]
TO-20-BDA-T102-01 ISO week: 30mo - 31we Date: 20 Jul - 29 Jul Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
CA | BDA | - | 901129202 | CLO | 5 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | BDA | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | BDA | - | 901129127 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - BELCAMP DARNDALE 1
TO-20-BLC-DND-1-01 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ DND + BLC-DND-1: Energise Darndale T123
110kV FEEDER - BELCAMP DARNDALE 3
TO-20-BLC-DND-3-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1013_OS | DO | 2 |  | EI: EI for T124 also requires outage of Belcamp 3 cubicle
TO-20-BLC-DND-3-02 ISO week: 47we - 47th Date: 18 Nov - 19 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1013 | DO | 2 |  | EI: Simultaneous 110 kV A2/B2 IN TURN @ DND + BLC-DND-3: Energise Darndale T122
220kV FEEDER - BELCAMP FINGLAS
TO-20-BLC-FIN-1-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
TRANSFORMER - BELCAMP T2103
TO-20-BLC-T2103-01 ISO week: 36fr - 37we Date: 04 Sep - 09 Sep Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0437 | DO | 4 |  | As a consequence of BLC-FIN-1: Earthgrid, impedance testing along with the busbar to busbar phasing test will require outages.
TSO CUSTOMER TRANSFORMER - BRINNY T101 [Merck Sharp & Dohme]
TO-20-BRI-T101-02 ISO week: 36we - 36th Date: 02 Sep - 03 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-BRI-1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BRI-T101-01 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | BRI | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CAHIR DOON
TO-20-CAH-DOO-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900897597 | DO | 5 | 2 | 2017HP-5[5,12,13,33,37]Off Plumb
FO_MISC |  | - | 900897598 | DO | 3 | 2 | 2017HP-4[47,56,72,75]Off Plumb
FO_MISC |  |  | 901084938 | DO | 3 | 2 | 2019HP-5[14,29,30,37,38]Off Plumb
FO_MISC |  |  | 901084939 | DO | 1 | 2 | 2019HP-3[53,56,72]Off Plumb -plumb poles
|  |  | 901132793 |  |  |  | Poles currently in crop, good chance it will be cut by 13th of July KK
CM | CAH | - | 901134764 | CLO | 2 | 1 | T Phase Doon 110kV Cubicle. TPhase CB connection DUE : 17-Nov-2 hotspot
OPT | CAH |  | 901129607 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | DOO | - | 901129615 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CASTLEFARM T101 [Aughinish Alumina]
TO-20-CFM-T101-01 ISO week: 46mo - 47fr Date: 09 Nov - 20 Nov Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | As a consequence of AUG-CFM-1
| CFM |  |  |  | 15 |  | Customer works
TSO CUSTOMER TRANSFORMER - CASTLEFARM T102 [Aughinish Alumina]
TO-20-CFM-T102-01 ISO week: 38mo - 40fr Date: 14 Sep - 02 Oct Duration: 19 Days (15 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | As a consequence of AUG-CFM-2
| CFM |  |  |  | 15 |  | Customer works
110kV FEEDER - CLOGHRAN CORDUFF
TO-20-CLG-CDU-1-02 ISO week: 27tu - 27th Date: 30 Jun - 02 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | CDU |  | 900637313 | CLO | 2 | 2 | O/1 SURGE ARRESTOR BROKEN
OPT | CDU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CLG |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLOGHRAN FINGLAS GIS
TO-20-CLG-FIN GIS-1-01 ISO week: 48we - 48fr Date: 25 Nov - 27 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | CLO | - | 900840443 | DO | 2 | 3 | Annual Insp. 110kV Feeder XLPE Cable
AMCAB | FIN | - | 901115062 | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - CLOGHRAN T121 [Amazon]
TO-20-CLG-T121-01 ISO week: 43mo - 43fr Date: 19 Oct - 23 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
| CLG |  |  |  | 5 |  | 5 Day Customer Outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T122 [Amazon]
TO-20-CLG-T122-01 ISO week: 40mo - 40fr Date: 28 Sep - 02 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
TSO CUSTOMER TRANSFORMER - CLOGHRAN T123 [Amazon]
TO-20-CLG-T123-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 5 |  | 5 Day Customer outage
OPT | CLG | 110 | 901030848 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLOGHRAN T124 [Amazon]
TO-20-CLG-T124-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
| CLG |  |  |  | 4 |  | 4 day customer outage
AMCAB | CLG | 110 | 901006517 | DO | 3 | 3 | Annual Insp. 110kV Feeder XLPE Cable
TSO CUSTOMER TRANSFORMER - CLOGHRAN T126 [Amazon]
TO-20-CLG-T126-01 ISO week: 45mo - 45fr Date: 02 Nov - 06 Nov Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  |  | 5 |  | 5 day customer outage
220kV FEEDER - CLONEE CORDUFF
TO-20-CLE-CDU-1-01 ISO week: 47th - 49we Date: 19 Nov - 02 Dec Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OPT | CLE | - | 901045472 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - CLONEE T221 [Facebook]
TO-20-CLE-T221-02 ISO week: 39mo - 41mo Date: 21 Sep - 05 Oct Duration: 15 Days (11 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 10 |  | Customer outage request
TSO CUSTOMER TRANSFORMER - CLONEE T224 [Facebook]
TO-20-CLE-T224-01 ISO week: 37we - 38th Date: 09 Sep - 17 Sep Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 7 |  | Customer outage
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CLE |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
220kV FEEDER - CLONEE WOODLAND
TO-20-CLE-WOO-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985608 | DO | 1 | 4 | 2018HP-1[3]Check Struct/Found/etc-base
OS | WOO | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | WOO | - | 901046058 | DO | 1 | 4 | HV Pressure Vessel Inspection
110kV FEEDER - COLLEGE PARK CORDUFF
TO-20-COL-CDU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1 @ COL: Proximity outage for work on College Park 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-COL-CDU-1-01 Status: Unscheduled
PROX |  |  | PR0004 | DO | 3 |  | 110 kV A1/A3 @ COL: Proximity outage for work on College Park 110kV SA1-3 Sect / Dist Ordinary Service
TO-20-COL-CDU-1-02 Status: Unscheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | COL | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | COL |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
TO-20-COL-CDU-1-04 Status: Unscheduled
CM | COR | - | 900981227 | CLO | 2 | 1 | R Phase Hotspot found on R Phase CT HV Connection DUE IMMEDIATELY0
110kV FEEDER - COLLEGE PARK FINGLAS GIS
TO-20-COL-FIN GIS-1-01 ISO week: 9th - 10tu Date: 27 Feb - 03 Mar Duration: 6 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FOSTRHW |  |  | 901086432 | CLO | 2 | 2 | 2019HP-1[14]Replace Pole only -Rot
OS | COL | - | 901128698 | CLO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
110kV FEEDER - CORDUFF MACETOWN
TO-20-CDU-MCE-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CDU | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
CORRECT | MCE |  | 901072034 | CLO | 2 | 2 | CORDUFF SCADA SWITCH FAULTY
OPT | MCE |  | 901129598 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CORDUFF RYEBROOK GIS
TO-20-CDU-RYB GIS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0668 | DO | 30 |  | EI: Replacement of tower 29 on Corduff Ryebrook OHL.
TO-20-CDU-RYB GIS-1-01 ISO week: 48th - 48fr Date: 26 Nov - 27 Nov Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T133
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A3 @ RYB GIS + CDU-RYB GIS-1: Energise T133
110kV FEEDER - CORDUFF SNUGBOROUGH
TO-20-CDU-SNU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T101 and Coupler K1
TO-20-CDU-SNU-1-02 Status: Unscheduled
CAPX |  |  | CP1014 | DO | 2 |  | EI: Energise T103
TO-20-CDU-SNU-1-03 Status: Unscheduled
De-gas 110kV Cubicles for repair
BUSBAR SECTION - CORRACLASSY 110 kV A1
TO-20-110 kV A1 @ COR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | COR |  |  |  | 5 |  | Busbar outage for cubicle assessment on COR-ENS PST
110kV FEEDER - CORRACLASSY GORTAWEE
TO-20-COR-GWE-1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084872 | DO | 1 | 4 | 2019HP-1[69]Earths-Replace L/pole e/w
OS | COR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | COR | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | COR | 110-DA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - COW CROSS OLDCOURT 2 [SDCC]
TO-20-COW-OLD-2-01 ISO week: 9tu Date: 25 Feb Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
110kV FEEDER - COW CROSS WHITEGATE [Irving Oil]
TO-20-COW-WHI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900985959 | DO | 1 | 4 | "2018HP-2[50,73]Off PlumbPlumb poles"
FO_MISC |  |  | 901084968 | DO | 1 | 2 | 2019HP-2[71,72]Off Plumb -plumb poles
CORRECT | WHI |  | 901059047 | NS |  | 1 | O1- Disconnects heavily corroded.
TO-20-COW-WHI-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084140 | DO | 1 | 2 | 2019HP-1[40]Arching Horns -Replace
FO_MISC |  |  | 901084141 | DO | 1 | 2 | 2019HP-1[38]Arching Horns -Replace
FO_MISC |  |  | 901084142 | DO | 1 | 2 | 2019HP-1[36]Arching Horns -Replace
OPT | COW |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - DERRYIRON KINNEGAD
TO-20-DER-KIN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-DER-KIN-1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084275 | CLO | 1 | 4 | 2019HP-1[71]Bird Nests
CORRECT | DER |  | 900623151 | CLO | 1 | 1 | ESBI N01 non outage (important) Misc- wo
CORRECT | KIN |  | 901087474 | CLO | 1 | 2 | Measurement of copper conductor diameter
110kV FEEDER - DERRYIRON MAYNOOTH
TO-20-DER-MAY-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | MAY | - | 901045929 | CANC | 3 | 1 | Investigate CB gas leak & repair if possible
TO-20-DER-MAY-1-01 ISO week: 39mo - 42fr Date: 21 Sep - 16 Oct Duration: 26 Days (20 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  |  |  | 2 |  | proximity needed of Derryiron - Maynooth for maintenance on Dunstown - Maynooth 2
FO_MISC |  |  | 901084970 | DO | 2 | 4 | 2019HP-1[4]Off Plumb -plumb poles
FO_MISC |  |  | 901084971 | DO | 2 | 4 | 2019HP-1[28]Off Plumb -plumb poles
FO_MISC |  |  | 901084972 | DO | 2 | 4 | 2019HP-1[29]Off Plumb -plumb poles
FO_MISC |  |  | 901084973 | DO | 2 | 4 | 2019HP-1[160]Off Plumb -plumb poles
FO_MISC |  |  | 901084974 | DO | 2 | 4 | 2019HP-1[161]Off Plumb -plumb poles
FO_MISC |  |  | 901084975 | DO | 2 | 4 | 2019HP-1[164]Off Plumb -plumb poles
FO_MISC |  |  | 901084976 | DO | 2 | 4 | 2019HP-1[181]Off Plumb -plumb poles
FO_MISC |  |  | 901084977 | DO | 2 | 4 | 2019HP-1[182]Off Plumb -plumb poles
FO_MISC |  |  | 901084978 | DO | 2 | 4 | 2019HP-1[183]Off Plumb -plumb poles
FOSTRHW |  |  | 901086429 | DO | 2 | 1 | 2019HP-1[75]Replace Pole only -Rot
FOSTRHW |  |  | 901086430 | DO | 2 | 1 | 2019HP-1[106]Replace Pole only -Rot
FOSTRHW |  |  | 901086431 | DO | 2 | 1 | 2019HP-1[124]Replace Pole only -Rot
PROX |  |  | PR0001 | DO | 2 |  | Proximity outage for work on Dunstown-Maynooth-2 220 kV
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
| - | Line | 901150823 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 116 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150824 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 117 need to be replaced by the autumn 2020 before winter storms commence.
| - | Line | 901150825 | DO | 2 | 1 | As a result of fire damage, polesets, hardware and insulators at positions 118 need to be replaced by the autumn 2020 before winter storms commence.
OPT | DER |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAY |  | 901080694 | DO | 3 | 2 | Missing Earths on Earths on CB
AMCAB | MAY | - | 900944029 | DO | 2 | 3 | Annual Insp. 110 Feeder OF Cable
110kV FEEDER - DUNDALK LOUTH
TO-20-DDK-LOU-1-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | DDK |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-DDK-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 901087469 | DO | 1 | 1 | EMP AMS Replace CB Counter
TO-20-DDK-LOU-1-03 Status: Unscheduled
CORRECT | DDK |  | 901082258 | CANC |  | 1 | N O 1 Louth H4 (Mal)Louth DL Fault
110kV FEEDER - DUNDALK MULLAGHARLIN
TO-20-DDK-MLN-1-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
110kV FEEDER - DUNFIRTH tee KINNEGAD
TO-20-DFR,T-KIN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | KIN | - | 901042225 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-DFR,T-KIN-1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-DFR,T-KIN-1-03 Status: Unscheduled
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee RINAWADE
TO-20-DFR,T-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DFR,T-RNW-1-01 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | RNW | - |  | DO | 10 | 4 | 110kV SF6 Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - DUNMANWAY 110SA1-2CB
TO-20-DMY-110SA1-2CB-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-110SA1-2CB-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-110SA1-2CB-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-DMY-110SA1-2CB-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-110SA1-2CB-02 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
OS | DMY | 110-SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - DUNMANWAY MACROOM
TO-20-DMY-MAC-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-DMY-MAC-1-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-DMY-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-DMY-MAC-1-10 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-MAC-1-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-MAC-1-07 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-MAC-1-04 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
TRAN |  | - | 900986469 | DO | 1 | 4 | 2018HP-1[84]Off PlumbPlumb poles
TRAN |  | - | 901148535 | DO | 1 | 1 | Oxlip earth position movement
Work on Location 124 to stop tripping
OPT | DMY | - | 901058948 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | MAC | - | 901050325 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - FLAGFORD GILRA
TO-20-FLA-GIL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
[5 empty] | 1 |  | Extra day required for covid restrictions
OS | FLA | - | 901129904 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - GILRA T121 [Masonite]
TO-20-GIL-T121-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
As a consequence of work on Flagford-Gilra 110 kV
TSO CUSTOMER TRANSFORMER - GORTAWEE T101 [Sean Quinn Cement]
TO-20-GWE-T101-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
| GOR |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Sean Quinn Cement]
TO-20-GWE-T102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-T102-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | GWE |  | 901073971 | DO | 2 | 1 | T102 110kV CB: SF6 Gauge corroded and ne
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILTEEL MAYNOOTH
TO-20-KTL-MAY-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900247574 | DO | 2 | 3 | Replace Member mast no 86 replace bent b
FO_MISC |  | - | 900897418 | DO | 1 | 2 | 2017HP-1[11]Off Plumb -Poles
OPT | KTL | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILTEEL MONREAD
TO-20-KTL-MON-1-01 ISO week: 23tu - 24mo Date: 02 Jun - 08 Jun Duration: 7 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CORRECT | MON |  | 901076758 | CLO | 5 | 1 | Low Gas
OPT | MON | - | 901055117 | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - KINNEGAD 110SA1-2CB
TO-20-KIN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | KIN | - | 901042251 | DO | 2 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KIN | 110-SA1 | 901042964 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-KIN-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | KIN | 110-SA2 | 901042963 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TSO CUSTOMER TRANSFORMER - KINNEGAD T101 [Lagan Cement]
TO-20-KIN-T101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-KIN-T101-03 Status: Unscheduled
CORRECT | KIN |  | 901068813 | CANC |  | 1 | replacement of the CT’s in Kinnegad T101
TO-20-KIN-T101-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KIN | - | 901042268 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - KINNEGAD T102 [Lagan Cement]
TO-20-KIN-T102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | KIN | TRAFO | 901080654 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LIMERICK MONETEEN
TO-20-LIM-MTN-1-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ LIM: Proximity outage for work on Limerick 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_STDMG |  | - | 900567326 | DO | 2 | 1 | 3[509,510,511] DCIMP5 badly kinked (IMP49 KIL-LIM 1)
OPT | LIM |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LOUTH MULLAGHARLIN
TO-20-LOU-MLN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-LOU-MLN-1-03 Status: Unscheduled
CORRECT | LOU |  | 901059534 | CANC |  | 1 | N O 1 H01 Mullagharlin Switching and
TO-20-LOU-MLN-1-02 ISO week: 45fr Date: 06 Nov Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MACETOWN SNUGBOROUGH
TO-20-MCE-SNU-1-01 ISO week: 47mo - 47we Date: 16 Nov - 18 Nov Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901068538 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | SNU | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | SNU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MACETOWN T121 [IBM]
TO-20-MCE-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ511
TSO CUSTOMER TRANSFORMER - MACETOWN T124 [IBM]
TO-20-MCE-T124-01 ISO week: 47tu Date: 17 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MCE | - | 901038753 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MAYNOOTH RINAWADE
TO-20-MAY-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 220 kV K3-4
TO-20-MAY-RNW-1-03 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-MAY-RNW-1-01 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MAY | - | 901042239 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | RNW | - | 901038949 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - MAYNOOTH RYEBROOK GIS
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-05 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Maynooth 110 kV K3-4
TO-20-MAY-RYB GIS-1-01 ISO week: 43we - 43th Date: 21 Oct - 22 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1056 | DO | 2 |  | EI: T132 EI - outage of feeder bay required for 2 days
TO-20-MAY-RYB GIS-1-04 ISO week: 46th - 46fr Date: 12 Nov - 13 Nov Duration: 2 Days (2 WD) Status: Proposed
CAPX |  |  | CP1056 | DO | 2 |  | EI: Energise T131
CAPX |  |  | CP1056 | DO | 2 |  | EI: Simultaneous 110 kV A1 @ RYB GIS + MAY-RYB GIS-1: Energise T131
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-20-MID-WHI-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988883 | DO | 2 | 4 | "2018HP-2[41,42]Sus/Dup 110kV replace"
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084330 | DO | 1 | 2 | 2019HP-1[22]Bird Nests Over Right phase
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
OPT | MID |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - MONETEEN MUNGRET 1
TO-20-MTN-MUN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | MTN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - MONETEEN MUNGRET 2
TO-20-MTN-MUN-2-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Tentative
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | MTN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T121 [Xerox]
TO-20-MLN-T121-02 ISO week: 32th - 32fr Date: 06 Aug - 07 Aug Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Customer outage request
TO-20-MLN-T121-01 ISO week: 33th - 38fr Date: 13 Aug - 18 Sep Duration: 37 Days (27 WD) Status: Scheduled
CAPX |  |  | CP1101 | DO | 27 |  | 110 kV A1 @ MLN: Civil works on bay H1 and H0
CAPX |  |  | CP1101 | DO | 2 |  | T121 Trafo Relabelling to T123
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLN | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - MULLAGHARLIN T122 [Xerox]
TO-20-MLN-T122-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MLN: Proximity outage for work on Mullagharlin 110kV Sect / Dist Ordinary Service (SA2)
TO-20-MLN-T122-03 ISO week: 32tu - 32we Date: 04 Aug - 05 Aug Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Customer outage request
TSO CUSTOMER TRANSFORMER - MUNGRET T101 [Irish Cement]
TO-20-MUN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Customer outage requestfor tap changer maintenance on incoming transformer T101
TSO CUSTOMER TRANSFORMER - MUNGRET T102 [Irish Cement]
TO-20-MUN-T102-01 ISO week: 37mo - 37fr Date: 07 Sep - 11 Sep Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 5 |  | As a consequence of MTN-MUN-2: 110 kV A2 @ MTN: Proximity outage for work on Moneteen 110kV Sect / Dist Ordinary Service (SA2)
TSO CUSTOMER TRANSFORMER - PLATIN T105 [Irish Cement]
TO-20-PLA-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
Customer works
CORRECT | PLA |  | 901087478 | DO | 5 | 2 | Replace CB Counter
TSO CUSTOMER TRANSFORMER - RINAWADE T121 [Hewlett Packard]
TO-20-RNW-T121-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RNW-T121-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SJ511
OPT | RNW | - | 901038951 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - RINAWADE T122 [Hewlett Packard]
TO-20-RNW-T122-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RNW | - | 901038952 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T105 [Intel]
TO-20-RYB GIS-T105-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T106 [Intel]
TO-20-RYB GIS-T106-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TO-20-RYB GIS-T106-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T107 [Intel]
TO-20-RYB GIS-T107-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | RYB | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
AMCAB | RYB | - | 900926063 | DO | 2 | 3 | INSP. 110 STATION XLPE CABLE
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T108 [Intel]
TO-20-RYB GIS-T108-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB | RYB | - |  | DO | 2 | 4 | INSP. 110 STATION XLPE CABLE
TO-20-RYB GIS-T108-02 Status: Unscheduled
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T109 [Intel]
TO-20-RYB GIS-T109-01 ISO week: 22tu - 23tu Date: 26 May - 02 Jun Duration: 8 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | RYB | - | 901129747 | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - RYEBROOK GIS T131 [Intel]
TO-20-RYB GIS-T131-01 ISO week: 47mo Date: 16 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1056 | DO | 1 |  | Intel request to test transformer oil from T131. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
CAPX |  |  | CP1056 | DO | 1 |  | 110 kV A3/B3 @ RYB GIS: Intel request to test transformer oil from T133. Test is required after enerigisation. HV CB, busbar & transformer disconnects will need to be switched.
TSO CUSTOMER TRANSFORMER - SHELTON ABBEY T102 [Holfeld Plastics]
TO-20-SHE-T102-01 ISO week: 48mo - 51th Date: 23 Nov - 17 Dec Duration: 25 Days (19 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
proximity outage to allow ESBN carry out the replacement of the corroded gantry in Shelton Abbey compound
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T101 [Irving Oil]
TO-20-WHI-CKB-T101-02 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
| WHI |  |  | DO | 5 |  | Customer outage request
OS | WHI | - | 901042301 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | WHI |  | 901039125 | DO | 1 | 2 | O1-Water in CB Mech Box.
TO-20-WHI-CKB-T101-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T102 [Irving Oil]
TO-20-WHI-CKB-T102-01 ISO week: 39mo - 39fr Date: 21 Sep - 25 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | WHI |  | 901059048 | DO | 1 | 2 | O1-Replace bird guard on CB.Severely rus

## CORK (Rgn)
BUSBAR SECTION - AGHADA 220 kV A1
TO-20-220 kV A1 @ AD-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV A2
TO-20-220 kV A2 @ AD-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV B1
TO-20-220 kV B1 @ AD-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A1/B1 IN TURN @ AD: Busbar Changeover
BUSBAR SECTION - AGHADA 220 kV B1/B2
TO-20-220 kV B1/B2 @ AD-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart test
BUSBAR SECTION - AGHADA 220 kV B2
TO-20-220 kV B2 @ AD-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0001 | DO | 1 |  | 220 kV A2/B2 IN TURN @ AD: Busbar Changeover
COUPLER/SECTIONALISING CB - AGHADA 220K1-2
TO-20-AD-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of ISM21
CORRECT | AD |  | 900891284 | DO | 3 | 2 | V-string busbar insulator has corrosion
CORRECT | AD |  | 900912297 | DO | 2 | 1 | O1-Hotspot Sectionaliser SA
FM | AD | - | 901045781 | DO | 1 | 4 | HV Pressure Vessel Inspection
220kV FEEDER - AGHADA GLANAGOW
TO-20-AD-GGO-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | - |  | DO | 3 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TO-20-AD-GGO-1-01 Status: Unscheduled
Blackstart Test
220kV FEEDER - AGHADA KNOCKRAHA 1
TO-20-AD-KRA-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-AD-KRA-1-05 Status: Unscheduled
OS | AD | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
FM | AD | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
OS | KRA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | KRA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KRA | - | 900719850 | DO | 1 | 2 | O1-Surge Counters have moisture inside.
TO-20-AD-KRA-1-06 ISO week: 29su - 30sa Date: 19 Jul - 25 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901098961 | CLO | 2 | 1 | Hotspot 3 (Lwr 1 Span 28/29) Lower phase midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098964 | CLO | 2 | 1 | Hotspot 4 (Lwr 2 Span 28/29) Lower phase midspan joint (Repair by 30th Jul 2020)
TRAN | - | Line | 901098965 | CLO | 2 | 1 | Hotspot 1 (C1 Span 61/62) Centre Midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098966 | CLO | 2 | 1 | Hotspot 2 (Upr 1 Span 61 / 62) Upper midspan joint (Measure resistance during next available outage)
220kV FEEDER - AGHADA KNOCKRAHA 2
TO-20-AD-KRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-AD-KRA-2-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-AD-KRA-2-05 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-AD-KRA-2-04 ISO week: 29su - 30sa Date: 19 Jul - 25 Jul Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
TRAN | - | Line | 901098967 | CLO | 2 | 1 | Hotspot 3 (C2 Span 28/29) Centre Midspan (Repair by 30th Jul 2020)
TRAN | - | Line | 901098968 | CLO | 2 | 1 | Hotspot 4 (Upr 1 Span 28/29) Upper Midspan (Repair by 30th Oct 2020)
TRAN | - | Line | 901098969 | CLO | 2 | 1 | Hotspot 5 (Upr 2 Span 28/29) Upper Midspan (Repair by 30th Oct 2020)
TRAN | - | Line | 901098970 | CLO | 2 | 1 | Hotspot 2 (C1 Span 61/62) Centre midspan joint (Repair by 30th Oct 2020)
TRAN | - | Line | 901098971 | CLO | 2 | 1 | Hotspot 1 (C2 Span 61/62) Centre midspan joint (Repair by 30th Jul 2020)
220kV FEEDER - AGHADA LONG POINT
TO-20-AD-LPT-1-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | CABLE | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
220kV FEEDER - AGHADA RAFFEEN
TO-20-AD-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2)
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-AD-RAF-1-01 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
TRAN |  | - | 900983098 | DO | 1 | 4 | 2018HP-1[9]Vib Dampers-Replace
OS | AD | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | AD | - |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CORRECT | RAF |  | 901028751 | DO |  | 2 | O1-Aghada 220kv Gantree Glass Insulator
GENERATOR TRANSFORMER - AGHADA ST101 [ESB GWM]
TO-20-AD-ST101-03 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | CP0794 |  | 2 |  | Proximity outge for civil works
GENERATOR TRANSFORMER - AGHADA T2011/12 [ESB GWM AT11/AT12]
TO-20-AD-T2011/12-02 ISO week: 9mo - 23tu Date: 24 Feb - 02 Jun Duration: 100 Days (67 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | AD | - | 901130028 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | AD | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
AMCAB | AD | - | 901129053 | CLO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
FM | AD | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
GENERATOR TRANSFORMER - AGHADA T2014 [ESB GWM AT4]
TO-20-AD-T2014-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-AD-T2014-02 ISO week: 32we - 32th Date: 05 Aug - 06 Aug Duration: 2 Days (2 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, 7UT92
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | AD | - |  | DO | 2 | 4 | Annual Insp. 400 & 220 Station OF Cable
TRANSFORMER - AGHADA T2102
TO-20-AD-T2102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 10 |  | Total Maintenance Outage Duration Requested
OS | AD | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | AD | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | AD | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TRAFO | AD | TRAFO |  | DO | 3 | 4 | 220/110kV Trafo Tap Changer Inspection
TRAFO | AD | TRAFO |  | DO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CA | AD | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | AD | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | AD | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-AD-T2102-01 ISO week: 32we - 32fr Date: 05 Aug - 07 Aug Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | AD |  | 900908020 | DO | 3 | 2 | Oil sampling of cable boxes on T2102 Tra
TO-20-AD-T2102-04 ISO week: 48mo - 48th Date: 23 Nov - 26 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | CP0794 |  | 2 |  | Proximity outage. To facilitate crossing of 110kV cable
110kV FEEDER - AGHADA WHITEGATE [Irving Oil]
TO-20-AD-WHI-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 | 2 | Total Maintenance Outage Duration Requested
OS | AD | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BALLYLICKEY DUNMANWAY [SDCC]
TO-20-BLI-DMY-1-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-DMY-1-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BALLYLICKEY T142 [SDCC]
TO-20-BLI-T142-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-BLI-T142-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-BLI-T142-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-BLI-T142-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | As a consequence of BLI-DMY-1: 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
220kV FEEDER - BALLYVOUSKILL CLASHAVOON
TO-20-BVK-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101
TO-20-BVK-CLA-1-02 Status: Unscheduled
CM | BVK | - |  | DO | 6 | 2 | Aux Relay - replace contactors
TO-20-BVK-CLA-1-03 Status: Unscheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | BVK | - | 901050433 | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
OS | CLA | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CLA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
SECTIONALISING DISCONNECT - BANDON 110SA1
TO-20-BAN-110SA1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OS | BAN | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - BANDON 110SA2
TO-20-BAN-110SA2-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-110SA1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BANDON BRINNY 1
TO-20-BAN-BRI-1-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON BRINNY 2
TO-20-BAN-BRI-2-01 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| BAN | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BAN | - |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
CAPACITOR/SVC/REACTOR - BANDON CAP1
TO-20-BAN-CAP1-02 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BAN-CAP1-01 ISO week: 23tu - 23fr Date: 02 Jun - 05 Jun Duration: 4 Days (4 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | BAN | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
| BAN | CAP1/CAP3 |  | DO | 3 | 2 | Resolve the issue regarding the isolator switch to the motor circuit for manual charging of closing coil.
CORRECT | BAN |  | 901079629 | CLO |  | 1 | O1- R Phase Manual Handle Limit Switch n
110kV FEEDER - BANDON DUNMANWAY
TO-20-BAN-DMY-1-02 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BAN-DMY-1-04 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Scheduled
As consequence of Bandon-Brinny 110kV outage
TO-20-BAN-DMY-1-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  | 901129476 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - BANDON RAFFEEN
TO-20-BAN-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900984137 | DO | 1 | 4 | 2018HP-1[MP141]Arcing horns-Replace
FO_MISC |  |  | 900995455 | DO | 1 | 2 | 2019HP-1[141]Arching Horns -Missing
TO-20-BAN-RAF-1-01 ISO week: 37we - 38tu Date: 09 Sep - 15 Sep Duration: 7 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084834 | DO | 2 | 2 | 2019HP-1[151]Insulator broken aux insul
TRAN |  | - | 900984142 | DO | 1 | 4 | 2018HP-1[77]Off PlumbPlumb poles
OPT | BAN |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | RAF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | RAF | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | RAF | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | RAF |  | 901147760 | DO | 2 | 1 | Hotspot 1 (Strain Pole No.114, Span 114/115) Centre Jumper Terminal (Repair by 6th Nov)
CORRECT | RAF |  | 901028752 | DO | 1 | 1 | O1-Bandon 110kv Cubicle Moss Build Up
CORRECT | RAF |  | 901028753 | DO | 1 | 1 | O1-Bandon 110kv CB SF6 Indicator corrode
DISTRIBUTION TRANSFORMER - BANDON T101 [SDCC]
TO-20-BAN-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - BANDON T141 [SDCC]
TO-20-BAN-T141-01 ISO week: 40mo - 40we Date: 28 Sep - 30 Sep Duration: 3 Days (3 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - BARNAHELY RAFFEEN 1 [SDCC]
TO-20-BRY-RAF-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
110kV FEEDER - BARNAHELY RAFFEEN 2 [SDCC]
TO-20-BRY-RAF-2-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
110kV FEEDER - BARRYMORE tee KNOCKRAHA
TO-20-BAR,T-KRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_COND | - | - | 901046848 | CANC | 2 | 1 | Hotspot 5 (Angle Tower No.278, span 278/279) Left Deadend (repair by October 2019)
TO-20-BAR,T-KRA-1-03 Status: Unscheduled
FO_COND | - | - | 901046847 | CANC | 2 | 2 | Hotspot 4 (Angle Tower No. 278, span 277/278) Right Deadend (repair by October 2019)
SECTIONALISING DISCONNECT - BOGGERAGH 110SA1
TO-20-BGH-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
SECTIONALISING DISCONNECT - BOGGERAGH 110SA2
TO-20-BGH-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-110SA2-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | BGH | 110-SA2 | 901130115 | CLO | 1 | 4 | 110kV Sect / Dist Operational Test
110kV FEEDER - BOGGERAGH CLASHAVOON
TO-20-BGH-CLA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-CLA-1-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
AMCAB | Cable | - | 901129114 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
CORRECT | CLA |  | 900989872 | CLO | 2 | 1 | O1- Hotspot Boggeragh CT T Phase.
CORRECT | CLA |  | 900973236 | CLO |  | 1 | O1-Main ON sign in c.b. chassis is very
GENERATOR TRANSFORMER - BOGGERAGH T121 [Boggeragh BG1]
TO-20-BGH-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T121-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
GENERATOR TRANSFORMER - BOGGERAGH T132 [Boggeragh BG2]
TO-20-BGH-T132-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T132-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Scheduled
As a consequence of work on Boggeragh-Clashavoon 110 kV
DISTRIBUTION TRANSFORMER - BOGGERAGH T142 [SDCC]
TO-20-BGH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | As a consequence of BGH-CLA-1: Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-BGH-T142-02 ISO week: 31we - 31fr Date: 29 Jul - 31 Jul Duration: 3 Days (3 WD) Status: Reference
As a consequence of work on Boggeragh-Clashavoon 110 kV
TSO CUSTOMER TRANSFORMER - BRINNY T101 [Merck Sharp & Dohme]
TO-20-BRI-T101-02 ISO week: 36we - 36th Date: 02 Sep - 03 Sep Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | As a consequence of BAN-BRI-1: 110 kV A1 @ BAN: Proximity outage for work on Bandon 110kV Sect / Dist Ordinary Service (SA1)
TO-20-BRI-T101-01 ISO week: 36we - 36fr Date: 02 Sep - 04 Sep Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | BRI | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CARRIGADROHID KILBARRY
TO-20-CD-KBY-1-02 ISO week: 30mo - 35fr Date: 20 Jul - 28 Aug Duration: 40 Days (29 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1037 | DO | 21 |  | Proximity outage due to proximity of the bays within the station.
TO-20-CD-KBY-1-01 ISO week: 38mo - 48fr Date: 14 Sep - 27 Nov Duration: 75 Days (54 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 55 |  | Terminating 110 kV cable at station bay and end masts
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
FO_MISC |  |  | 901084947 | DO |  | 2 | 2019HP-1[120]Off Plumb -plumb poles
OS | CD | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | CD | - | 900973233 | DO | 1 | 1 | O1-Cb,CT & DA slight algae growth.
OS | KBY | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CORRECT | KBY |  | 900894946 | DO |  | 1 | O1-DA not showing open position indicati
110kV FEEDER - CARRIGADROHID MACROOM
TO-20-CD-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-CD-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-CD-MAC-1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-CD-MAC-1-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of REL521, REL551
OPT | CD |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | MAC | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
GENERATOR TRANSFORMER - CARRIGADROHID T103 [ESB GWM LE3]
TO-20-CD-T103-01 ISO week: 25tu - 26tu Date: 16 Jun - 23 Jun Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | CD |  | 901129579 | CLO | 1 | 4 | 110KV SF6 Cubicle Operational Test
110kV FEEDER - CARRIGDANGAN DUNMANWAY [Carrigdangan CDN1]
TO-20-CDN-DMY-1-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-CDN-DMY-1-07 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-CDN-DMY-1-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-CDN-DMY-1-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA1
TO-20-CVW-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - CASTLEVIEW 110SA2
TO-20-CVW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | CVW | SA2 | 901038579 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - CASTLEVIEW COW CROSS
TO-20-CVW-COW-1-01 ISO week: 19tu - 19fr Date: 05 May - 08 May Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, R1Z23b
OPT | COW |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
AMCAB | CVW | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CVW |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | CVW |  | 901023280 | CLO | 1 | 1 | O1-Cowcross 7SA5111 Relay faulty display
CORRECT | CVW |  | 901052222 | CLO | 1 | 1 | O1-Scada not commissioned on this bay.
110kV FEEDER - CASTLEVIEW KNOCKRAHA
TO-20-CVW-KRA-1-01 ISO week: 35mo - 35fr Date: 24 Aug - 28 Aug Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
OS | CVW | - | 901042211 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
AMCAB | CVW | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OS | KRA | - | 901042300 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CHARLEVILLE MALLOW
TO-20-CHA-MAL-1-01 ISO week: 31mo - 31fr Date: 27 Jul - 31 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985441 | CLO | 4 | 4 | "2018HP-6[16,19,62,72,81,92]Off Plumb"
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FO_MISC |  |  | 901084959 | CLO | 1 | 2 | 2019HP-2[61,62]Off Plumb -plumb poles
OPT | CHA | - |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MAL | - | 901076481 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
BUSBAR SECTION - CLASHAVOON 110 kV A1
TO-20-110 kV A1 @ CLA-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1)
TO-20-110 kV A1 @ CLA-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
TO-20-110 kV A1 @ CLA-02 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV A2
TO-20-110 kV A2 @ CLA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2)
TO-20-110 kV A2 @ CLA-01 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV B1
TO-20-110 kV B1 @ CLA-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A1/B1 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA1)
TO-20-110 kV B1 @ CLA-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
TO-20-110 kV B1 @ CLA-02 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A1/B1 IN TURN @ CLA: Busbar Changeover
BUSBAR SECTION - CLASHAVOON 110 kV B2
TO-20-110 kV B2 @ CLA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0001 | DO | 2 |  | 110 kV A2/B2 IN TURN @ CLA: Proximity outage for work on Cashla 110kV Coupler/Sectionalising CB (SA2)
TO-20-110 kV B2 @ CLA-01 ISO week: 37th Date: 10 Sep Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 | DO | 1 |  | 110 kV A2/B2 IN TURN @ CLA: Busbar Changeover
COUPLER/SECTIONALISING CB - CLASHAVOON 110K1-2
TO-20-CLA-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
COUPLER/SECTIONALISING CB - CLASHAVOON 220K1-2
TO-20-CLA-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | CLA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | CLA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | CLA | 110-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | CLA | 110-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
110kV FEEDER - CLASHAVOON CLONKEEN
TO-20-CLA-CKN-1-01 ISO week: 9we - 22su Date: 26 Feb - 31 May Duration: 96 Days (64 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0996 | DO | 60 |  | EI: Realingment of the line to allow for the construction of the new N22 bypass. A number of new towers are being constructed and polesets moved
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084961 | CLO | 1 | 2 | 2019HP-1[131]Off Plumb -plumb poles
FO_MISC |  |  | 901084962 | CLO | 1 | 2 | 2019HP-2[91,92]Off Plumb -plumb poles
FO_MISC |  |  | 901084963 | CLO | 1 | 2 | 2019HP-2[76,77]Off Plumb -plumb poles
FO_MISC |  |  | 901084964 | DO | 1 | 2 | 2019HP-2[19,20]Off Plumb -plumb poles
AMCAB | CKN | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | CKN |  | 901129659 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
AMCAB | CLA | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - CLASHAVOON DUNMANWAY
TO-20-CLA-DMY-1-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
220kV FEEDER - CLASHAVOON KNOCKRAHA
TO-20-CLA-KRA-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-CLA-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-CLA-KRA-1-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-CLA-KRA-1-05 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | Proximity outage to allow for A1B1 busbar section to be retired
TO-20-CLA-KRA-1-04 ISO week: 48mo - 48fr Date: 23 Nov - 27 Nov Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | Proximity outage to allow for A1/B1 busbar section to be retired
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA513, GRL100
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA513, GRL100
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | CLA | - | 901050471 | DO | 1 | 3 | 220kV SF6 Cubicle Operational Test
CORRECT | KRA | - | 901091471 | DO | 5 | 1 | Replace stolen earths
OPT | KRA | - | 901038860 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - CLASHAVOON MACROOM 1
TO-20-CLA-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
TO-20-CLA-MAC-1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-CLA-MAC-1-01 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-CLA-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-CLA-MAC-1-05 Status: Unscheduled
[5 empty] | 3 |  | Offline PD test on new cable
| - | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | MAC | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CLASHAVOON MACROOM 2
TO-20-CLA-MAC-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-CLA-MAC-2-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-CLA-MAC-2-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-CLA-MAC-2-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084965 | CLO | 1 | 2 | 2019HP-1[12]Off Plumb -plumb poles
OPT | MAC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MAC |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
TRANSFORMER - CLASHAVOON T2101
TO-20-CLA-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 85 |  | Remove old 125 MVA trafo and bund, constuct new bund, install and commission new 250 MVA trafo.
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1/B1 @ CLA + CLA-T2101: Half station for replacement of bay conductor and VTs in T2101 bay
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV B1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
CAPX |  |  | CP0829 | DO | 15 |  | Simultaneous 110 kV A1 @ CLA + CLA-T2101: Install foundations for post insulators in T2101 bay
CAPX |  |  | CP0829 | DO | 2 |  | EI: Simultaneous BVK-CLA-1 + CLA-T2101: EI of new T2101
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | CLA | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | CLA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CLA | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | CLA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | CLA | - | 900973237 | DO | 1 | 2 | O1- S phase bushing low in oil.
TO-20-CLA-T2101-04 Status: Unscheduled
CORRECT | CLA |  | 900908038 | NS |  | 2 | Replace timber supports on T2101 Transfo
TRANSFORMER - CLASHAVOON T2102
TO-20-CLA-T2102-01 ISO week: 28mo - 30tu Date: 06 Jul - 21 Jul Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | CLA | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | CLA | TRAFO |  | DO | 4 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | CLA | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | CLA | 220 |  | DO | 3 | 4 | 220kV CUBICLE CONDITION ASSESSMENT
CA | CLA | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | CLA |  | 900879219 | DO | 3 | 2 | O1-OLTC Tap position not corresponding w
TRAFO | CLA | TRAFO | 901130541 | CLO | 3 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
CORRECT | CLA | TRAFO | 900909472 | CLO | 2 | 2 | O1- Moss on all equipment in Cubicle
TRAFO | CLA | TRAFO | 901130545 | CLO | 1 | 4 | 220/110kV Trafo Tap Changer Inspection
110kV FEEDER - COOLROE INNISCARRA
TO-20-CRO-IA-1-01 ISO week: 23we - 23fr Date: 03 Jun - 05 Jun Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084967 | CLO | 1 | 2 | 2019HP-2[8,9]Off Plumb -plumb poles
OPT | IA |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - COOLROE KILBARRY
TO-20-CRO-KBY-1-02 ISO week: 39mo - 41fr Date: 21 Sep - 09 Oct Duration: 19 Days (15 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1037 | DO | 34 |  | Proximity outage to facilitate the civil works and installation of the commercial fibre, cable pull, scaffolding erection and calbe termination
TO-20-CRO-KBY-1-01 ISO week: 27mo - 37fr Date: 29 Jun - 11 Sep Duration: 75 Days (54 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 55 |  | Terminating 110 kV cable at station bay and end masts
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA511, REL521
AMCAB | KBY | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
SECTIONALISING DISCONNECT - COW CROSS 110SA2
TO-20-COW-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | COW | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - COW CROSS OLDCOURT 2 [SDCC]
TO-20-COW-OLD-2-01 ISO week: 9tu Date: 25 Feb Duration: 1 Day (1 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 1 | P1 Protection maintenance of 7SA612
110kV FEEDER - COW CROSS RAFFEEN
TO-20-COW-RAF-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CM | RAF |  | 901065864 | CLO | 3 | 1 | Replacement of Stolen Earths
TO-20-COW-RAF-1-01 ISO week: 31mo - 32tu Date: 27 Jul - 04 Aug Duration: 9 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
FOINSHW |  |  | 901085552 | DO | 2 | 2 | 2019HP-2[13,14]Insul&HW Replac check
OS | COW | - | 901129844 | CLO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CORRECT | COW |  | 900934544 | CLO |  | 1 | O1-Maintenance reqd on Raffeen 110 KV su
CORRECT | COW |  | 901068560 | CLO |  | 1 | O1-Top up with oil pole of CB as glass w
AMCAB | RAF | - | 901129143 | CLO | 2 | 4 | Cable Insp. 110kV XLPE
FM | RAF | - |  | DO | 1 | 4 | HV Pressure Vessel Inspection
110kV FEEDER - COW CROSS WHITEGATE [Irving Oil]
TO-20-COW-WHI-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900985959 | DO | 1 | 4 | "2018HP-2[50,73]Off PlumbPlumb poles"
FO_MISC |  |  | 901084968 | DO | 1 | 2 | 2019HP-2[71,72]Off Plumb -plumb poles
CORRECT | WHI |  | 901059047 | NS |  | 1 | O1- Disconnects heavily corroded.
TO-20-COW-WHI-1-01 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084140 | DO | 1 | 2 | 2019HP-1[40]Arching Horns -Replace
FO_MISC |  |  | 901084141 | DO | 1 | 2 | 2019HP-1[38]Arching Horns -Replace
FO_MISC |  |  | 901084142 | DO | 1 | 2 | 2019HP-1[36]Arching Horns -Replace
OPT | COW |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
220kV FEEDER - CULLENAGH KNOCKRAHA
TO-20-CUL-KRA-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 7 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-CUL-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-CUL-KRA-1-01 ISO week: 9mo - 18th Date: 24 Feb - 30 Apr Duration: 67 Days (46 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 4 |  | Proximity outage for work on Knockraha-Raffeen 220 kV
CORRECT | KRA |  | 901081935 | CLO | 3 | 2 | Ordinary service required on DB followin
COUPLER/SECTIONALISING CB - DUNMANWAY 110SA1-2CB
TO-20-DMY-110SA1-2CB-08 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-110SA1-2CB-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-110SA1-2CB-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | DMY |  |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
TO-20-DMY-110SA1-2CB-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-110SA1-2CB-02 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
OS | DMY | 110-SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service
CAPACITOR/SVC/REACTOR - DUNMANWAY CAP2
TO-20-DMY-CAP2-01 ISO week: 22mo - 22fr Date: 25 May - 29 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 4 |  | Total Maintenance Outage Duration Requested
OS | DMY | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-DMY-CAP2-02 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
110kV FEEDER - DUNMANWAY MACROOM
TO-20-DMY-MAC-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-DMY-MAC-1-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-DMY-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-DMY-MAC-1-10 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-MAC-1-09 Status: Unscheduled
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-MAC-1-07 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Scheduled
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-MAC-1-04 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Tentative
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
TRAN |  | - | 900986469 | DO | 1 | 4 | 2018HP-1[84]Off PlumbPlumb poles
TRAN |  | - | 901148535 | DO | 1 | 1 | Oxlip earth position movement
Work on Location 124 to stop tripping
OPT | DMY | - | 901058948 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
OS | MAC | - | 901050325 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
DISTRIBUTION TRANSFORMER - DUNMANWAY T141 [SDCC]
TO-20-DMY-T141-06 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: Installation of busbar dropper.
TO-20-DMY-T141-07 Status: Reference (Unscheduled)
CAPX |  |  | CP0930 | DO | 3 |  | 110 kV A1 @ DMY: EI to prove the new station & customer transformer including 24 hour soak.
TO-20-DMY-T141-04 ISO week: 38we - 39fr Date: 16 Sep - 25 Sep Duration: 10 Days (8 WD) Status: Reference
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Errection of disconnect and circuit breaker for H7 bay
TO-20-DMY-T141-01 ISO week: 32tu - 34mo Date: 04 Aug - 17 Aug Duration: 14 Days (10 WD) Status: Reference (Tentative)
CAPX |  |  | CP0930 | DO | 10 |  | 110 kV A1 @ DMY: Isolate M21BBP Cabinet Busbar disconnect civil works for H7 bay
PROX |  |  | PR0001 | DO | 3 |  | 110 kV A1 @ DMY: Proximity outage for work on Dunmanway 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - DUNMANWAY T142 [SDCC]
TO-20-DMY-T142-01 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0930 | DO | 5 |  | 110 kV A2 @ DMY: Isolate M21BBP Cabinet
COUPLER/SECTIONALISING CB - GLANAGOW 220K1-2
TO-20-GGO-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | GGO | - |  | DO | 4 | 4 | 110kV GIS Cubicle Ordinary Service
CA | GGO | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | GGO | 220-SB1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GGO | 220-SA1-2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
220kV FEEDER - GLANAGOW RAFFEEN
TO-20-GGO-RAF-1-01 ISO week: 35mo - 36mo Date: 24 Aug - 31 Aug Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
AMCAB |  | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OS | GGO | - |  | DO | 4 | 4 | 220kV GIS Cubicle Ordinary Service
CA | GGO | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
OS | RAF | - |  | DO | 6 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | RAF | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | RAF |  | 901028746 | DO |  | 2 | O1-220kv Cable sealing ends moss build u
GENERATOR TRANSFORMER - GLANAGOW T2001 [Bord Gáis WG1]
TO-20-GGO-T2001-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Blackstart Test
TO-20-GGO-T2001-02 ISO week: 35we Date: 26 Aug Duration: 1 Day (1 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | GGO | - |  | DO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
CORRECT | GGO |  | 900951244 | DO |  | 2 | O1- T2001 Protection Maintenance
110kV FEEDER - INNISCARRA MACROOM
TO-20-IA-MAC-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-IA-MAC-1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-IA-MAC-1-01 ISO week: 24mo - 24fr Date: 08 Jun - 12 Jun Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987656 | DO | 2 | 4 | "2018HP-4[22,24,52,58]Off Plumb-Poles"
TRAN |  | - | 900987657 | DO | 2 | 4 | "2018HP-3[59,60,64]Off PlumbPlumb poles"
PROT |  |  |  | DO | 1 | 2 | P2 Protection maintenance of REL521
FO_MISC |  |  | 901084983 | CLO |  | 2 | 2019HP-5[22,46,47,57,59]Off Plumb
FO_MISC |  |  | 901085222 | CLO |  | 2019 - Urgent | 2019HP-1[91]Vib Dampers Replace EW VD
OS | IA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OPT | MAC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAC |  | 901028589 | CLO |  | 2 | 01-Surge Counter Covers Needs replacing
CORRECT | MAC |  | 901059059 | CLO |  | 2 | O1-Moisture in Inniscarra 110kv Lighteni
GENERATOR TRANSFORMER - INNISCARRA T101 [ESB GWM LE1/LE2]
TO-20-IA-T101-01 ISO week: 21mo Date: 18 May Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 | 2 | Total Maintenance Outage Duration Requested
OPT | IA |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
BUSBAR SECTION - KILBARRY 110 kV A1
TO-20-110 kV A1 @ KBY-03 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV A1 @ KBY-02 Status: Unscheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning
TO-20-110 kV A1 @ KBY-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning
BUSBAR SECTION - KILBARRY 110 kV A2
TO-20-110 kV A2 @ KBY-01 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - KILBARRY 110 kV B1
TO-20-110 kV B1 @ KBY-03 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
TO-20-110 kV B1 @ KBY-02 Status: Unscheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Carrigadrohid at station bay, commissioning
TO-20-110 kV B1 @ KBY-01 ISO week: 34mo - 37fr Date: 17 Aug - 11 Sep Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1037 | DO | 20 |  | 110 kV A1/B1 IN TURN @ KBY: EI: Terminating Coolroe at station bay, commissioning
BUSBAR SECTION - KILBARRY 110 kV B2
TO-20-110 kV B2 @ KBY-01 ISO week: 43th Date: 22 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
COUPLER/SECTIONALISING CB - KILBARRY 110K1-2
TO-20-KBY-110K1-2-01 ISO week: 34mo - 35fr Date: 17 Aug - 28 Aug Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | PROX |  | 10 |  | Proiximity for placement of 38kV cables (HI2192_Kilbarry_38kV Asset Replacement)
110kV FEEDER - KILBARRY KNOCKRAHA 1
TO-20-KBY-KRA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 901128775 | CLO | 1 | 1 | Replace Pole No 42 due to lightening damage
TRAN |  | - | 901128776 | CLO | 1 | 1 | Replace Pole No 45 due to Lightening Damage
TO-20-KBY-KRA-1-01 ISO week: 16tu - 17tu Date: 14 Apr - 21 Apr Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
TRAN |  | - | 900987688 | DO | 2 | 4 | 2018HP-1[61]Replace Pole only
TRAN |  | - | 900987690 | DO | 1 | 4 | "2018HP-2[50,57]Off PlumbPlumb poles"
FOSTRHW |  |  | 901086433 | CLO | 1 | 1 | 2019HP-1[60]Replace Pole only -Rot
OS | KBY | - | 901050330 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | KBY | - | 901038491 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OPT | KRA | - | 900942501 | CLO | 1 | 3 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - KILBARRY KNOCKRAHA 2
TO-20-KBY-KRA-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
CORRECT | KBY |  | 900938041 | DO |  | 2 | O1- T lightening arrester -Arcing Horns
CORRECT | KBY |  | 901061010 | DO |  | 2 | O1-Wire P.F. to next available contact.
CORRECT | KRA |  | 901058701 | DO |  | 2 | Replace Bay Singnage
CORRECT | KRA |  | 901061013 | DO |  | 2 | O1-Change Signage on DL and DE
110kV FEEDER - KILBARRY MALLOW
TO-20-KBY-MAL-1-01 ISO week: 23th Date: 04 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | MAL |  | 901129483 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - KILBARRY MARINA 1
TO-20-KBY-MR-1-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRZ100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA511, REL521
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KBY | - | 901050280 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - KILBARRY MARINA 2
TO-20-KBY-MR-2-01 ISO week: 9mo - 11tu Date: 24 Feb - 10 Mar Duration: 16 Days (12 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
DISTRIBUTION TRANSFORMER - KILBARRY T142 [SDCC]
TO-20-KBY-T142-01 ISO week: 34mo - 35fr Date: 17 Aug - 28 Aug Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | KBY |  |  |  | 10 |  | Proximity for Kilbarry K1-2
220kV FEEDER - KILLONAN KNOCKRAHA
TO-20-KLN-KRA-1-04 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KLN-KRA-1-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KLN-KRA-1-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KLN-KRA-1-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | EI: Install base(s) for post insulator(s) Post curing time - erect steel + post insulator(s) Line transfer, and tubular uprate and civil works on Killonan bay.
TO-20-KLN-KRA-1-05 ISO week: 47mo - 47tu Date: 16 Nov - 17 Nov Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084917 | DO | 2 | 2 | 2019HP-1[178]Insulator broken disc
TRAN |  | - | 900987776 | DO | 1 | 4 | "2018HP-3[173,174,175]Stud RailingRepair
TRAN |  | - | 900987793 | DO | 1 | 4 | 2018HP-1[40]ACGFit ACG
BUSBAR SECTION - KNOCKRAHA 110 kV A1
TO-20-110 kV A1 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-110 kV A1 @ KRA-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103
BUSBAR SECTION - KNOCKRAHA 110 kV A2
TO-20-110 kV A2 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - KNOCKRAHA 110 kV B1
TO-20-110 kV B1 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-110 kV B1 @ KRA-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 110 kV A1/B1 IN TURN @ KRA: Remove droppers and disconnects to T2103
BUSBAR SECTION - KNOCKRAHA 110 kV B2
TO-20-110 kV B2 @ KRA-01 ISO week: 44th Date: 29 Oct Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
COUPLER/SECTIONALISING CB - KNOCKRAHA 110K1-2
TO-20-KRA-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KRA | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KRA | 110-SB1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SB2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | KRA | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
BUSBAR SECTION - KNOCKRAHA 220 kV A1
TO-20-220 kV A1 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A1 @ KRA-03 ISO week: 41su - 42mo Date: 11 Oct - 12 Oct Duration: 2 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
BUSBAR SECTION - KNOCKRAHA 220 kV A2
TO-20-220 kV A2 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
TO-20-220 kV A2 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV A2 @ KRA-03 ISO week: 25we - 25fr Date: 17 Jun - 19 Jun Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 3 |  | Droppers to be connected, followed by EI.
BUSBAR SECTION - KNOCKRAHA 220 kV B1
TO-20-220 kV B1 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + CLA-KRA-1: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-220 kV B1 @ KRA-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections
TO-20-220 kV B1 @ KRA-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | 220 kV A1/B1 IN TURN @ KRA: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A1/B1 IN TURN @ KRA: Simultaneous 220 kV A1/B1 IN TURN @ KRA + AD-KRA-2: Install bases for Post Insulators on Aghada 2 and Clashavoon under A1/B1 BBs
TO-20-220 kV B1 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV B1 @ KRA-05 ISO week: 41su - 42mo Date: 11 Oct - 12 Oct Duration: 2 Days (1 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 IN TURN @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
BUSBAR SECTION - KNOCKRAHA 220 kV B2
TO-20-220 kV B2 @ KRA-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Simultaneous 220 kV A2/B2 IN TURN @ KRA + AD-KRA-1: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | 220 kV A2/B2 IN TURN @ KRA: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
TO-20-220 kV B2 @ KRA-04 ISO week: 45th Date: 05 Nov Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar Changeover
TO-20-220 kV B2 @ KRA-03 ISO week: 26mo - 26we Date: 22 Jun - 24 Jun Duration: 3 Days (3 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 3 |  | Droppers to be connected, followed by EI.
COUPLER/SECTIONALISING CB - KNOCKRAHA 220K1-2
TO-20-KRA-220K1-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KRA-220K1-2-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KRA-220K1-2-01 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
OS | KRA | 220-SB2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 220-SB1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 110-SA2 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | KRA | 110-SA1 |  | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OPT | KRA | 220-SA1 | 901039154 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | KRA | 220-SA2 | 901039155 | DO | 1 | 4 | 220kV Sect / Dist Operational Test
TO-20-KRA-220K1-2-04 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KRA-220K1-2-05 ISO week: 47mo - 47fr Date: 16 Nov - 20 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | KRA | - |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | KRA | - |  | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KRA |  | 901047457 | DO | 3 | 1 | O1-Hotspot 220kv SA2 T Phase on A2 Side
110kV FEEDER - KNOCKRAHA MIDLETON
TO-20-KRA-MID-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21
studied outage to move 12 day outage for CP0868
TO-20-KRA-MID-1-01 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084995 | CLO |  | 2 | 2019HP-7[7,8,9,10,11,12,13]Off Plumb
TRAN | - | Line | 901130581 | DO | 3 | 1 | Hotspot 1 (AT No.50 Span 49/50) Right phase jumper terminal (Repair by 28th August 2020)
CORRECT | KRA |  | 901059062 | CLO | 1 | 1 | O1-Repair SF6 Gauge signs of corrosion
OPT | MID | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MID |  | 901078152 | CLO | 1 | 2 | Replce Bay Signage
220kV FEEDER - KNOCKRAHA RAFFEEN
TO-20-KRA-RAF-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 90 |  | 220 kV Line refurbishment, re-sagging and foundation reinforcement works.
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen (part 2)
CAPX |  |  | CP0868 | DO | 30 |  | Simultaneous AD-RAF-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-MID-1 + KRA-RAF-1: Proximity during re-sagging works AT6 - AT21
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
CAPX |  |  | CP0796 + CP0973 | DO | 2 |  | For Energisation of A4/B4 busbar
CAPX |  |  | CP0868 | DO | 1 |  | EI: Simultaneous KRA-RAF-1 + KRA-RAF-1: Energisation using either feeder bay CB
TO-20-KRA-RAF-1-04 ISO week: 25we - 26we Date: 17 Jun - 24 Jun Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 6 |  | EI: Outage for EI, line switched out at start of works
TO-20-KRA-RAF-1-02 ISO week: 9mo - 18th Date: 24 Feb - 30 Apr Duration: 67 Days (46 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 30 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Cullenagh circuit to new section of busbar. Overlaps with Raffeen circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0796 + CP0973 | DO | 30 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
CAPX |  |  | CP0868 | DO | 7 |  | Simultaneous CUL-KRA-1 + KRA-RAF-1: DC section with with Knockraha Raffeen
TO-20-KRA-RAF-1-01 ISO week: 9mo - 21sa Date: 24 Feb - 23 May Duration: 90 Days (61 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 44 |  | Transfer Raffeen circuit to new section of busbar. Overlaps with Cullenagh circuit outage as they share a dbl circuit tower.
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900727347 | DO | 3 | 3 | 2015HP-1[54]Insulator Broken str insul
FO_MISC |  | - | 900897879 | DO | 1 | 3 | 2017HP-1[DCET1]Arching Horns -Replace
FO_MISC |  | - | 900897880 | DO | 1 | 3 | 2017HP-1[DCAT5]Arching Horns -Replace
PROX |  |  | PR0001 | DO | 1 |  | Proximity outage for work on Aghada-Raffeen 220 kV
FO_MISC |  |  | 901085223 | DO |  | 4 | 2019HP-2[2,3]Vib Dampers Replace EW VD
CORRECT | KRA | - | 901129378 | CLO | 5 | 1 | Replace stolen earths
TRANSFORMER - KNOCKRAHA T2101
TO-20-KRA-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: A1 + B1 Outage To install tubular sections in F1 Aghada 2 + F7 Clashavoon
TO-20-KRA-T2101-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A1/B1 @ KRA: Retire last section of A1/B1 BB to make way for F9 Coupler
TO-20-KRA-T2101-04 ISO week: 28we - 30th Date: 08 Jul - 23 Jul Duration: 16 Days (12 WD) Status: Scheduled
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | KRA | 220 | 901042177 | CLO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | KRA | 110 | 901042315 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KRA |  | 900908018 | DO | 3 | 2 | Carry out oil regeneration, wire up PRD
OS | KRA | Trafo | 901130039 | CLO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | KRA |  | 900877126 | CLO | 2 | 2 | Spare Parts for Disconnect
CORRECT | KRA | - | 900973655 | CLO | 2 | 2 | O2-Fans 2,6,9 not working
CORRECT | KRA | - | 900959190 | CLO | 1 | 2 | O2- OLTC silica gel needs changing
TRANSFORMER - KNOCKRAHA T2102
TO-20-KRA-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0796 + CP0973 | DO | 20 |  | Simultaneous 220 kV A2/B2 IN TURN @ KRA + KRA-T2102: Civil works for adjacent Post Insulators in F2 (Aghada 1) and F6 (T2102) under A2 /B2 BBs Install Tubular sections
CAPX |  |  | CP0796 + CP0973 | DO | 10 |  | 220 kV A2/B2 @ KRA: EI: Tubular work on F4 (OldCullenagh), F2 (Aghada1) cubicles, , F6 (T2102). Possibly retire plant F8 Raffeen
TO-20-KRA-T2102-03 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 40 |  | Simultaneous 220 kV A1/B1 IN TURN @ KRA + KRA-T2102: Retire stranded conductor, retire plant, retire gantry, civil works for new gantry, bases for PIs + Sas Erect new gantries, plant, tubular sections
TO-20-KRA-T2102-02 Status: Unscheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | KRA | 110 | 901129577 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KRA | 220 | 901129728 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
OPT | KRA | TRAFO | 901129737 | CLO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
TRANSFORMER - KNOCKRAHA T2103
TO-20-KRA-T2103-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 2 | P2 Protection maintenance of 7SA612, 7SA612, RET670
OPT | KRA | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | KRA | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | KRA | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
CORRECT | KRA | - | 900959193 | DO | 1 | 2 | O2- Low oil level on OLTC tank
TO-20-KRA-T2103-02 Status: Unscheduled
CAPX |  |  | CP0796 + CP0973 | DO | 5 |  | 220 kV A1/B1 @ KRA: 1/2 station outage for the retirement of last section of busbar to allow for new K1 to be built offline
TO-20-KRA-T2103-03 ISO [year]week: 42mo - [21]9we Date: 12 Oct - 03 Mar 21 Duration: 143 Days (100 WD) Status: Scheduled
CAPX |  |  | CP0796 + CP0973 | DO | 100 |  | Remove from system to allow for offline F9 wing coupler build
110kV FEEDER - KNOCKRAHA WOODHOUSE
TO-20-KRA-WOH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0868 | DO | 12 |  | Simultaneous KRA-RAF-1 + KRA-WOH-1: Proximity during re-sagging works AT6 - AT21
TO-20-KRA-WOH-1-01 ISO week: 28mo - 29mo Date: 06 Jul - 13 Jul Duration: 8 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | KRA | - | 901129859 | CLO | 6 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | KRA |  | 901036906 | CLO |  | 2 | O1-Replace Surge Counter
OS | WOO | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - LIBERTY STREET MARINA 1 [SDCC]
TO-20-LIB-MR-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | MR |  |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
GENERATOR TRANSFORMER - LONG POINT T2002 [ESB GWM AD2]
TO-20-LPT-T2002-01 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | LPT | - | 901129020 | CLO | 2 | 4 | Cable Insp. 400 & 220kV Feeder XLPE
OPT | LPT | 220 | 901129732 | CLO | 1 | 4 | 2200kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MACROOM 110SA1
TO-20-MAC-110SA1-06 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 15 |  | Proximity outage (SA2)
TO-20-MAC-110SA1-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 2 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove droppers from A1 to old SA1
TO-20-MAC-110SA1-03 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 32 |  | Old SA 1 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 25 |  | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-110SA1-04 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Remove old SA1 and install new SA1
TO-20-MAC-110SA1-05 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 5 |  | Simultaneous 110 kV A1 @ MAC + MAC-110SA1: Install droppers to new SA1.
TO-20-MAC-110SA1-01 ISO week: 11mo - 12mo Date: 09 Mar - 16 Mar Duration: 8 Days (6 WD) Status: Scheduled
CAPX |  |  | CP0829 | DO | 15 |  | 110 kV A1 @ MAC: Civil works to install foundations for new SA 1. Also run LV cables from under A1 to new H0 bay.
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | MAC | - | 900955833 | CLO | 2 | 2 | NO 2 -"T" missing from upright support
SECTIONALISING DISCONNECT - MACROOM 110SA2
TO-20-MAC-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-110SA2-02 Status: Unscheduled
CAPX |  |  | CP0829 | DO | 25 |  | Simultaneous MAC-110SA1 + MAC-110SA2: Old SA 2 is to be decommissioned and removed from underneath the busbar.
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
TO-20-MAC-110SA2-03 Status: Unscheduled
15 | [6 empty] | Proximity outage (SA1)
DISTRIBUTION TRANSFORMER - MACROOM T142 [SDCC]
TO-20-MAC-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0829 | DO | 10 |  | 110 kV A2 @ MAC: Civil works to install foundations for new SA 2.
TO-20-MAC-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 10 |  | Simultaneous 110 kV A2 @ MAC + MAC-110SA1: Remove droppers from A2 to old SA2, remove old SA2 and install new SA2
TO-20-MAC-T142-03 Status: Reference (Unscheduled)
CAPX |  |  | CP0829 | DO | 5 |  | EI: Simultaneous 110 kV A2 @ MAC + MAC-110SA2: Install droppers to new SA2 and energise the new H0 bay up to the physical break at SA1.
COUPLER/SECTIONALISING CB - MARINA 110K1-2
TO-20-MR-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
YM03 |  | - | 900981433 | DO | 2 | 4 | O1-110kv SA interlocking not working cor
GENERATOR TRANSFORMER - MARINA T107 [ESB GWM MR7]
TO-20-MR-T107-02 ISO week: 30th Date: 23 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
OPT | MR |  |  | DO | 1 | 4 | 110KV GIS Cubicle Operational Test
110kV FEEDER - MARINA TRABEG 1
TO-20-MR-TBG-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
110kV FEEDER - MARINA TRABEG 2
TO-20-MR-TBG-2-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
AMCAB | MR | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
OPT | TBG | - | 901038815 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MIDLETON 110SA1
TO-20-MID-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of MID-110SA2: 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - MIDLETON 110SA2
TO-20-MID-110SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
OS | MID | SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MID-110SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-20-MID-T102-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-20-MID-WHI-1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900988883 | DO | 2 | 4 | "2018HP-2[41,42]Sus/Dup 110kV replace"
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ MID: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA2)
FO_MISC |  |  | 901084330 | DO | 1 | 2 | 2019HP-1[22]Bird Nests Over Right phase
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
OPT | MID |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | WHI |  |  | DO | 1 | 4 | 110kV MO Cubicle Operational Test
COUPLER/SECTIONALISING CB - RAFFEEN 110K1-2
TO-20-RAF-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - RAFFEEN 220K1-2
TO-20-RAF-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | RAF | - | 901042176 | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | RAF | 220-SB | 900942645 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
OS | RAF | 220-SA | 901039742 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
FM | RAF | - | 901045776 | DO | 1 | 4 | HV Pressure Vessel Inspection
TO-20-RAF-220K1-2-02 Status: Unscheduled
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
CAPACITOR/SVC/REACTOR - RAFFEEN CAP2
TO-20-RAF-CAP2-01 ISO week: 41tu - 42tu Date: 06 Oct - 13 Oct Duration: 8 Days (6 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 6 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of KVFG142, SPAJ 160C
OS | RAF | - | 901129961 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - RAFFEEN RINGASKIDDY [SDCC]
TO-20-RAF-RSY-1-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | RAF | - | 900942660 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
TO-20-RAF-RSY-1-02 Status: Reference (Unscheduled)
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA612, GRZ100
TRANSFORMER - RAFFEEN T2101
TO-20-RAF-T2101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OS | RAF | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
OS | RAF | 110 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | RAF | Trafo |  | DO |  | 4 | 220/110 & 275/220 Trafo Ordinary Service
TO-20-RAF-T2101-01 ISO week: 43tu - 43we Date: 20 Oct - 21 Oct Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
|  |  | PROT |  |  |  | P2 Protection maintenance of 7SA511, 7SA511, 7UT512
CORRECT | RAF |  | 900908059 | DO |  | 2 | Degas oil completely T2101
TO-20-RAF-T2101-03 ISO week: 43tu - 43th Date: 20 Oct - 22 Oct Duration: 3 Days (3 WD) Status: Scheduled
CORRECT | RAF | - |  | DO | 2 | 1 | Replace stolen earths
TRANSFORMER - RAFFEEN T2102
TO-20-RAF-T2102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
OPT | RAF | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | RAF | TRAFO |  | DO | 1 | 4 | 220/110 & 275/220 Trafo Operational Test
OPT | RAF | 220 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
FM | RAF | 110 |  | DO | 1 | 1 | HV Pressure Vessel Inspection
CORRECT | RAF |  | 901060347 | DO | 1 | 2 | Replace Signs on Trafo's and Assoicated
TO-20-RAF-T2102-02 Status: Unscheduled
CORRECT | RAF |  | 901075226 | CANC |  | 1 | Replace Earths
110kV FEEDER - RAFFEEN TRABEG 1
TO-20-RAF-TBG-1-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
CORRECT | RAF | - |  | DO | 2 | 1 | Replace stolen earths
CORRECT | RAF |  | 901074427 | DO | 1 | 2 | Replce Bay Signage
110kV FEEDER - RAFFEEN TRABEG 2
TO-20-RAF-TBG-2-02 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
AMCAB |  | - | 901133690 | DO | 2 | 2 | Clean cable sealing ends (and stand-off insulators) at line/cable interface compound at Trabeg station.
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
TO-20-RAF-TBG-2-01 ISO week: 12mo - 13tu Date: 16 Mar - 24 Mar Duration: 9 Days (6 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085002 | DO | 3 | 4 | 2019HP-3[20,22,23]Off Plumb -plumb poles
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
BUSBAR SECTION - TRABEG 110 kV A1
TO-20-110 kV A1 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | A1/A2 BB in turn
BUSBAR SECTION - TRABEG 110 kV A2
TO-20-110 kV A2 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | A1/A2 BB in turn
BUSBAR SECTION - TRABEG 110 kV B1
TO-20-110 kV B1 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | B1/B2 BB in turn
BUSBAR SECTION - TRABEG 110 kV B2
TO-20-110 kV B2 @ TBG-01 ISO week: 32th Date: 06 Aug Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB0001 |  |  |  |  | 1 |  | B1/B2 BB in turn
COUPLER/SECTIONALISING CB - TRABEG 110K1-2
TO-20-TBG-110K1-2-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SJ611
| TBG | 110-SA1 |  | DO | 2 | 1 | Clean busbar insulators (Indoor AIS)
TO-20-TBG-110K1-2-02 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Scheduled
| TBG | 110-SA2 |  | DO | 2 | 1 | Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T101 [SDCC]
TO-20-TBG-T101-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T102 [SDCC]
TO-20-TBG-T102-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T141 [SDCC]
TO-20-TBG-T141-01 ISO week: 38mo - 38th Date: 14 Sep - 17 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
DISTRIBUTION TRANSFORMER - TRABEG T142 [SDCC]
TO-20-TBG-T142-01 ISO week: 39mo - 39th Date: 21 Sep - 24 Sep Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for work on 110 K1-2: Clean busbar insulators (Indoor AIS)
SECTIONALISING DISCONNECT - WHITEGATE 110SA1
TO-20-WHI-110SA1-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
OS | WHI | SA1 | 901039691 | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CORRECT | WHI |  | 901059046 | DO | 5 | 2 | O1- Replace disconnect due to severe rus
CORRECT | WHI |  | 901059045 | DO |  | 1 | 01-investigate interlocking issue betwee
SECTIONALISING DISCONNECT - WHITEGATE 110SA2
TO-20-WHI-110SA2-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T101 [Irving Oil]
TO-20-WHI-CKB-T101-02 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
| WHI |  |  | DO | 5 |  | Customer outage request
OS | WHI | - | 901042301 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | WHI |  | 901039125 | DO | 1 | 2 | O1-Water in CB Mech Box.
TO-20-WHI-CKB-T101-01 ISO week: 38mo - 38fr Date: 14 Sep - 18 Sep Duration: 5 Days (5 WD) Status: Scheduled
PROX | [6 empty] | 110 kV A1 @ WHI: Proximity outage for work on Midleton 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - WHITEGATE CKB-T102 [Irving Oil]
TO-20-WHI-CKB-T102-01 ISO week: 39mo - 39fr Date: 21 Sep - 25 Sep Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 1 |  | Total Maintenance Outage Duration Requested
CORRECT | WHI |  | 901059048 | DO | 1 | 2 | O1-Replace bird guard on CB.Severely rus

## CAVAN (Rgn)
110kV FEEDER - ARVA CARRICK ON SHANNON
TO-20-ARV-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | COS | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-ARV-COS-1-02 Status: Unscheduled
|  | - | 901148340 | CLO | 2 | 1 | Hotspot 1 (ET No.1, Span 1-2) Left Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148341 | CLO | 2 | 1 | Hotspot 2 (AT No.6, Span 6-7) Right Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148343 | CLO | 2 | 1 | Hotspot 4 (AT No.10, Span 10-11) Centre Deadend Terminiation (Repair by 6th June 2020)
|  | - | 901148345 | CLO | 2 | 1 | Hotspot 5 (AT No.11, Span 10-11) Right Deadend Termination (Repair by 6th Aug 2020)
|  | - | 901148346 | CLO | 2 | 1 | Hotspot 6 (AT No.154, Span 153-154) Centre Jumper Terminal (Repair by 6th Nov 2020)
|  | - | 901148348 | CLO | 2 | 1 | Hotspot 7 (R1, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148349 | CLO | 2 | 1 | Hotspot 8 (R2, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148350 | CLO | 2 | 1 | Hotspot 9 (C1, Span 204-205) Centre Midspan Joint (Repair Immediately)
|  | - | 901148351 | CLO | 2 | 1 | Hotspot 10 (C1, Span 204-205) Right Midspan Joint (Measure resistance by while repairing Hotspot 9))
|  | - | 901148352 | CLO | 2 | 1 | Hotspot 11 (R2, Span 168-169) Centre Midspan Joints (Measure resistance by 6th Aug 2020)
TO-20-ARV-COS-1-03 ISO week: 47mo - 47th Date: 16 Nov - 19 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | 901148342 | DO | 2 |  | Hotspot 3 (AT No.10, Span 9-10) Centre Deadend Terminiation (Repair by 6th Nov 2020)
110kV FEEDER - ARVA GORTAWEE
TO-20-ARV-GWE-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-ARV-GWE-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084866 | DO | 1 | 4 | 2019HP-1[157]Earths-Replace LPH e/w
FO_MISC |  |  | 901084867 | DO | 1 | 4 | 2019HP-1[158]Earths-Replace RPH e/w
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA612, REL521
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA NAVAN
TO-20-ARV-NAV-1-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086419 | DO | 2 | 1 | 2019HP-1[132]Replace Pole only -Rot
FOSTRHW |  |  | 901086420 | DO | 2 | 1 | 2019HP-1[191]Replace Pole only -Rot
TO-20-ARV-NAV-1-01 ISO week: 9mo - 10fr Date: 24 Feb - 06 Mar Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084868 | DO | 2 | 4 | 2019HP-1[6]Earths-Replace earth lead
FOSTRHW |  |  | 901086415 | DO | 2 | 1 | 2019HP-1[4]Replace Pole only -Rot
FOSTRHW |  |  | 901086416 | DO | 2 | 1 | 2019HP-1[58]Replace Pole only -Rot
FOSTRHW |  |  | 901086417 | DO | 2 | 1 | 2019HP-1[63]Replace Pole only -Rot
FOSTRHW |  |  | 901086418 | CLO | 2 | 1 | 2019HP-1[128]Replace Pole only -Rot
FOSTRHW |  |  | 901086421 | CLO | 2 | 1 | 2019HP-1[199]Replace Pole only -Rot
FOSTRHW |  |  | 901086422 | CLO | 2 | 1 | 2019HP-1[229]Replace Pole only -Rot
FOSTRHW |  |  | 901086423 | CLO | 2 | 1 | 2019HP-1[230]Replace Pole only -Rot
FOSTRHW |  |  | 901086424 | CLO | 2 | 1 | 2019HP-1[319]Replace Pole only -Rot
CA | NAV | - | 901129179 | CLO | 5 | 4 | 110kV CUBICLE CONDITION ASSESSMENT
OS | NAV | - | 901129885 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA SHANKILL 1
TO-20-ARV-SKL-1-01 ISO week: 44th - 44fr Date: 29 Oct - 30 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  |  | 901084300 | DO | 2 | 4 | 2019HP-1[21]Bird Nests
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | SKL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARVA SHANKILL 2
TO-20-ARV-SKL-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | SKL |  | 901028567 | CANC |  | 1 | O 1 O 1 ARVA 2 C.B. MONITORING TEMI
CORRECT | SKL |  | 901045926 | CANC |  | 1 | Investigate CB gas leak & repair if poss
TO-20-ARV-SKL-2-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
PROT |  | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983642 | DO | 2 | 4 | 2018HP-1[Am 35]Bird Nests
PROX |  |  | PR0001 |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
TRAN |  | - | 900983641 | DO | 1 | 4 | 2018HP-1[Am 29]Bird Nests
FO_MISC |  |  | 901084301 | DO | 1 | 4 | 2019HP-1[143]Bird Nests
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612, GRL100
OS | SKL | - |  | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
AMCAB | SKL | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | SKL | 110 | 901068797 | CANC | 2 | 1 | Visual inspection of HIS HV cable sealin
110kV FEEDER - CATHALEENS FALL CORRACLASSY
TO-20-CF-COR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  | - | 900819396 | DO | 8 | 2 | 2016HP-1[14]Off Plumb
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900649865 | DO | 2 | 1 | 2014HP-1[299]Off Plumb
FO_MISC |  | - | 900649866 | DO | 2 | 1 | 2014HP-1[298]Off Plumb
FO_MISC |  | - | 900649867 | DO | 2 | 1 | 2014HP-1[296]Off Plumb
FO_MISC |  | - | 900649868 | DO | 2 | 1 | 2014HP-1[295]Off Plumb
FO_MISC |  |  | 901084870 | DO | 2 | 4 | 2019HP-1[13]Earths-Replace Left pole e/w
FO_MISC |  |  | 901084950 | DO | 2 | 4 | 2019HP-1[277]Off Plumb -plumb poles
FO_MISC |  | - | 900898249 | DO | 1 | 3 | 2017HP-1[4]Vib Damps Dampers fatigue (Landowner access available May-July)
TRAN |  | - | 900985204 | DO | 1 | 4 | 2018HP-1[287]Check(General)-rusty Xarm
TRAN |  | - | 900985205 | DO | 1 | 4 | 2018HP-1[282]Check(General)-rusty Xarm
TRAN |  | - | 900985206 | DO | 1 | 4 | 2018HP-1[281]Check(General)-rusty Xarm
TRAN |  | - | 900985207 | DO | 1 | 4 | 2018HP-1[278]Check(General)-rusty Xarm
TRAN |  | - | 900985208 | DO | 1 | 4 | 2018HP-1[228]Check(General)-rusty Xarm
TRAN |  | - | 900985209 | DO | 1 | 4 | 2018HP-1[169]Check(General)-rusty Xarm
OS | CF | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - CORRACLASSY 110 kV A1
TO-20-110 kV A1 @ COR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX | COR |  |  |  | 5 |  | Busbar outage for cubicle assessment on COR-ENS PST
TRANSFORMER - CORRACLASSY ENNISKILLEN PST
TO-20-COR-PST-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
CA | COR | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | COR | 110-DA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - CORRACLASSY GORTAWEE
TO-20-COR-GWE-1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084872 | DO | 1 | 4 | 2019HP-1[69]Earths-Replace L/pole e/w
OS | COR | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | COR | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
OS | COR | 110-DA |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
BUSBAR SECTION - GORMAN 110 kV A1
TO-20-110 kV A1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV A2
TO-20-110 kV A2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV B1
TO-20-110 kV B1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 110 kV B2
TO-20-110 kV B2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 220 kV A1
TO-20-220 kV A1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 220 kV B1
TO-20-220 kV B1 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
BUSBAR SECTION - GORMAN 220 kV B2
TO-20-220 kV B2 @ GOR-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | BB0002 | DO | 1 |  | Busbar Changeover
SECTIONALISING DISCONNECT - GORTAWEE 110SA1
TO-20-GWE-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA2: 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-110SA1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
OS | GWE | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
CORRECT | GWE |  | 900788599 | DO | 3 | 1 | Replace disconnect spindles
SECTIONALISING DISCONNECT - GORTAWEE 110SA2
TO-20-GWE-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
OS | GWE | SA2 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-GWE-110SA2-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of GWE-110SA1: 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - GORTAWEE CAP1
TO-20-GWE-CAP1-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
TSO CUSTOMER TRANSFORMER - GORTAWEE T101 [Sean Quinn Cement]
TO-20-GWE-T101-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA1)
| GOR |  |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Sean Quinn Cement]
TO-20-GWE-T102-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-GWE-T102-01 ISO week: 40we - 40fr Date: 30 Sep - 02 Oct Duration: 3 Days (3 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | GWE |  | 901073971 | DO | 2 | 1 | T102 110kV CB: SF6 Gauge corroded and ne
OPT | GWE | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - GORTAWEE T142 [NDCC]
TO-20-GWE-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - LISDRUM 110SA1
TO-20-LIS-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
OS | LIS | SA1 | 901039705 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-LIS-110SA1-02 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 1 |  | As a consequence of LIS-110SA2: 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
SECTIONALISING DISCONNECT - LISDRUM 110SA2
TO-20-LIS-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of LIS-110SA1: 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
TO-20-LIS-110SA2-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
CAPACITOR/SVC/REACTOR - LISDRUM CAP1
TO-20-LIS-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - LISDRUM CAP2
TO-20-LIS-CAP2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
|  | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
TO-20-LIS-CAP2-02 ISO week: 33mo Date: 10 Aug Duration: 1 Day (1 WD) Status: Scheduled
CORRECT | LIS |  | 901078676 | CLO | 1 | 1 | Contact resistance measurement on the ci
110kV FEEDER - LISDRUM LOUTH
TO-20-LIS-LOU-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
CORRECT | LOU |  |  | DO | 3 | 1 | Hotspot 1 (SC AM No.52 Span 51/52) Jumper terminal (Repair ASAP)
TO-20-LIS-LOU-1-02 Status: Unscheduled
CORRECT | LOU |  | 900982920 | DO | 3 | 1 | Surge counters need replacement on R/S/T
TO-20-LIS-LOU-1-01 ISO week: 29th - 29fr Date: 16 Jul - 17 Jul Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | LIS |  | 901129596 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - LISDRUM SHANKILL
TO-20-LIS-SKL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  | DO | 13 |  | Total Maintenance Outage Duration Requested
TO-20-LIS-SKL-1-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Proposed
|  | - |  | CANC | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
TO-20-LIS-SKL-1-04 ISO week: 39mo - 39fr Date: 21 Sep - 25 Sep Duration: 5 Days (5 WD) Status: Proposed
OS | LIS | - | 901129864 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service. do under OD1391
OS | SKL | - | 901129823 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service.do under OD1391
TO-20-LIS-SKL-1-02 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
| SKL |  |  |  | 2 |  | Hot spot detected on Lisdrum Cubicle DA S Pha
DISTRIBUTION TRANSFORMER - LISDRUM T141 [NDCC]
TO-20-LIS-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ LIS: Proximity outage for work on Lisdrum 110kV Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - LISDRUM T142 [NDCC]
TO-20-LIS-T142-01 ISO week: 20mo - 20fr Date: 11 May - 15 May Duration: 5 Days (5 WD) Status: Reference (Proposed)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 5 |  | 110 kV A2 @ LIS: Proximity outage for work on Lisdrum-Shankill 110 kV
110kV FEEDER - LOUTH RATRUSSAN
TO-20-LOU-RRU-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084279 | CLO | 1 | 4 | 2019HP-1[123]Bird Nests
FO_MISC |  |  | 901084320 | CLO | 1 | 4 | 2019HP-1[126]Bird Nests
FO_MISC |  |  | 901084321 | CLO | 1 | 4 | 2019HP-1[128]Bird Nests
FO_MISC |  |  | 901084322 | CLO | 1 | 4 | 2019HP-1[130]Bird Nests
FO_MISC |  |  | 901084924 | CLO | 1 | 4 | 2019HP-1[197]Insulator broken aux string
OS | LOU | - | 901050323 | CLO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OPT | RRU | - |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-LOU-RRU-1-03 Status: Unscheduled
YM03 | - | Line | 901110486 | CLO | 5 | 1 | Am No.165 165 - 166 Right Dead end termination Replace joint within 3 months pending TSO review.
YM03 | - | Line | 901110487 | CLO | 5 | 1 | R1 107 - 108 Right Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110488 | CLO | 5 | 1 | Am No.51 51 - 52 Right Dead end termination Replace joint immediately pending TSO review.
SECTIONALISING DISCONNECT - RATRUSSAN 110SA1
TO-20-RRU-110SA1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 2 | 4 | Total Maintenance Outage Duration Requested
OS | RAT | SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-RRU-110SA1-01 ISO week: 11mo - 11tu Date: 09 Mar - 10 Mar Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RRU-110SA1-02 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 3 |  | As a consequence of RRU-110SA2: 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - RATRUSSAN 110SA2
TO-20-RRU-110SA2-02 ISO week: 11mo - 11tu Date: 09 Mar - 10 Mar Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of RRU-110SA1: 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
TO-20-RRU-110SA2-01 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
OS | RAT | SA2 |  | DO | 5 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
110kV FEEDER - RATRUSSAN SHANKILL
TO-20-RRU-SKL-1-01 ISO week: 21mo - 21fr Date: 18 May - 22 May Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, GRL100
TRAN |  | - | 900989485 | DO | 1 | 4 | 2018HP-1[48]Bird Nests
FO_MISC |  |  | 901084326 | DO | 1 | 4 | 2019HP-1[33]Bird Nests
FO_MISC |  |  | 901084327 | DO | 1 | 4 | 2019HP-1[48]Bird Nests
OPT | RRU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SKL | - | 901129889 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SKL | - | 901129196 | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-RRU-SKL-1-02 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
GENERATOR TRANSFORMER - RATRUSSAN T121 [Bindoo BD1]
TO-20-RRU-T121-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA1)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
GENERATOR TRANSFORMER - RATRUSSAN T122 [Mountain Lodge ML1]
TO-20-RRU-T122-01 ISO week: 21mo - 21we Date: 18 May - 20 May Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 3 |  | 110 kV A2 @ RRU: Proximity outage for work on Ratrussan 110kV Sect / Dist Ordinary Service (SA2)
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612
CORRECT | RRU |  | 900990024 | CLO | 3 | 1 | Re-Test - Condition Assessment of the Cu
OPT | RRU |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-RRU-T122-02 ISO week: 40tu - 40th Date: 29 Sep - 01 Oct Duration: 3 Days (3 WD) Status: Scheduled
[5 empty] | 3 |  | Customer outage request
SECTIONALISING DISCONNECT - SHANKILL 110SA1
TO-20-SKL-110SA1-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
DISTRIBUTION TRANSFORMER - SHANKILL T141 [NDCC]
TO-20-SKL-T141-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  |  |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle

## ATHLONE (Rgn)
SECTIONALISING DISCONNECT - AGANNYGAL 110SA1
TO-20-AGL-110SA1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
OS | AGL | SA1 |  | DO | 3 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-AGL-110SA1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-110SA2: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - AGANNYGAL 110SA2
TO-20-AGL-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 3 |  | Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0002 | DO | 3 |  | As a consequence of AGL-110SA1: 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - AGANNYGAL DERRYBRIEN [Derrybrien DY1]
TO-20-AGL-DYN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous AGL-DYN-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-AGL-DYN-1-03 Status: Unscheduled
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-AGL-DYN-1-02 ISO week: 37mo - 37sa Date: 07 Sep - 12 Sep Duration: 6 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | AGL | - |  | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
CM | AGL | - | 900713712 | DO | 3 | 2 | CB - Siemens 3AP mod required to prevent spring charging lockout with loss of AC.
110kV FEEDER - AGANNYGAL ENNIS
TO-20-AGL-ENN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
OPT | ENN | - | 901129481 | CLO | 1 | 4 | 110kV MO Cubicle Operational Test
TO-20-AGL-ENN-1-01 ISO week: 25mo - 25fr Date: 15 Jun - 19 Jun Duration: 5 Days (5 WD) Status: Scheduled
TRAN |  | - | 900982973 | DO | 1 | 4 | 2018HP-1[124]Off PlumbPlumb insulators
OS | AGL | - | 901129954 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - AGANNYGAL SHANNONBRIDGE
TO-20-AGL-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous AGL-SH-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
PROX |  |  | PR0002 | DO | 3 |  | 110 kV A1 @ AGL: Proximity outage for work on Agannygal 110kV Sect / Dist Ordinary Service (SA1)
TO-20-AGL-SH-1-03 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-AGL-SH-1-01 ISO week: 32tu - 32fr Date: 04 Aug - 07 Aug Duration: 4 Days (4 WD) Status: Scheduled
OS | AGL | - | 901129955 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | SH |  | 901081611 | DO | 3 | 1 | Replace faulty isolation block.
CORRECT | SH |  | 901087472 | DO | 3 | 1 | EMP AMS: Spring charge locking out with
CORRECT | SH |  | 901087473 | DO | 3 | 2 | EMP AMS: Peplace Fuse Holders on all CTV
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - ARVA CARRICK ON SHANNON
TO-20-ARV-COS-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 8 |  | Total Maintenance Outage Duration Requested
OS | COS | - |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
CA | COS | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
TO-20-ARV-COS-1-02 Status: Unscheduled
|  | - | 901148340 | CLO | 2 | 1 | Hotspot 1 (ET No.1, Span 1-2) Left Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148341 | CLO | 2 | 1 | Hotspot 2 (AT No.6, Span 6-7) Right Deadend Terminiation (Repair by 6th Nov 2020)
|  | - | 901148343 | CLO | 2 | 1 | Hotspot 4 (AT No.10, Span 10-11) Centre Deadend Terminiation (Repair by 6th June 2020)
|  | - | 901148345 | CLO | 2 | 1 | Hotspot 5 (AT No.11, Span 10-11) Right Deadend Termination (Repair by 6th Aug 2020)
|  | - | 901148346 | CLO | 2 | 1 | Hotspot 6 (AT No.154, Span 153-154) Centre Jumper Terminal (Repair by 6th Nov 2020)
|  | - | 901148348 | CLO | 2 | 1 | Hotspot 7 (R1, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148349 | CLO | 2 | 1 | Hotspot 8 (R2, Span 168-169) Right Midspan Joint (Repair by 6th Aug 2020)
|  | - | 901148350 | CLO | 2 | 1 | Hotspot 9 (C1, Span 204-205) Centre Midspan Joint (Repair Immediately)
|  | - | 901148351 | CLO | 2 | 1 | Hotspot 10 (C1, Span 204-205) Right Midspan Joint (Measure resistance by while repairing Hotspot 9))
|  | - | 901148352 | CLO | 2 | 1 | Hotspot 11 (R2, Span 168-169) Centre Midspan Joints (Measure resistance by 6th Aug 2020)
TO-20-ARV-COS-1-03 ISO week: 47mo - 47th Date: 16 Nov - 19 Nov Duration: 4 Days (4 WD) Status: Scheduled
|  |  | 901148342 | DO | 2 |  | Hotspot 3 (AT No.10, Span 9-10) Centre Deadend Terminiation (Repair by 6th Nov 2020)
110kV FEEDER - ARVA GORTAWEE
TO-20-ARV-GWE-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ GWE: Proximity outage for work on Gortawee 110kV Sect / Dist Ordinary Service (SA2)
TO-20-ARV-GWE-1-01 ISO week: 46mo - 46fr Date: 09 Nov - 13 Nov Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084866 | DO | 1 | 4 | 2019HP-1[157]Earths-Replace LPH e/w
FO_MISC |  |  | 901084867 | DO | 1 | 4 | 2019HP-1[158]Earths-Replace RPH e/w
PROT |  |  |  | DO |  |  | P2 Protection maintenance of 7SA612, REL521
OS | GWE | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA NAVAN
TO-20-ARV-NAV-1-02 ISO week: 41mo - 41fr Date: 05 Oct - 09 Oct Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FOSTRHW |  |  | 901086419 | DO | 2 | 1 | 2019HP-1[132]Replace Pole only -Rot
FOSTRHW |  |  | 901086420 | DO | 2 | 1 | 2019HP-1[191]Replace Pole only -Rot
TO-20-ARV-NAV-1-01 ISO week: 9mo - 10fr Date: 24 Feb - 06 Mar Duration: 12 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084868 | DO | 2 | 4 | 2019HP-1[6]Earths-Replace earth lead
FOSTRHW |  |  | 901086415 | DO | 2 | 1 | 2019HP-1[4]Replace Pole only -Rot
FOSTRHW |  |  | 901086416 | DO | 2 | 1 | 2019HP-1[58]Replace Pole only -Rot
FOSTRHW |  |  | 901086417 | DO | 2 | 1 | 2019HP-1[63]Replace Pole only -Rot
FOSTRHW |  |  | 901086418 | CLO | 2 | 1 | 2019HP-1[128]Replace Pole only -Rot
FOSTRHW |  |  | 901086421 | CLO | 2 | 1 | 2019HP-1[199]Replace Pole only -Rot
FOSTRHW |  |  | 901086422 | CLO | 2 | 1 | 2019HP-1[229]Replace Pole only -Rot
FOSTRHW |  |  | 901086423 | CLO | 2 | 1 | 2019HP-1[230]Replace Pole only -Rot
FOSTRHW |  |  | 901086424 | CLO | 2 | 1 | 2019HP-1[319]Replace Pole only -Rot
CA | NAV | - | 901129179 | CLO | 5 | 4 | 110kV CUBICLE CONDITION ASSESSMENT
OS | NAV | - | 901129885 | CLO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - ARVA SHANKILL 1
TO-20-ARV-SKL-1-01 ISO week: 44th - 44fr Date: 29 Oct - 30 Oct Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO_MISC |  |  | 901084300 | DO | 2 | 4 | 2019HP-1[21]Bird Nests
|  | - |  |  |  |  | Total Maintenance Outage Duration Requested
OPT | SKL |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - ARVA SHANKILL 2
TO-20-ARV-SKL-2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | SKL |  | 901028567 | CANC |  | 1 | O 1 O 1 ARVA 2 C.B. MONITORING TEMI
CORRECT | SKL |  | 901045926 | CANC |  | 1 | Investigate CB gas leak & repair if poss
TO-20-ARV-SKL-2-01 ISO week: 38mo - 39fr Date: 14 Sep - 25 Sep Duration: 12 Days (10 WD) Status: Scheduled
PROT |  | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983642 | DO | 2 | 4 | 2018HP-1[Am 35]Bird Nests
PROX |  |  | PR0001 |  | 2 |  | Proximity for hot spot work LIS-SKL cubicle
TRAN |  | - | 900983641 | DO | 1 | 4 | 2018HP-1[Am 29]Bird Nests
FO_MISC |  |  | 901084301 | DO | 1 | 4 | 2019HP-1[143]Bird Nests
PROT |  |  |  | DO |  |  | P3 Protection maintenance of 7SA612, GRL100
OS | SKL | - |  | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
AMCAB | SKL | 110 |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
CM | SKL | 110 | 901068797 | CANC | 2 | 1 | Visual inspection of HIS HV cable sealin
COUPLER/SECTIONALISING CB - ATHLONE 110SA1-2CB
TO-20-ATH-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | ATH | - | 901039013 | DO | 1 | 3 | 110kV SF6 Cubicle Operational Test
OPT | ATH | 110-SA1 | 901039204 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
OPT | ATH | 110-SA2 | 901039205 | DO | 1 | 3 | 110kV Sect / Dist Operational Test
TO-20-ATH-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
CAPACITOR/SVC/REACTOR - ATHLONE CAP3
TO-20-ATH-CAP3-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
TO-20-ATH-CAP3-01 ISO week: 26mo - 26fr Date: 22 Jun - 26 Jun Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
CORRECT | ATH |  | 901078674 | CLO | 2 | 2 | Contact resistance measurement on the ci
110kV FEEDER - ATHLONE LANESBORO
TO-20-ATH-LA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
YM03 |  | - | 901046063 | CLO | 5 | 4 | Conductor Sampling section 179-199
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-ATH-LA-1-03 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
CAPACITOR/SVC/REACTOR - ATHLONE M/CAP1
TO-20-ATH-M/CAP1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
TO-20-ATH-M/CAP1-01 ISO week: 27tu - 27we Date: 30 Jun - 01 Jul Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
CORRECT | ATH |  | 901067981 | CLO | 2 | 2 | O1- Spray Weeds Cap 1 Cubicle
110kV FEEDER - ATHLONE SHANNONBRIDGE
TO-20-ATH-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900983699 | DO | 1 | 4 | 2018HP-1[Am 75]Bird Nests
FO_MISC |  |  | 901084302 | DO | 1 | 4 | 2019HP-1[75]Bird Nests
FOSTRHW |  |  | 901086374 | DO | 1 | 4 | 2019HP-1[23]Check Structure -Check Rot
FOSTRHW |  |  | 901086375 | DO | 1 | 4 | 2019HP-1[43]Check Structure -Check Rot
OPT | ATH |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TO-20-ATH-SH-1-02 Status: Unscheduled
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - ATHLONE T141 [SDCC]
TO-20-ATH-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A1 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA1)
DISTRIBUTION TRANSFORMER - ATHLONE T142 [SDCC]
TO-20-ATH-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 1 |  | 110 kV A2 @ ATH: Proximity outage for work on Athlone 110kV Coupler/Sectionalising CB Opt Test including busbar disconnects (SA2)
220kV FEEDER - CASHLA TYNAGH
TO-20-CSH-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-CSH-TY-1-05 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder as breakers are being completed in Flagford and Cashla station
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-FLA-1 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-01 Status: Unscheduled
CAPX |  |  | MC0237 | DO | 2 |  | Commission new Sync Scheme - all bays in turn
CAPX |  |  | MC9999 | DO | 2 |  | 220 kV A1/B1 @ CSH: Uprate bay conductor on Cashla - Flagford circuit
TO-20-CSH-TY-1-06 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-T2102 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder- EI Required
TO-20-CSH-TY-1-04 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-220K1-2 + CSH-TY-1: Energise new Circuit Breaker replacement via the 220 kV Cashla Tynagh feeder
TO-20-CSH-TY-1-09 Status: Unscheduled
CM | CSH | 220-DL | 901148822 | CLO | 2 | 1 | 01 Tynagh DL Fault
TO-20-CSH-TY-1-07 Status: Unscheduled
CAPX |  |  | CP1019 | DO | 7 |  | Fibre wrapping of the line - to be installed on OPGW earthwire
TO-20-CSH-TY-1-03 ISO week: 16th - 21th Date: 16 Apr - 21 May Duration: 36 Days (25 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900985040 | DO | 1 | 4 | 2018HP-1[104]Vib DampersR/Ph
FO_MISC |  |  | 901084267 | DO | 1 | 4 | 2019HP-1[57]Bird Nests
FO_MISC |  |  | 901084268 | DO | 1 | 4 | 2019HP-1[107]Bird Nests
OPT | CSH | - | 901038878 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
YM03 | TYN | - | 900979523 | DO | 3 | 4 | DISC CONTACTS DAMAGED
OPT | TYN | - | 901039106 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - CLOON LANESBORO
TO-20-CLN-LA-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ CLN: Proximity outage for work on Cloon 110kV Sect / Dist Ordinary Service (SA2)
TO-20-CLN-LA-1-03 Status: Unscheduled
[5 empty] | 2 |  | Proximity for EI of CLN T142
TO-20-CLN-LA-1-04 Status: Unscheduled
CORRECT | LA | - | 900957961 | CANC | 3 | 1 | Repair fault busbar disconnect
TO-20-CLN-LA-1-05 Status: Unscheduled
FO_MISC |  | - | 900819454 | CANC | 1 | 2 | 2016HP-1[97]Stays - Check Check stays
TO-20-CLN-LA-1-01 ISO week: 42mo - 42fr Date: 12 Oct - 16 Oct Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901085132 | DO | 1 | 4 | 2019HP-1[97]Stays-Replace Broken
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
OS | CLN | - | 901042219 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | LA | - | 901042220 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - CORDUFF MULLINGAR
TO-20-CDU-MUL-1-02 ISO week: 28mo - 28we Date: 06 Jul - 08 Jul Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084099 | CLO | 2 | 2 | 2019HP-1[48]Arching Horns check
FO_MISC |  | - | 900902317 | DO | 1 | 3 | 2017CP-1[285]Off Plumb pole
AMCAB | CDU | - |  | DO | 3 | 4 | Cable Insp. 110kV XLPE
TO-20-CDU-MUL-1-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
110kV FEEDER - CUSHALING MOUNTLUCAS
TO-20-CUS-MLC-1-01 ISO week: 24tu - 24we Date: 09 Jun - 10 Jun Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | CUS |  |  | DO | 2 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MLC |  |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - DALLOW tee DALLOW
TO-20-DAL,T-DAL-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-04 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-DAL-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-DAL-1-09 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous 110 kV A2 @ SH + DLW-PLS-SH-1: Energise new Derrycarney 110kV and Derrycarney T121
CAPX |  |  | CP1057_OS | DO | 2 |  | DLW-PLS-SH-1: EI: Simultaneous DLW-PLS-SH-1 + SH-T2102: Energise new Derrycarney 110kV and Derrycarney T121
TO-20-DAL,T-DAL-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-DAL-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-DAL-1-03 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-DAL-1-11 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee PORTLAOISE
TO-20-DAL,T-PLS-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-06 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
TO-20-DAL,T-PLS-1-08 Status: Unscheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | PLS | - |  | DO | 3 | 4 | 110kV SF6 Cubicle Ordinary Service
CORRECT | PLS |  | 900965558 | DO | 3 | 1 | Moisture in LAs
CORRECT | PLS |  | 901072096 | DO | 3 | 1 | H6 , loose stripped cores in mech box ,
TO-20-DAL,T-PLS-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-PLS-1-03 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-PLS-1-01 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-PLS-1-04 ISO week: 39tu - 41mo Date: 22 Sep - 05 Oct Duration: 14 Days (10 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-PLS-1-13 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
110kV FEEDER - DALLOW tee SHANNONBRIDGE
TO-20-DAL,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1057 | DO | 10 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Dallow T to new Derrycarney station Dallow- to be tail fed from Shannonbridge
TO-20-DAL,T-SH-1-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-DAL,T-SH-1-11 Status: Unscheduled
CAPX |  |  | CP1057_OS | DO | 47 |  | DLW-PLS-SH-1: EI: Remote end works in Portlaoise and energise Derrycarney - Portlaoise
TO-20-DAL,T-SH-1-05 ISO week: 41mo - 41tu Date: 05 Oct - 06 Oct Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 3 |  | DLW-PLS-SH-1: Complete fibre wrap. Start remote end works in Shannonbridge Cross over. Prepare tailing Dallow from Portlaoise. Break at (T260) Full line outage
TO-20-DAL,T-SH-1-02 ISO week: 33mo - 33fr Date: 10 Aug - 14 Aug Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Break Shannonbridge line at Dallow Tee (at T260) Full line outage
TO-20-DAL,T-SH-1-04 ISO week: 38tu - 39mo Date: 15 Sep - 21 Sep Duration: 7 Days (5 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 5 |  | DLW-PLS-SH-1: Cross over. Prepare tailing Dallow from Shannonbridge. Break at (T252) Full line outage
TO-20-DAL,T-SH-1-12 ISO week: 47mo - 49mo Date: 16 Nov - 30 Nov Duration: 15 Days (11 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 20 |  | DLW-PLS-SH-1: Final tie in at Derrycarney station Full line outage
TO-20-DAL,T-SH-1-03 ISO week: 34mo - 38mo Date: 17 Aug - 14 Sep Duration: 29 Days (21 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 21 |  | DLW-PLS-SH-1: OHL works and fibre wrap from Shannonbridge to Dallow T Dallow - to be tail fed from Portlaoise
TO-20-DAL,T-SH-1-06 ISO week: 41we - 48fr Date: 07 Oct - 27 Nov Duration: 52 Days (37 WD) Status: Scheduled
CAPX |  |  | CP1057 | DO | 37 |  | DLW-PLS-SH-1: Remote end works Shannonbridge Dallow Tee - to be tail fed from Portlaoise
|  | - |  |  | 7 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084339 | DO | 1 | 4 | 2019HP-1[252]Bird Nests -Remove
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | - |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CM | SH | - | 901133675 | DO | 2 | 1 | T Phase DA Disconnect DUE: 17-Jul-20
SECTIONALISING DISCONNECT - DERRYIRON 110SA1
TO-20-DER-110SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-110SA2: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DER-110SA1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
[5 empty] | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
OS | DER | SA1 | 901039703 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service including busbar disconnects
SECTIONALISING DISCONNECT - DERRYIRON 110SA2
TO-20-DER-110SA2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
OS | DER | SA2 | 900666902 | DO | 3 | 1 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-DER-110SA2-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-110SA1: 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
110kV FEEDER - DERRYIRON KINNEGAD
TO-20-DER-KIN-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-DER-KIN-1-01 ISO week: 9mo - 9tu Date: 24 Feb - 25 Feb Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A1 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA1)
FO_MISC |  |  | 901084275 | CLO | 1 | 4 | 2019HP-1[71]Bird Nests
CORRECT | DER |  | 900623151 | CLO | 1 | 1 | ESBI N01 non outage (important) Misc- wo
CORRECT | KIN |  | 901087474 | CLO | 1 | 2 | Measurement of copper conductor diameter
GENERATOR TRANSFORMER - DERRYIRON RHODE T1/T2 [SSE Generation RP1/RP2]
TO-20-DER-T1/T2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
|  |  | PROT |  |  |  | P2 Protection maintenance of 7SA513
OPT | DER |  |  | DO | 1 | 4 | 110KV SF6 Cubicle Operational Test
110kV FEEDER - DERRYIRON THORNSBERRY
TO-20-DER-TSB-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DER-TSB-1-01 Status: Unscheduled
PROT |  |  |  | DO |  |  | P3 Protection maintenance of REL521
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SA511, REL521
| - | 110 |  |  | 7 |  | Total Maintenance Outage Duration Requested
OS | DER | - | 900775276 | DO | 4 | 1 | 110kV SF6 Cubicle Ordinary Service
CA | DER | - | 900775914 | DO | 3 | 1 | 110KV CUBICLE CONDITION ASSESSMENT
DISTRIBUTION TRANSFORMER - DUNFIRTH T122 [NDCC]
TO-20-DFR-T122-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR-T122-02 Status: Reference (Unscheduled)
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee DUNFIRTH
TO-20-DFR,T-DFR-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
Full tee outage
TO-20-DFR,T-DFR-1-02 Status: Unscheduled
[5 empty] | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee KINNEGAD
TO-20-DFR,T-KIN-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | KIN | - | 901042225 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-DFR,T-KIN-1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
TO-20-DFR,T-KIN-1-03 Status: Unscheduled
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
110kV FEEDER - DUNFIRTH tee RINAWADE
TO-20-DFR,T-RNW-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | 110 kV A2 @ RNW: Proximity outage for work on Rinawade 110kV Sect / Dist Ordinary Service (SA2)
TO-20-DFR,T-RNW-1-01 Status: Unscheduled
|  | - |  |  | 15 |  | Total Maintenance Outage Duration Requested
|  |  |  | DO | 1 |  | Remake jumpers following maintenance on Dunfirth tee Rinawade
|  |  |  | DO | 1 |  | Break jumpers for maintenance on Dunfirth tee Rinawade
OS | RNW | - |  | DO | 10 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - FLAGFORD SLIABH BAWN
TO-20-FLA-SLB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1031 | DO | 40 |  | EI: Install Sprecher & Schuh type HPF-511 Circuit breaker replacement in the 110 kV flagford Sliabh Bawn bay at flagford station
TO-20-FLA-SLB-1-02 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remove droppers (FLA - SLB)
TO-20-FLA-SLB-1-03 Status: Unscheduled
CAPX |  |  | CP1031 | DO | 2 |  | Simultaneous 110 kV A1/B1 IN TURN @ FLA + FLA-SLB-1: Remake droppers (FLA - SLB)
TO-20-FLA-SLB-1-05 Status: Unscheduled
SAG6_HV | - | Line | 901160383 | DO | 2 | 1 | SPAN 1-2 of 0.98m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160384 | DO | 2 | 1 | SPAN 15-16 of 0.76m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160385 | DO | 2 | 1 | SPAN 16-17 of 1.99m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160386 | DO | 2 | 1 | SPAN 19-20 of 2.75m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160387 | DO | 2 | 1 | SPAN 31-32 of 0.92m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160388 | DO | 2 | 1 | SPAN 46-47 of 2.52m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160389 | DO | 2 | 1 | SPAN 76-77 of 2.23m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160390 | DO | 2 | 1 | SPAN 95-96 of 0.34m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160391 | DO | 2 | 1 | SPAN 1-2 of 0.43m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160392 | DO | 2 | 1 | SPAN 15-16 of 0.91m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160393 | DO | 2 | 1 | SPAN 16-17 of 2.58m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160394 | DO | 2 | 1 | SPAN 19-20 of 3.69m, LV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160395 | DO | 2 | 1 | SPAN 31-32 of 1.63m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160396 | DO | 2 | 1 | SPAN 46-47 of 3.89m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160397 | DO | 2 | 1 | SPAN 60-61 of 0.10m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160398 | DO | 2 | 1 | SPAN 76-77 of 2.48m, 20kV UNDER-GROUND CLEARENCE INFRINGEMENT
SAG6_HV | - | Line | 901160399 | DO | 2 | 1 | SPAN 95-96 of 0.90m, 10kV UNDER-GROUND CLEARENCE INFRINGEMENT
TO-20-FLA-SLB-1-06 Status: Unscheduled
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 44-45
| - | Line |  | NS | 2 | 1 | Clearance Infringment Spans 43-44
TO-20-FLA-SLB-1-04 ISO week: 32tu - 35fr Date: 04 Aug - 28 Aug Duration: 25 Days (19 WD) Status: Scheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
TRAN |  | - | 900987019 | DO | 1 | 4 | 2018HP-1[Am 64]Bird Nests
FO_MISC |  |  | 901084413 | DO | 1 | 4 | 2019HP-1[64]Bird Nests
OS | FLA | - | 901050316 | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | SLB | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
110kV FEEDER - IKERRIN tee SHANNONBRIDGE
TO-20-IKE,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
Proximity outage for IKE-THU
TO-20-IKE,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | IKE-SH-THU-1: Proximity outage to cross OHL
220kV FEEDER - KILLONAN SHANNONBRIDGE
TO-20-KLN-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
[5 empty] | 5 |  | Studied proximity CP1058
TO-20-KLN-SH-1-01 ISO week: 20mo - 22th Date: 11 May - 28 May Duration: 18 Days (14 WD) Status: Scheduled
PROT |  |  |  | DO | 2 | 1 | P1 Protection maintenance of 7SA513, REL521
FO_MISC |  |  | 901084918 | DO | 2 | 4 | 2019HP-1[22]Insulator broken insulator
FO_MISC |  |  | 901084919 | DO | 2 | 4 | 2019HP-1[240]Insulator broken insulator
FO_MISC |  | - | 900404035 | DO | 1 | 1 | 1[180]Fit anti climb device
YM03 | - | - | 900978885 | DO | 5 | 1 | 1[57]Repairs of damaged members on Tower
OS | KLN | - | 900858887 | CLO | 10 | 2 | 220kV Air Blast Cubicle Ordinary Service
CA | KLN | - | 901038533 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
CORRECT | KLN |  | 901045697 | CLO | 2 | 1 | Pressure Vessel Statutory Inspection
OPT | KLN | 220-1 |  | DO | 1 | 4 | 220kV Air Blast Cubicle Operational Test
CA | SH | - | 900775936 | CLO | 3 | 1 | 220kV Cubicle Condition Assessment
OPT | SH | 220-1 |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - KINNEGAD 110SA1-2CB
TO-20-KIN-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
OS | KIN | - | 901042251 | DO | 2 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | KIN | 110-SA1 | 901042964 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-KIN-110SA1-2CB-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | KIN | 110-SA2 | 901042963 | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - KINNEGAD MULLINGAR
TO-20-KIN-MUL-1-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-KIN-MUL-1-02 ISO week: 30mo - 30tu Date: 20 Jul - 21 Jul Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OPT | KIN | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | MUL | - | 901118292 | CLO | 1 | 4 | 110kV SF6 Cubicle Operational Test
TO-20-KIN-MUL-1-01 ISO week: 30mo - 41fr Date: 20 Jul - 09 Oct Duration: 82 Days (59 WD) Status: Scheduled
CAPX |  |  | CP1054 | DO | 58 |  | EI: Install 2 new towers under the line, divert line and re-energise from remote end
TSO CUSTOMER TRANSFORMER - KINNEGAD T101 [Lagan Cement]
TO-20-KIN-T101-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-KIN-T101-03 Status: Unscheduled
CORRECT | KIN |  | 901068813 | CANC |  | 1 | replacement of the CT’s in Kinnegad T101
TO-20-KIN-T101-01 ISO week: 44tu - 44fr Date: 27 Oct - 30 Oct Duration: 4 Days (4 WD) Status: Scheduled
|  | - |  |  | 4 |  | Total Maintenance Outage Duration Requested
OS | KIN | - | 901042268 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
TSO CUSTOMER TRANSFORMER - KINNEGAD T102 [Lagan Cement]
TO-20-KIN-T102-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ KIN: Proximity outage for work on Kinnegad 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | KIN | TRAFO | 901080654 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - LANESBORO 110SA1-2CB
TO-20-LA-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
OS | LA | - | 901129877 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | LA | - |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | LA | - |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
110kV FEEDER - LANESBORO MULLINGAR
TO-20-LA-MUL-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
TO-20-LA-MUL-1-03 Status: Unscheduled
YM03 | - | Line | 901110465 | CLO | 5 | 1 | R1 206 - 207 Right Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110466 | CLO | 5 | 1 | C1 206 - 207 Centre Mid span joint Replace joint within 3 months pending TSO review.
YM03 | - | Line | 901110467 | CLO | 5 | 1 | L1 206 - 207 Left Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110468 | CLO | 5 | 1 | R2 205 - 206 Right Mid span joint Replace joint within 6 months pending TSO review
YM03 | - | Line | 901110469 | CLO | 5 | 1 | L2 205 - 206 Left Mid span joint. Replace joint during the next planned outage
YM03 | - | Line | 901110514 | CLO | 5 | 1 | C2 205 - 206 Centre Mid span joint Replace joint within 6 months pending TSO review.
YM03 | - | Line | 901110515 | CLO | 5 | 1 | Am No.75 75 - 76 Left Dead end termination Replace joint within 1 month pending TSO review
YM03 | - | Line | 901110516 | CLO | 5 | 1 | R1 74 - 75 Right Mid span joint Replace joint during the next planned outage.
110kV FEEDER - LANESBORO RICHMOND 1 [NDCC]
TO-20-LA-RIC-1-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
110kV FEEDER - LANESBORO RICHMOND 2 [NDCC]
TO-20-LA-RIC-2-02 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
110kV FEEDER - LANESBORO SLIABH BAWN
TO-20-LA-SLB-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
OS | SLB | - | 901042297 | DO | 5 | 4 | 110kV SF6 Cubicle Ordinary Service
TO-20-LA-SLB-1-02 Status: Unscheduled
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
GENERATOR TRANSFORMER - LANESBORO T104 [ESB GWM LR4]
TO-20-LA-T104-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A2 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA2)
DISTRIBUTION TRANSFORMER - LANESBORO T141 [NDCC]
TO-20-LA-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ LA: Proximity outage for work on Lanesboro 110kV SA1-2 Sect / Dist Ordinary Service including busbar disconnects (SA1)
220kV FEEDER - MAYNOOTH SHANNONBRIDGE
TO-20-MAY-SH-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN | - | Line | 901110127 | CLO | 2 | 1 | Hotspot 1 (R1 Span 81/82) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110131 | DO | 2 | 1 | Hotspot 2 (R2 Span 255/256) Right phase midspan (Repair by 17th July 2020)
TRAN | - | Line | 901110136 | DO | 2 | 1 | Hotspot 3 (R1 Span 271/272) Right phase midspan (Repair by 17th July 2020)
TO-20-MAY-SH-1-01 ISO week: 26mo - 27th Date: 22 Jun - 02 Jul Duration: 11 Days (9 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
FO_MISC |  | - | 900819839 | DO | 4 | 2 | 2016HP-2[2 & 3]Insulator Fit Dups
FO_MISC |  |  | 901090694 | DO | 2 | 4 | 2019HP-1[47-48]Conflicts 10/20kV pole
FO_MISC |  |  | 901090695 | DO | 2 | 4 | 2019HP-1[51-52]Conflicts 10/20kV pole
CM | MAY | - | 901076415 | CLO | 4 | 1 | Copper earths stolen from 220kV CT and VT to be reinstalled
CA | SH | - | 901038544 | DO | 3 | 4 | 220kV Cubicle Condition Assessment
400kV FEEDER - MONEYPOINT GIS OLDSTREET
TO-20-MP GIS-OST-1-05 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
TRAN |  | - | 900988931 | NS |  | 1 | 2018HP-1[166]Bird Nestsremove asap
TRAN |  | - | 900988938 | NS |  | 1 | 2018HP-1[176]Bird Nestsremove asap
TRAN |  | - | 900988946 | NS |  | 1 | 2018HP-1[191]Bird Nestsremove asap
TRAN |  | - | 900988976 | NS |  | 1 | 2018HP-1[74]Bird Nestsremove asap
TO-20-MP GIS-OST-1-04 Status: Unscheduled
studied outage for CP0824
TO-20-MP GIS-OST-1-03 ISO week: 29mo - 29fr Date: 13 Jul - 17 Jul Duration: 5 Days (5 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 5 |  | Simultaneous CSH-PRO-1 + MP GIS-OST-1: Proximity outage for refurb works on Moneypoint Oldstreet
TO-20-MP GIS-OST-1-01 ISO week: 9mo - 14th Date: 24 Feb - 02 Apr Duration: 39 Days (28 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting
TO-20-MP GIS-OST-1-02 ISO week: 21th - 41fr Date: 21 May - 09 Oct Duration: 142 Days (100 WD) Status: Scheduled
CAPX |  |  | CP0824 | DO | 100 |  | EI: Moneypoint - Oldstreet 400 kV Line Refurbishment - hardware replacements and remaining painting (part 2)
|  |  | OD0321 |  | 5 |  | Total Maintenance Outage Duration Requested
|  | MP | 19EG23677 | CLO | 2 |  | Cable Insp. 400kV XLPE
|  |  | 20LN4755 |  | 2 |  | 2019HP-1[11]Insulator Broken
|  |  | 18LN1616 |  | 1 |  | 2017HP-1[199]Earths-Check S/W hardware
|  |  | 18LN1618 |  | 1 |  | 2017HP-1[55A]Insulator Broken
|  |  | 18LN1631 |  | 1 |  | 2017HP-1[139]Earths-Check S/W hardware
|  |  | 19LN6391 |  | 1 |  | 2018HP-3[3]Insul&HW Replace check
|  |  | 19LN6392 |  | 1 |  | 2018HP-3[8]Insul&HW Replace check
|  |  | 19LN6393 |  | 1 |  | 2018HP-2[11]Insul&HW Replace check
|  |  | 19LN6394 |  | 1 |  | 2018HP-3[15]Insul&HW Replace check
|  |  | 19LN6395 |  | 1 |  | 2018HP-1[13]Insul&HW Replace check
|  |  | 19LN6396 |  | 1 |  | 2018HP-1[27]Insul&HW Replace check
|  |  | 19LN6398 |  | 1 |  | 2018HP-1[55A]Insulator-replace
|  |  | 20LN4741 |  | 1 |  | 2019HP-1[166]Bird Nests
|  |  | 20LN4743 |  | 1 |  | 2019HP-1[175]Bird Nests
|  |  | 20LN4744 |  | 1 |  | 2019HP-1[183]Bird Nests
|  |  | 20LN4745 |  | 1 |  | 2019HP-1[191]Bird Nests
|  |  | 20LN4756 |  | 1 |  | 2019HP-1[55A]Insulator Broken
| OST |  | 18EG10486 |  | 2 |  | 400kV SF6 Cubicle Operational Test
GENERATOR TRANSFORMER - MOUNTLUCAS T121 [Mountlucas MO1]
TO-20-MLC-T121-01 ISO week: 24we Date: 10 Jun Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROT |  |  |  | DO | 1 | 3 | P3 Protection maintenance of 7SA612
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
OPT | MLC | 110 |  | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - MULLINGAR 110SA1-2CB
TO-20-MUL-110SA1-2CB-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
TO-20-MUL-110SA1-2CB-02 Status: Unscheduled
|  | - |  |  | 6 |  | Total Maintenance Outage Duration Requested
OS | MUL | - | 901129883 | CLO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | MUL | SA1 | 901039452 | DO | 2 | 3 | 110kV Sect / Dist Ordinary Service including busbar disconnects
TO-20-MUL-110SA1-2CB-03 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
CAPACITOR/SVC/REACTOR - MULLINGAR CAP1
TO-20-MUL-CAP1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
CAPACITOR/SVC/REACTOR - MULLINGAR CAP2
TO-20-MUL-CAP2-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
TO-20-MUL-CAP2-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Scheduled
CORRECT | MUL | - | 900869763 | CLO | 4 | 1 | Replace Densimeters on Circuit Breaker
OPT | MUL |  | 901129545 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test
DISTRIBUTION TRANSFORMER - MULLINGAR T101 [NDCC]
TO-20-MUL-T101-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - MULLINGAR T102 [NDCC]
TO-20-MUL-T102-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
DISTRIBUTION TRANSFORMER - MULLINGAR T141 [NDCC]
TO-20-MUL-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0002 | DO | 2 |  | 110 kV A1 @ MUL: Proximity outage for work on Mullingar 110kV SA1-2 Sect / Dist Ordinary Service (SA1)
DISTRIBUTION TRANSFORMER - MULLINGAR T142 [NDCC]
TO-20-MUL-T142-01 ISO week: 28mo - 28th Date: 06 Jul - 09 Jul Duration: 4 Days (4 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0001 | DO | 4 |  | 110 kV A2 @ MUL: Proximity outage for work on CAP2
220kV FEEDER - OLDSTREET TYNAGH
TO-20-OST-TY-1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
TO-20-OST-TY-1-01 Status: Unscheduled
|  | - |  |  | 1 |  | Total Maintenance Outage Duration Requested
MO |  |  | 901039105 |  | 1 |  | 220kV SF6 Cubicle Operational Test
FO_MISC |  |  | 901084335 | DO | 1 | 4 | 2019HP-1[17]Bird Nests
CM | TYN | - | 901133678 | DO | 2 | 1 | 220kV SF6 Cubicle Ordinary Service DUE : 17-Jul-20
OPT | TYN | - |  | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
400kV FEEDER - OLDSTREET WOODLAND
TO-20-OST-WOO-1-01 ISO week: 42sa - 44fr Date: 17 Oct - 30 Oct Duration: 14 Days (9 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 14 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084928 | DO | 2 | 4 | 2019HP-1[103]Insulator Broken
FO_MISC |  |  | 901084929 | DO | 2 | 4 | 2019HP-1[115]Insulator Broken
FO_MISC |  |  | 901084930 | DO | 2 | 4 | 2019HP-1[272]Insulator Remove old insul
FO_STDMG |  |  | 901086387 | DO | 2 | 4 | 2019HP-1[90 ]Replace Member
FO_STDMG |  |  | 901086388 | DO | 2 | 4 | 2019HP-1[100]Replace Member
FO_STDMG |  |  | 901086389 | DO | 2 | 4 | 2019HP-1[120]Replace Member
TRAN |  | - | 900989127 | DO | 1 | 4 | 2018HP-1[99]Replace Memberrakers
TRAN |  | - | 900989128 | DO | 1 | 4 | 2018HP-1[100]Replace Memberrakers
TRAN |  | - | 900989185 | DO | 1 | 4 | 2018HP-1[115]Insulator-broken c/ph
TRAN |  | - | 900989188 | DO | 1 | 4 | 2018HP-1[162]Check(General)Remove object
FO_MISC |  |  | 901084336 | DO | 1 | 4 | 2019HP-1[76]Bird Nests
FO_MISC |  |  | 901084337 | DO | 1 | 4 | 2019HP-1[79]Bird Nests
FO_MISC |  |  | 901084338 | DO | 1 | 4 | 2019HP-1[93]Bird Nests
PROT |  |  |  | DO |  |  | P1 Protection maintenance of 7SL32, FYS3L, FYG2L
OPT | OST | - | 901039088 | DO | 2 | 4 | 400kV SF6 Cubicle Operational Test
CORRECT | WOO | R4001 | 900821342 | DO | 10 | 1 | Some work done in 2014 Beltec 2 leaks HV
CORRECT | WOO |  | 900724385 | DO | 5 | 1 | O/1 Repair to leak in concrete of Bund
CORRECT | WOO |  | 901046071 | DO | 3 | 1 | SF6 leak repair
FM | WOO | 400-1 |  | DO | 1 | 4 | HV Pressure Vessel Inspection
CORRECT | WOO |  | 900788839 | DO |  | 2 | Misc- work not on other CORRECT counters
BUSBAR SECTION - SHANNONBRIDGE 110 kV A1
TO-20-110 kV A1 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV A1 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV A2
TO-20-110 kV A2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV A2 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV B1
TO-20-110 kV B1 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV B1 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
BUSBAR SECTION - SHANNONBRIDGE 110 kV B2
TO-20-110 kV B2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | PR0002 | DO | 2 |  | 110 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 110kV K1-2
TO-20-110 kV B2 @ SH-02 ISO week: 40th Date: 01 Oct Duration: 1 Day (1 WD) Status: Scheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110K1-2
TO-20-SH-110K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 12 |  | Total Maintenance Outage Duration Requested
OS | SH | - |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
OS | SH | 110-SB2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SB1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SA2 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
OS | SH | 110-SA1 |  | DO | 2 | 4 | 110kV Sect / Dist Ordinary Service
TO-20-SH-110K1-2-02 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
BUSBAR SECTION - SHANNONBRIDGE 220 kV A1
TO-20-220 kV A1 @ SH-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A1 @ SH-01 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
BUSBAR SECTION - SHANNONBRIDGE 220 kV A2
TO-20-220 kV A2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 10 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs
TO-20-220 kV A2 @ SH-03 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo).
TO-20-220 kV A2 @ SH-05 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV A2 @ SH-06 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 20 |  | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs.
TO-20-220 kV A2 @ SH-04 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
TO-20-220 kV A2 @ SH-02 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1058 | DO | 20 |  | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs.
BUSBAR SECTION - SHANNONBRIDGE 220 kV B1
TO-20-220 kV B1 @ SH-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B1 @ SH-01 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A1/B1 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
BUSBAR SECTION - SHANNONBRIDGE 220 kV B2
TO-20-220 kV B2 @ SH-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 10 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn. A2/B2 outage to accommodate civil works for new pantographs
TO-20-220 kV B2 @ SH-04 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 4 |  | Installation of tube between DA, DB and to CB
TO-20-220 kV B2 @ SH-05 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Bars in turn to accommodate EI of T224 (DA, DB and trafo).
TO-20-220 kV B2 @ SH-02 Status: Unscheduled
CAPX |  |  | CP1058 | DO | 3 |  | Errection and installation of circuti breaker. B2 proximity outage required
TO-20-220 kV B2 @ SH-07 Status: Unscheduled
BB |  |  | BB0001 |  | 1 |  | Busbar changeover
TO-20-220 kV B2 @ SH-08 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 20 |  | 220 kV A2/B2 IN TURN @ SH: Installation of pantographs.
TO-20-220 kV B2 @ SH-06 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
CAPX |  |  | PR0002 | DO | 2 |  | 220 kV A2/B2 IN TURN @ SH: Proximity outage for work on Shannonbridge 220kV K1-2
TO-20-220 kV B2 @ SH-03 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
CAPX |  |  | CP1058 | DO | 20 |  | 220 kV A2/B2 @ SH: A2/B2 outage to accommodate installation of pantographs.
COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220K1-2
TO-20-SH-220K1-2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 1 |  | Coupler outage. Testing of interlocking between new trafo and coupler (drive sharfts on pantographs removed)
TO-20-SH-220K1-2-02 ISO week: 13tu - 13we Date: 24 Mar - 25 Mar Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 3 |  | Total Maintenance Outage Duration Requested
CORRECT | SH |  | 900315850 | DO | 3 | 1 | O.2.esbi reqd.moving contact to be repla
OPT | SH | 220-SA1 | 901130125 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | SH | 220-SA2 | 901130126 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
OPT | SH | 220-SB1 | 901130127 | CLO | 1 | 4 | 220kV Sect / Dist Operational Test
GENERATOR TRANSFORMER - SHANNONBRIDGE T104 [ESB GWM WO4]
TO-20-SH-T104-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SH-T104-01 ISO week: 36tu - 36we Date: 01 Sep - 02 Sep Duration: 2 Days (2 WD) Status: Scheduled
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
TRANSFORMER - SHANNONBRIDGE T2101
TO-20-SH-T2101-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1058 | DO | 2 |  | EI: Feeder outage to accmodate EI of T224 (DA, DB and trafo).
TO-20-SH-T2101-02 ISO week: 21mo - 22tu Date: 18 May - 26 May Duration: 9 Days (7 WD) Status: Scheduled
|  | - |  |  | 9 |  | Total Maintenance Outage Duration Requested
OS | SH | 110 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
OS | SH | 220 |  | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service
CA | SH | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
OS | SH | Trafo |  | DO | 3 | 4 | 220/110 & 275/220 Trafo Ordinary Service
CORRECT | SH |  | 901059910 | CLO | 1 | 1 | Replace Sensor
TRANSFORMER - SHANNONBRIDGE T2102
TO-20-SH-T2102-03 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CORRECT | SH |  | 901059909 | CANC |  | 1 | Investigate unit fault
TO-20-SH-T2102-05 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SH-T2102-02 Status: Unscheduled
CAPX |  |  | CP1057 | DO | 2 |  | EI: EI to prove the new station & customer transformer T121 including 24 hour soak. Use T2102 in Shannonbridge to energise Derrycarney station on tail
TO-20-SH-T2102-01 ISO week: 22we - 24we Date: 27 May - 10 Jun Duration: 15 Days (10 WD) Status: Scheduled
|  | - |  |  | 10 |  | Total Maintenance Outage Duration Requested
OS | SH | TRAFO |  | DO | 6 | 4 | 220/110 & 275/220 Trafo Ordinary Service
OS | SH | 110 |  | DO | 6 | 4 | 110kV MO Cubicle Ordinary Service
TRAFO | SH | TRAFO |  | DO | 5 | 4 | 220/110 & 275/220 TRAFO COND. ASSESSMENT
OS | SH | 220 |  | DO | 5 | 4 | 220kV SF6 Cubicle Ordinary Service
CA | SH | 220 |  | DO | 3 | 4 | 220KV CUBICLE CONDITION ASSESSMENT
CA | SH | 110 |  | DO | 3 | 4 | 110KV CUBICLE CONDITION ASSESSMENT
CORRECT | SH |  | 900867382 | CLO | 2 | 1 | ESBIN01 GE are to supply replacement hyd
TO-20-SH-T2102-04 ISO week: 45mo - 48fr Date: 02 Nov - 27 Nov Duration: 26 Days (20 WD) Status: Scheduled
Shannonbridge T2102 - VT replacement required
BUSBAR SECTION - SLIABH BAWN 110 kV A2
TO-20-110 kV A2 @ SLB-01 ISO week: 27th Date: 02 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
BUSBAR SECTION - SLIABH BAWN 110 kV B2
TO-20-110 kV B2 @ SLB-01 ISO week: 27th Date: 02 Jul Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
BB |  |  | BB0000 |  | 1 |  | Busbar Changeover
DISTRIBUTION TRANSFORMER - SOMERSET T142 [SDCC]
TO-20-SOM-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM-T142-02 Status: Reference (Unscheduled)
CAPX |  |  | CP1032 | DO | 1 |  | As a consequence of SOM,T-SOM-1: EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM-T142-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Reference
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
110kV FEEDER - SOMERSET tee CASHLA
TO-20-SOM,T-CSH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 40 |  | Install Sprecher & Schuh type HPF-511 110 kV Circuit breaker replacement in the Cashla Shannonbridge 110 kV bay at cashla station.
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remake droppers
CAPX |  |  | CP1032 | DO | 2 |  | Simultaneous 110 kV A2/B2 IN TURN @ CSH + SOM,T-CSH-1: Remove droppers
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-CSH-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-CSH-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
FO_MISC |  |  | 901084838 | DO | 2 | 4 | 2019HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900727084 | DO | 1 | 1 | 2015HP-1[77]Insulator Broken R/ph
FO_MISC |  | - | 900902253 | DO | 1 | 3 | 2017CP-1[87]Off Plumb Poles
FO_STDMG |  | - | 900902255 | DO | 1 | 3 | 2017CP-1[95]Found/Site repair -Sleeper
FO_MISC |  | - | 900902263 | CLO | 1 | 3 | 2017CP-1[173]Off Plumb Poles
FO_MISC |  | - | 900902264 | CLO | 1 | 3 | 2017CP-1[175]Off Plumb Poles
FO_MISC |  | - | 900902266 | DO | 1 | 3 | 2017CP-1[184]Off Plumb Insuls
FO_MISC |  | - | 900902268 | CLO | 1 | 3 | 2017CP-1[220]Off Plumb Insuls
TRAN |  | - | 900984945 | DO | 1 | 4 | 2018HP-1[152]Foundation/Site repair-stay
FO_MISC |  |  | 901084265 | CLO | 1 | 4 | 2019HP-1[181]Bird Nests
FO_MISC |  |  | 901084266 | CLO | 1 | 4 | 2019HP-1[260]Bird Nests
CORRECT | CSH |  | 900907890 | DO | 1 | 1 | Counter not working. To be replaced.
OPT | CSH | - | 901076462 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
110kV FEEDER - SOMERSET tee SHANNONBRIDGE
TO-20-SOM,T-SH-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-SH-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-SH-1-04 Status: Unscheduled
CAPX |  |  | CP1058_OS | DO | 3 |  | 110 kV A2/B2 @ SH: Installation of tube between DA, DB and to CB
TO-20-SOM,T-SH-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
|  | - |  |  | 5 |  | Total Maintenance Outage Duration Requested
PROT |  |  |  | DO | 2 | 3 | P3 Protection maintenance of 7SA612, REL521
FO_MISC |  | - | 900902328 | DO | 1 | 3 | 2017CP-1[3]Vibration Dampers -Replace
AMCAB | SH | - |  | DO | 2 | 4 | Cable Insp. 110kV XLPE
110kV FEEDER - SOMERSET tee SOMERSET
TO-20-SOM,T-SOM-1-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1032 | DO | 1 |  | Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remove line dropper in Cashla, once the line dropper is removed Shannonbridge Somerset can be switched back in for the 39 days until CB replaced and energised
TO-20-SOM,T-SOM-1-02 Status: Unscheduled
CAPX |  |  | CP1032 | DO | 1 |  | EI: Simultaneous CSH-SH-SOM-1 + SOM,T-CSH-1: Remake line dropper and EI CB
TO-20-SOM,T-SOM-1-03 ISO week: 28mo - 28fr Date: 06 Jul - 10 Jul Duration: 5 Days (5 WD) Status: Scheduled
Full tee outage for work on Cashla-tee-Somerset and Shannonbridge-tee-Somerset
DISTRIBUTION TRANSFORMER - THORNSBERRY T141 [NDCC]
TO-20-TSB-T141-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
DISTRIBUTION TRANSFORMER - THORNSBERRY T142 [NDCC]
TO-20-TSB-T142-01 Status: Reference (Unscheduled)
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of DER-TSB-1: 110 kV A2 @ DER: Proximity outage for work on Derryiron 110kV Sect / Dist Ordinary Service (SA2)
SECTIONALISING DISCONNECT - TYNAGH 220SA1
TO-20-TY-220SA1-02 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA2: 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
TO-20-TY-220SA1-01 ISO week: 14mo - 14tu Date: 30 Mar - 31 Mar Duration: 2 Days (2 WD) Status: Planned
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
OS | TYN | 220-SA1 | 901039728 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
SECTIONALISING DISCONNECT - TYNAGH 220SA2
TO-20-TY-220SA2-01 Status: Unscheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
OS | TYN | 220-SA2 | 901039729 | DO | 2 | 4 | 220kV Sect / Dist Ordinary Service
TO-20-TY-220SA2-02 Status: Unscheduled
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A2 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA2)
PROX |  |  | PR0003 | DO | 2 |  | As a consequence of TY-220SA1: 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
GENERATOR TRANSFORMER - TYNAGH T2001/2 [Tynagh Energy TYC]
TO-20-TY-T2001/2-01 ISO week: 14mo - 14tu Date: 30 Mar - 31 Mar Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  | - |  |  | 2 |  | Total Maintenance Outage Duration Requested
PROX |  |  | PR0003 | DO | 2 |  | 220 kV A1 @ TY: Proximity outage for work on Tynagh 220kV Sect / Dist Ordinary Service (SA1)
CORRECT | TYN |  | 900990025 | CLO | 2 | 1 | Hot spot detected on T 2001/2 220kV R phase DA
OPT | TYN |  | 901129555 | CLO | 1 | 4 | 220kV SF6 Cubicle Operational Test