## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 95 | 65 | 65 | Scheduled | 08/02/2021 | 13/05/2021
TO-21-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 22/02/2021 | 05/03/2021
TO-21-220 kV A1 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 16 | 12 | 12 | Scheduled | 22/02/2021 | 09/03/2021
TO-21-220 kV B1 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 16 | 12 |  | Scheduled | 22/02/2021 | 09/03/2021
TO-21-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 16 | 12 | 12 | Scheduled | 22/02/2021 | 09/03/2021
TO-21-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 103 | 71 |  | Scheduled | 22/02/2021 | 04/06/2021
TO-21-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 131 | 90 |  | Scheduled | 22/02/2021 | 02/07/2021
TO-21-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 3 | 3 |  | Scheduled | 22/02/2021 | 24/02/2021
TO-21-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 59 | 40 |  | Scheduled | 22/02/2021 | 21/04/2021
TO-21-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 22/02/2021 | 24/02/2021
TO-21-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 3 | 3 | 3 | Scheduled | 22/02/2021 | 24/02/2021
TO-21-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 3 | 3 |  | Reference | 22/02/2021 | 24/02/2021
TO-21-220 kV A1/A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1-A2 | 74 | 50 |  | Scheduled | 22/02/2021 | 06/05/2021
TO-21-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 277 | 192 | 192 | Scheduled | 22/02/2021 | 25/11/2021
TO-21-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 116 | 79 | 79 | Scheduled | 22/02/2021 | 17/06/2021
TO-21-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 14 | 10 | 10 | Scheduled | 23/02/2021 | 08/03/2021
TO-21-AD-T2001-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G1-T2001 | 3 | 3 | 3 | Scheduled | 24/02/2021 | 26/02/2021
TO-21-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 3 | 3 | 3 | Scheduled | 24/02/2021 | 26/02/2021
TO-21-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 7 | 5 | 5 | Scheduled | 24/02/2021 | 02/03/2021
TO-21-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 2 | 2 | 2 | Scheduled | 24/02/2021 | 25/02/2021
TO-21-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 1 | 1 |  | Scheduled | 24/02/2021 | 24/02/2021
TO-21-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 2 | 2 | 2 | Scheduled | 25/02/2021 | 26/02/2021
TO-21-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 1 | 1 | 1 | Scheduled | 26/02/2021 | 26/02/2021
TO-21-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 14 | 10 | 10 | Scheduled | 26/02/2021 | 11/03/2021
TO-21-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 01/03/2021 | 01/03/2021
TO-21-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 | 5 |  | Reference | 01/03/2021 | 05/03/2021
TO-21-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 12 | 10 | 10 | Scheduled | 01/03/2021 | 12/03/2021
TO-21-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 241 | 166 |  | Scheduled | 01/03/2021 | 27/10/2021
TO-21-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 263 | 182 | 182 | Scheduled | 01/03/2021 | 18/11/2021
TO-21-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 2 | 2 |  | Scheduled | 01/03/2021 | 02/03/2021
TO-21-220 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 2 | 2 |  | Scheduled | 01/03/2021 | 02/03/2021
TO-21-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-AD-ST101-06 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-AD-T2102-04 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-AD-WHI-1-07 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 02/03/2021 | 02/03/2021
TO-21-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 7 | 5 | 5 | Scheduled | 02/03/2021 | 08/03/2021
TO-21-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 42 | 27 | 27 | Scheduled | 02/03/2021 | 12/04/2021
TO-21-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 14 | 10 | 10 | Scheduled | 02/03/2021 | 15/03/2021
TO-21-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 7 | 5 | 5 | Scheduled | 03/03/2021 | 09/03/2021
TO-21-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | 1 | 1 | 1 | Scheduled | 03/03/2021 | 03/03/2021
TO-21-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 2 | 2 |  | Scheduled | 03/03/2021 | 04/03/2021
TO-21-220 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 2 | 2 |  | Scheduled | 03/03/2021 | 04/03/2021
TO-21-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 59 | 40 |  | Scheduled | 03/03/2021 | 30/04/2021
TO-21-MLN-T123-05 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 35 | 22 | 22 | Scheduled | 06/03/2021 | 09/04/2021
TO-21-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 2 | 2 | 2 | Scheduled | 08/03/2021 | 09/03/2021
TO-21-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 08/03/2021 | 12/03/2021
TO-21-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 17 | 12 | 12 | Scheduled | 09/03/2021 | 25/03/2021
TO-21-KNR-T2102-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 3 | 3 | 3 | Scheduled | 09/03/2021 | 11/03/2021
TO-21-BVK-COT-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-110 kV A1/A2 @ COT-01 | BUSBAR SECTION - COOMATAGGART 110-COOMATAGGART 110-110A1-A2 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-110SA1-02 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-110SA2-02 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-T141-02 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 2 | 2 | 2 | Reference | 10/03/2021 | 11/03/2021
TO-21-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 16 | 11 | 11 | Scheduled | 11/03/2021 | 26/03/2021
TO-21-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 13 | 8 | 8 | Scheduled | 12/03/2021 | 24/03/2021
TO-21-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 62 | 40 | 40 | Scheduled | 12/03/2021 | 12/05/2021
TO-21-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 15/03/2021 | 15/03/2021
TO-21-220 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 3 | 3 | Scheduled | 15/03/2021 | 18/03/2021
TO-21-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 9 | 6 |  | Scheduled | 15/03/2021 | 23/03/2021
TO-21-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 5 | 4 | 4 | Scheduled | 15/03/2021 | 19/03/2021
TO-21-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 15/03/2021 | 16/03/2021
TO-21-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 16/03/2021 | 16/03/2021
TO-21-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 4 | 3 |  | Scheduled | 16/03/2021 | 19/03/2021
TO-21-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Scheduled | 18/03/2021 | 18/03/2021
TO-21-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 132 | 90 | 90 | Scheduled | 18/03/2021 | 27/07/2021
TO-21-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 7 | 5 | 5 | Scheduled | 18/03/2021 | 24/03/2021
TO-21-KRA-MID-1-02 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 18 | 12 | 12 | Scheduled | 22/03/2021 | 08/04/2021
TO-21-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 18 | 12 | 12 | Scheduled | 22/03/2021 | 08/04/2021
TO-21-CBR-SVC-03 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 43 | 28 | 28 | Scheduled | 23/03/2021 | 04/05/2021
TO-21-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Tentative | 23/03/2021 | 24/03/2021
TO-21-BYH-KNR-1-04 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 44 | 29 | 29 | Scheduled | 25/03/2021 | 07/05/2021
TO-21-220 kV B2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 5 |  | Scheduled | 25/03/2021 | 31/03/2021
TO-21-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 5 | 5 | Scheduled | 25/03/2021 | 31/03/2021
TO-21-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Scheduled | 26/03/2021 | 26/03/2021
TO-21-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 2 | 2 | 2 | Reference | 30/03/2021 | 31/03/2021
TO-21-LOU-AT3-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | 2 | Scheduled | 31/03/2021 | 01/04/2021
TO-21-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV A2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV B2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 25 | 19 | 19 | Scheduled | 06/04/2021 | 30/04/2021
TO-21-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 14 | 10 | 10 | Scheduled | 06/04/2021 | 19/04/2021
TO-21-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-PRO-1-02 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | 3 | 3 | 3 | Reference | 07/04/2021 | 09/04/2021
TO-21-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 1 | 1 | 1 | Scheduled | 07/04/2021 | 07/04/2021
TO-21-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 16 | 12 | 12 | Scheduled | 08/04/2021 | 23/04/2021
TO-21-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 8 | 6 | 6 | Scheduled | 12/04/2021 | 19/04/2021
TO-21-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-KRA-RAF-1-04 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 26 | 19 |  | Scheduled | 12/04/2021 | 07/05/2021
TO-21-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 26 | 19 | 19 | Scheduled | 12/04/2021 | 07/05/2021
TO-21-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/04/2021 | 14/04/2021
TO-21-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-TAW-T1/T2-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 1 | 1 | 1 | Scheduled | 12/04/2021 | 12/04/2021
TO-21-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 1 | 1 | 1 | Scheduled | 12/04/2021 | 12/04/2021
TO-21-TAW-T3-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 7 | 5 | 5 | Scheduled | 13/04/2021 | 19/04/2021
TO-21-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 1 | 1 | 1 | Scheduled | 14/04/2021 | 14/04/2021
TO-21-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 14 | 10 | 10 | Scheduled | 14/04/2021 | 27/04/2021
TO-21-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 22 | 15 | 15 | Reference | 14/04/2021 | 05/05/2021
TO-21-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 14 | 10 | 10 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 15/04/2021 | 15/04/2021
TO-21-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 14 | 10 | 10 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 14 | 10 | 3 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 15 | 11 | 11 | Scheduled | 15/04/2021 | 29/04/2021
TO-21-CCG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 9 | 7 | 7 | Scheduled | 19/04/2021 | 27/04/2021
TO-21-110 kV A1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-110 kV B1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 |  | Scheduled | 19/04/2021 | 23/04/2021
TO-21-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 8 | 6 | 6 | Scheduled | 20/04/2021 | 27/04/2021
TO-21-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 8 | 6 | 6 | Scheduled | 20/04/2021 | 27/04/2021
TO-21-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 2 | 2 | 2 | Reference | 20/04/2021 | 21/04/2021
TO-21-CUL-WAT-1-03 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 1 | 1 | 1 | Scheduled | 21/04/2021 | 21/04/2021
TO-21-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 7 | 5 | 5 | Scheduled | 21/04/2021 | 27/04/2021
TO-21-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 7 | 5 |  | Scheduled | 21/04/2021 | 27/04/2021
TO-21-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 7 | 5 |  | Scheduled | 21/04/2021 | 27/04/2021
TO-21-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 9 | 6 | 6 | Scheduled | 26/04/2021 | 04/05/2021
TO-21-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 19 | 14 | 13 | Scheduled | 26/04/2021 | 14/05/2021
TO-21-ISH-T2001-02 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 19 | 14 | 14 | Scheduled | 26/04/2021 | 14/05/2021
TO-21-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 5 | 5 | 5 | Tentative | 26/04/2021 | 30/04/2021
TO-21-GLE-KCR-1-02 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 2 | 2 | 2 | Scheduled | 27/04/2021 | 28/04/2021
TO-21-KCR-T121-02 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 2 | 2 | 2 | Scheduled | 27/04/2021 | 28/04/2021
TO-21-110 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 2 | 2 | 2 | Tentative | 27/04/2021 | 28/04/2021
TO-21-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 2 | 2 | 2 | Tentative | 27/04/2021 | 28/04/2021
TO-21-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 8 | 6 |  | Scheduled | 04/05/2021 | 11/05/2021
TO-21-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 8 | 6 |  | Scheduled | 04/05/2021 | 11/05/2021
TO-21-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-220 kV A1 @ ISH-02 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 1 | 1 | 1 | Scheduled | 04/05/2021 | 04/05/2021
TO-21-220 kV B1 @ ISH-02 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 1 | 1 | 1 | Scheduled | 04/05/2021 | 04/05/2021
TO-21-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 7 | 5 | 5 | Reference | 04/05/2021 | 10/05/2021
TO-21-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-MAC-110SA1-05 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 14 | 10 | 10 | Scheduled | 04/05/2021 | 17/05/2021
TO-21-CD-T103-03 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 10 | 8 | 8 | Scheduled | 05/05/2021 | 14/05/2021
TO-21-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 7 | 5 | 5 | Reference | 05/05/2021 | 11/05/2021
TO-21-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 3 | 3 | 5 | Scheduled | 05/05/2021 | 07/05/2021
TO-21-GGO-T2001-04 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Tentative | 05/05/2021 | 06/05/2021
TO-21-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 05/05/2021 | 06/05/2021
TO-21-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 16 | 12 | 12 | Scheduled | 06/05/2021 | 21/05/2021
TO-21-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 13 | 9 |  | Scheduled | 07/05/2021 | 19/05/2021
TO-21-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 8 | 6 | 6 | Scheduled | 07/05/2021 | 14/05/2021
TO-21-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 8 | 6 | 6 | Scheduled | 07/05/2021 | 14/05/2021
TO-21-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 1 | 1 | 1 | Scheduled | 07/05/2021 | 07/05/2021
TO-21-GGO-T2001-03 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 22 | 16 | 16 | Scheduled | 07/05/2021 | 28/05/2021
TO-21-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 10/05/2021 | 14/05/2021
TO-21-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 15 | 11 | 11 | Scheduled | 10/05/2021 | 24/05/2021
TO-21-110 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 5 | 5 | 5 | Scheduled | 10/05/2021 | 14/05/2021
TO-21-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 1 | 1 | 1 | Scheduled | 11/05/2021 | 11/05/2021
TO-21-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 1 | 1 | 1 | Scheduled | 11/05/2021 | 11/05/2021
TO-21-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-110SA1-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-110SA2-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 7 | 5 | 5 | Reference | 11/05/2021 | 17/05/2021
TO-21-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-110SA1-03 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-110SA2-03 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-T124-04 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 36 | 25 | 25 | Scheduled | 11/05/2021 | 15/06/2021
TO-21-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 2 | 2 |  | Scheduled | 12/05/2021 | 13/05/2021
TO-21-ARK-T2101-02 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 1 | 1 | 1 | Scheduled | 13/05/2021 | 13/05/2021
TO-21-FIN-220K1-2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 19 | 13 | 13 | Scheduled | 14/05/2021 | 01/06/2021
TO-21-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 14 | 10 | 10 | Scheduled | 14/05/2021 | 27/05/2021
TO-21-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 6 | 4 | 4 | Scheduled | 14/05/2021 | 19/05/2021
TO-21-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 4 | 4 | 4 | Scheduled | 17/05/2021 | 20/05/2021
TO-21-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 17/05/2021 | 21/05/2021
TO-21-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 4 | 4 | 4 | Scheduled | 17/05/2021 | 20/05/2021
TO-21-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | 10 | Scheduled | 17/05/2021 | 28/05/2021
TO-21-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 10 | 8 | 8 | Scheduled | 17/05/2021 | 26/05/2021
TO-21-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 5 | 5 | 5 | Scheduled | 17/05/2021 | 21/05/2021
TO-21-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Tentative | 18/05/2021 | 18/05/2021
TO-21-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 5 | 5 | Scheduled | 18/05/2021 | 24/05/2021
TO-21-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 19/05/2021 | 21/05/2021
TO-21-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 3 | 3 | 3 | Scheduled | 19/05/2021 | 21/05/2021
TO-21-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2021 | 25/05/2021
TO-21-AA GIS-LIM-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 24/05/2021 | 28/05/2021
TO-21-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 24/05/2021 | 26/05/2021
TO-21-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 24/05/2021 | 26/05/2021
TO-21-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 14 | 14 | Scheduled | 24/05/2021 | 11/06/2021
TO-21-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 24/05/2021 | 26/05/2021
TO-21-CF-CLO-1-05 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-CLO-MRY-1-02 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 50 | 35 | 35 | Scheduled | 24/05/2021 | 12/07/2021
TO-21-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 5 | 5 |  | Scheduled | 24/05/2021 | 28/05/2021
TO-21-MRY-T131-02 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 5 | 5 | 5 | Scheduled | 24/05/2021 | 28/05/2021
TO-21-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 43 | 30 | 30 | Scheduled | 25/05/2021 | 06/07/2021
TO-21-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 29 | 20 | 20 | Scheduled | 25/05/2021 | 22/06/2021
TO-21-110 kV A1 @ CLO-03 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 6 | 4 | 4 | Scheduled | 26/05/2021 | 31/05/2021
TO-21-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 2 | 2 | 2 | Scheduled | 27/05/2021 | 28/05/2021
TO-21-AA GIS-T103-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 4 | 4 | 4 | Scheduled | 31/05/2021 | 03/06/2021
TO-21-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 26 | 19 | 19 | Scheduled | 31/05/2021 | 25/06/2021
TO-21-220 kV A1/A2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220A1-A2 | 2 | 2 | 2 | Scheduled | 31/05/2021 | 01/06/2021
TO-21-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/05/2021 | 01/06/2021
TO-21-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 3 | 3 | 3 | Scheduled | 31/05/2021 | 02/06/2021
TO-21-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 4 | 4 | 4 | Scheduled | 31/05/2021 | 03/06/2021
TO-21-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-220 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-220 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 29 | 20 | 20 | Scheduled | 31/05/2021 | 28/06/2021
TO-21-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 5 | 5 | 5 | Scheduled | 31/05/2021 | 04/06/2021
TO-21-GOL-T101-04 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Scheduled | 01/06/2021 | 01/06/2021
TO-21-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 1 | 1 | 3 | Scheduled | 01/06/2021 | 01/06/2021
TO-21-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 02/06/2021 | 03/06/2021
TO-21-220 kV A1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 3 | 3 | 3 | Scheduled | 02/06/2021 | 04/06/2021
TO-21-ARV-NAV-1-02 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 2 | 2 | 3 | Scheduled | 03/06/2021 | 04/06/2021
TO-21-AA GIS-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 8 | 6 | 6 | Scheduled | 08/06/2021 | 15/06/2021
TO-21-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 7 | 5 | 5 | Scheduled | 08/06/2021 | 14/06/2021
TO-21-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 4 | 4 | 5 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 4 | 4 | 5 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-FIN-220K1-2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 207 | 145 | 145 | Scheduled | 08/06/2021 | 31/12/2021
TO-21-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 80 | 57 | 57 | Scheduled | 08/06/2021 | 26/08/2021
TO-21-KPG-KNR-1-220-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-220 kV A1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-220 kV B1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 165 | 117 | 117 | Reference | 08/06/2021 | 19/11/2021
TO-21-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-ARV-SKL-2-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 27 | 19 | 19 | Scheduled | 09/06/2021 | 05/07/2021
TO-21-BAR-T141-05 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 09/06/2021 | 11/06/2021
TO-21-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-T101-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 7 | 5 | 5 | Reference | 09/06/2021 | 15/06/2021
TO-21-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 7 | 5 | 5 | Reference | 09/06/2021 | 15/06/2021
TO-21-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 8 | 6 | 6 | Scheduled | 09/06/2021 | 16/06/2021
TO-21-RRU-SKL-1-06 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-SKL-110SA1-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-SKL-T141-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 3 | 3 | 3 | Reference | 09/06/2021 | 11/06/2021
TO-21-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 14/06/2021 | 25/06/2021
TO-21-CF-T103-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 19 | 15 | 15 | Scheduled | 14/06/2021 | 02/07/2021
TO-21-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-220 kV A1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-220 kV B1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 1 | 1 | 3 | Scheduled | 14/06/2021 | 14/06/2021
TO-21-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 3 | 3 | 3 | Scheduled | 14/06/2021 | 16/06/2021
TO-21-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV A2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 4 | 4 | 4 | Reference (Tentative) | 15/06/2021 | 18/06/2021
TO-21-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-220 kV B1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 154 | 108 | 108 | Scheduled | 15/06/2021 | 15/11/2021
TO-21-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | 4 | 4 | 4 | Reference (Tentative) | 15/06/2021 | 18/06/2021
TO-21-220 kV B1/B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1-B2 | 2 | 2 | 2 | Scheduled | 16/06/2021 | 17/06/2021
TO-21-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 1 | 1 | 1 | Scheduled | 17/06/2021 | 17/06/2021
TO-21-220 kV A1/A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 4 | 2 | 2 | Scheduled | 18/06/2021 | 21/06/2021
TO-21-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 19 | 15 | 15 | Scheduled | 21/06/2021 | 09/07/2021
TO-21-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Scheduled | 21/06/2021 | 25/06/2021
TO-21-220 kV A1/A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 2 | 2 | 2 | Scheduled | 21/06/2021 | 22/06/2021
TO-21-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 21/06/2021 | 25/06/2021
TO-21-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 14 | 10 | 10 | Scheduled | 22/06/2021 | 05/07/2021
TO-21-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-DSN-MAY-1-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-220 kV B1/B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1-B2 | 75 | 53 |  | Scheduled | 22/06/2021 | 04/09/2021
TO-21-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 4 | 4 | 4 | Reference | 22/06/2021 | 25/06/2021
TO-21-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 23/06/2021 | 23/06/2021
TO-21-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | 7 | 5 | 5 | Scheduled | 23/06/2021 | 29/06/2021
TO-21-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 1 | 1 | 1 | Scheduled | 24/06/2021 | 24/06/2021
TO-21-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 24/06/2021 | 24/06/2021
TO-21-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-110 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 19 | 15 | 15 | Scheduled | 28/06/2021 | 16/07/2021
TO-21-110 kV A1/A2/A4 @ LSN-01 | BUSBAR SECTION - LISHEEN 110-LISHEEN 110-110A1-A2-A4 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | 10 | Reference | 28/06/2021 | 09/07/2021
TO-21-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 14 | 10 | 10 | Scheduled | 29/06/2021 | 12/07/2021
TO-21-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 2 | 2 |  | Scheduled | 29/06/2021 | 30/06/2021
TO-21-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 2 | 2 |  | Scheduled | 29/06/2021 | 30/06/2021
TO-21-KBY-T101-01 | DISTRIBUTION TRANSFORMER - KILBARRY 110-KILBARRY 10-T101 | 2 | 2 | 2 | Reference | 29/06/2021 | 30/06/2021
TO-21-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 1 | 1 | 1 | Scheduled | 30/06/2021 | 30/06/2021
TO-21-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 16 | 12 | 12 | Scheduled | 01/07/2021 | 16/07/2021
TO-21-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 9 | 7 | 7 | Scheduled | 01/07/2021 | 09/07/2021
TO-21-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 6 | 4 | 4 | Scheduled | 01/07/2021 | 06/07/2021
TO-21-CRA-WEX-1-06 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 1 | 1 |  | Scheduled | 02/07/2021 | 02/07/2021
TO-21-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 10 | 8 | 8 | Reference | 05/07/2021 | 14/07/2021
TO-21-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 05/07/2021 | 09/07/2021
TO-21-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 5 | 5 | 5 | Reference | 05/07/2021 | 09/07/2021
TO-21-GGO-T2001-05 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-DER-MAY-1-04 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-220 kV A4 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A4 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-220 kV B4 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B4 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 18 | 14 | 14 | Scheduled | 06/07/2021 | 23/07/2021
TO-21-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 9 | 7 | 7 | Reference | 07/07/2021 | 15/07/2021
TO-21-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 08/07/2021 | 09/07/2021
TO-21-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 08/07/2021 | 08/07/2021
TO-21-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 1 | 1 | 1 | Scheduled | 08/07/2021 | 08/07/2021
TO-21-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 |  | Scheduled | 12/07/2021 | 16/07/2021
TO-21-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-BDN-MRK1-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Scheduled | 12/07/2021 | 19/07/2021
TO-21-BLI-DMY-1-01 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | 9 | 7 | 7 | Reference | 12/07/2021 | 20/07/2021
TO-21-BLI-T142-01 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | 9 | 7 | 7 | Reference | 12/07/2021 | 20/07/2021
TO-21-CCG-DMY-1-02 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CCG-T131-03 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CCG-T131-02 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 5 | 5 | 5 | Reference | 12/07/2021 | 16/07/2021
TO-21-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-KTL-MON-1-02 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 9 | 7 |  | Scheduled | 12/07/2021 | 20/07/2021
TO-21-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 13/07/2021 | 14/07/2021
TO-21-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 2 | 2 | 2 | Scheduled | 14/07/2021 | 15/07/2021
TO-21-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 7 | 5 | 5 | Reference | 15/07/2021 | 21/07/2021
TO-21-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 15/07/2021 | 16/07/2021
TO-21-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 2 | 2 | 2 | Scheduled | 15/07/2021 | 16/07/2021
TO-21-CHA-T141-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | 2 | 2 | 2 | Reference | 15/07/2021 | 16/07/2021
TO-21-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 19/07/2021 | 23/07/2021
TO-21-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 12 | 10 | 10 | Scheduled | 19/07/2021 | 30/07/2021
TO-21-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 3 | 3 | 3 | Tentative | 19/07/2021 | 21/07/2021
TO-21-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 5 | 5 | 5 | Scheduled | 19/07/2021 | 23/07/2021
TO-21-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 9 | 7 | 7 | Scheduled | 20/07/2021 | 28/07/2021
TO-21-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 4 | 4 | 4 | Scheduled | 20/07/2021 | 23/07/2021
TO-21-GAL-KNY-1-03 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 9 | 7 | 7 | Scheduled | 20/07/2021 | 28/07/2021
TO-21-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 3 | 3 | 3 | Reference | 21/07/2021 | 23/07/2021
TO-21-GRI,T-GCA-1-04 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-GRI,T-MAY-1-02 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 58 | 41 | 41 | Reference | 22/07/2021 | 17/09/2021
TO-21-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | 1 | Scheduled | 22/07/2021 | 22/07/2021
TO-21-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 12 | 9 | 9 | Scheduled | 26/07/2021 | 06/08/2021
TO-21-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 3 | 3 | 3 | Scheduled | 26/07/2021 | 28/07/2021
TO-21-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 3 | 3 | 3 | Reference (Tentative) | 26/07/2021 | 28/07/2021
TO-21-FLA-GIL-1-02 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 26/07/2021 | 30/07/2021
TO-21-GIL-T121-02 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 26/07/2021 | 30/07/2021
TO-21-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 2 | 2 | 2 | Scheduled | 26/07/2021 | 27/07/2021
TO-21-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 3 | 3 | 3 | Scheduled | 26/07/2021 | 28/07/2021
TO-21-BEG-CKM GIS-1-05 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Scheduled | 27/07/2021 | 30/07/2021
TO-21-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 27/07/2021 | 27/07/2021
TO-21-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference | 27/07/2021 | 28/07/2021
TO-21-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 7 | 4 | 4 | Scheduled | 29/07/2021 | 04/08/2021
TO-21-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 7 | 4 | 4 | Scheduled | 29/07/2021 | 04/08/2021
TO-21-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | 8 | 5 | 2 | Scheduled | 29/07/2021 | 05/08/2021
TO-21-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 8 | 5 | 6 | Scheduled | 29/07/2021 | 05/08/2021
TO-21-TIP-T141-01 | DISTRIBUTION TRANSFORMER - TIPPERARY 110-TIPPERARY 38-T141 | 2 | 2 | 2 | Reference | 29/07/2021 | 30/07/2021
TO-21-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 16 | 11 | 10 | Scheduled | 29/07/2021 | 13/08/2021
TO-21-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | 8 | 5 | 2 | Reference | 29/07/2021 | 05/08/2021
TO-21-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | 8 | 5 | 3 | Reference | 29/07/2021 | 05/08/2021
TO-21-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 11 | 9 | 4 | Scheduled | 03/08/2021 | 13/08/2021
TO-21-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 | 4 | Scheduled | 03/08/2021 | 06/08/2021
TO-21-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 9 | 7 | 7 | Scheduled | 03/08/2021 | 11/08/2021
TO-21-MLN-T124-05 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 03/08/2021 | 04/08/2021
TO-21-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 2 | 2 | 2 | Scheduled | 04/08/2021 | 05/08/2021
TO-21-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 2 | 2 | 2 | Scheduled | 04/08/2021 | 05/08/2021
TO-21-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 3 | 3 | 3 | Scheduled | 04/08/2021 | 06/08/2021
TO-21-MLN-T123-06 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 05/08/2021 | 06/08/2021
TO-21-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | 8 | 6 | 6 | Scheduled | 06/08/2021 | 13/08/2021
TO-21-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 8 | 6 | 5 | Scheduled | 06/08/2021 | 13/08/2021
TO-21-TBG-T102-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T102 | 8 | 6 | 2 | Reference | 06/08/2021 | 13/08/2021
TO-21-TBG-T142-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T142 | 8 | 6 | 2 | Reference | 06/08/2021 | 13/08/2021
TO-21-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 54 | 40 | 40 | Scheduled | 09/08/2021 | 01/10/2021
TO-21-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 5 | 5 | 5 | Scheduled | 09/08/2021 | 13/08/2021
TO-21-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 19 | 15 | 15 | Scheduled | 09/08/2021 | 27/08/2021
TO-21-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 5 | 5 | 5 | Tentative | 09/08/2021 | 13/08/2021
TO-21-CUN-110SA1-02 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-CUN-110SA2-02 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 8 | 6 | 6 | Scheduled | 09/08/2021 | 16/08/2021
TO-21-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-KPG-TB-2-05 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 5 | 5 | 5 | Tentative | 09/08/2021 | 13/08/2021
TO-21-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-SLI-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-SLI-SRA-2-04 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 4 | 4 | 4 | Reference | 09/08/2021 | 12/08/2021
TO-21-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-TB-T2003-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 3 | 3 | 3 | Scheduled | 09/08/2021 | 11/08/2021
TO-21-TB-T2102-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-CNO-KPG-1-02 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-CNO-T131-02 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 12/08/2021 | 13/08/2021
TO-21-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 9 | 7 | 7 | Scheduled | 12/08/2021 | 20/08/2021
TO-21-CSH-GAL-1-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 48 | 34 | 34 | Scheduled | 12/08/2021 | 28/09/2021
TO-21-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 96 | 67 | 67 | Scheduled | 12/08/2021 | 15/11/2021
TO-21-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 13/08/2021 | 13/08/2021
TO-21-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 117 | 84 | 64 | Reference | 16/08/2021 | 10/12/2021
TO-21-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 | 5 | Tentative | 16/08/2021 | 20/08/2021
TO-21-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 16/08/2021 | 20/08/2021
TO-21-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 46 | 34 |  | Scheduled | 17/08/2021 | 01/10/2021
TO-21-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 4 | 4 | 4 | Reference | 17/08/2021 | 20/08/2021
TO-21-110 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-110 kV B1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 1 | 1 | 1 | Scheduled | 19/08/2021 | 19/08/2021
TO-21-220 kV A1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 7 | 5 | 5 | Scheduled | 20/08/2021 | 26/08/2021
TO-21-220 kV B1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 7 | 5 | 5 | Scheduled | 20/08/2021 | 26/08/2021
TO-21-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 3 | 3 | 3 | Scheduled | 23/08/2021 | 25/08/2021
TO-21-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 25 | 19 | 19 | Scheduled | 23/08/2021 | 16/09/2021
TO-21-DMY-MAC-1-02 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-220 kV A1 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV A2 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV B1 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV B2 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 |  | Scheduled | 23/08/2021 | 27/08/2021
TO-21-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-CAP1-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 11 | 9 | 9 | Reference | 23/08/2021 | 02/09/2021
TO-21-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 3 | 3 | Scheduled | 23/08/2021 | 25/08/2021
TO-21-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Scheduled | 24/08/2021 | 27/08/2021
TO-21-CKM GIS-DSN-1-04 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 1 | 1 | 1 | Scheduled | 30/08/2021 | 30/08/2021
TO-21-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 4 | 4 | 4 | Scheduled | 30/08/2021 | 02/09/2021
TO-21-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 4 | 4 | 4 | Scheduled | 30/08/2021 | 02/09/2021
TO-21-CVW-KRA-1-04 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-CVW-T102-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T102 | 3 | 3 | 2 | Reference | 30/08/2021 | 01/09/2021
TO-21-SHL-D1/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-SHL-D1/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-SHL-T2014-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-BDA-T102-03 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 31/08/2021 | 02/09/2021
TO-21-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 111 | 78 | 78 | Scheduled | 01/09/2021 | 20/12/2021
TO-21-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 6 | 4 | 4 | Scheduled | 01/09/2021 | 06/09/2021
TO-21-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 03/09/2021 | 03/09/2021
TO-21-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 1 | 0 | 0 | Tentative | 04/09/2021 | 04/09/2021
TO-21-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/09/2021 | 13/09/2021
TO-21-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | 3 | Scheduled | 06/09/2021 | 08/09/2021
TO-21-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 19 | 15 | 15 | Scheduled | 06/09/2021 | 24/09/2021
TO-21-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 |  | Scheduled | 06/09/2021 | 08/09/2021
TO-21-COS-FLA-1-02 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 3 | 3 |  | Scheduled | 06/09/2021 | 08/09/2021
TO-21-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 |  | Reference | 06/09/2021 | 08/09/2021
TO-21-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 5 |  | Scheduled | 06/09/2021 | 10/09/2021
TO-21-KNR-TRI-2-03 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-PB-TF4-03 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 12 | 10 | 10 | Reference | 06/09/2021 | 17/09/2021
TO-21-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | 4 | 4 | 4 | Reference | 07/09/2021 | 10/09/2021
TO-21-DGN-WOH-1-05 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Scheduled | 08/09/2021 | 08/09/2021
TO-21-BEG-110SA1-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/09/2021 | 10/09/2021
TO-21-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/09/2021 | 10/09/2021
TO-21-BEG-T102-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T102 | 2 | 2 | 2 | Reference | 09/09/2021 | 10/09/2021
TO-21-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 7 | 5 |  | Scheduled | 09/09/2021 | 15/09/2021
TO-21-AUG-CFM-1-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Tentative | 13/09/2021 | 17/09/2021
TO-21-BK-SKY-1-02 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-220 kV A2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference (Tentative) | 13/09/2021 | 17/09/2021
TO-21-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 11 | 9 | 9 | Scheduled | 13/09/2021 | 23/09/2021
TO-21-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-220 kV A1 @ ISH-04 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-220 kV B1 @ ISH-04 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 13/09/2021 | 14/09/2021
TO-21-SKY-110SA1-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-110SA2-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 13/09/2021 | 14/09/2021
TO-21-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 10 | 8 | 8 | Scheduled | 14/09/2021 | 23/09/2021
TO-21-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 4 | 4 | 4 | Scheduled | 14/09/2021 | 17/09/2021
TO-21-CLE-T222-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 1 | 1 | 1 | Trip Testing | 15/09/2021 | 15/09/2021
TO-21-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 2 | 2 | 2 | Scheduled | 15/09/2021 | 16/09/2021
TO-21-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 6 | 4 | 4 | Scheduled | 15/09/2021 | 20/09/2021
TO-21-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 6 | 4 | 4 | Scheduled | 16/09/2021 | 21/09/2021
TO-21-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/09/2021 | 21/09/2021
TO-21-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 2 | 2 |  | Scheduled | 20/09/2021 | 21/09/2021
TO-21-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 20/09/2021 | 21/09/2021
TO-21-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 3 | 3 | 3 | Scheduled | 20/09/2021 | 22/09/2021
TO-21-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 1 | 1 |  | Scheduled | 20/09/2021 | 20/09/2021
TO-21-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 10 | 8 | 8 | Scheduled | 21/09/2021 | 30/09/2021
TO-21-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/09/2021 | 22/09/2021
TO-21-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/09/2021 | 22/09/2021
TO-21-DOO-T142-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 2 | 2 | 2 | Reference | 21/09/2021 | 22/09/2021
TO-21-MCE-T121-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 3 | 3 | 3 | Scheduled | 22/09/2021 | 24/09/2021
TO-21-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 14 | 10 |  | Scheduled | 24/09/2021 | 07/10/2021
TO-21-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 14 | 10 |  | Scheduled | 24/09/2021 | 07/10/2021
TO-21-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 14 | 10 | 10 | Scheduled | 24/09/2021 | 07/10/2021
TO-21-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 14 | 10 | 10 | Scheduled | 24/09/2021 | 07/10/2021
TO-21-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-SH-1-04 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Tentative | 27/09/2021 | 01/10/2021
TO-21-CD-MAC-1-05 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 31 | 22 | 22 | Scheduled | 27/09/2021 | 27/10/2021
TO-21-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference (Tentative) | 27/09/2021 | 01/10/2021
TO-21-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 31 | 22 | 22 | Scheduled | 27/09/2021 | 27/10/2021
TO-21-DYN-T121-02 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 2 | 2 | 2 | Reference (Tentative) | 27/09/2021 | 28/09/2021
TO-21-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 3 | 3 | 3 | Scheduled | 28/09/2021 | 30/09/2021
TO-21-CVW-KRA-1-03 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 9 | 7 | 7 | Scheduled | 29/09/2021 | 07/10/2021
TO-21-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 3 | 3 | 3 | Scheduled | 29/09/2021 | 01/10/2021
TO-21-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 15 | 11 | 7 | Scheduled | 30/09/2021 | 14/10/2021
TO-21-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 04/10/2021 | 06/10/2021
TO-21-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 04/10/2021 | 06/10/2021
TO-21-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 04/10/2021 | 06/10/2021
TO-21-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 17 | 13 | 13 | Scheduled | 04/10/2021 | 20/10/2021
TO-21-CDU-MUL-1-06 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | 15 | Scheduled | 04/10/2021 | 22/10/2021
TO-21-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-ISH-SHL-1-06 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 4 | 4 | 4 | Scheduled | 04/10/2021 | 07/10/2021
TO-21-220 kV A1 @ LWD-01 | BUSBAR SECTION - LODGEWOOD 220-LODGEWOOD 220-220A1 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-220 kV A2 @ LWD-01 | BUSBAR SECTION - LODGEWOOD 220-LODGEWOOD 220-220A2 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-NEW-PLS-1-05 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 2 | 2 | 2 | Scheduled | 04/10/2021 | 05/10/2021
TO-21-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 4 | 4 | 4 | Scheduled | 04/10/2021 | 07/10/2021
TO-21-220 kV A1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV A2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV B2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-D2/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-T2015-04 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 32 | 23 | 23 | Scheduled | 05/10/2021 | 05/11/2021
TO-21-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 50 | 35 | 35 | Scheduled | 08/10/2021 | 26/11/2021
TO-21-BVK-CLA-1-08 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 26 | 19 | 20 | Scheduled | 11/10/2021 | 05/11/2021
TO-21-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-DSN-220K1-2-03 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-GOR-NAV-3-03 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 2 | 2 | 2 | Scheduled | 11/10/2021 | 12/10/2021
TO-21-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 2 | 2 | 2 | Scheduled | 11/10/2021 | 12/10/2021
TO-21-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 8 | 6 | 6 | Scheduled | 11/10/2021 | 18/10/2021
TO-21-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-SHL-D2/CB3-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 1 | 1 | 1 | Scheduled | 12/10/2021 | 12/10/2021
TO-21-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 12/10/2021 | 13/10/2021
TO-21-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-AA GIS-LIM-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 1 | 1 | 1 | Scheduled | 13/10/2021 | 13/10/2021
TO-21-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 8 | 5 | 5 | Scheduled | 18/10/2021 | 25/10/2021
TO-21-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 18/10/2021 | 20/10/2021
TO-21-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 18/10/2021 | 20/10/2021
TO-21-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 18/10/2021 | 20/10/2021
TO-21-CBR-SVC-07 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-CLH-TRI-1-03 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 18/10/2021 | 19/10/2021
TO-21-220 kV A1 @ CDU-06 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV A3 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV B1 @ CDU-06 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV B3 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-DRY-PLA-1-03 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-220 kV A2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-220 kV B1 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-220 kV B2 @ KNR-05 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 4 | 4 |  | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 12 | 9 | 9 | Scheduled | 18/10/2021 | 29/10/2021
TO-21-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 5 | 5 |  | Scheduled | 18/10/2021 | 22/10/2021
TO-21-ARK-BOG-1-03 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 3 | 3 | 3 | Scheduled | 19/10/2021 | 21/10/2021
TO-21-220 kV A1 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV A2 @ MAY-09 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV B1 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV B2 @ MAY-09 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-MAY-220K1-2-03 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 1 | 1 | 1 | Tentative | 20/10/2021 | 20/10/2021
TO-21-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 15 | 10 | 10 | Scheduled | 21/10/2021 | 04/11/2021
TO-21-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 2 | 2 | 2 | Scheduled | 21/10/2021 | 22/10/2021
TO-21-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 1 | 1 |  | Tentative | 22/10/2021 | 22/10/2021
TO-21-AD-KRA-1-12 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 1 | 1 | 1 | Tentative | 26/10/2021 | 26/10/2021
TO-21-BOG-CRA-1-02 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 8 | 6 | 6 | Scheduled | 26/10/2021 | 02/11/2021
TO-21-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/10/2021 | 26/10/2021
TO-21-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 4 | 4 | 4 | Reference | 26/10/2021 | 29/10/2021
TO-21-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-DEY-1-01 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 14 | 10 | 10 | Scheduled | 26/10/2021 | 08/11/2021
TO-21-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 4 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 27/10/2021 | 28/10/2021
TO-21-CBT-INC-1-03 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 3 | 3 | 3 | Scheduled | 27/10/2021 | 29/10/2021
TO-21-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 01/11/2021 | 05/11/2021
TO-21-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Scheduled | 01/11/2021 | 12/11/2021
TO-21-CGL-T122-03 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 1 | 1 | 1 | Scheduled | 02/11/2021 | 02/11/2021
TO-21-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 1 | 1 | 1 | Scheduled | 02/11/2021 | 02/11/2021
TO-21-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 1 | 1 | 1 | Scheduled | 03/11/2021 | 03/11/2021
TO-21-KLN-T2101-04 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 1 | 1 | 1 | Tentative | 03/11/2021 | 03/11/2021
TO-21-CLA-DMY-1-02 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 9 | 7 | 7 | Scheduled | 08/11/2021 | 16/11/2021
TO-21-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-IA-MAC-1-05 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-KPG-MP GIS-2-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 5 | 5 | 5 | Reference | 08/11/2021 | 12/11/2021
TO-21-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Tentative | 08/11/2021 | 12/11/2021
TO-21-SK-T104-06 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Scheduled | 08/11/2021 | 10/11/2021
TO-21-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 5 | 5 | Reference | 08/11/2021 | 12/11/2021
TO-21-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SOM,T-SH-1-06 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-400 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 1 | 1 | 1 | Scheduled | 11/11/2021 | 11/11/2021
TO-21-400 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 1 | 1 | 1 | Scheduled | 11/11/2021 | 11/11/2021
TO-21-AA GIS-DRU-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-FLA-T2102-03 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-KLS-220K1-2-03 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | 2 | Scheduled | 15/11/2021 | 16/11/2021
TO-21-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 1 | 1 | 1 | Scheduled | 15/11/2021 | 15/11/2021
TO-21-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 15/11/2021 | 17/11/2021
TO-21-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 1 | 1 | 1 | Scheduled | 15/11/2021 | 15/11/2021
TO-21-110 kV A3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-110 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-CDU-110K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-220K1-2-05 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-T2004-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 4 | 4 | 4 | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-T2101-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 8 | 6 | 6 | Scheduled | 17/11/2021 | 24/11/2021
TO-21-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-KPG-TB-1-04 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-TB-220K1-2-06 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Tentative | 22/11/2021 | 23/11/2021
TO-21-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 19 | 15 | 15 | Scheduled | 22/11/2021 | 10/12/2021
TO-21-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-CLA-CKN-1-04 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 4 | 4 | 4 | Scheduled | 22/11/2021 | 25/11/2021
TO-21-CLA-T2102-05 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-CLO-DRM-1-03 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-110SA1-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-110SA2-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-LET-1-06 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-DRM-LET-1-08 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-MEE-1-04 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-LET-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-PST-04 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-T141-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 1 | 1 | Reference | 22/11/2021 | 22/11/2021
TO-21-MEE-T121-03 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-220 kV A1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-TB-T2004-04 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV A3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A3 | 5 | 3 | 3 | Scheduled | 26/11/2021 | 30/11/2021
TO-21-110 kV B3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B3 | 5 | 3 | 3 | Scheduled | 26/11/2021 | 30/11/2021

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-220 kV A1 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 16 | 12 | 12 | Scheduled | 22/02/2021 | 09/03/2021
TO-21-220 kV B1 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 16 | 12 |  | Scheduled | 22/02/2021 | 09/03/2021
TO-21-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 16 | 12 | 12 | Scheduled | 22/02/2021 | 09/03/2021
TO-21-220 kV A1/A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1-A2 | 74 | 50 |  | Scheduled | 22/02/2021 | 06/05/2021
TO-21-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 277 | 192 | 192 | Scheduled | 22/02/2021 | 25/11/2021
TO-21-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 2 | 2 | 2 | Scheduled | 25/02/2021 | 26/02/2021
TO-21-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 01/03/2021 | 01/03/2021
TO-21-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 02/03/2021 | 02/03/2021
TO-21-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 7 | 5 | 5 | Scheduled | 03/03/2021 | 09/03/2021
TO-21-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 59 | 40 |  | Scheduled | 03/03/2021 | 30/04/2021
TO-21-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 08/03/2021 | 12/03/2021
TO-21-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 17 | 12 | 12 | Scheduled | 09/03/2021 | 25/03/2021
TO-21-KNR-T2102-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 3 | 3 | 3 | Scheduled | 09/03/2021 | 11/03/2021
TO-21-BVK-COT-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-110 kV A1/A2 @ COT-01 | BUSBAR SECTION - COOMATAGGART 110-COOMATAGGART 110-110A1-A2 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-110SA1-02 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-110SA2-02 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 2 | 2 | 2 | Scheduled | 10/03/2021 | 11/03/2021
TO-21-COT-T141-02 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 2 | 2 | 2 | Reference | 10/03/2021 | 11/03/2021
TO-21-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 13 | 8 | 8 | Scheduled | 12/03/2021 | 24/03/2021
TO-21-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 62 | 40 | 40 | Scheduled | 12/03/2021 | 12/05/2021
TO-21-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 15/03/2021 | 15/03/2021
TO-21-220 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 3 | 3 | Scheduled | 15/03/2021 | 18/03/2021
TO-21-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 16/03/2021 | 16/03/2021
TO-21-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 7 | 5 | 5 | Scheduled | 18/03/2021 | 24/03/2021
TO-21-BYH-KNR-1-04 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 44 | 29 | 29 | Scheduled | 25/03/2021 | 07/05/2021
TO-21-220 kV B2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 5 |  | Scheduled | 25/03/2021 | 31/03/2021
TO-21-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 5 | 5 | Scheduled | 25/03/2021 | 31/03/2021
TO-21-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Scheduled | 26/03/2021 | 26/03/2021
TO-21-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 2 | 2 | 2 | Reference | 30/03/2021 | 31/03/2021
TO-21-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV A2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-220 kV B2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 4 | 4 | Scheduled | 01/04/2021 | 08/04/2021
TO-21-AA GIS-110K3-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 25 | 19 | 19 | Scheduled | 06/04/2021 | 30/04/2021
TO-21-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 |  | Scheduled | 06/04/2021 | 19/04/2021
TO-21-KPG-MP GIS-1-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-MP GIS-PRO-1-02 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 16 | 12 | 12 | Scheduled | 08/04/2021 | 23/04/2021
TO-21-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 26 | 19 |  | Scheduled | 12/04/2021 | 07/05/2021
TO-21-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 26 | 19 | 19 | Scheduled | 12/04/2021 | 07/05/2021
TO-21-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 7 | 5 | 5 | Scheduled | 13/04/2021 | 19/04/2021
TO-21-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 1 | 1 | 1 | Scheduled | 14/04/2021 | 14/04/2021
TO-21-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 8 | 6 | 6 | Scheduled | 20/04/2021 | 27/04/2021
TO-21-GLE-KCR-1-02 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 2 | 2 | 2 | Scheduled | 27/04/2021 | 28/04/2021
TO-21-KCR-T121-02 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 2 | 2 | 2 | Scheduled | 27/04/2021 | 28/04/2021
TO-21-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 |  | Scheduled | 10/05/2021 | 14/05/2021
TO-21-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 5 | 5 | 5 | Scheduled | 10/05/2021 | 14/05/2021
TO-21-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 6 | 4 | 4 | Scheduled | 14/05/2021 | 19/05/2021
TO-21-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 17/05/2021 | 21/05/2021
TO-21-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 10 | 8 | 8 | Scheduled | 17/05/2021 | 26/05/2021
TO-21-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Tentative | 18/05/2021 | 18/05/2021
TO-21-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 19/05/2021 | 21/05/2021
TO-21-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 3 | 3 | 3 | Scheduled | 19/05/2021 | 21/05/2021
TO-21-AA GIS-LIM-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 24/05/2021 | 28/05/2021
TO-21-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 5 | 5 |  | Scheduled | 24/05/2021 | 28/05/2021
TO-21-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 2 | 2 | 2 | Scheduled | 27/05/2021 | 28/05/2021
TO-21-AA GIS-T103-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 4 | 4 | 4 | Scheduled | 31/05/2021 | 03/06/2021
TO-21-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 4 | 4 | 4 | Scheduled | 31/05/2021 | 03/06/2021
TO-21-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 02/06/2021 | 03/06/2021
TO-21-AA GIS-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 8 | 6 | 6 | Scheduled | 08/06/2021 | 15/06/2021
TO-21-KPG-KNR-1-220-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-220 kV A1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-220 kV B1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 15 | 11 | 11 | Scheduled | 08/06/2021 | 22/06/2021
TO-21-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 27 | 19 | 19 | Scheduled | 09/06/2021 | 05/07/2021
TO-21-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 14/06/2021 | 25/06/2021
TO-21-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 1 | 1 | 3 | Scheduled | 14/06/2021 | 14/06/2021
TO-21-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 4 | 4 | 4 | Reference (Tentative) | 15/06/2021 | 18/06/2021
TO-21-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-220 kV B1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 154 | 108 | 108 | Scheduled | 15/06/2021 | 15/11/2021
TO-21-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 2 | 2 | 2 | Scheduled | 15/06/2021 | 16/06/2021
TO-21-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | 4 | 4 | 4 | Tentative | 15/06/2021 | 18/06/2021
TO-21-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | 4 | 4 | 4 | Reference (Tentative) | 15/06/2021 | 18/06/2021
TO-21-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 19 | 15 | 15 | Scheduled | 21/06/2021 | 09/07/2021
TO-21-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 21/06/2021 | 25/06/2021
TO-21-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 23/06/2021 | 23/06/2021
TO-21-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 1 | 1 | 1 | Scheduled | 24/06/2021 | 24/06/2021
TO-21-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-110 kV A1/A2/A4 @ LSN-01 | BUSBAR SECTION - LISHEEN 110-LISHEEN 110-110A1-A2-A4 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 12 | 10 | 10 | Reference | 28/06/2021 | 09/07/2021
TO-21-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 12 | 10 | 10 | Scheduled | 28/06/2021 | 09/07/2021
TO-21-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Tentative | 28/06/2021 | 02/07/2021
TO-21-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 1 | 1 | 1 | Scheduled | 30/06/2021 | 30/06/2021
TO-21-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 16 | 12 | 12 | Scheduled | 01/07/2021 | 16/07/2021
TO-21-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 05/07/2021 | 09/07/2021
TO-21-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 5 | 5 | 5 | Reference | 05/07/2021 | 09/07/2021
TO-21-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 08/07/2021 | 08/07/2021
TO-21-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 1 | 1 | 1 | Scheduled | 08/07/2021 | 08/07/2021
TO-21-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 |  | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 15 | 11 | 11 | Scheduled | 12/07/2021 | 26/07/2021
TO-21-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 2 | 2 | 2 | Scheduled | 14/07/2021 | 15/07/2021
TO-21-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 15/07/2021 | 16/07/2021
TO-21-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 2 | 2 | 2 | Scheduled | 15/07/2021 | 16/07/2021
TO-21-CHA-T141-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | 2 | 2 | 2 | Reference | 15/07/2021 | 16/07/2021
TO-21-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 12 | 10 | 10 | Scheduled | 19/07/2021 | 30/07/2021
TO-21-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 3 | 3 | 3 | Tentative | 19/07/2021 | 21/07/2021
TO-21-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 4 | 4 | 4 | Scheduled | 20/07/2021 | 23/07/2021
TO-21-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 58 | 41 | 41 | Reference | 22/07/2021 | 17/09/2021
TO-21-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | 1 | Scheduled | 22/07/2021 | 22/07/2021
TO-21-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 12 | 9 | 9 | Scheduled | 26/07/2021 | 06/08/2021
TO-21-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 2 | 2 | 2 | Scheduled | 26/07/2021 | 27/07/2021
TO-21-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 3 | 3 | 3 | Scheduled | 26/07/2021 | 28/07/2021
TO-21-TIP-T141-01 | DISTRIBUTION TRANSFORMER - TIPPERARY 110-TIPPERARY 38-T141 | 2 | 2 | 2 | Reference | 29/07/2021 | 30/07/2021
TO-21-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 3 | 3 | 3 | Scheduled | 04/08/2021 | 06/08/2021
TO-21-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 54 | 40 | 40 | Scheduled | 09/08/2021 | 01/10/2021
TO-21-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 19 | 15 | 15 | Scheduled | 09/08/2021 | 27/08/2021
TO-21-KPG-TB-2-05 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-PRO-TB-1-05 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-TB-T2003-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 3 | 3 | 3 | Scheduled | 09/08/2021 | 11/08/2021
TO-21-TB-T2102-05 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 3 | 3 | Tentative | 09/08/2021 | 11/08/2021
TO-21-CNO-KPG-1-02 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-CNO-T131-02 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 96 | 67 | 67 | Scheduled | 12/08/2021 | 15/11/2021
TO-21-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 | 5 | Tentative | 16/08/2021 | 20/08/2021
TO-21-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 16/08/2021 | 20/08/2021
TO-21-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 16/08/2021 | 20/08/2021
TO-21-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 4 | 4 | 4 | Reference | 17/08/2021 | 20/08/2021
TO-21-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 4 | 4 | 4 | Scheduled | 17/08/2021 | 20/08/2021
TO-21-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 |  | Scheduled | 23/08/2021 | 27/08/2021
TO-21-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 3 | 3 | Scheduled | 23/08/2021 | 25/08/2021
TO-21-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 5 |  | Scheduled | 06/09/2021 | 10/09/2021
TO-21-KNR-TRI-2-03 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-AUG-CFM-1-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Tentative | 13/09/2021 | 17/09/2021
TO-21-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference (Tentative) | 13/09/2021 | 17/09/2021
TO-21-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Tentative | 27/09/2021 | 01/10/2021
TO-21-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference (Tentative) | 27/09/2021 | 01/10/2021
TO-21-BVK-CLA-1-08 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 1 | 1 | 1 | Scheduled | 12/10/2021 | 12/10/2021
TO-21-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 12/10/2021 | 13/10/2021
TO-21-AA GIS-LIM-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 1 | 1 | 1 | Scheduled | 13/10/2021 | 13/10/2021
TO-21-CLH-TRI-1-03 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 18/10/2021 | 19/10/2021
TO-21-220 kV A2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-220 kV B1 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-220 kV B2 @ KNR-05 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 4 | 4 |  | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-KNR-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 18/10/2021 | 21/10/2021
TO-21-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 12 | 9 | 9 | Scheduled | 18/10/2021 | 29/10/2021
TO-21-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 2 | 2 | 2 | Scheduled | 21/10/2021 | 22/10/2021
TO-21-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 4 | 4 | 4 | Reference | 26/10/2021 | 29/10/2021
TO-21-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-CGL-T122-03 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 1 | 1 | 1 | Scheduled | 02/11/2021 | 02/11/2021
TO-21-KLN-T2101-04 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 1 | 1 | 1 | Tentative | 03/11/2021 | 03/11/2021
TO-21-KPG-MP GIS-2-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SK-T104-06 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Scheduled | 08/11/2021 | 10/11/2021
TO-21-400 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 1 | 1 | 1 | Scheduled | 11/11/2021 | 11/11/2021
TO-21-400 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 1 | 1 | 1 | Scheduled | 11/11/2021 | 11/11/2021
TO-21-AA GIS-DRU-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 1 | 1 | 1 | Scheduled | 15/11/2021 | 15/11/2021
TO-21-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 1 | 1 | 1 | Scheduled | 15/11/2021 | 15/11/2021
TO-21-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-220K1-2-05 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-T2004-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 4 | 4 | 4 | Scheduled | 16/11/2021 | 19/11/2021
TO-21-TB-T2101-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 4 | 4 |  | Scheduled | 16/11/2021 | 19/11/2021
TO-21-KPG-TB-1-04 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-TB-220K1-2-06 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-CLA-CKN-1-04 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 4 | 4 | 4 | Scheduled | 22/11/2021 | 25/11/2021
TO-21-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-220 kV A1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-TB-T2004-04 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 22/02/2021 | 05/03/2021
TO-21-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 131 | 90 |  | Scheduled | 22/02/2021 | 02/07/2021
TO-21-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 116 | 79 | 79 | Scheduled | 22/02/2021 | 17/06/2021
TO-21-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 14 | 10 | 10 | Scheduled | 26/02/2021 | 11/03/2021
TO-21-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 2 | 2 |  | Scheduled | 01/03/2021 | 02/03/2021
TO-21-220 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 2 | 2 |  | Scheduled | 01/03/2021 | 02/03/2021
TO-21-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 2 | 2 |  | Scheduled | 03/03/2021 | 04/03/2021
TO-21-220 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 2 | 2 |  | Scheduled | 03/03/2021 | 04/03/2021
TO-21-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 18 | 12 | 12 | Scheduled | 22/03/2021 | 08/04/2021
TO-21-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-KLS-T2101-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 22 | 15 | 15 | Reference | 14/04/2021 | 05/05/2021
TO-21-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-CUL-WAT-1-03 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 1 | 1 | 1 | Scheduled | 21/04/2021 | 21/04/2021
TO-21-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-110SA1-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-110SA2-01 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 7 | 5 | 5 | Scheduled | 04/05/2021 | 10/05/2021
TO-21-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 7 | 5 | 5 | Reference | 04/05/2021 | 10/05/2021
TO-21-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 05/05/2021 | 06/05/2021
TO-21-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 1 | 1 | 1 | Scheduled | 11/05/2021 | 11/05/2021
TO-21-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 1 | 1 | 1 | Scheduled | 11/05/2021 | 11/05/2021
TO-21-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-110SA1-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA1 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-110SA2-02 | SECTIONALISING DISCONNECT - KILKENNY 110-KILKENNY 110-110SA2 | 7 | 5 | 5 | Scheduled | 11/05/2021 | 17/05/2021
TO-21-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 7 | 5 | 5 | Reference | 11/05/2021 | 17/05/2021
TO-21-ARK-T2101-02 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 1 | 1 | 1 | Scheduled | 13/05/2021 | 13/05/2021
TO-21-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 5 | 5 | Scheduled | 18/05/2021 | 24/05/2021
TO-21-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 14 | 14 | Scheduled | 24/05/2021 | 11/06/2021
TO-21-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 10 | 8 | 8 | Scheduled | 08/06/2021 | 17/06/2021
TO-21-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV A2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 14 | 10 | 10 | Scheduled | 22/06/2021 | 05/07/2021
TO-21-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 4 | 4 | 4 | Reference | 22/06/2021 | 25/06/2021
TO-21-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 9 | 7 | 7 | Scheduled | 01/07/2021 | 09/07/2021
TO-21-CRA-WEX-1-06 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 1 | 1 |  | Scheduled | 02/07/2021 | 02/07/2021
TO-21-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 05/07/2021 | 09/07/2021
TO-21-DER-MAY-1-04 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 08/07/2021 | 09/07/2021
TO-21-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-BDN-MRK1-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Scheduled | 12/07/2021 | 19/07/2021
TO-21-KTL-MON-1-02 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 9 | 7 |  | Scheduled | 12/07/2021 | 20/07/2021
TO-21-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 19/07/2021 | 23/07/2021
TO-21-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 9 | 7 | 7 | Scheduled | 20/07/2021 | 28/07/2021
TO-21-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 3 | 3 | 3 | Scheduled | 26/07/2021 | 28/07/2021
TO-21-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 3 | 3 | 3 | Reference (Tentative) | 26/07/2021 | 28/07/2021
TO-21-BEG-CKM GIS-1-05 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Scheduled | 27/07/2021 | 30/07/2021
TO-21-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 27/07/2021 | 27/07/2021
TO-21-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 7 | 4 | 4 | Scheduled | 29/07/2021 | 04/08/2021
TO-21-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 7 | 4 | 4 | Scheduled | 29/07/2021 | 04/08/2021
TO-21-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 5 | 5 | 5 | Scheduled | 09/08/2021 | 13/08/2021
TO-21-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 117 | 84 | 64 | Reference | 16/08/2021 | 10/12/2021
TO-21-BDA-T102-03 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 31/08/2021 | 02/09/2021
TO-21-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 6 | 4 | 4 | Scheduled | 01/09/2021 | 06/09/2021
TO-21-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 03/09/2021 | 03/09/2021
TO-21-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 19 | 15 | 15 | Scheduled | 06/09/2021 | 24/09/2021
TO-21-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | 4 | 4 | 4 | Reference | 07/09/2021 | 10/09/2021
TO-21-DGN-WOH-1-05 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 4 | 4 | 4 | Scheduled | 07/09/2021 | 10/09/2021
TO-21-BEG-110SA1-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/09/2021 | 10/09/2021
TO-21-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/09/2021 | 10/09/2021
TO-21-BEG-T102-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T102 | 2 | 2 | 2 | Reference | 09/09/2021 | 10/09/2021
TO-21-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 13/09/2021 | 14/09/2021
TO-21-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 10 | 8 | 8 | Scheduled | 21/09/2021 | 30/09/2021
TO-21-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 21/09/2021 | 22/09/2021
TO-21-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 2 | 2 | 2 | Scheduled | 21/09/2021 | 22/09/2021
TO-21-DOO-T142-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 2 | 2 | 2 | Reference | 21/09/2021 | 22/09/2021
TO-21-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 04/10/2021 | 06/10/2021
TO-21-GI GIS-LWD-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-220 kV A1 @ LWD-01 | BUSBAR SECTION - LODGEWOOD 220-LODGEWOOD 220-220A1 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-220 kV A2 @ LWD-01 | BUSBAR SECTION - LODGEWOOD 220-LODGEWOOD 220-220A2 | 4 | 4 | 4 | Tentative | 04/10/2021 | 07/10/2021
TO-21-NEW-PLS-1-05 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 2 | 2 | 2 | Scheduled | 04/10/2021 | 05/10/2021
TO-21-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 18/10/2021 | 20/10/2021
TO-21-ARK-BOG-1-03 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 3 | 3 | 3 | Scheduled | 19/10/2021 | 21/10/2021
TO-21-KLS-T2101-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 15 | 10 | 10 | Scheduled | 21/10/2021 | 04/11/2021
TO-21-BOG-CRA-1-02 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 8 | 6 | 6 | Scheduled | 26/10/2021 | 02/11/2021
TO-21-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-DEY-1-01 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-KLS-220K1-2-03 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 2 | 2 | 2 | Scheduled | 15/11/2021 | 16/11/2021
TO-21-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 1 | 1 | 1 | Scheduled | 19/11/2021 | 19/11/2021
TO-21-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 19 | 15 | 15 | Scheduled | 22/11/2021 | 10/12/2021

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 3 | 3 |  | Scheduled | 22/02/2021 | 24/02/2021
TO-21-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 59 | 40 |  | Scheduled | 22/02/2021 | 21/04/2021
TO-21-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 22/02/2021 | 24/02/2021
TO-21-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 3 | 3 | 3 | Scheduled | 22/02/2021 | 24/02/2021
TO-21-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 3 | 3 |  | Reference | 22/02/2021 | 24/02/2021
TO-21-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 12 | 10 | 10 | Scheduled | 01/03/2021 | 12/03/2021
TO-21-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | 1 | 1 | 1 | Scheduled | 03/03/2021 | 03/03/2021
TO-21-LET-PST-03 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 15/03/2021 | 16/03/2021
TO-21-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 5 | 4 | 4 | Scheduled | 15/03/2021 | 19/03/2021
TO-21-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Scheduled | 18/03/2021 | 18/03/2021
TO-21-CBR-SVC-03 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 43 | 28 | 28 | Scheduled | 23/03/2021 | 04/05/2021
TO-21-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 8 | 6 | 6 | Scheduled | 12/04/2021 | 19/04/2021
TO-21-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/04/2021 | 14/04/2021
TO-21-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-TAW-T1/T2-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 1 | 1 | 1 | Scheduled | 12/04/2021 | 12/04/2021
TO-21-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 1 | 1 | 1 | Scheduled | 12/04/2021 | 12/04/2021
TO-21-TAW-T3-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 15 | 11 | 11 | Scheduled | 12/04/2021 | 26/04/2021
TO-21-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 14 | 10 | 10 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 |  | Scheduled | 19/04/2021 | 23/04/2021
TO-21-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 2 | 2 | 2 | Scheduled | 20/04/2021 | 21/04/2021
TO-21-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 2 | 2 | 2 | Reference | 20/04/2021 | 21/04/2021
TO-21-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 5 | 5 | 5 | Tentative | 26/04/2021 | 30/04/2021
TO-21-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 16 | 12 | 12 | Scheduled | 06/05/2021 | 21/05/2021
TO-21-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 13 | 9 |  | Scheduled | 07/05/2021 | 19/05/2021
TO-21-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 15 | 11 | 11 | Scheduled | 10/05/2021 | 24/05/2021
TO-21-CF-CLO-1-05 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-CLO-MRY-1-02 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 50 | 35 | 35 | Scheduled | 24/05/2021 | 12/07/2021
TO-21-MRY-T131-02 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 24/05/2021 | 31/05/2021
TO-21-CSH-FLA-1-01 | 220kV FEEDER - CASHLA 220-FLAGFORD 220-1 | 29 | 20 | 20 | Scheduled | 25/05/2021 | 22/06/2021
TO-21-110 kV A1 @ CLO-03 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 6 | 4 | 4 | Scheduled | 26/05/2021 | 31/05/2021
TO-21-GOL-T101-04 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 1 | 1 | 1 | Scheduled | 01/06/2021 | 01/06/2021
TO-21-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 4 | 4 | 5 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 4 | 4 | 5 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 165 | 117 | 117 | Reference | 08/06/2021 | 19/11/2021
TO-21-CF-T103-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 19 | 15 | 15 | Scheduled | 14/06/2021 | 02/07/2021
TO-21-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 1 | 1 | 1 | Scheduled | 17/06/2021 | 17/06/2021
TO-21-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | 7 | 5 | 5 | Scheduled | 23/06/2021 | 29/06/2021
TO-21-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 14 | 10 | 10 | Scheduled | 29/06/2021 | 12/07/2021
TO-21-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 10 | 8 | 8 | Reference | 05/07/2021 | 14/07/2021
TO-21-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 10 | 8 | 8 | Scheduled | 05/07/2021 | 14/07/2021
TO-21-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 9 | 7 |  | Scheduled | 07/07/2021 | 15/07/2021
TO-21-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 9 | 7 | 7 | Reference | 07/07/2021 | 15/07/2021
TO-21-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 4 | 4 | 4 | Scheduled | 12/07/2021 | 15/07/2021
TO-21-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 7 | 5 | 5 | Scheduled | 15/07/2021 | 21/07/2021
TO-21-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 7 | 5 | 5 | Reference | 15/07/2021 | 21/07/2021
TO-21-GAL-KNY-1-03 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 9 | 7 | 7 | Scheduled | 20/07/2021 | 28/07/2021
TO-21-FLA-GIL-1-02 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 26/07/2021 | 30/07/2021
TO-21-GIL-T121-02 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 26/07/2021 | 30/07/2021
TO-21-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 2 | 2 | 2 | Scheduled | 04/08/2021 | 05/08/2021
TO-21-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 2 | 2 | 2 | Scheduled | 04/08/2021 | 05/08/2021
TO-21-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 5 | 5 | 5 | Tentative | 09/08/2021 | 13/08/2021
TO-21-CUN-110SA1-02 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-CUN-110SA2-02 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 8 | 6 | 6 | Scheduled | 09/08/2021 | 16/08/2021
TO-21-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 5 | 5 | 5 | Tentative | 09/08/2021 | 13/08/2021
TO-21-SLI-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-SLI-SRA-2-04 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 09/08/2021 | 12/08/2021
TO-21-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 4 | 4 | 4 | Reference | 09/08/2021 | 12/08/2021
TO-21-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 9 | 7 | 7 | Scheduled | 12/08/2021 | 20/08/2021
TO-21-CSH-GAL-1-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 48 | 34 | 34 | Scheduled | 12/08/2021 | 28/09/2021
TO-21-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 46 | 34 |  | Scheduled | 17/08/2021 | 01/10/2021
TO-21-110 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-110 kV B1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 18 | 14 | 14 | Scheduled | 17/08/2021 | 03/09/2021
TO-21-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/09/2021 | 13/09/2021
TO-21-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | 3 | Scheduled | 06/09/2021 | 08/09/2021
TO-21-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 |  | Scheduled | 06/09/2021 | 08/09/2021
TO-21-COS-FLA-1-02 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 3 | 3 |  | Scheduled | 06/09/2021 | 08/09/2021
TO-21-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 |  | Reference | 06/09/2021 | 08/09/2021
TO-21-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Scheduled | 08/09/2021 | 08/09/2021
TO-21-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 7 | 5 |  | Scheduled | 09/09/2021 | 15/09/2021
TO-21-BK-SKY-1-02 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-110SA1-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-110SA2-02 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 6 | 4 | 4 | Scheduled | 16/09/2021 | 21/09/2021
TO-21-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 5 | 5 | 5 | Scheduled | 20/09/2021 | 24/09/2021
TO-21-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/09/2021 | 21/09/2021
TO-21-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 2 | 2 |  | Scheduled | 20/09/2021 | 21/09/2021
TO-21-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 2 | 2 | 2 | Reference | 20/09/2021 | 21/09/2021
TO-21-DYN-T121-02 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 2 | 2 | 2 | Reference (Tentative) | 27/09/2021 | 28/09/2021
TO-21-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 3 | 3 | 3 | Scheduled | 28/09/2021 | 30/09/2021
TO-21-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 26 | 19 | 20 | Scheduled | 11/10/2021 | 05/11/2021
TO-21-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 8 | 6 | 6 | Scheduled | 11/10/2021 | 18/10/2021
TO-21-CBR-SVC-07 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/10/2021 | 26/10/2021
TO-21-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 9 | 7 | 7 | Scheduled | 08/11/2021 | 16/11/2021
TO-21-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-FLA-T2102-03 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 5 | 5 | 5 | Scheduled | 15/11/2021 | 19/11/2021
TO-21-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 3 | 3 | 3 | Scheduled | 17/11/2021 | 19/11/2021
TO-21-CLO-DRM-1-03 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-110SA1-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-110SA2-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-LET-1-06 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-DRM-LET-1-08 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-DRM-MEE-1-04 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-LET-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-PST-04 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 1 | 1 | Scheduled | 22/11/2021 | 22/11/2021
TO-21-LET-T141-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 1 | 1 | Reference | 22/11/2021 | 22/11/2021
TO-21-MEE-T121-03 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 14 | 10 | 10 | Scheduled | 23/02/2021 | 08/03/2021
TO-21-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 2 | 2 | 2 | Scheduled | 24/02/2021 | 25/02/2021
TO-21-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 1 | 1 |  | Scheduled | 24/02/2021 | 24/02/2021
TO-21-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 42 | 27 | 27 | Scheduled | 02/03/2021 | 12/04/2021
TO-21-MLN-T123-05 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 35 | 22 | 22 | Scheduled | 06/03/2021 | 09/04/2021
TO-21-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 16 | 11 | 11 | Scheduled | 11/03/2021 | 26/03/2021
TO-21-LOU-AT3-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 2 | 2 | Scheduled | 31/03/2021 | 01/04/2021
TO-21-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 3 | 3 | 3 | Scheduled | 07/04/2021 | 09/04/2021
TO-21-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | 3 | 3 | 3 | Reference | 07/04/2021 | 09/04/2021
TO-21-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 1 | 1 | 1 | Scheduled | 07/04/2021 | 07/04/2021
TO-21-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 26 | 19 | 19 | Scheduled | 12/04/2021 | 07/05/2021
TO-21-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 14 | 10 | 10 | Scheduled | 14/04/2021 | 27/04/2021
TO-21-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 14 | 10 | 10 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | 14 | 10 | 10 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | 14 | 10 | 3 | Scheduled | 15/04/2021 | 28/04/2021
TO-21-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 15 | 11 | 11 | Scheduled | 15/04/2021 | 29/04/2021
TO-21-DRY-PLA-1-01 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 8 | 6 | 6 | Scheduled | 20/04/2021 | 27/04/2021
TO-21-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 7 | 5 | 5 | Scheduled | 21/04/2021 | 27/04/2021
TO-21-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 7 | 5 |  | Scheduled | 21/04/2021 | 27/04/2021
TO-21-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 7 | 5 |  | Scheduled | 21/04/2021 | 27/04/2021
TO-21-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 9 | 6 | 6 | Scheduled | 26/04/2021 | 04/05/2021
TO-21-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 13 | 9 |  | Scheduled | 07/05/2021 | 19/05/2021
TO-21-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 8 | 6 | 6 | Scheduled | 07/05/2021 | 14/05/2021
TO-21-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 8 | 6 | 6 | Scheduled | 07/05/2021 | 14/05/2021
TO-21-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-110SA1-03 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-110SA2-03 | SECTIONALISING DISCONNECT - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA2 | 36 | 25 |  | Scheduled | 11/05/2021 | 15/06/2021
TO-21-MLN-T124-04 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 36 | 25 | 25 | Scheduled | 11/05/2021 | 15/06/2021
TO-21-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 15 | 11 | 11 | Scheduled | 21/05/2021 | 04/06/2021
TO-21-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2021 | 25/05/2021
TO-21-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 26 | 19 | 19 | Scheduled | 31/05/2021 | 25/06/2021
TO-21-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 1 | 1 | 3 | Scheduled | 01/06/2021 | 01/06/2021
TO-21-ARV-NAV-1-02 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 2 | 2 | 3 | Scheduled | 03/06/2021 | 04/06/2021
TO-21-ARV-SKL-2-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 8 | 6 | 6 | Scheduled | 09/06/2021 | 16/06/2021
TO-21-RRU-SKL-1-06 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-SKL-110SA1-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-SKL-T141-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 3 | 3 | 3 | Reference | 09/06/2021 | 11/06/2021
TO-21-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 12 | 10 | 10 | Scheduled | 14/06/2021 | 25/06/2021
TO-21-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 13/07/2021 | 14/07/2021
TO-21-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 12 | 10 | 10 | Scheduled | 19/07/2021 | 30/07/2021
TO-21-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 5 | 5 | 5 | Scheduled | 19/07/2021 | 23/07/2021
TO-21-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 11 | 9 | 4 | Scheduled | 03/08/2021 | 13/08/2021
TO-21-MLN-T124-05 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 03/08/2021 | 04/08/2021
TO-21-MLN-T123-06 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 05/08/2021 | 06/08/2021
TO-21-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 10 | 8 | 8 | Scheduled | 09/08/2021 | 18/08/2021
TO-21-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 12/08/2021 | 13/08/2021
TO-21-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 12/08/2021 | 13/08/2021
TO-21-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 13/08/2021 | 13/08/2021
TO-21-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 46 | 34 |  | Scheduled | 17/08/2021 | 01/10/2021
TO-21-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 25 | 19 | 19 | Scheduled | 23/08/2021 | 16/09/2021
TO-21-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-CAP1-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 11 | 9 | 9 | Reference | 23/08/2021 | 02/09/2021
TO-21-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/09/2021 | 13/09/2021
TO-21-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 3 | 3 | 3 | Scheduled | 06/09/2021 | 08/09/2021
TO-21-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 10 | 8 | 8 | Scheduled | 14/09/2021 | 23/09/2021
TO-21-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-AGL-SH-1-04 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Tentative | 27/09/2021 | 28/09/2021
TO-21-CDU-MUL-1-06 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | 15 | Scheduled | 04/10/2021 | 22/10/2021
TO-21-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 2 | 2 | 2 | Scheduled | 11/10/2021 | 12/10/2021
TO-21-GOR-NAV-3-03 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 2 | 2 | 2 | Scheduled | 11/10/2021 | 12/10/2021
TO-21-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 8 | 5 | 5 | Scheduled | 18/10/2021 | 25/10/2021
TO-21-DRY-PLA-1-03 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 1 | 1 |  | Tentative | 22/10/2021 | 22/10/2021
TO-21-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 1 | 1 | 1 | Tentative | 26/10/2021 | 26/10/2021
TO-21-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 26/10/2021 | 29/10/2021
TO-21-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 27/10/2021 | 28/10/2021
TO-21-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 1 | 1 | 1 | Scheduled | 02/11/2021 | 02/11/2021
TO-21-SOM-T142-03 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 5 | 5 | 5 | Reference | 08/11/2021 | 12/11/2021
TO-21-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SOM,T-SH-1-06 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 15/11/2021 | 17/11/2021
TO-21-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 8 | 6 | 6 | Scheduled | 17/11/2021 | 24/11/2021
TO-21-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Tentative | 22/11/2021 | 23/11/2021
TO-21-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021
TO-21-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 2 | 2 | 2 | Scheduled | 23/11/2021 | 24/11/2021

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 95 | 65 | 65 | Scheduled | 08/02/2021 | 13/05/2021
TO-21-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 103 | 71 |  | Scheduled | 22/02/2021 | 04/06/2021
TO-21-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 1 | 1 | 1 | Scheduled | 26/02/2021 | 26/02/2021
TO-21-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 7 | 5 | 5 | Scheduled | 02/03/2021 | 08/03/2021
TO-21-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 14 | 10 | 10 | Scheduled | 02/03/2021 | 15/03/2021
TO-21-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 4 | 3 |  | Scheduled | 16/03/2021 | 19/03/2021
TO-21-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Tentative | 23/03/2021 | 24/03/2021
TO-21-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 8 | 4 | 4 | Scheduled | 03/04/2021 | 10/04/2021
TO-21-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 14 | 10 | 10 | Scheduled | 06/04/2021 | 19/04/2021
TO-21-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 11 | 9 | 9 | Scheduled | 06/04/2021 | 16/04/2021
TO-21-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 22 | 15 | 15 | Scheduled | 14/04/2021 | 05/05/2021
TO-21-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 15/04/2021 | 15/04/2021
TO-21-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 19 | 14 | 13 | Scheduled | 26/04/2021 | 14/05/2021
TO-21-ISH-T2001-02 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 19 | 14 | 14 | Scheduled | 26/04/2021 | 14/05/2021
TO-21-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 4 | 4 | 4 | Scheduled | 04/05/2021 | 07/05/2021
TO-21-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 8 | 6 |  | Scheduled | 04/05/2021 | 11/05/2021
TO-21-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 8 | 6 |  | Scheduled | 04/05/2021 | 11/05/2021
TO-21-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 8 | 6 | 6 | Scheduled | 04/05/2021 | 11/05/2021
TO-21-220 kV A1 @ ISH-02 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 1 | 1 | 1 | Scheduled | 04/05/2021 | 04/05/2021
TO-21-220 kV B1 @ ISH-02 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 1 | 1 | 1 | Scheduled | 04/05/2021 | 04/05/2021
TO-21-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 3 | 3 | 5 | Scheduled | 05/05/2021 | 07/05/2021
TO-21-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 2 | 2 |  | Scheduled | 12/05/2021 | 13/05/2021
TO-21-FIN-220K1-2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 19 | 13 | 13 | Scheduled | 14/05/2021 | 01/06/2021
TO-21-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 14 | 10 | 10 | Scheduled | 14/05/2021 | 27/05/2021
TO-21-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | 10 | Scheduled | 17/05/2021 | 28/05/2021
TO-21-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 5 | 5 | 5 | Scheduled | 17/05/2021 | 21/05/2021
TO-21-DSN-KLS-1-02 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 5 | 5 | Scheduled | 18/05/2021 | 24/05/2021
TO-21-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 5 | 5 | 5 | Scheduled | 24/05/2021 | 28/05/2021
TO-21-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-220 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-220 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 5 | 5 |  | Scheduled | 31/05/2021 | 04/06/2021
TO-21-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 29 | 20 | 20 | Scheduled | 31/05/2021 | 28/06/2021
TO-21-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 5 | 5 | 5 | Scheduled | 31/05/2021 | 04/06/2021
TO-21-220 kV A1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 3 | 3 | 3 | Scheduled | 02/06/2021 | 04/06/2021
TO-21-FIN-220K1-2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 207 | 145 | 145 | Scheduled | 08/06/2021 | 31/12/2021
TO-21-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 80 | 57 | 57 | Scheduled | 08/06/2021 | 26/08/2021
TO-21-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 7 | 5 | 5 | Scheduled | 09/06/2021 | 15/06/2021
TO-21-COL-T101-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 7 | 5 | 5 | Reference | 09/06/2021 | 15/06/2021
TO-21-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 7 | 5 | 5 | Reference | 09/06/2021 | 15/06/2021
TO-21-220 kV A1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-220 kV B1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 5 | 5 | 5 | Scheduled | 14/06/2021 | 18/06/2021
TO-21-220 kV B1/B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1-B2 | 2 | 2 | 2 | Scheduled | 16/06/2021 | 17/06/2021
TO-21-220 kV A1/A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 4 | 2 | 2 | Scheduled | 18/06/2021 | 21/06/2021
TO-21-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Scheduled | 21/06/2021 | 25/06/2021
TO-21-220 kV A1/A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 2 | 2 | 2 | Scheduled | 21/06/2021 | 22/06/2021
TO-21-DSN-MAY-1-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 22/06/2021 | 25/06/2021
TO-21-220 kV B1/B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1-B2 | 75 | 53 |  | Scheduled | 22/06/2021 | 04/09/2021
TO-21-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 24/06/2021 | 24/06/2021
TO-21-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-110 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 28/06/2021 | 02/07/2021
TO-21-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 19 | 15 | 15 | Scheduled | 28/06/2021 | 16/07/2021
TO-21-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 2 | 2 |  | Scheduled | 29/06/2021 | 30/06/2021
TO-21-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 2 | 2 |  | Scheduled | 29/06/2021 | 30/06/2021
TO-21-DER-MAY-1-04 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-220 kV A4 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A4 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-220 kV B4 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B4 | 4 | 4 | 4 | Scheduled | 06/07/2021 | 09/07/2021
TO-21-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 18 | 14 | 14 | Scheduled | 06/07/2021 | 23/07/2021
TO-21-KTL-MON-1-02 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 9 | 7 |  | Scheduled | 12/07/2021 | 20/07/2021
TO-21-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 3 | 3 | 3 | Reference | 21/07/2021 | 23/07/2021
TO-21-GRI,T-GCA-1-04 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-GRI,T-MAY-1-02 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV A3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-110 kV B3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 3 | 3 | 3 | Scheduled | 21/07/2021 | 23/07/2021
TO-21-BEG-CKM GIS-1-05 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Scheduled | 27/07/2021 | 30/07/2021
TO-21-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 | 4 | Scheduled | 03/08/2021 | 06/08/2021
TO-21-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | 1 | Scheduled | 10/08/2021 | 10/08/2021
TO-21-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 1 | 1 | 1 | Scheduled | 19/08/2021 | 19/08/2021
TO-21-220 kV A1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 7 | 5 | 5 | Scheduled | 20/08/2021 | 26/08/2021
TO-21-220 kV B1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 7 | 5 | 5 | Scheduled | 20/08/2021 | 26/08/2021
TO-21-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 25 | 19 | 19 | Scheduled | 23/08/2021 | 16/09/2021
TO-21-220 kV A1 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV A2 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV B1 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-220 kV B2 @ ISH-03 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 11 | 9 | 3 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 11 | 9 | 9 | Scheduled | 23/08/2021 | 02/09/2021
TO-21-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Scheduled | 24/08/2021 | 27/08/2021
TO-21-CKM GIS-DSN-1-04 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 1 | 1 | 1 | Scheduled | 30/08/2021 | 30/08/2021
TO-21-SHL-D1/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-SHL-D1/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-SHL-T2014-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 111 | 78 | 78 | Scheduled | 01/09/2021 | 20/12/2021
TO-21-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 1 | 0 | 0 | Tentative | 04/09/2021 | 04/09/2021
TO-21-BEG-CKM GIS-1-02 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 19 | 15 | 15 | Scheduled | 06/09/2021 | 24/09/2021
TO-21-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | 10 | Scheduled | 06/09/2021 | 17/09/2021
TO-21-PB-TF4-03 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 12 | 10 | 10 | Reference | 06/09/2021 | 17/09/2021
TO-21-220 kV A2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 11 | 9 | 9 | Scheduled | 13/09/2021 | 23/09/2021
TO-21-220 kV A1 @ ISH-04 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-220 kV B1 @ ISH-04 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 13/09/2021 | 24/09/2021
TO-21-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 13/09/2021 | 14/09/2021
TO-21-CLE-T222-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 1 | 1 | 1 | Trip Testing | 15/09/2021 | 15/09/2021
TO-21-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 2 | 2 | 2 | Scheduled | 15/09/2021 | 16/09/2021
TO-21-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 6 | 4 | 4 | Scheduled | 15/09/2021 | 20/09/2021
TO-21-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 | 10 | Scheduled | 20/09/2021 | 01/10/2021
TO-21-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 3 | 3 | 3 | Scheduled | 20/09/2021 | 22/09/2021
TO-21-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 1 | 1 |  | Scheduled | 20/09/2021 | 20/09/2021
TO-21-MCE-T121-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 3 | 3 | 3 | Scheduled | 22/09/2021 | 24/09/2021
TO-21-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 14 | 10 |  | Scheduled | 24/09/2021 | 07/10/2021
TO-21-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 14 | 10 |  | Scheduled | 24/09/2021 | 07/10/2021
TO-21-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 14 | 10 | 10 | Scheduled | 24/09/2021 | 07/10/2021
TO-21-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 14 | 10 | 10 | Scheduled | 24/09/2021 | 07/10/2021
TO-21-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 3 | 3 | 3 | Scheduled | 29/09/2021 | 01/10/2021
TO-21-CDU-MUL-1-06 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | 15 | Scheduled | 04/10/2021 | 22/10/2021
TO-21-ISH-SHL-1-06 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 4 | 4 | 4 | Scheduled | 04/10/2021 | 07/10/2021
TO-21-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 4 | 4 | 4 | Scheduled | 04/10/2021 | 07/10/2021
TO-21-220 kV A1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV A2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-220 kV B2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 1 | 1 | 1 | Scheduled | 05/10/2021 | 05/10/2021
TO-21-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-D2/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-SHL-T2015-04 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 32 | 23 | 23 | Scheduled | 05/10/2021 | 05/11/2021
TO-21-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 05/10/2021 | 07/10/2021
TO-21-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 43 | 30 | 30 | Scheduled | 08/10/2021 | 19/11/2021
TO-21-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 50 | 35 | 35 | Scheduled | 08/10/2021 | 26/11/2021
TO-21-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-DSN-220K1-2-03 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-SHL-D2/CB3-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV A1 @ CDU-06 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV A3 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV B1 @ CDU-06 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-220 kV B3 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 5 | 5 |  | Tentative | 18/10/2021 | 22/10/2021
TO-21-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 18/10/2021 | 22/10/2021
TO-21-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 5 | 5 |  | Scheduled | 18/10/2021 | 22/10/2021
TO-21-220 kV A1 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV A2 @ MAY-09 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV B1 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-220 kV B2 @ MAY-09 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-MAY-220K1-2-03 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 4 | 4 | 4 | Scheduled | 19/10/2021 | 22/10/2021
TO-21-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 1 | 1 | 1 | Tentative | 20/10/2021 | 20/10/2021
TO-21-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 3 | 3 | 4 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-BAL-DRY-1-01 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 27/10/2021 | 28/10/2021
TO-21-CBT-INC-1-03 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 3 | 3 | 3 | Scheduled | 27/10/2021 | 29/10/2021
TO-21-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Scheduled | 01/11/2021 | 12/11/2021
TO-21-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 1 | 1 | 1 | Scheduled | 03/11/2021 | 03/11/2021
TO-21-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 5 | 5 | 5 | Reference | 08/11/2021 | 12/11/2021
TO-21-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 5 | 5 | 5 | Scheduled | 08/11/2021 | 12/11/2021
TO-21-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Tentative | 08/11/2021 | 12/11/2021
TO-21-110 kV A3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-110 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-CDU-110K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Scheduled | 16/11/2021 | 16/11/2021
TO-21-110 kV A3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A3 | 5 | 3 | 3 | Scheduled | 26/11/2021 | 30/11/2021
TO-21-110 kV B3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B3 | 5 | 3 | 3 | Scheduled | 26/11/2021 | 30/11/2021

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-21-AD-T2001-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G1-T2001 | 3 | 3 | 3 | Scheduled | 24/02/2021 | 26/02/2021
TO-21-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 3 | 3 | 3 | Scheduled | 24/02/2021 | 26/02/2021
TO-21-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 7 | 5 | 5 | Scheduled | 24/02/2021 | 02/03/2021
TO-21-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | 5 | Scheduled | 01/03/2021 | 05/03/2021
TO-21-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 | 5 |  | Reference | 01/03/2021 | 05/03/2021
TO-21-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 241 | 166 |  | Scheduled | 01/03/2021 | 27/10/2021
TO-21-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | 263 | 182 | 182 | Scheduled | 01/03/2021 | 18/11/2021
TO-21-AD-ST101-06 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-AD-T2102-04 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-AD-WHI-1-07 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 18 | 13 | 13 | Scheduled | 02/03/2021 | 19/03/2021
TO-21-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 2 | 2 | 2 | Scheduled | 08/03/2021 | 09/03/2021
TO-21-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 9 | 6 |  | Scheduled | 15/03/2021 | 23/03/2021
TO-21-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 132 | 90 | 90 | Scheduled | 18/03/2021 | 27/07/2021
TO-21-KRA-MID-1-02 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 18 | 12 | 12 | Scheduled | 22/03/2021 | 08/04/2021
TO-21-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 18 | 12 | 12 | Scheduled | 22/03/2021 | 08/04/2021
TO-21-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 233 | 163 | 163 | Scheduled | 12/04/2021 | 30/11/2021
TO-21-KRA-RAF-1-04 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Scheduled | 12/04/2021 | 16/04/2021
TO-21-CCG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 9 | 7 | 7 | Scheduled | 19/04/2021 | 27/04/2021
TO-21-110 kV A1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-110 kV B1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Tentative | 19/04/2021 | 26/04/2021
TO-21-110 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 2 | 2 | 2 | Tentative | 27/04/2021 | 28/04/2021
TO-21-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 2 | 2 | 2 | Tentative | 27/04/2021 | 28/04/2021
TO-21-MAC-110SA1-05 | SECTIONALISING DISCONNECT - MACROOM 110-MACROOM 110-110SA1 | 14 | 10 | 10 | Scheduled | 04/05/2021 | 17/05/2021
TO-21-CD-T103-03 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 10 | 8 | 8 | Scheduled | 05/05/2021 | 14/05/2021
TO-21-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 7 | 5 | 5 | Reference | 05/05/2021 | 11/05/2021
TO-21-GGO-T2001-04 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 2 | 2 | 2 | Tentative | 05/05/2021 | 06/05/2021
TO-21-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 1 | 1 | 1 | Scheduled | 07/05/2021 | 07/05/2021
TO-21-GGO-T2001-03 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 22 | 16 | 16 | Scheduled | 07/05/2021 | 28/05/2021
TO-21-110 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 12 | 10 | 10 | Scheduled | 10/05/2021 | 21/05/2021
TO-21-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 4 | 4 | 4 | Scheduled | 17/05/2021 | 20/05/2021
TO-21-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 4 | 4 | 4 | Scheduled | 17/05/2021 | 20/05/2021
TO-21-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 24/05/2021 | 26/05/2021
TO-21-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 24/05/2021 | 26/05/2021
TO-21-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 14 | 14 | Scheduled | 24/05/2021 | 11/06/2021
TO-21-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 24/05/2021 | 26/05/2021
TO-21-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 43 | 30 | 30 | Scheduled | 25/05/2021 | 06/07/2021
TO-21-220 kV A1/A2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220A1-A2 | 2 | 2 | 2 | Scheduled | 31/05/2021 | 01/06/2021
TO-21-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/05/2021 | 01/06/2021
TO-21-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 3 | 3 | 3 | Scheduled | 31/05/2021 | 02/06/2021
TO-21-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 4 | 4 | 4 | Scheduled | 08/06/2021 | 11/06/2021
TO-21-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 7 | 5 | 5 | Scheduled | 08/06/2021 | 14/06/2021
TO-21-BAR-T141-05 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 09/06/2021 | 11/06/2021
TO-21-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2021 | 11/06/2021
TO-21-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 3 | 3 | 3 | Scheduled | 14/06/2021 | 16/06/2021
TO-21-KBY-T101-01 | DISTRIBUTION TRANSFORMER - KILBARRY 110-KILBARRY 10-T101 | 2 | 2 | 2 | Reference | 29/06/2021 | 30/06/2021
TO-21-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 9 | 7 | 7 | Scheduled | 01/07/2021 | 09/07/2021
TO-21-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 6 | 4 | 4 | Scheduled | 01/07/2021 | 06/07/2021
TO-21-GGO-T2001-05 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 3 | 3 | 3 | Scheduled | 05/07/2021 | 07/07/2021
TO-21-BLI-DMY-1-01 | 110kV FEEDER - BALLYLICKEY 110-DUNMANWAY 110-1 | 9 | 7 | 7 | Reference | 12/07/2021 | 20/07/2021
TO-21-BLI-T142-01 | DISTRIBUTION TRANSFORMER - BALLYLICKEY 110-BALLYLICKEY 38-T142 | 9 | 7 | 7 | Reference | 12/07/2021 | 20/07/2021
TO-21-CCG-DMY-1-02 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CCG-T131-02 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CCG-T131-03 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 12/07/2021 | 16/07/2021
TO-21-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 5 | 5 | 5 | Reference | 12/07/2021 | 16/07/2021
TO-21-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference | 27/07/2021 | 28/07/2021
TO-21-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | 8 | 5 | 2 | Scheduled | 29/07/2021 | 05/08/2021
TO-21-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 8 | 5 | 6 | Scheduled | 29/07/2021 | 05/08/2021
TO-21-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 16 | 11 | 10 | Scheduled | 29/07/2021 | 13/08/2021
TO-21-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | 8 | 5 | 2 | Reference | 29/07/2021 | 05/08/2021
TO-21-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | 8 | 5 | 3 | Reference | 29/07/2021 | 05/08/2021
TO-21-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 9 | 7 | 7 | Scheduled | 03/08/2021 | 11/08/2021
TO-21-MR-TBG-2-01 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | 8 | 6 | 6 | Scheduled | 06/08/2021 | 13/08/2021
TO-21-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 8 | 6 | 5 | Scheduled | 06/08/2021 | 13/08/2021
TO-21-TBG-T102-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T102 | 8 | 6 | 2 | Reference | 06/08/2021 | 13/08/2021
TO-21-TBG-T142-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T142 | 8 | 6 | 2 | Reference | 06/08/2021 | 13/08/2021
TO-21-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 3 | 3 | 3 | Scheduled | 23/08/2021 | 25/08/2021
TO-21-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-DMY-MAC-1-02 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 31 | 23 | 23 | Scheduled | 23/08/2021 | 22/09/2021
TO-21-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 5 | 5 | 5 | Scheduled | 23/08/2021 | 27/08/2021
TO-21-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 4 | 4 | 4 | Scheduled | 30/08/2021 | 02/09/2021
TO-21-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 4 | 4 | 4 | Scheduled | 30/08/2021 | 02/09/2021
TO-21-CVW-KRA-1-04 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 30/08/2021 | 01/09/2021
TO-21-CVW-T102-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T102 | 3 | 3 | 2 | Reference | 30/08/2021 | 01/09/2021
TO-21-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 6 | 4 | 4 | Scheduled | 01/09/2021 | 06/09/2021
TO-21-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 06/09/2021 | 10/09/2021
TO-21-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 13/09/2021 | 17/09/2021
TO-21-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 4 | 4 | 4 | Scheduled | 14/09/2021 | 17/09/2021
TO-21-CD-MAC-1-05 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 31 | 22 | 22 | Scheduled | 27/09/2021 | 27/10/2021
TO-21-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 31 | 22 | 22 | Scheduled | 27/09/2021 | 27/10/2021
TO-21-CVW-KRA-1-03 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 9 | 7 | 7 | Scheduled | 29/09/2021 | 07/10/2021
TO-21-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 15 | 11 | 7 | Scheduled | 30/09/2021 | 14/10/2021
TO-21-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 04/10/2021 | 06/10/2021
TO-21-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 04/10/2021 | 06/10/2021
TO-21-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 04/10/2021 | 06/10/2021
TO-21-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 17 | 13 | 13 | Scheduled | 04/10/2021 | 20/10/2021
TO-21-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 5 | 5 | 5 | Scheduled | 11/10/2021 | 15/10/2021
TO-21-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-220 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 10 | 8 | 8 | Scheduled | 12/10/2021 | 21/10/2021
TO-21-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 18/10/2021 | 20/10/2021
TO-21-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 18/10/2021 | 20/10/2021
TO-21-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 18/10/2021 | 20/10/2021
TO-21-AD-KRA-1-12 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Scheduled | 26/10/2021 | 28/10/2021
TO-21-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 14 | 10 | 10 | Scheduled | 26/10/2021 | 08/11/2021
TO-21-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 01/11/2021 | 05/11/2021
TO-21-CLA-DMY-1-02 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-IA-MAC-1-05 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 08/11/2021 | 19/11/2021
TO-21-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021
TO-21-CLA-CKN-1-04 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 4 | 4 | 4 | Scheduled | 22/11/2021 | 25/11/2021
TO-21-CLA-T2102-05 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 5 | 5 | 5 | Scheduled | 22/11/2021 | 26/11/2021