## Info
Transmission Outage Planning Process
EirGrid, in cooperation with ESB Networks, has implemented a new transmission outage planning process for 2016. In the past, all maintenance and capital work was scheduled at the start of the year. This process of early scheduling of outages sometimes up to nine months in advance led to a large number of alterations in outage dates due for example to changes in generator outage dates, capital project changes, forced outages of transmission plant and other factors.
The new outage planning process aims to increase flexibility in the outage programme to the benefit of our customers by better accommodating project changes as they occur with the least disruption. In doing so it is hoped to maximise the amount of work which can be carried out on the transmission system in a given outage season with a nominal amount of schedule changes.
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Indicative'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Indicative', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from 16 May 2016 until the end of the year is presented in this spreadsheet. Outages which have already begun and will run beyond 16 May 2016 are also included. For information on outages which have already taken place in 2016 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all planned outages while separate tabs are provided which list the outages in the various regions around the country.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Indicative - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season, for example works which are not expected to take place until several months in the future. These works are given an indicative outage window (date range) in which a fixed duration of work will be carried out. The 'Calendar Day' duration of indicative outages is 'Unknown' until specific start and end dates are proposed and scheduled.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
In some instances, there will be two overlapping outages for the same item of plant with a different status for each outage e.g. 'Proposed' and 'Indicative'. In these instances there are separate works to be completed on the same item of plant e.g. capital works and maintenance works, and both sets of work are in different stages of the outage confirmation process. It is EirGrid’s intention wherever possible/practicable to overlap maintenance/capital works on items of plant to minimise impact on customers and the transmission system.
Date of publication: DD MMM YYYY
Update interval: The first week of each month
All: This tab produces a basic excel table listing all outages currently planned for the annual transmission outage season. The format of the report can be seen in figure 1 below. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Working Day Duration - This shows the amount of working days (i.e. non- weekend, bank holidays or Good Friday) proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of working days required is unknown and this field is populated with “Unknown”
Work Days - This shows the amount of days Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is a status showing the certainty associated with the outage.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
SouthWest: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the South West of the Transmission Grid.
SouthEast: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the South East of the Transmission Grid.
NorthWest: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the North West of the Transmission Grid.
NorthEast: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the North East of the Transmission Grid.
Dublin: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the Dublin area of the Transmission Grid.
Cork: This tab is in the same format and a subset of the “All” worksheet but only includes feeders that are contained in the Cork area of the Transmission Grid.

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 177 | 125 | Scheduled | 07/06/2016 | 30/11/2016
TO-16-MOY-TAW-1-06 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 114 | 81 | Scheduled | 02/08/2016 | 23/11/2016
TO-16-MOY-TAW-2-09 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 120 | 85 | Scheduled | 02/08/2016 | 29/11/2016
TO-16-TAW-T1/T2-05 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 114 | 81 | Reference | 02/08/2016 | 23/11/2016
TO-16-TAW-T101-06 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T101 | 114 | 81 | Reference | 02/08/2016 | 23/11/2016
TO-16-TAW-T102-08 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T102 | 120 | 85 | Reference | 02/08/2016 | 29/11/2016
TO-16-TAW-T3-06 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 120 | 85 | Reference | 02/08/2016 | 29/11/2016
TO-16-RYB-RYB GIS-2-13 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | 1 | 0 | Scheduled | 06/09/2016 | 25/12/2500
TO-16-CTN-KLN-1-03 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 80 | 57 | Scheduled | 12/09/2016 | 30/11/2016
TO-16-110 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 43 | 31 | Scheduled | 12/09/2016 | 24/10/2016
TO-16-KLN-T2102-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 43 | 31 | Scheduled | 12/09/2016 | 24/10/2016
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 70 | 49 | Scheduled | 22/09/2016 | 30/11/2016
TO-16-GOL-T101-04 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-CF-1-01 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-GOL-1-04 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 29 | 21 | Scheduled | 27/09/2016 | 25/10/2016
TO-16-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 16 | 12 | Scheduled | 03/10/2016 | 18/10/2016
TO-16-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 16 | 12 | Scheduled | 03/10/2016 | 18/10/2016
TO-16-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220K2 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220SA1-2CB | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220SB1-2CB | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-LWD-1-06 | 220kV FEEDER - GREAT ISLAND 220-LODGEWOOD 220-1 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND G4-T2004 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-T2102-04 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-BAN-DMY-1-05 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-CHA-110SA1-01 | SECTIONALISING DISCONNECT - CHARLEVILLE 110-CHARLEVILLE 110-110SA1 | 29 | 20 | Scheduled | 10/10/2016 | 07/11/2016
TO-16-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 29 | 20 | Scheduled | 10/10/2016 | 07/11/2016
TO-16-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | 19 | 15 | Reference | 10/10/2016 | 28/10/2016
TO-16-DMY-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-DMY-CAP2-03 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-DMY-T142-02 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 10 | 8 | Reference (Tentative) | 10/10/2016 | 19/10/2016
TO-16-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-GLE-T141-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-KCR-T121-01 | DISTRIBUTION TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 14 | 10 | Scheduled | 10/10/2016 | 23/10/2016
TO-16-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 17 | 13 | Proposed | 11/10/2016 | 27/10/2016
TO-16-BK-CBR-1-07 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 48 | 33 | Scheduled | 13/10/2016 | 29/11/2016
TO-16-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 14 | 10 | Scheduled | 17/10/2016 | 30/10/2016
TO-16-CDU-RYB-1-09 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | 43 | 30 | Scheduled | 17/10/2016 | 28/11/2016
TO-16-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 9 | 7 | Scheduled | 17/10/2016 | 25/10/2016
TO-16-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 1 | 1 | Reference | 17/10/2016 | 17/10/2016
TO-16-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 1 | 1 | Scheduled | 17/10/2016 | 17/10/2016
TO-16-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 1 | 1 | Scheduled | 17/10/2016 | 17/10/2016
TO-16-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 43 | 30 | Scheduled | 17/10/2016 | 28/11/2016
TO-16-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 10 | 8 | Scheduled | 17/10/2016 | 26/10/2016
TO-16-CLG-T121-04 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 2 | 2 | Proposed | 18/10/2016 | 19/10/2016
TO-16-CDU-RYB-1-11 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | 4 | 4 | Scheduled | 18/10/2016 | 21/10/2016
TO-16-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 3 | 3 | Scheduled | 18/10/2016 | 20/10/2016
TO-16-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 3 | 3 | Scheduled | 18/10/2016 | 20/10/2016
TO-16-RYB-110SA1-2CB-14 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | 4 | 4 | Scheduled | 18/10/2016 | 21/10/2016
TO-16-RYB-T101-09 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | 44 | 31 | Scheduled | 18/10/2016 | 30/11/2016
TO-16-CLG-T123-05 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 2 | 2 | Proposed | 20/10/2016 | 21/10/2016
TO-16-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 11 | 6 | Scheduled | 21/10/2016 | 31/10/2016
TO-16-AHA-KLN-2-02 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | Reference | 22/10/2016 | 23/10/2016
TO-16-AHA-T102-02 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 0 | Reference | 22/10/2016 | 23/10/2016
TO-16-KLN-110K1-2-03 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-LIM-2-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-SNG-1-05 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-T2104-05 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 9 | 6 | Scheduled | 24/10/2016 | 01/11/2016
TO-16-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 4 | 4 | Reference (Proposed) | 24/10/2016 | 27/10/2016
TO-16-CLG-MCE-1-04 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | 2 | 2 | Proposed | 26/10/2016 | 27/10/2016
TO-16-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | 3 | 3 | Proposed | 26/10/2016 | 28/10/2016
TO-16-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 15 | 10 | Scheduled | 26/10/2016 | 09/11/2016
TO-16-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-AD-LPT-1-03 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-LPT-T2002-03 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 10 | 8 | Scheduled | 01/11/2016 | 10/11/2016
TO-16-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 3 | 3 | Scheduled | 01/11/2016 | 03/11/2016
TO-16-TB-TRL-2-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-2 | 8 | 6 | Scheduled | 01/11/2016 | 08/11/2016
TO-16-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 10 | Scheduled | 08/11/2016 | 23/11/2016
TO-16-FIN-T2102-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | 16 | 12 | Scheduled | 10/11/2016 | 25/11/2016
TO-16-GI-110K1-2-07 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI GIS-T2102-03 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 5 | 5 | Reference | 14/11/2016 | 18/11/2016
TO-16-KLN-T2104-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 7 | 5 | Scheduled | 17/11/2016 | 23/11/2016
TO-16-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 6 | 4 | Reference | 18/11/2016 | 23/11/2016
TO-16-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 8 | 6 | Scheduled | 18/11/2016 | 25/11/2016
TO-16-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 10 | 8 | Scheduled | 21/11/2016 | 30/11/2016
TO-16-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | 3 | 3 | Scheduled | 21/11/2016 | 23/11/2016
TO-16-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 5 | 4 | Scheduled | 22/11/2016 | 26/11/2016
TO-16-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 5 | 4 | Scheduled | 22/11/2016 | 26/11/2016
TO-16-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 2 | 0 | Reference | 26/11/2016 | 27/11/2016
TO-16-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 2 | 0 | Reference | 26/11/2016 | 27/11/2016
TO-16-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016
TO-16-DFR-T122-04 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 1 | 1 | Reference | 28/11/2016 | 28/11/2016
TO-16-DFR,T-DFR-1-04 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016
TO-16-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016
TO-16-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | 5 | 5 | Scheduled | 28/11/2016 | 02/12/2016
TO-16-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | Scheduled | 30/11/2016 | 30/11/2016
TO-16-RYB-RYB GIS-1-15 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 2 | 2 | Scheduled | 30/11/2016 | 01/12/2016

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-CTN-KLN-1-03 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 80 | 57 | Scheduled | 12/09/2016 | 30/11/2016
TO-16-110 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 43 | 31 | Scheduled | 12/09/2016 | 24/10/2016
TO-16-KLN-T2102-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 43 | 31 | Scheduled | 12/09/2016 | 24/10/2016
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 70 | 49 | Scheduled | 22/09/2016 | 30/11/2016
TO-16-CHA-110SA1-01 | SECTIONALISING DISCONNECT - CHARLEVILLE 110-CHARLEVILLE 110-110SA1 | 29 | 20 | Scheduled | 10/10/2016 | 07/11/2016
TO-16-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 29 | 20 | Scheduled | 10/10/2016 | 07/11/2016
TO-16-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-GLE-T141-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-KCR-T121-01 | DISTRIBUTION TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 29 | 20 | Reference | 10/10/2016 | 07/11/2016
TO-16-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 14 | 10 | Scheduled | 17/10/2016 | 30/10/2016
TO-16-AHA-KLN-2-02 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | Reference | 22/10/2016 | 23/10/2016
TO-16-AHA-T102-02 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 0 | Reference | 22/10/2016 | 23/10/2016
TO-16-KLN-110K1-2-03 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-LIM-2-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-SNG-1-05 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-KLN-T2104-05 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 2 | 2 | Scheduled | 22/10/2016 | 23/10/2016
TO-16-TB-TRL-2-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-2 | 8 | 6 | Scheduled | 01/11/2016 | 08/11/2016
TO-16-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 16 | 10 | Scheduled | 08/11/2016 | 23/11/2016
TO-16-KLN-T2104-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 7 | 5 | Scheduled | 17/11/2016 | 23/11/2016

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220K2 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220SA1-2CB | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 220-GREAT ISLAND 220-220SB1-2CB | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-LWD-1-06 | 220kV FEEDER - GREAT ISLAND 220-LODGEWOOD 220-1 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND G4-T2004 | 20 | 20 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-GI GIS-T2102-04 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | 20 | 15 | Scheduled | 03/10/2016 | 22/10/2016
TO-16-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 14 | 10 | Scheduled | 10/10/2016 | 23/10/2016
TO-16-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 9 | 6 | Scheduled | 24/10/2016 | 01/11/2016
TO-16-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-GI-110K1-2-07 | COUPLER/SECTIONALISING CB - GREAT ISLAND AIS 110-GREAT ISLAND AIS 110-110K1-2 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI GIS-T2102-03 | TRANSFORMER - GREAT ISLAND 220-GREAT ISLAND AIS 110-T2102 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND AIS 110-WATERFORD 110-2 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-GI-WEX-1-06 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-GI-WEX-1-03 | 110kV FEEDER - GREAT ISLAND AIS 110-WEXFORD 110-1 | 12 | 10 | Proposed | 14/11/2016 | 25/11/2016
TO-16-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-WEX-110SA2-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 5 | 5 | Scheduled | 14/11/2016 | 18/11/2016
TO-16-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 5 | 5 | Reference | 14/11/2016 | 18/11/2016
TO-16-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-110SA1-02 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 2 | 0 | Scheduled | 26/11/2016 | 27/11/2016
TO-16-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 2 | 0 | Reference | 26/11/2016 | 27/11/2016
TO-16-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 2 | 0 | Reference | 26/11/2016 | 27/11/2016

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-MOY-TAW-1-06 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 114 | 81 | Scheduled | 02/08/2016 | 23/11/2016
TO-16-MOY-TAW-2-09 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 120 | 85 | Scheduled | 02/08/2016 | 29/11/2016
TO-16-TAW-T1/T2-05 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 114 | 81 | Reference | 02/08/2016 | 23/11/2016
TO-16-TAW-T101-06 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T101 | 114 | 81 | Reference | 02/08/2016 | 23/11/2016
TO-16-TAW-T102-08 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T102 | 120 | 85 | Reference | 02/08/2016 | 29/11/2016
TO-16-TAW-T3-06 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 120 | 85 | Reference | 02/08/2016 | 29/11/2016
TO-16-GOL-T101-04 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-CF-1-01 | 110kV FEEDER - GOLAGH tee-CATHALEENS FALL 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-GOL-1-04 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 53 | 36 | Scheduled | 23/09/2016 | 14/11/2016
TO-16-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 29 | 21 | Scheduled | 27/09/2016 | 25/10/2016
TO-16-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | 19 | 15 | Reference | 10/10/2016 | 28/10/2016
TO-16-BK-CBR-1-07 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 48 | 33 | Scheduled | 13/10/2016 | 29/11/2016
TO-16-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 177 | 125 | Scheduled | 07/06/2016 | 30/11/2016
TO-16-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 1 | 1 | Reference | 17/10/2016 | 17/10/2016
TO-16-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 1 | 1 | Scheduled | 17/10/2016 | 17/10/2016
TO-16-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 1 | 1 | Scheduled | 17/10/2016 | 17/10/2016
TO-16-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 43 | 30 | Scheduled | 17/10/2016 | 28/11/2016
TO-16-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 4 | 4 | Reference (Proposed) | 24/10/2016 | 27/10/2016
TO-16-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 6 | 4 | Scheduled | 18/11/2016 | 23/11/2016
TO-16-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 6 | 4 | Reference | 18/11/2016 | 23/11/2016
TO-16-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | 3 | 3 | Scheduled | 21/11/2016 | 23/11/2016
TO-16-DFR-T122-04 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 1 | 1 | Reference | 28/11/2016 | 28/11/2016
TO-16-DFR,T-DFR-1-04 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016
TO-16-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 1 | 1 | Scheduled | 28/11/2016 | 28/11/2016
TO-16-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | Scheduled | 30/11/2016 | 30/11/2016

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-RYB-RYB GIS-2-13 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-2 | 1 | 0 | Scheduled | 06/09/2016 | 25/12/2500
TO-16-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 16 | 12 | Scheduled | 03/10/2016 | 18/10/2016
TO-16-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 16 | 12 | Scheduled | 03/10/2016 | 18/10/2016
TO-16-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 17 | 13 | Proposed | 11/10/2016 | 27/10/2016
TO-16-CDU-RYB-1-09 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | 43 | 30 | Scheduled | 17/10/2016 | 28/11/2016
TO-16-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 9 | 7 | Scheduled | 17/10/2016 | 25/10/2016
TO-16-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 43 | 30 | Scheduled | 17/10/2016 | 28/11/2016
TO-16-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 10 | 8 | Scheduled | 17/10/2016 | 26/10/2016
TO-16-CLG-T121-04 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 2 | 2 | Proposed | 18/10/2016 | 19/10/2016
TO-16-CDU-RYB-1-11 | 110kV FEEDER - CORDUFF 110-RYEBROOK 110-1 | 4 | 4 | Scheduled | 18/10/2016 | 21/10/2016
TO-16-RYB-110SA1-2CB-14 | COUPLER/SECTIONALISING CB - RYEBROOK 110-RYEBROOK 110-110SA1-2CB | 4 | 4 | Scheduled | 18/10/2016 | 21/10/2016
TO-16-RYB-T101-09 | TSO CUSTOMER TRANSFORMER - RYEBROOK 110-RYEBROOK 10-T101 | 44 | 31 | Scheduled | 18/10/2016 | 30/11/2016
TO-16-CLG-T123-05 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 2 | 2 | Proposed | 20/10/2016 | 21/10/2016
TO-16-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 4 | 4 | Proposed | 24/10/2016 | 27/10/2016
TO-16-CLG-MCE-1-04 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | 2 | 2 | Proposed | 26/10/2016 | 27/10/2016
TO-16-FIN-110K2-3-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | 3 | 3 | Proposed | 26/10/2016 | 28/10/2016
TO-16-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 15 | 10 | Scheduled | 26/10/2016 | 09/11/2016
TO-16-MAY-WOO-1-01 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 10 | 8 | Scheduled | 01/11/2016 | 10/11/2016
TO-16-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 3 | 3 | Scheduled | 01/11/2016 | 03/11/2016
TO-16-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 3 | Scheduled | 02/11/2016 | 06/11/2016
TO-16-FIN-T2102-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2102 | 16 | 12 | Scheduled | 10/11/2016 | 25/11/2016
TO-16-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 8 | 6 | Scheduled | 18/11/2016 | 25/11/2016
TO-16-CKM-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES 220-CARRICKMINES 220-R2001 | 10 | 8 | Scheduled | 21/11/2016 | 30/11/2016
TO-16-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 5 | 4 | Scheduled | 22/11/2016 | 26/11/2016
TO-16-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 5 | 4 | Scheduled | 22/11/2016 | 26/11/2016
TO-16-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | 5 | 5 | Scheduled | 28/11/2016 | 02/12/2016
TO-16-RYB-RYB GIS-1-15 | 110kV FEEDER - RYEBROOK 110-RYEBROOK GIS 110-1 | 2 | 2 | Scheduled | 30/11/2016 | 01/12/2016

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-16-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 70 | 49 | Scheduled | 22/09/2016 | 30/11/2016
TO-16-BAN-DMY-1-05 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-DMY-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-DMY-CAP2-03 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 10 | 8 | Tentative | 10/10/2016 | 19/10/2016
TO-16-DMY-T142-02 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 10 | 8 | Reference (Tentative) | 10/10/2016 | 19/10/2016
TO-16-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 3 | 3 | Scheduled | 18/10/2016 | 20/10/2016
TO-16-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 3 | 3 | Scheduled | 18/10/2016 | 20/10/2016
TO-16-KRA-220K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 11 | 6 | Scheduled | 21/10/2016 | 31/10/2016
TO-16-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-AD-LPT-1-03 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016
TO-16-LPT-T2002-03 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 4 | Scheduled | 01/11/2016 | 05/11/2016