## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2018 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Date of publication: 28 09 2018
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 122 |  | Scheduled | 23/06/2018 | 22/10/2018
TO-18-KNR-TB-1-01 | 110kV FEEDER - KNOCKANURE 110-TARBERT 110-1 | 124 |  | Scheduled | 23/06/2018 | 24/10/2018
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | 117 | 83 | Scheduled | 09/07/2018 | 02/11/2018
TO-18-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-110 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A2 | 121 | 85 | Scheduled | 09/07/2018 | 06/11/2018
TO-18-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 121 | 85 | Scheduled | 09/07/2018 | 06/11/2018
TO-18-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 86 | 61 | Scheduled | 19/07/2018 | 12/10/2018
TO-18-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 117 |  | Scheduled | 23/07/2018 | 16/11/2018
TO-18-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 88 | 61 | Scheduled | 26/07/2018 | 21/10/2018
TO-18-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 66 | 48 | Scheduled | 20/08/2018 | 24/10/2018
TO-18-GI-ST101-02 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 134 | 93 | Scheduled | 20/08/2018 | 31/12/2018
TO-18-CBR-DLT-1-08 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 56 | 40 | Scheduled | 03/09/2018 | 28/10/2018
TO-18-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | 40 | 30 | Reference | 10/09/2018 | 19/10/2018
TO-18-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 21 | 15 | Scheduled | 12/09/2018 | 02/10/2018
TO-18-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 32 | 22 | Scheduled | 14/09/2018 | 15/10/2018
TO-18-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 32 | 22 | Scheduled | 14/09/2018 | 15/10/2018
TO-18-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 31 | 23 | Scheduled | 19/09/2018 | 19/10/2018
TO-18-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 27 | 19 | Scheduled | 21/09/2018 | 17/10/2018
TO-18-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 14 | 10 | Scheduled | 24/09/2018 | 07/10/2018
TO-18-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 9 | 7 | Scheduled | 24/09/2018 | 02/10/2018
TO-18-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 12 | 10 | Scheduled | 24/09/2018 | 05/10/2018
TO-18-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 12 | 10 | Scheduled | 24/09/2018 | 05/10/2018
TO-18-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 8 | 6 | Scheduled | 25/09/2018 | 02/10/2018
TO-18-GI-110K1-2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 19 | 13 | Scheduled | 26/09/2018 | 14/10/2018
TO-18-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 19 | 13 | Scheduled | 26/09/2018 | 14/10/2018
TO-18-CLG-T124-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 8 | 6 | Scheduled | 28/09/2018 | 05/10/2018
TO-18-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 8 | 6 | Scheduled | 01/10/2018 | 08/10/2018
TO-18-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 50 | 35 | Reference | 02/10/2018 | 20/11/2018
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Scheduled | 03/10/2018 | 05/10/2018
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Tentative | 03/10/2018 | 05/10/2018
TO-18-INC-MAY-1-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 04/10/2018 | 05/10/2018
TO-18-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 0 | Scheduled | 07/10/2018 | 07/10/2018
TO-18-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 7 |  | Scheduled | 08/10/2018 | 14/10/2018
TO-18-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 10 | 8 | Scheduled | 08/10/2018 | 17/10/2018
TO-18-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 1 | 1 | Scheduled | 08/10/2018 | 08/10/2018
TO-18-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-COL-T102-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T102 | 2 | 2 | Reference | 08/10/2018 | 09/10/2018
TO-18-110 kV A6 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110K6-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110SA4-6CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 5 |  | Scheduled | 08/10/2018 | 12/10/2018
TO-18-GI-WEX-1-08 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 12 | 10 | Tentative | 08/10/2018 | 19/10/2018
TO-18-KLG-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | 5 | 5 | Reference | 08/10/2018 | 12/10/2018
TO-18-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-MAY-T2104-03 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-NW-PB-1-06 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 4 | 4 | Scheduled | 08/10/2018 | 11/10/2018
TO-18-220 kV B4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 1 | 1 | Scheduled | 08/10/2018 | 08/10/2018
TO-18-PB-TF4-06 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 1 | 1 | Reference | 08/10/2018 | 08/10/2018
TO-18-SCR-T142-01 | DISTRIBUTION TRANSFORMER - SCREEBE 110-SCREEBE 38-T142 | 5 | 5 | Reference | 08/10/2018 | 12/10/2018
TO-18-SKL-M/CAP2-02 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 7 |  | Scheduled | 08/10/2018 | 14/10/2018
TO-18-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 12 | 10 | Scheduled | 08/10/2018 | 19/10/2018
TO-18-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 12 | 10 | Scheduled | 08/10/2018 | 19/10/2018
TO-18-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 12 | 10 | Reference | 08/10/2018 | 19/10/2018
TO-18-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 4 | 4 | Scheduled | 09/10/2018 | 12/10/2018
TO-18-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-CDU-110K1-2-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 1 | 1 | Scheduled | 09/10/2018 | 09/10/2018
TO-18-PB-R223-4-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-PB-SHL-1-05 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 3 | 3 | Scheduled | 10/10/2018 | 12/10/2018
TO-18-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 2 | 2 | Reference | 10/10/2018 | 11/10/2018
TO-18-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 3 | 3 | Scheduled | 10/10/2018 | 12/10/2018
TO-18-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 1 | 1 | Scheduled | 11/10/2018 | 11/10/2018
TO-18-CSH-GAL-3-05 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Scheduled | 11/10/2018 | 12/10/2018
TO-18-CLO-DRM-1-02 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 1 | 0 | Scheduled | 13/10/2018 | 13/10/2018
TO-18-110 kV B4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B4 | 9 | 5 | Scheduled | 13/10/2018 | 21/10/2018
TO-18-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-CSH-GAL-1-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 5 | 5 | Scheduled | 15/10/2018 | 19/10/2018
TO-18-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 5 | Proposed | 15/10/2018 | 19/10/2018
TO-18-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-GI-110K1-2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 10 | 8 | Reference | 15/10/2018 | 24/10/2018
TO-18-GI-T2101-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 5 | 5 | Scheduled | 15/10/2018 | 19/10/2018
TO-18-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 6 | 5 | Reference | 15/10/2018 | 20/10/2018
TO-18-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 5 | 3 | Scheduled | 17/10/2018 | 21/10/2018
TO-18-FIN-FIN GIS-2-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 2 | 2 | Scheduled | 18/10/2018 | 19/10/2018
TO-18-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 7 | 5 | Scheduled | 18/10/2018 | 24/10/2018
TO-18-KBY-MAL-1-03 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 1 | Scheduled | 19/10/2018 | 19/10/2018
TO-18-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 1 | 0 | Reference | 21/10/2018 | 21/10/2018
TO-18-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 1 | 0 | Scheduled | 21/10/2018 | 21/10/2018
TO-18-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 0 | Scheduled | 21/10/2018 | 21/10/2018
TO-18-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 2 | 1 | Scheduled | 21/10/2018 | 22/10/2018
TO-18-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 5 | 5 | Scheduled | 22/10/2018 | 26/10/2018
TO-18-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 25 | 18 | Proposed | 22/10/2018 | 15/11/2018
TO-18-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 1 | 1 | Scheduled | 22/10/2018 | 22/10/2018
TO-18-CDY-110SA1-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-CDY-110SA2-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | Proposed | 22/10/2018 | 25/10/2018
TO-18-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | Proposed | 22/10/2018 | 25/10/2018
TO-18-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | 2 | 2 | Reference (Proposed) | 22/10/2018 | 23/10/2018
TO-18-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 1 | 1 | Proposed | 22/10/2018 | 22/10/2018
TO-18-FIN GIS-T2106-09 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 12 | 9 | Proposed | 22/10/2018 | 02/11/2018
TO-18-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 3 | 3 | Scheduled | 22/10/2018 | 24/10/2018
TO-18-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 6 | 5 | Proposed | 22/10/2018 | 27/10/2018
TO-18-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 3 | 3 | Scheduled | 22/10/2018 | 24/10/2018
TO-18-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 1 | 1 | Proposed | 23/10/2018 | 23/10/2018
TO-18-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 3 | 3 | Scheduled | 23/10/2018 | 25/10/2018
TO-18-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | Scheduled | 24/10/2018 | 24/10/2018
TO-18-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | Scheduled | 24/10/2018 | 24/10/2018
TO-18-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-1-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-2-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-3-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 3 | 2 | Scheduled | 29/10/2018 | 31/10/2018
TO-18-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 12 | 9 | Scheduled | 29/10/2018 | 09/11/2018
TO-18-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 12 | 9 | Proposed | 29/10/2018 | 09/11/2018
TO-18-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 12 | 9 | Scheduled | 29/10/2018 | 09/11/2018
TO-18-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 4 | 3 | Scheduled | 29/10/2018 | 01/11/2018
TO-18-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 2 | 2 | Reference (Proposed) | 01/11/2018 | 02/11/2018
TO-18-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | Proposed | 05/11/2018 | 09/11/2018
TO-18-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 1 | 1 | Scheduled | 05/11/2018 | 05/11/2018
TO-18-CLG-T121-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 4 | 4 | Scheduled | 05/11/2018 | 08/11/2018
TO-18-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 12 | 10 | Scheduled | 05/11/2018 | 16/11/2018
TO-18-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 1 | 1 | Scheduled | 05/11/2018 | 05/11/2018
TO-18-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 3 | 3 | Proposed | 05/11/2018 | 07/11/2018
TO-18-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 2 | 2 | Scheduled | 06/11/2018 | 07/11/2018
TO-18-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 1 | 1 | Scheduled | 09/11/2018 | 09/11/2018
TO-18-WOO-T4202-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 1 | 1 | Scheduled | 09/11/2018 | 09/11/2018
TO-18-CRO-KBY-1-03 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 2 | 2 | Proposed | 12/11/2018 | 13/11/2018
TO-18-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 1 | 1 | Scheduled | 12/11/2018 | 12/11/2018
TO-18-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 3 | 3 | Scheduled | 12/11/2018 | 14/11/2018
TO-18-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 3 | 3 | Scheduled | 13/11/2018 | 15/11/2018
TO-18-INC-MAY-1-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 21 |  | Scheduled | 14/11/2018 | 04/12/2018
TO-18-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 21 |  | Scheduled | 14/11/2018 | 04/12/2018
TO-18-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 4 | 2 | Proposed | 15/11/2018 | 18/11/2018
TO-18-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 9 | 7 | Proposed | 15/11/2018 | 23/11/2018
TO-18-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 4 | 2 | Reference (Proposed) | 15/11/2018 | 18/11/2018
TO-18-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November
TO-18-CDU-110SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 1 | 1 | Scheduled | 19/11/2018 | 19/11/2018
TO-18-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 3 | 3 | Scheduled | 19/11/2018 | 21/11/2018
TO-18-SRA-110K1-2-01 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | 5 | 5 | Scheduled | 19/11/2018 | 23/11/2018
TO-18-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-RAF-1-03 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 2 | 2 | Scheduled | 20/11/2018 | 21/11/2018
TO-18-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | Reference | 20/11/2018 | 20/11/2018
TO-18-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 2 | 2 | Scheduled | 22/11/2018 | 23/11/2018
TO-18-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 2 | 2 | Scheduled | 22/11/2018 | 23/11/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | Proposed | 24/11/2018 | 25/11/2018

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 122 |  | Scheduled | 23/06/2018 | 22/10/2018
TO-18-KNR-TB-1-01 | 110kV FEEDER - KNOCKANURE 110-TARBERT 110-1 | 124 |  | Scheduled | 23/06/2018 | 24/10/2018
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | 117 | 83 | Scheduled | 09/07/2018 | 02/11/2018
TO-18-110 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A2 | 121 | 85 | Scheduled | 09/07/2018 | 06/11/2018
TO-18-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 121 | 85 | Scheduled | 09/07/2018 | 06/11/2018
TO-18-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | 117 |  | Scheduled | 23/07/2018 | 16/11/2018
TO-18-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 27 | 19 | Scheduled | 21/09/2018 | 17/10/2018
TO-18-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 6 | 5 | Scheduled | 15/10/2018 | 20/10/2018
TO-18-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 6 | 5 | Reference | 15/10/2018 | 20/10/2018
TO-18-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 7 | 5 | Scheduled | 18/10/2018 | 24/10/2018
TO-18-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 2 | 1 | Scheduled | 21/10/2018 | 22/10/2018
TO-18-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 5 | 5 | Scheduled | 22/10/2018 | 26/10/2018
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 3 | 2 | Scheduled | 29/10/2018 | 31/10/2018
TO-18-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | Proposed | 05/11/2018 | 09/11/2018
TO-18-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 1 | 1 | Scheduled | 05/11/2018 | 05/11/2018
TO-18-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 2 | 2 | Scheduled | 06/11/2018 | 07/11/2018
TO-18-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November
TO-18-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 2 | 2 | Scheduled | 22/11/2018 | 23/11/2018
TO-18-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 2 | 2 | Scheduled | 22/11/2018 | 23/11/2018

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 66 | 48 | Scheduled | 20/08/2018 | 24/10/2018
TO-18-GI-ST101-02 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 134 | 93 | Scheduled | 20/08/2018 | 31/12/2018
TO-18-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 32 | 22 | Scheduled | 14/09/2018 | 15/10/2018
TO-18-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 32 | 22 | Scheduled | 14/09/2018 | 15/10/2018
TO-18-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 31 | 23 | Scheduled | 19/09/2018 | 19/10/2018
TO-18-GI-110K1-2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 19 | 13 | Scheduled | 26/09/2018 | 14/10/2018
TO-18-GI-KKY-1-07 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 19 | 13 | Scheduled | 26/09/2018 | 14/10/2018
TO-18-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 5 |  | Scheduled | 08/10/2018 | 12/10/2018
TO-18-GI-WEX-1-08 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 12 | 10 | Tentative | 08/10/2018 | 19/10/2018
TO-18-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | 12 | 10 | Scheduled | 08/10/2018 | 19/10/2018
TO-18-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | 12 | 10 | Scheduled | 08/10/2018 | 19/10/2018
TO-18-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 12 | 10 | Reference | 08/10/2018 | 19/10/2018
TO-18-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-GI-110K1-2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 10 | 8 | Reference | 15/10/2018 | 24/10/2018
TO-18-GI-T2101-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 10 | 8 | Scheduled | 15/10/2018 | 24/10/2018
TO-18-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 6 | 5 | Proposed | 22/10/2018 | 27/10/2018
TO-18-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 3 | 3 | Scheduled | 23/10/2018 | 25/10/2018
TO-18-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | Proposed | 24/11/2018 | 25/11/2018

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | 117 | 83 | Scheduled | 09/07/2018 | 02/11/2018
TO-18-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 88 | 61 | Scheduled | 26/07/2018 | 21/10/2018
TO-18-CBR-DLT-1-08 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 56 | 40 | Scheduled | 03/09/2018 | 28/10/2018
TO-18-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 8 | 6 | Scheduled | 25/09/2018 | 02/10/2018
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Tentative | 03/10/2018 | 05/10/2018
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Scheduled | 03/10/2018 | 05/10/2018
TO-18-KLG-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-KNY-SCR-1-01 | 110kV FEEDER - KNOCKRANNY-SCREEBE 110-1 | 5 | 5 | Reference | 08/10/2018 | 12/10/2018
TO-18-LET-SVC-03 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-SCR-T142-01 | DISTRIBUTION TRANSFORMER - SCREEBE 110-SCREEBE 38-T142 | 5 | 5 | Reference | 08/10/2018 | 12/10/2018
TO-18-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 3 | 3 | Scheduled | 10/10/2018 | 12/10/2018
TO-18-CSH-GAL-3-05 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Scheduled | 11/10/2018 | 12/10/2018
TO-18-CLO-DRM-1-02 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 1 | 0 | Scheduled | 13/10/2018 | 13/10/2018
TO-18-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-CSH-GAL-1-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 5 | 5 | Scheduled | 15/10/2018 | 19/10/2018
TO-18-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 5 | Proposed | 15/10/2018 | 19/10/2018
TO-18-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 3 | 3 | Scheduled | 15/10/2018 | 17/10/2018
TO-18-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 1 | 0 | Reference | 21/10/2018 | 21/10/2018
TO-18-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 1 | 0 | Scheduled | 21/10/2018 | 21/10/2018
TO-18-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 0 | Scheduled | 21/10/2018 | 21/10/2018
TO-18-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 25 | 18 | Proposed | 22/10/2018 | 15/11/2018
TO-18-CDY-110SA1-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-CDY-110SA2-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | Proposed | 22/10/2018 | 25/10/2018
TO-18-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | Proposed | 22/10/2018 | 25/10/2018
TO-18-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | 2 | 2 | Reference (Proposed) | 22/10/2018 | 23/10/2018
TO-18-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 12 | 9 | Proposed | 22/10/2018 | 02/11/2018
TO-18-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 3 | 3 | Scheduled | 22/10/2018 | 24/10/2018
TO-18-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-1-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-2-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-3-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 12 | 9 | Scheduled | 29/10/2018 | 09/11/2018
TO-18-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 12 | 9 | Proposed | 29/10/2018 | 09/11/2018
TO-18-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 12 | 9 | Scheduled | 29/10/2018 | 09/11/2018
TO-18-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 4 | 3 | Scheduled | 29/10/2018 | 01/11/2018
TO-18-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 1 | 1 | Scheduled | 05/11/2018 | 05/11/2018
TO-18-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 3 | 3 | Scheduled | 12/11/2018 | 14/11/2018
TO-18-SRA-110K1-2-01 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | 5 | 5 | Scheduled | 19/11/2018 | 23/11/2018

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Scheduled | 03/10/2018 | 05/10/2018
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 3 | 3 | Tentative | 03/10/2018 | 05/10/2018
TO-18-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 7 |  | Scheduled | 08/10/2018 | 14/10/2018
TO-18-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-SKL-M/CAP2-02 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 7 |  | Scheduled | 08/10/2018 | 14/10/2018
TO-18-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 1 | 1 | Scheduled | 11/10/2018 | 11/10/2018
TO-18-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 5 | 5 | Proposed | 15/10/2018 | 19/10/2018
TO-18-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 5 | 3 | Scheduled | 17/10/2018 | 21/10/2018
TO-18-FLA-LOU-1-01 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 12 | 9 | Proposed | 22/10/2018 | 02/11/2018
TO-18-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 3 | 3 | Scheduled | 22/10/2018 | 24/10/2018
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 3 | 3 | Proposed | 31/10/2018 | 02/11/2018
TO-18-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 2 | 2 | Proposed | 01/11/2018 | 02/11/2018
TO-18-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 2 | 2 | Reference (Proposed) | 01/11/2018 | 02/11/2018
TO-18-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 12 | 10 | Scheduled | 05/11/2018 | 16/11/2018
TO-18-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 1 | 1 | Scheduled | 09/11/2018 | 09/11/2018
TO-18-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 4 | 2 | Proposed | 15/11/2018 | 18/11/2018
TO-18-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 9 | 7 | Proposed | 15/11/2018 | 23/11/2018
TO-18-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 4 | 2 | Reference (Proposed) | 15/11/2018 | 18/11/2018

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 91 | 64 | Scheduled | 09/07/2018 | 07/10/2018
TO-18-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | 40 | 30 | Reference | 10/09/2018 | 19/10/2018
TO-18-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 21 | 15 | Scheduled | 12/09/2018 | 02/10/2018
TO-18-FIN-220K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 14 | 10 | Scheduled | 24/09/2018 | 07/10/2018
TO-18-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 9 | 7 | Scheduled | 24/09/2018 | 02/10/2018
TO-18-CLG-T124-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 8 | 6 | Scheduled | 28/09/2018 | 05/10/2018
TO-18-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 8 | 6 | Scheduled | 01/10/2018 | 08/10/2018
TO-18-INC-MAY-1-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 04/10/2018 | 05/10/2018
TO-18-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 0 | Scheduled | 07/10/2018 | 07/10/2018
TO-18-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 10 | 8 | Scheduled | 08/10/2018 | 17/10/2018
TO-18-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 1 | 1 | Scheduled | 08/10/2018 | 08/10/2018
TO-18-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 9 | 7 | Scheduled | 08/10/2018 | 16/10/2018
TO-18-COL-T102-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T102 | 2 | 2 | Reference | 08/10/2018 | 09/10/2018
TO-18-110 kV A6 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110K6-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110SA4-6CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-MAY-T2104-03 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | 5 | 5 | Scheduled | 08/10/2018 | 12/10/2018
TO-18-NW-PB-1-06 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 4 | 4 | Scheduled | 08/10/2018 | 11/10/2018
TO-18-220 kV B4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 1 | 1 | Scheduled | 08/10/2018 | 08/10/2018
TO-18-PB-TF4-06 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 1 | 1 | Reference | 08/10/2018 | 08/10/2018
TO-18-CDU-110K1-2-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 1 | 1 | Scheduled | 09/10/2018 | 09/10/2018
TO-18-PB-R223-4-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-PB-SHL-1-05 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 3 | 3 | Scheduled | 09/10/2018 | 11/10/2018
TO-18-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 2 | 2 | Reference | 10/10/2018 | 11/10/2018
TO-18-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 3 | 3 | Scheduled | 10/10/2018 | 12/10/2018
TO-18-110 kV B4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B4 | 9 | 5 | Scheduled | 13/10/2018 | 21/10/2018
TO-18-FIN-FIN GIS-2-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 2 | 2 | Scheduled | 18/10/2018 | 19/10/2018
TO-18-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 2 | 2 | Scheduled | 22/10/2018 | 23/10/2018
TO-18-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 1 | 1 | Proposed | 22/10/2018 | 22/10/2018
TO-18-FIN GIS-T2106-09 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Proposed | 22/10/2018 | 23/10/2018
TO-18-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 1 | 1 | Proposed | 23/10/2018 | 23/10/2018
TO-18-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 1 | 1 | Scheduled | 24/10/2018 | 24/10/2018
TO-18-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | Scheduled | 24/10/2018 | 24/10/2018
TO-18-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 | Proposed | 24/10/2018 | 25/10/2018
TO-18-CLG-T121-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 4 | 4 | Scheduled | 05/11/2018 | 08/11/2018
TO-18-WOO-T4202-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 1 | 1 | Scheduled | 09/11/2018 | 09/11/2018
TO-18-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 1 | 1 | Scheduled | 12/11/2018 | 12/11/2018
TO-18-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 3 | 3 | Scheduled | 13/11/2018 | 15/11/2018
TO-18-INC-MAY-1-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 21 |  | Scheduled | 14/11/2018 | 04/12/2018
TO-18-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 21 |  | Scheduled | 14/11/2018 | 04/12/2018
TO-18-CDU-110SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 1 | 1 | Scheduled | 19/11/2018 | 19/11/2018
TO-18-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 3 | 3 | Scheduled | 19/11/2018 | 21/11/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | Proposed | 24/11/2018 | 25/11/2018

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 86 | 61 | Scheduled | 19/07/2018 | 12/10/2018
TO-18-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 12 | 10 | Scheduled | 24/09/2018 | 05/10/2018
TO-18-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 12 | 10 | Scheduled | 24/09/2018 | 05/10/2018
TO-18-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 50 | 35 | Reference | 02/10/2018 | 20/11/2018
TO-18-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 4 | 4 | Scheduled | 09/10/2018 | 12/10/2018
TO-18-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | 5 | 5 | Scheduled | 15/10/2018 | 19/10/2018
TO-18-KBY-MAL-1-03 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 1 | 1 | Scheduled | 19/10/2018 | 19/10/2018
TO-18-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 1 | 1 | Scheduled | 22/10/2018 | 22/10/2018
TO-18-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 3 | 3 | Proposed | 05/11/2018 | 07/11/2018
TO-18-CRO-KBY-1-03 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 2 | 2 | Proposed | 12/11/2018 | 13/11/2018
TO-18-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BAN-RAF-1-03 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 2 | 2 | Scheduled | 20/11/2018 | 21/11/2018
TO-18-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 1 | 1 | Scheduled | 20/11/2018 | 20/11/2018
TO-18-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | Reference | 20/11/2018 | 20/11/2018